## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Piling ITP |  |  |  |  | Yes | Piling ITP | 0f97168c-6235-4219-8340-8235d7c224e8
checkpoint-group |  |  | section | Pre-construction
checkpoint-status |  |  | checkpoint | 1.1 - JSA signed off
label | 90a6dab7-0b6e-585d-bdc9-65125f7eae31 |  | note | Acceptance Criteria - Written Notification from Downer
label | 09d350e6-83c1-5568-8239-341d27abf117 |  | note | Applicable Standard -
label | 78cfbc6f-e84d-5493-b572-10d1f6659362 |  | note | Frequency - Once
label | eda43e0c-4e46-5fc8-936a-2f2296efdee7 |  | note | Verifying Records - This ITP
checkpoint-status |  |  | checkpoint | 1.2 - PIP, Piling Installation Plan Signed off
label | 7e9d7f28-e836-5482-87f3-cbb9d8b66e86 |  | note | Acceptance Criteria - Written Notification from Downer
label | 52434016-6f7a-598f-a9b1-98690bff116f |  | note | Applicable Standard -
label | 082cb9f6-9ab3-57df-bd10-94d03e0b3a66 |  | note | Frequency - Once
label | 60253a93-acdc-5ffc-952e-e63daa82f146 |  | note | Verifying Records - This ITP
checkpoint-status |  |  | checkpoint | 1.3 - Shop Drawings: Steel Detail Sheets
label | 912ec419-0df9-5a39-a552-02d0c4efe46d |  | note | Acceptance Criteria - Written Notification from Downer
label | b1d0d643-6b88-561f-8afb-cbb9e00905cc |  | note | Applicable Standard - AS/NZS 1554.3,
label | f45ffe6a-533a-5cc3-8303-6e20019827bf |  | note | Frequency - Once, before fixing cages
label | 692e57c2-bfbe-540b-8c30-e4ba33e69b94 |  | note | Verifying Records - This ITP
checkpoint-status |  |  | checkpoint | 1.4 - Mix Designed signed off
label | 36c9d3fa-3a72-5542-ba7b-d2164337317a |  | note | Acceptance Criteria - Written Notification from Downer
label | ab1d0a1f-61dc-5fa4-9c84-be46bec36273 |  | note | Applicable Standard - Waka Kotahi Technical Specifications, BBO Specifications, Construction Drawing Set
label | 5e05a9a0-4434-527d-bbce-13411a0e79e9 |  | note | Frequency - Once
label | 37c409ba-63ac-5bd9-b9a6-9f0d27902def |  | note | Verifying Records - This ITP
checkpoint-group |  |  | section | Construction of Piles
checkpoint-status |  |  | checkpoint | 2.1 - Traffic Management
label | 543b6d54-de68-5704-b8fb-b6a3d528e33d |  | note | Acceptance Criteria - As shown in the Traffic Management Plan
label | b2dff3e1-5751-56d8-9ff7-f112ddb8faa8 |  | note | Applicable Standard - Contract Documents
label | 28fbe13b-c9ba-5f96-81a8-20f1b3af0d8f |  | note | Method - As per the TMP
label | 4da9b357-f5c4-561c-9d97-78628a1f2a67 |  | note | Frequency - Before mobilising piling equipment
label | d00febc9-304a-5dc2-b49e-f6176bc11fe5 |  | note | Verifying Records - This ITP
checkpoint-status |  |  | checkpoint | 2.2 - Water and Power supply
label | a4525a2f-d127-55f3-9cc5-96012a77e73f |  | note | Acceptance Criteria - 2 phase power, tab suitable for hose connections
label | 3b4fa2d0-8e99-5aa1-a46a-fa3f39864d25 |  | note | Applicable Standard - Contract Documents
label | 05fe3572-7142-55c7-b965-6d7330eb67eb |  | note | Method - Visual
label | d442f056-a679-5216-98c0-abb4a4a58197 |  | note | Frequency - Before mobilising piling equipment
label | 4505ec9e-ed85-5e41-8b52-3f104df19986 |  | note | Verifying Records - This ITP
checkpoint-status |  |  | checkpoint | 2.3 - Working platform
label | 41a40f14-6fc5-5b15-87ea-d7ae92279844 |  | note | Acceptance Criteria - Working Platform Certificate
label | 9aeba5f6-1db7-5fd1-8c2e-7cfcf7331208 |  | note | Applicable Standard - Construction Drawings and PIP
label | 302e21f9-fef3-5ec5-95fc-6f83b23224d3 |  | note | Frequency - Before moving piling equipment into position over pile location
label | 8f3a7317-4f6b-569f-a8ae-de916ff61b54 |  | note | Verifying Records - This ITP or Working Platform Certificate
checkpoint-status |  |  | checkpoint | 2.4 - Proof Bores
label | 62c30b0b-8f7c-57be-996c-650c9c69602f |  | note | Acceptance Criteria - Engineer`s review and comment
label | e49af653-2a73-5bb5-8d25-d683089895c0 |  | note | Applicable Standard - Drawing 4001 rev.2
label | e4a1a51e-e98f-5b67-befa-9490795bf0db |  | note | Method - Machine Drilling
label | 80b4e2e6-be50-5f7c-a25a-4b936f568820 |  | note | Frequency - Before drilling commences
label | ed82477b-a84c-5606-bca3-a8bbdca4392d |  | note | Verifying Records - Borehole Records
checkpoint-status |  |  | checkpoint | 2.5 - Surveying Pile Centres
label | 11dc36bf-06c4-591b-bf5c-b02b5276b98f |  | note | Acceptance Criteria - Placing the survey peg on the pile centre
label | abfde72a-b5c0-526d-a1dd-ee512b42045d |  | note | Applicable Standard - Surveying industry standards
label | ffa6696f-fe71-5e46-8dcc-f52cba98b6f4 |  | note | Method - Survey
label | 3755e16f-d50f-5825-b43a-8f1fd1876770 |  | note | Frequency - Before drilling commences
label | efd052ec-9cfa-5f5c-8c85-e27f566c43d2 |  | note | Verifying Records - This ITP
checkpoint-status |  |  | checkpoint | 2.6 - Sediment Ponds
label | 1d4304c1-99e6-5d3a-aea6-34686cfd717d |  | note | Acceptance Criteria - Close to the piling locations, big enough to accommodate water coming from pile holes
label | 216b62c3-3806-5430-9fc2-48169cb74364 |  | note | Applicable Standard - Resource Content, PIP,
label | c908d0c0-2b30-5dc5-ad46-b5bd480cedba |  | note | Frequency - Before drilling commences
label | f580640a-eae0-528c-87a7-6a7fd6d4376d |  | note | Verifying Records - This ITP
checkpoint-status |  |  | checkpoint | 2.7 - Reinforcing Cage
label | 33bccac6-992a-5606-b84b-d3150650a6ea |  | note | Acceptance Criteria - As per approved details sheet (item 1.3 of this ITP) For example lap length is minimum 1.8m for RB32, Grade 500 steel
label | 41b83122-d0a7-58d5-b999-7188943f59da |  | note | Applicable Standard - Waka Kotahi Specifications, BBO, Specifications, Construction Drawings
label | 17df4c0e-986e-5511-abbd-397ca9f9a80c |  | note | Method - Visual
label | 5a945a17-e457-5547-8e74-0ff11eee79ab |  | note | Frequency - Every Pile Cage
label | 5bb40c13-0641-5e73-9517-ffbbe1b0e555 |  | note | Verifying Records - This ITP and Site Inspection Record Documents
checkpoint-status |  |  | checkpoint | 2.8 - Drilling borehole and Pile socket length
label | 2c984c4b-b416-522d-a78b-534db09ce717 |  | note | Acceptance Criteria - Engineer`s Acceptance, sockets lengths as per approved drawing
label | 9b63f8ce-0885-5da9-b5ae-bff16ff46abb |  | note | Applicable Standard - Waka Kotahi Specifications, BBO Specifications, Construction Drawings, PIP, Drawing 4010 rev.2
label | 9c4d7d78-1103-5a1e-8949-e3a6167e7f05 |  | note | Method - Visual
label | 2d215fe4-0c69-5fa5-a479-1408027565dd |  | note | Frequency - Every Pile
label | 269f886d-64e6-5967-9936-7be4abcdf456 |  | note | Verifying Records - This ITP and Site Inspection Record Documents, Pile Card
checkpoint-status |  |  | checkpoint | 2.9 - Placing pile cage and concreting
label | c2dd1cb2-ff0a-52d1-b2ae-2594a8d5d1e0 |  | note | Acceptance Criteria - Pile cage identification tag matches with pile number. Downer confirms that cage orientation and position are under tolerances.
label | ef6d3820-06c5-54f0-a99d-3d101a899ceb |  | note | Applicable Standard - Waka Kotahi Specifications, BBO Specifications, Construction Drawings, PIP
label | d38fbcd5-fac5-5f01-a517-21c34937a6c9 |  | note | Method - Survey
label | 0241683c-02c0-5a46-9919-b9491b673ff4 |  | note | Frequency - Every pile
label | e142c4e7-51bf-5593-ab2c-ac76cbddff5b |  | note | Verifying Records - This ITP and Pile Card
checkpoint-status |  |  | checkpoint | 2.10 - On site concrete testing
label | 7f3efc84-4ad1-5e77-b59d-3e776c959862 |  | note | Acceptance Criteria - As per approved mix design (item 1.4 of this ITP)
label | 339548fe-cf24-502b-b2c8-75b21d08d291 |  | note | Applicable Standard - PIP, Waka Kotahi Specifications, BBO
label | 9142b370-4771-5ea2-9464-e50964162aea |  | note | Method - In-situ test
label | 41d04a1d-197f-5596-9c43-8985e3a40e9a |  | note | Frequency - Each delivery
label | c447892c-25a6-57c1-963b-5bdd21b832df |  | note | Verifying Records - Concrete docket
checkpoint-status |  |  | checkpoint | 2.11 - Removal of permanent casing
label | 46896bc0-d9c8-5e09-9cf0-ef714a24a266 |  | note | Acceptance Criteria - As per tolerances
label | f791f8a0-bc73-5a7d-9a8d-7b4ea16359ae |  | note | Applicable Standard - Construction drawing 4010 Rev.2, Waka Kotahi Specifications, BBO
label | aa352b5c-1102-5080-aea7-b9c6c21fb730 |  | note | Method - Survey
label | df428316-662b-5dca-8073-363404875a6f |  | note | Frequency - Every pile
label | e227f944-42da-5c48-a544-4da41b085e49 |  | note | Verifying Records - Pile Card
checkpoint-status |  |  | checkpoint | 2.12 - Concrete crush test
label | 485117cc-aa26-5bf1-b747-2e3a159b057f |  | note | Acceptance Criteria - Minimum 40 MPa for 28 days samples (3 samples for 28 days and 1 sample for 7 days)
label | cc600708-96e0-5e55-9c8a-d0db6d8e7c6a |  | note | Applicable Standard - Waka Kotahi Specifications, BBO
label | 3cd5267c-849d-56ef-aee0-256a2d72a642 |  | note | Method - Laboratory Crush Test
label | 71c35469-65cf-5fdd-9cfe-40cc1ab835f7 |  | note | Frequency - Each pouring day
label | f8749333-659b-5c8c-8dee-46cf427e7f55 |  | note | Verifying Records - Concrete test results
checkpoint-status |  |  | checkpoint | 2.13 - Integrity testing
label | eecdc486-3157-5ca4-be0d-04b627ad0d01 |  | note | Acceptance Criteria - No major defects or flows
label | 85eeea85-0ad4-53e6-9627-87b575789a94 |  | note | Applicable Standard - Drawing 4001 rev.2, PIT Specifications
label | f73a0898-2a09-5152-b536-4e1eb16a0b4a |  | note | Method - Pile Integrity Testing
label | 3fcb72c0-5d12-5b03-88d3-dcacd866a5f5 |  | note | Frequency - 50% of piles
label | f3e0b905-dc31-5531-87cc-d14a580f8bb5 |  | note | Verifying Records - Test results
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 27d6248d-9e58-535f-bed8-6d349dea1fa0 |  | textbox | Contractor's Rep Name:
text | 93b9a3a8-b03e-5a27-90f1-54f0133565f8 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP 300 Stormwater Drainage |  |  |  |  | Yes | ITP 300 Stormwater Drainage | 1a2b86b0-90d1-4e31-8a91-1218667ef284
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 300.1 - Mark out works
label | ece4a993-0bb5-562a-b1bf-b8fa47b360a3 |  | note | Detail of Activity: Set out and mark up proposed drainage features by surveyor
label | f4e675df-d71d-56c4-b116-a4879f22660b |  | note | Action: H
label | ee90696f-7f1d-5a69-a0d0-1ec1b47e3f8d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All drainage features
label | 96dd21a1-6737-51d8-8089-e4682e79b659 |  | note | Inspection / Test Method: Visual Inspection
label | 6bee180a-7189-5dfa-95f0-980e4380ab37 |  | note | Acceptance Criteria: N/A
label | 25324f16-b857-580b-afd4-2b1084988f7e |  | note | Record Documents: Contractor's site diary
label | 99e24245-b63f-5f6e-bd1d-76b3f87c4dc6 |  | note | Responsibility: Contractor
label | 137e20e9-6926-5358-8ee9-d77f3c09eb18 |  | note | Comments: Treatment area marked up jointly by Contractor and Eng.Rep. Approved by Designer
checkpoint-status |  |  | checkpoint | 300.2 - Underground services
label | ea2292c6-4fe6-5e13-8fed-66f689e45703 |  | note | Detail of Activity: Identify and positively locate services
label | c580f05c-56ed-59f9-b67f-3e34432d6cce |  | note | Action: H
label | d8995efe-868a-519d-805b-7342f06680a1 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All drainage features
label | 3f2bf0a8-b084-5b99-ad12-17d76caf21e6 |  | note | Inspection / Test Method: Hydoexcavation
label | 76567db6-f696-5454-bae1-2c6818879a85 |  | note | Acceptance Criteria: N/A
label | c514a171-555a-5b34-b707-7c4469b62113 |  | note | Record Documents: Drawings
label | c59b730d-6f17-58e9-b8c3-f209d4261ac7 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.3 - Precast Concrete Pipes
label | 2fcf6c27-0307-5ee1-be25-408ec52d9646 |  | note | Detail of Activity: Contract to provide manufacturer dwgs of the proposed design for approval
label | 6f10ddb4-5be7-5df9-8398-e5a73432e320 |  | note | Action: H
label | 63d72ed3-63d5-5935-943e-e26a558f2116 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per culvert size/type
label | 10dba40b-a9a2-5f6b-ac6f-179e3ca9006a |  | note | Inspection / Test Method: Supplier Producer Statement
label | ba85e3b7-bcd8-51a2-acbc-1370c0116925 |  | note | Acceptance Criteria: NZS 4058:2007
label | 44e2456f-1767-5fbf-9a6c-01c9f2a9847e |  | note | Record Documents: NTC / Site instruction
label | e2a98a02-b9a3-5515-abc0-383edb12665f |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.4 - Precast headwall/wingwall units
label | b729bd87-7b22-55d5-8a4d-1e6ba63dfa50 |  | note | Detail of Activity: Contract to provide manufacturer dwgs of the proposed structure design for approval
label | 92ea4182-55e1-5738-a8b9-cf687b4727b3 |  | note | Action: H
label | 39ee7d85-21f9-5731-8742-62bba9ef4c4a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per wingwall type
label | 6ecb438f-87d9-5638-873a-516a543d6f3c |  | note | Inspection / Test Method: N/A
label | 83bab304-2ccb-5b63-947b-135e07c7135d |  | note | Acceptance Criteria: Engineer to review and approve proposed design
label | f83a92a1-6400-5483-82db-90c001930e8e |  | note | Record Documents: NTC / Site instruction
label | 007e4ed7-81fe-56a6-b131-65672e38ea21 |  | note | Responsibility: Contractor
label | 17c79590-7e29-53d5-b51e-92b7d4922ec0 |  | note | Comments: This requirement acknowledges minor variances in manufacturer design details for precast wingwalls
checkpoint-group |  |  | section | Construction and Finishing - Stormwater Line 1- Ch 225m Kopaki Rd; 750mm Dia
checkpoint-status |  |  | checkpoint | 300.5 - Determine Subgrade Strength
label | eb9fbef6-eabb-5a94-8b5c-bf07938d25a0 |  | note | Detail of Activity: Determine bearing strength of subgrade
label | 823614b7-7d25-5da8-ac23-8a144044a06c |  | note | Action: H
label | b3dafaf6-a809-5be7-8a85-d59aa237eab6 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 136a5e69-02eb-5202-9478-5f7f652c4213 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | b2417739-6da5-5573-8884-6276a38c2ae5 |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | 4cf9d084-6010-535d-b539-4f85cdde2175 |  | note | Record Documents: Contractor's site diary
label | 73d25cc5-6a01-52c7-9e45-753eddca685d |  | note | Responsibility: Contractor
label | 588f7f90-97e4-5b2a-840b-e5b34ba2595d |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.6 - Pipe bedding
label | 547619a2-1cf1-5180-9bec-61fdfe922093 |  | note | Detail of Activity: Bedding
label | eebd8348-693c-5213-81e9-0aa2919c3cb8 |  | note | Action: M
label | 64fcddb6-e7f9-5530-a66a-77b66dcadd3d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench
label | f8665f9a-ad3d-50e2-a1f5-fa445a6ee32f |  | note | Inspection / Test Method: NZS 3725:2007
label | 9d55f0b1-9a87-55a8-9cdf-ec6200f67658 |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | 6ff9ab30-a3de-5e1d-8682-9575a85f394e |  | note | Record Documents: Contractor's site diary
label | 7b6040d9-0335-5d68-9e27-77a1dbce2c49 |  | note | Responsibility: Contractor
label | fe2d1a0b-076d-5958-bf6a-d490740bfd87 |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.7 - Jointing of pipes
label | 6e745fff-a7ff-5256-bfc9-6f464cf871be |  | note | Detail of Activity: Jointing
label | 6b4fee89-b502-510d-bdc5-f37e79ab294d |  | note | Action: M
label | 8620e0c0-c8eb-5d7b-93ef-dd9ca491431b |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Every Pipe Joint
label | 24252ac5-1561-50c5-a41c-4d421ab4e43f |  | note | Inspection / Test Method: Visual Inspection
label | 4290baa3-f707-50a1-b611-4af368e6c5b3 |  | note | Acceptance Criteria: In Accordance with section 5.2 of the Project Technical Spec.
label | 7f81fd3b-41b7-5d33-bf46-d08759e869e5 |  | note | Record Documents: Contractor's site diary
label | 4e84ac8c-221c-543c-9733-cf88bbd499a9 |  | note | Responsibility: Contractor
label | 3ef338ec-8ebd-5961-a2a1-2d8bdaed6702 |  | note | Comments: Rubber rings to be mounted evenly and lined up truly concentric with pipe. Gap between spigot and shoulder to of pipes to be even and between 5mm and 10mm.
checkpoint-status |  |  | checkpoint | 300.8 - Pipe haunching
label | f7744520-2318-5c0c-bc3d-c4c962c91142 |  | note | Detail of Activity: Haunching
label | 2ef1a5ae-b4b7-5f38-9c14-17bed7804a8e |  | note | Action: M
label | 80214caf-b984-5d25-a741-638024946214 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench
label | 56be8321-aee0-548f-a75d-4f64d8a320cd |  | note | Inspection / Test Method: NZS 3725:2007
label | ed4d4914-17c0-5f0c-bb05-abb7aa5ba9e3 |  | note | Acceptance Criteria: In Accordance with HS2, Minimum haunching depth of 0.3D, CIV Value on compacted haunching >25 (CBR = 30).
label | e59f7f5d-1e2a-5d7a-b20e-2899e16831f9 |  | note | Record Documents: Contractor's site diary
label | 2c2c8dfa-829b-5f26-8833-de827341dbe7 |  | note | Responsibility: Contractor
label | 437ee093-1f5f-5b33-ae27-eacccf784582 |  | note | Comments: PAP 7 material to be used.
checkpoint-status |  |  | checkpoint | 300.9 - Trench backfill
label | dffb20f0-379f-5c02-b903-50e99aaa2be4 |  | note | Detail of Activity: Backfilling
label | 70794d30-e6f9-597b-a49a-db5a154ef599 |  | note | Action: M
label | c68cc380-2a30-5790-bc39-74cd92e6474e |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | d9a1e1b4-3026-5581-ab38-1fcdd0fdad5d |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | ac50c1c5-1b40-54ec-be86-9c3f7190d895 |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | e33c6276-0853-52e0-b190-72eca99ed2a0 |  | note | Record Documents: Contractor's site diary
label | 507742bf-33d5-5614-86d2-76ba18a35fb2 |  | note | Responsibility: Contractor
label | f14a04a7-f97a-5379-a53d-65b823eb9895 |  | note | Comments: Clean Pumice Fill to be used
checkpoint-status |  |  | checkpoint | 300.10 - Visual Structural Inspection
label | 3d0c7a56-9b1b-5cb6-9e62-1f01209220b2 |  | note | Detail of Activity: Visual inspection of concrete components
label | 14f7f6c0-45af-52ea-aed5-49f1901b5aa5 |  | note | Action: W
label | 9d494c4c-593e-5ef8-b0ef-dc7fb278ad9d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | 4a5ef465-3d97-5ec3-8581-fe0a42c58dc7 |  | note | Inspection / Test Method: Visual Inspection
label | 52c3ed27-e857-543e-ad2f-e3d46c0e6486 |  | note | Acceptance Criteria: No visible damage, especially around collars and spiggots
label | 817b7ea4-52c0-59b5-94a2-c68b1ee9d51a |  | note | Record Documents: Contractor's site diary/Photos
label | 6364df05-d7ba-596f-afb2-22761ee8e5d2 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.11 - CCTV Inspection
label | d8a8ad92-bb64-588b-b4f6-12e8afcfe575 |  | note | Detail of Activity: Visual record of Existing works
label | e4f58cfc-16e4-5211-bb69-9dbe9425edf9 |  | note | Action: W
label | 77efd114-3a2b-5e39-805a-20339fc55877 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All drainage pipelines
label | ab860684-2241-5a6d-b3bb-9fe653125f0c |  | note | Inspection / Test Method: CCTV Inspection
label | 0e4c7c53-1549-52a0-8c75-9094534220a0 |  | note | Acceptance Criteria: No significant cracks, level deformation, faulty joints
label | e14e651e-1207-5fbd-a407-fa812f1b6225 |  | note | Record Documents: CCTV Footage
label | 63c02250-fcc9-595c-b2cf-930ca1c4c93f |  | note | Responsibility: Contractor
label | d0970c56-07d8-5256-ab7e-b4773f555780 |  | note | Comments: CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practicle Completion
checkpoint-group |  |  | section | Construction and Finishing - Inlet 1-1 1400mmDia Standpipe with Scruffy Dome - Ch 220m Kopaki Rd
checkpoint-status |  |  | checkpoint | 300.12 - Determine Subgrade Strength
label | 0a64ea8f-7260-5b6d-8a0d-d623887a9eb0 |  | note | Detail of Activity: Determine bearing strength of subgrade
label | 88b41596-7703-5c62-8d1f-7f9a08e9d972 |  | note | Action: H
label | 9a74d470-694d-5856-b138-ec1987c4cadf |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 593dec1f-f899-54cc-9617-526dee3a0b8c |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 779d2171-dbd8-5f01-a2a8-2a14dd95c733 |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | 13e5798d-1455-5a40-80e5-737b0151ff23 |  | note | Record Documents: Contractor's site diary
label | e3a3f9c9-b269-53b9-9235-20be862b07a3 |  | note | Responsibility: Contractor
label | ef9800fb-6ba6-5597-ad22-3667a369d138 |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.13 - Structures (manholes, head walls etc.)
label | 629286e9-23a4-5f48-9dd8-2d6d8e556a17 |  | note | Detail of Activity: Visual inspection of concrete components
label | 2fadf4dc-2111-5e5e-997c-721d4d64ef49 |  | note | Action: W
label | 202b859f-1c8c-528a-b5c2-2c294d4fc726 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | 429b847e-6438-5cc7-ac12-c0b6d9b515ec |  | note | Inspection / Test Method: Visual Inspection
label | 7b3b6fd4-1209-52d8-8aa7-e06dd08f8b3c |  | note | Acceptance Criteria: No visible damage, especially around collars and joints
label | c8ff5357-4c95-5bca-a710-d049bbfdcaca |  | note | Record Documents: Contractor's site diary/Photos
label | 1af4db62-a41c-54d3-98dd-4ea94f017f50 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.14 - Structures (manholes, head walls etc.)
label | df306cd3-fc84-5201-9691-e933a185dd89 |  | note | Detail of Activity: Bedding
label | 92fe3efc-9219-5897-96e5-c8e6313a8879 |  | note | Action: M
label | 8eb67411-9637-5cba-8972-c8d3a0891b71 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 061cfbe6-96d0-5a2d-8e7e-5c34c8cea865 |  | note | Inspection / Test Method: NZS 3725:2007
label | 2b32e7e6-fc59-516e-a639-476340644826 |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | e088c1ea-d929-5f4f-a3f7-0b62a7423081 |  | note | Record Documents: Contractor's site diary
label | 89903dce-53e1-5c12-a0d5-bebd0c152785 |  | note | Responsibility: Contractor
label | 70ddc005-9319-592a-9773-d28b3f9eabb1 |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.15 - Structures (manholes, head walls etc.)
label | 80b19db8-7614-5b6a-8de9-fe422e5a658e |  | note | Detail of Activity: Backfilling
label | 307e871a-41b7-570d-ad97-d6a110c54c79 |  | note | Action: M
label | 16a527d6-95a7-5b08-883e-0cb9392815a1 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 494cfe57-ae73-52b7-bf24-8fb3aa3656a8 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 7a7c4dd6-0fc2-5bfb-984d-34bd86de81e6 |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | 587fa8b6-a508-5a26-999d-b1addf95383a |  | note | Record Documents: Contractor's site diary
label | 2f3691df-7faa-546c-81ee-8de120996060 |  | note | Responsibility: Contractor
label | 966b154e-c756-5992-b0e3-2cdcd8c8caba |  | note | Comments: Clean Pumice Fill to be used
checkpoint-group |  |  | section | Construction and Finishing - Outlet 1-2 Precast Headwall- Ch 230m Kopaki Rd
checkpoint-status |  |  | checkpoint | 300.16 - Determine Subgrade Strength
label | ec28ce8a-5ec2-55eb-86f4-1bc7eed09a0a |  | note | Detail of Activity: Determine bearing strength of subgrade
label | 9868cd77-c82e-58ee-8d3b-446513032f69 |  | note | Action: H
label | fbb0ee79-fe9a-57c7-b477-c35e2bfb9c5d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 8f75ed72-1ce5-5480-ade2-60213e0ce340 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 2dce6391-99c1-5ec1-88b2-748e2d535e97 |  | note | Acceptance Criteria: No target - Engineer to advise undercut requirements prior to installation
label | 38b2f39e-1ccf-57ec-ace2-1b22ce1c3c2b |  | note | Record Documents: Contractor's site diary
label | 0d4069f6-8672-5fcd-99e4-51caac471ac8 |  | note | Responsibility: Contractor
label | fa076e2a-d89e-5b4b-ba57-5ad22a6bc9b2 |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.17 - Structures (manholes, head walls etc.)
label | 86ac1474-c435-507b-a8dd-e65ab8203cd7 |  | note | Detail of Activity: Visual inspection of concrete components
label | 3310c421-2b8a-5ae9-b1cf-4c1ea4286d6c |  | note | Action: W
label | 4cfedee3-88ae-51ad-8061-38654ba39ce9 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | d0ed4fde-584b-5e14-a8c3-c4bfdec02f8e |  | note | Inspection / Test Method: Visual Inspection
label | 5b55d84a-2279-54e0-815d-32d8edda8fb6 |  | note | Acceptance Criteria: No visible damage, especially around collars and joints
label | 5b3011d7-6b5a-596f-8607-b1b9de70e5e1 |  | note | Record Documents: Contractor's site diary/Photos
label | 2243ffc5-2a03-5b1c-9c7d-a530defc7a10 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.18 - Structures (manholes, head walls etc.)
label | c70a6900-0788-5758-9ae4-426698719682 |  | note | Detail of Activity: Bedding
label | 2f403b02-0a39-58c9-b190-4226b5ef9847 |  | note | Action: M
label | 82c0e993-1585-58f2-aaa7-3405f0597eea |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | c37b755e-4e74-57cb-bede-241fd59381a2 |  | note | Inspection / Test Method: NZS 3725:2007
label | 61c1b957-ce1a-5566-9282-7b98023072ef |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >15 (CBR = 20).
label | bbb9406b-6e49-5b1f-b9b5-97be0be4302f |  | note | Record Documents: Contractor's site diary
label | 956d201b-3512-510a-b8f9-fbfcb8e1015a |  | note | Responsibility: Contractor
label | e37aed33-2853-5555-a5a8-965bba5103db |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.19 - Structures (manholes, head walls etc.)
label | 0809e035-be6a-5a82-a7f7-18b5cd95fb18 |  | note | Detail of Activity: Backfilling
label | 9aa385d6-9ea8-5829-89f4-07f0b98cd3e8 |  | note | Action: M
label | fa485dd7-9562-5c8a-8e1c-09344f51dc1d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | a5d312a3-ca3f-5429-8c01-febbf5a3559b |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 43411300-5532-5041-979d-3dcec4dbc417 |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | 1b7e858c-87a0-5b08-8e3a-27a875b26283 |  | note | Record Documents: Contractor's site diary
label | 772131a3-a1dd-558c-a83b-5b46b5eb0715 |  | note | Responsibility: Contractor
label | 4621de6d-f628-58ad-b5b8-d395ec5f55eb |  | note | Comments: Clean Pumice Fill to be used
checkpoint-group |  |  | section | Construction and Finishing - Stormwater Line 2- Inlet 2.1 to SD 2.2 @ CH65 Kopaki Road - Bradcock Access Track ( Ø900mm)
checkpoint-status |  |  | checkpoint | 300.20 - Determine Subgrade Strength
label | a551ade8-4c7e-5dd6-a738-c170129e23d8 |  | note | Detail of Activity: Determine bearing strength of subgrade
label | d87c3764-00a8-5048-a5d3-43cf34dec362 |  | note | Action: H
label | 06092731-c176-5ceb-8529-6e6893f8e753 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 696e0a3c-1517-5030-b736-a5ab47f14dec |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | fab23e36-5496-5551-88bc-5678593def38 |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | cc68be3f-3b63-5754-9de1-87804a3b9024 |  | note | Record Documents: Contractor's site diary
label | 75b88ef5-960d-55ed-800b-fad2ae5c2688 |  | note | Responsibility: Contractor
label | 3fbdf450-5222-56ad-a4ce-b7b13762ce45 |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.21 - Pipe bedding
label | 464a7366-a8e6-53cb-b88a-a58fddf611cb |  | note | Detail of Activity: Bedding
label | af70221f-37e2-5e06-afff-6806825124ad |  | note | Action: M
label | 242523cb-11e0-57c6-83cc-1fb101239ea9 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench
label | 44856705-47fc-51df-900a-730eaf5c6902 |  | note | Inspection / Test Method: NZS 3725:2007
label | 6aec3aeb-2194-580d-8371-6f2509f6bacf |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | 2886c041-c451-5dd4-b8bc-0d98bc607048 |  | note | Record Documents: Contractor's site diary
label | 7732a7c6-3502-5347-b767-d09c83da0355 |  | note | Responsibility: Contractor
label | ab0f6c1a-b287-524a-99bc-5c17d04f2f1b |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.22 - Jointing of pipes
label | 366f50fe-ef2e-5077-a752-642abf520b4f |  | note | Detail of Activity: Jointing
label | 54e63045-1fe2-5cb1-8f95-9999f202e60e |  | note | Action: M
label | b41190c2-fd92-5153-ae20-de3df5f8d8c4 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Every Pipe Joint
label | fac742c9-37be-548f-b70e-4dca73432dff |  | note | Inspection / Test Method: Visual Inspection
label | 5894ef1a-2b28-54f1-920c-d391dd0411ff |  | note | Acceptance Criteria: In Accordance with section 5.2 of the Project Technical Spec.
label | ef63450f-e496-50cf-94ae-0b8502eac390 |  | note | Record Documents: Contractor's site diary
label | 125d8832-50c8-5f55-a73c-f89777f55fc8 |  | note | Responsibility: Contractor
label | 078de01b-a5b6-54af-8069-55281bb702f5 |  | note | Comments: Rubber rings to be mounted evenly and lined up truly concentric with pipe. Gap between spigot and shoulder to of pipes to be even and between 5mm and 10mm.
checkpoint-status |  |  | checkpoint | 300.23 - Pipe haunching
label | be5b7a9b-4d32-531e-b386-584f618f4f7f |  | note | Detail of Activity: Haunching
label | 85f25ccc-c7b8-5cde-80aa-329f554f1535 |  | note | Action: M
label | 203b5ebf-42e4-5c52-857a-6751d72a66d2 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench
label | b796a93f-11ca-56be-85e7-f78b53b9a885 |  | note | Inspection / Test Method: NZS 3725:2007
label | bd4b0ea2-5725-5646-a404-b09515e2f409 |  | note | Acceptance Criteria: In Accordance with HS2, Minimum haunching depth of 0.3D, CIV Value on compacted haunching >25 (CBR = 30).
label | fc11554c-7dcf-5f1c-b576-1972c9869729 |  | note | Record Documents: Contractor's site diary
label | e271f7e6-4c6d-51c6-8e2e-ad592a6f8145 |  | note | Responsibility: Contractor
label | b6f63c97-0a2a-5cb5-a6cd-c110e02059a6 |  | note | Comments: PAP 7 material to be used.
checkpoint-status |  |  | checkpoint | 300.24 - Trench backfill
label | 0781f62c-f5e3-5dbe-9621-b4399895e816 |  | note | Detail of Activity: Backfilling
label | bddfc49b-c243-569f-be63-e36e2b5d4d4c |  | note | Action: M
label | 47d5f185-d10b-5541-9c96-b90703e878f0 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | af9e7465-e1ed-5f98-8c10-b2dd1c2569cf |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 4f6a6f23-1499-5d48-9a98-403c5b4a1bfb |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | 817c48e5-f3be-55b7-bd16-d0661a0b4633 |  | note | Record Documents: Contractor's site diary
label | 43c9bb5a-1e10-5779-af87-44b4cdfad172 |  | note | Responsibility: Contractor
label | ab1f7260-82cf-5b34-95a9-a02e6c6e8c3e |  | note | Comments: Clean Pumice Fill to be used
checkpoint-status |  |  | checkpoint | 300.25 - Visual Structural Inspection
label | ceecf435-85d3-5325-a761-17b8397a2790 |  | note | Detail of Activity: Visual inspection of concrete components
label | 972e4e23-7d9c-5656-9795-dc4a0074a207 |  | note | Action: W
label | b31a2a6e-d117-5539-b81b-85b2d904fc68 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | 54b41bff-71c3-5053-8559-3b5c596307dd |  | note | Inspection / Test Method: Visual Inspection
label | 87a6e7e2-8a53-547d-b9b3-91141472fbd4 |  | note | Acceptance Criteria: No visible damage, especially around collars and spiggots
label | 92dd6cdd-b5ef-5445-87ed-71f728a0eb62 |  | note | Record Documents: Contractor's site diary/Photos
label | 63e52dce-866a-5d02-a43d-2752e55a7315 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.26 - CCTV Inspection
label | fce25802-da77-514b-83a4-6557e19f0f6b |  | note | Detail of Activity: Visual record of Existing works
label | 93995f4e-e8aa-5817-aebb-3ccbee27122e |  | note | Action: W
label | 3171c9ae-04a2-50da-9e45-dc0b524ebde3 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All drainage pipelines
label | beca50ce-dc44-5f71-af55-cb73af9c8068 |  | note | Inspection / Test Method: CCTV Inspection
label | 886c5489-65ed-5045-a8f1-759e9977be67 |  | note | Acceptance Criteria: No significant cracks, level deformation, faulty joints
label | d10f9b81-0a5e-5b9d-a5f7-bc26c15f321b |  | note | Record Documents: CCTV Footage
label | 82185ff5-9487-5267-9540-05811f1751f6 |  | note | Responsibility: Contractor
label | 84870904-2027-57fc-90aa-672ec00d36da |  | note | Comments: CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practicle Completion
checkpoint-group |  |  | section | Construction and Finishing - Inlet 2-1 : Precast Headwall Bradcock Access Track ( Ø900mm)
checkpoint-status |  |  | checkpoint | 300.27 - Determine Subgrade Strength
label | f3e17526-73de-5d9e-82ac-f6ea010b2d0a |  | note | Detail of Activity: Determine bearing strength of subgrade
label | 09468573-5604-5a9e-8011-d9f6f0d326c8 |  | note | Action: H
label | 40f42fec-3bd8-5114-a443-6f7198f7d1cc |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | c0049c8f-6016-52c7-a4bb-91936f4b37e3 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 0f06e0b9-52df-5fae-9f29-baa7196f3c19 |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | c91f2db6-7f37-5117-a3f6-082bb7b729fb |  | note | Record Documents: Contractor's site diary
label | 87952081-5cf5-5dcd-b0ed-7919158c6065 |  | note | Responsibility: Contractor
label | 5b4996d2-9f8a-5dba-8408-48918451d4b5 |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.28 - Structures (manholes, head walls etc.)
label | f732c435-49e6-5008-87f3-3c7a78982418 |  | note | Detail of Activity: Visual inspection of concrete components
label | 2b617aab-c81c-5e26-9304-10d9920fea8d |  | note | Action: W
label | c0a48435-4be4-52ba-a1c8-11a2aa34f3d0 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | 48e68c32-0645-57ee-9b6d-958508929639 |  | note | Inspection / Test Method: Visual Inspection
label | 4120efdb-bc1e-5ac5-a9d4-a0893258295b |  | note | Acceptance Criteria: No visible damage, especially around collars and joints
label | a91b140c-4e94-5370-b798-65161468aa9a |  | note | Record Documents: Contractor's site diary/Photos
label | 85c40a3c-4dd2-5a0a-8be2-e3f8c6907e47 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.29 - Structures (manholes, head walls etc.)
label | e83c028d-4b1d-5ca5-9897-894304beca4e |  | note | Detail of Activity: Bedding
label | 33f770d0-0eb7-5a2d-9de6-255b7c1ee1a7 |  | note | Action: M
label | d98fd0c5-b062-5e93-83c4-5ac94c41ff08 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 442d1645-715e-5719-80e4-1ba7d5bca5bb |  | note | Inspection / Test Method: NZS 3725:2007
label | 050a2083-1198-5187-b03d-95135c84f11b |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | fe06abed-577f-58dd-b88f-9edc8e891381 |  | note | Record Documents: Contractor's site diary
label | cd648be6-05fa-579d-96a9-3603a2909817 |  | note | Responsibility: Contractor
label | 943fb758-d69a-5e93-b3c0-5529a06a60fc |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.30 - Structures (manholes, head walls etc.)
label | ccfece17-1e7a-57a2-8afb-6052b40ca35b |  | note | Detail of Activity: Backfilling
label | bfb8c379-50f0-56e5-b93b-3709e14cf951 |  | note | Action: M
label | 92669232-8a8a-5c81-bad5-d907e03d12a0 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 3d5edbce-09e0-5511-8281-50194d114041 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 5b68350c-9d79-5597-a011-8dc1dc10d280 |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | f58cc4e2-788b-5710-ad2a-54fd61234fdf |  | note | Record Documents: Contractor's site diary
label | dee9dfc8-087a-5321-992b-454c23647253 |  | note | Responsibility: Contractor
label | 49cc8b78-72a5-5144-95da-6676b2b94e97 |  | note | Comments: Clean Pumice Fill to be used
checkpoint-group |  |  | section | Construction and Finishing - SD2.2 Manhole/Standpipe with Scruffy Dome Bradcock Access Track ( Ø1650mm)
checkpoint-status |  |  | checkpoint | 300.31 - Determine Subgrade Strength
label | 82cab35c-a1d8-54e2-a654-7db4c2b72b4c |  | note | Detail of Activity: Determine bearing strength of subgrade
label | faad82c5-bffb-5a74-aa25-45c16b3e04aa |  | note | Action: H
label | 1f4f9192-bb26-5197-9ab7-a06599ec11b7 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 89abd8dc-6096-5668-a874-a46b89599ac2 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 46ad1238-68ab-5cbc-9023-972f77ac178d |  | note | Acceptance Criteria: No target - Engineer to advise undercut requirements prior to installation
label | be842af1-cd55-525c-8736-093b6531e69a |  | note | Record Documents: Contractor's site diary
label | 41319a4c-9a93-5c42-adee-878f7797d74a |  | note | Responsibility: Contractor
label | e84ca942-80f6-5359-9951-474b045233b5 |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.32 - Structures (manholes, head walls etc.)
label | ee255cc5-3fc1-5ac4-a7e6-88ecdd097db5 |  | note | Detail of Activity: Visual inspection of concrete components
label | cc7c9f15-c34a-5ae7-a41c-6dbea2256eb4 |  | note | Action: W
label | 5ff563c5-4d40-501c-a31d-58ff5ce09f9a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | 0f2d62de-9484-5947-b23c-4c39875a8657 |  | note | Inspection / Test Method: Visual Inspection
label | ca919e66-ebd9-50a3-b36f-0be5dd0484d9 |  | note | Acceptance Criteria: No visible damage, especially around collars and joints
label | bb47772d-f1e3-506e-ac5f-952aff73fdaf |  | note | Record Documents: Contractor's site diary/Photos
label | b8b36854-86de-541c-9367-d3d0d6053763 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.33 - Structures (manholes, head walls etc.)
label | eeb759b7-3676-530f-811a-b4338d6ba044 |  | note | Detail of Activity: Bedding
label | 3091c5c6-d8cb-504b-8ac6-5ef7279094ab |  | note | Action: M
label | bf882ad5-5804-5ce4-aa7c-6dabe46a6a8f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 0d1db9c0-d63d-5f9f-b9d4-bd4fa61734ef |  | note | Inspection / Test Method: NZS 3725:2007
label | e7c81df3-4c13-5f79-bf5d-6417c1703837 |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >15 (CBR = 20).
label | ed9ab2aa-0469-5a3f-9ef7-201bb68fad55 |  | note | Record Documents: Contractor's site diary
label | c608d733-2a0f-5b90-a0f1-011d7e71c8ba |  | note | Responsibility: Contractor
label | b7a52e2c-71a2-542a-b87a-f29d4a6e8f62 |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.34 - Structures (manholes, head walls etc.)
label | 7c8fbc55-811c-57ab-b733-23826b659d8a |  | note | Detail of Activity: Backfilling
label | cbeca5da-4ada-5834-8d3d-fb365287db3b |  | note | Action: M
label | df49c710-a18d-54dc-abea-eece8f2b8977 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 9aa7864b-b42b-54b6-96b1-6201072d8fc6 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | f9248d55-6afa-5b4c-a741-8094b05d4d63 |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | 410653b2-7642-5424-b60b-84f4703907fc |  | note | Record Documents: Contractor's site diary
label | 5729cd9b-1ab7-5623-8df0-bf15d1b5e4cb |  | note | Responsibility: Contractor
label | 6189300a-04f6-597b-9797-af2c791026cd |  | note | Comments: Clean Pumice Fill to be used
checkpoint-group |  |  | section | Construction and Finishing - Stormwater Line 2 - SD 2-2 to Outlet 2-3 Kopaki Road (Ø900mm)
checkpoint-status |  |  | checkpoint | 300.35 - Determine Subgrade Strength
label | e62a7a1d-8bc0-5411-b8b8-d31ab73c4d71 |  | note | Detail of Activity: Determine bearing strength of subgrade
label | a130738f-4dc2-54c9-ab86-3084401aff35 |  | note | Action: H
label | 462386f1-9e81-565b-a789-634c4db077b7 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 6900c3c5-9401-5bc6-a913-955f73ea6f6a |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | b56af196-d840-559d-a455-d9311cad9da5 |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | 21079baf-d9e4-5ee7-ae08-fc011ace1b51 |  | note | Record Documents: Contractor's site diary
label | 2dc8bc14-fb2a-5039-9ca3-3e37b53ba746 |  | note | Responsibility: Contractor
label | 5b2c8d36-a21f-5356-b0ca-cb81a6dffbb4 |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.36 - Pipe bedding
label | e46b235e-87f4-583f-992c-7cdafbd6acd6 |  | note | Detail of Activity: Bedding
label | 07ce8bf3-4f36-5820-84b5-e083d561284a |  | note | Action: M
label | 8a5a5812-1fec-5631-847a-6171dfed7e19 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench
label | ecfbef21-6931-57ad-aa8c-91475fb5cf4a |  | note | Inspection / Test Method: NZS 3725:2007
label | 6abbe4f2-1501-5782-8f27-8243901739e0 |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | b28b1558-34cf-589b-8350-50ca84dfae2f |  | note | Record Documents: Contractor's site diary
label | ded2593c-4d56-5472-8e29-38549d067f27 |  | note | Responsibility: Contractor
label | 811ed986-9025-5ef3-bcf1-ab29605b3558 |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.37 - Jointing of pipes
label | cfeea789-928e-5e7c-ac04-70f83ea5b09f |  | note | Detail of Activity: Jointing
label | 53654a1e-10a1-5570-8c90-ce808e827671 |  | note | Action: M
label | eefb4c61-c3e0-5222-9e8d-1d81918d0b13 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Every Pipe Joint
label | e5ffacee-d62c-55a5-b860-7820b5c7495e |  | note | Inspection / Test Method: Visual Inspection
label | c92bcc8d-9c93-5525-958d-e205e3c1475a |  | note | Acceptance Criteria: In Accordance with section 5.2 of the Project Technical Spec.
label | 39337bad-b528-5848-b584-8c446764001e |  | note | Record Documents: Contractor's site diary
label | 92c62f6e-15fe-5bf8-bd9d-ee3dc492216f |  | note | Responsibility: Contractor
label | 48e8516f-6c3c-5247-9edf-0b2b8c3a78a9 |  | note | Comments: Rubber rings to be mounted evenly and lined up truly concentric with pipe. Gap between spigot and shoulder to of pipes to be even and between 5mm and 10mm.
checkpoint-status |  |  | checkpoint | 300.38 - Pipe haunching
label | 47595875-8bf1-5eae-a820-695df1e9a6f1 |  | note | Detail of Activity: Haunching
label | 454eea90-ab6c-546e-a93b-c808579bf762 |  | note | Action: M
label | 8b59236c-2b0e-5845-8386-a54850c3bfaa |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench
label | 649fd7aa-75a9-5017-bf16-666dcd38609d |  | note | Inspection / Test Method: NZS 3725:2007
label | b620dd2d-11f5-548a-a6f5-cc08633e158c |  | note | Acceptance Criteria: In Accordance with HS2, Minimum haunching depth of 0.3D, CIV Value on compacted haunching >25 (CBR = 30).
label | e55bd942-947d-5939-83cd-60f254e32196 |  | note | Record Documents: Contractor's site diary
label | c5544100-6dcb-5397-9e42-3f9ccadacbc9 |  | note | Responsibility: Contractor
label | 6d2916b5-3de9-531b-8039-d9cc2f4554fb |  | note | Comments: PAP 7 material to be used.
checkpoint-status |  |  | checkpoint | 300.39 - Trench backfill
label | 8be20c8f-de31-5bde-83ca-f65f0256f042 |  | note | Detail of Activity: Backfilling
label | c3797c54-30e3-5e1a-aa68-1a72134c3043 |  | note | Action: M
label | 1701d65d-2b8f-516a-ba3e-671735799927 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 91f1e075-4ec0-552b-a99e-8b7049b25bef |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 4cfb4367-ab9f-5ffa-86be-b0cd67c70dbc |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | c04a0114-66f4-567b-8592-bdde171e1cc4 |  | note | Record Documents: Contractor's site diary
label | 98fef729-ff83-5924-b6de-31ddcd9ad046 |  | note | Responsibility: Contractor
label | daa57fb0-cf4a-58eb-859b-228838f29448 |  | note | Comments: Clean Pumice Fill to be used
checkpoint-status |  |  | checkpoint | 300.40 - Visual Structural Inspection
label | 8778a6d9-c3c4-5595-a9a0-afde7525b131 |  | note | Detail of Activity: Visual inspection of concrete components
label | e5ce56dc-3c8d-5b4f-af59-b8ceda441ee8 |  | note | Action: W
label | 13158716-ef61-54ce-9b24-dcc7f39d0280 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | 3a8e15fa-abc0-5209-9a38-b76b925da55a |  | note | Inspection / Test Method: Visual Inspection
label | b1ca22aa-c6f7-56c0-ac0a-65b2957a0983 |  | note | Acceptance Criteria: No visible damage, especially around collars and spiggots
label | 8f59bb98-bc34-5f65-b9be-bbff04dfc67e |  | note | Record Documents: Contractor's site diary/Photos
label | dc375a5b-46d5-55d9-8cff-a5d807bff5db |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.41 - CCTV Inspection
label | f0c46c41-72eb-57df-a3de-ca3a860992ac |  | note | Detail of Activity: Visual record of Existing works
label | 9a671fa2-e7a4-50dc-8c66-8aa9d98cc549 |  | note | Action: W
label | ae0e77ab-fab9-5b5b-9ba2-2fb85450ced1 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All drainage pipelines
label | 239df559-39eb-56c6-8823-5df21bb01acb |  | note | Inspection / Test Method: CCTV Inspection
label | e600f208-811e-538a-8d22-77f8b3885a46 |  | note | Acceptance Criteria: No significant cracks, level deformation, faulty joints
label | 1cdaf91d-cfdd-5f13-9847-b5df0e8dae9b |  | note | Record Documents: CCTV Footage
label | 7cb14bf0-84a6-57e3-ba95-2e45bd5a8ade |  | note | Responsibility: Contractor
label | 846f8af4-1aad-507b-a134-e8cc0dab8d9b |  | note | Comments: CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practicle Completion
checkpoint-group |  |  | section | Construction and Finishing - Outlet 2-3 : Precast Headwall Kopaki Road ( Ø900mm)
checkpoint-status |  |  | checkpoint | 300.42 - Determine Subgrade Strength
label | c710e810-7546-596e-bd8b-b1509cd93c16 |  | note | Detail of Activity: Determine bearing strength of subgrade
label | a0183614-26bf-54cc-b59a-f395aa7983ff |  | note | Action: H
label | 3484fa9d-f9b7-540e-b26b-06dbf82a597f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 9daf94e4-8092-5f3d-8606-1f81b05d028f |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 45c515f0-a977-516a-9b5f-1cf5deb0f213 |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | 797c81e1-5f32-5a2e-bf5b-649de1d33b3f |  | note | Record Documents: Contractor's site diary
label | 2653f39e-09d6-5d5e-9e88-b268f44de079 |  | note | Responsibility: Contractor
label | 5433b69c-3ddb-515e-87e1-3f318c256b39 |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.43 - Structures (manholes, head walls etc.)
label | c9b36131-cabb-5bd1-b5c6-c463974e52df |  | note | Detail of Activity: Visual inspection of concrete components
label | 40848ce7-46fb-55d6-ac82-a9f679cefdc6 |  | note | Action: W
label | 1351d2f6-bbe0-576e-ba09-a825ee052d5f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | 5ebc7ce4-6d95-5e61-9ab9-544974f6347a |  | note | Inspection / Test Method: Visual Inspection
label | eca544d8-6747-51a6-8cd6-ace628d7244f |  | note | Acceptance Criteria: No visible damage, especially around collars and joints
label | 5fe805f8-e730-5e96-9819-996cb2b1345e |  | note | Record Documents: Contractor's site diary/Photos
label | a0e41c38-b3a5-5d43-8bf4-711c5c6e6075 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.44 - Structures (manholes, head walls etc.)
label | 9f3e44c5-f4b4-5fc0-9ed5-a0d1aec7f3a4 |  | note | Detail of Activity: Bedding
label | 2b7fd318-fc80-5e85-bbb6-22263bc7bb02 |  | note | Action: M
label | d65dd2cc-3c13-5e28-82d6-016620e99ab3 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 8375878a-25e2-5943-9679-47a6ca60ad57 |  | note | Inspection / Test Method: NZS 3725:2007
label | 92d78725-93b0-5843-bf32-fdcb331daedb |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | b99a53df-6bac-560b-8180-569b64c4e1c6 |  | note | Record Documents: Contractor's site diary
label | e1945b14-e8a3-5474-8869-6d7aaac6ddc5 |  | note | Responsibility: Contractor
label | 5124a3fe-fe67-5a6f-8cbd-4b02502df4c5 |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.45 - Structures (manholes, head walls etc.)
label | f2465cab-03a2-5d5d-a042-3482df1205da |  | note | Detail of Activity: Backfilling
label | 8b5c716e-9438-5832-801c-29921b58a3c0 |  | note | Action: M
label | 86391dbd-3564-542b-82f9-d2140f192d70 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | e9fbb215-6a21-594c-8c4b-e5dc861764f1 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 665d0412-997f-59a8-a0d5-624db2f7f9b0 |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | 20e868e2-550c-527d-aae0-0fb3561f3821 |  | note | Record Documents: Contractor's site diary
label | eefd2637-1eea-510d-b0b4-4b8479b0ceaf |  | note | Responsibility: Contractor
label | a378081f-7538-5826-83c6-76765695088d |  | note | Comments: Clean Pumice Fill to be used
checkpoint-group |  |  | section | Construction and Finishing - Inlet 2-4 : Precast headwall/wingwall - CH 290 State Highway 30 (Ø1050mm)
checkpoint-status |  |  | checkpoint | 300.46 - Determine Subgrade Strength
label | e06a220a-8fca-526d-b374-520325982ef0 |  | note | Detail of Activity: Determine bearing strength of subgrade
label | 6b96314c-5e13-5478-ac96-616957ed48a0 |  | note | Action: H
label | ea9e818c-e8ac-5540-9e63-c08ae103c4f8 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | c719bb6d-b363-5062-b414-380dc5a35af5 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 6155f655-c5fc-5f3a-988e-6c3003bf54aa |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | 46fcf5de-9ab6-5d9b-8875-edd72bc8bab8 |  | note | Record Documents: Contractor's site diary
label | aa597012-b1a3-5970-959c-9ce37a50a14a |  | note | Responsibility: Contractor
label | c9034910-c5c2-5b80-82dd-216277b0226c |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.47 - Structures (manholes, head walls etc.)
label | 8b442316-f051-5453-9f54-d4e9d3d38a18 |  | note | Detail of Activity: Visual inspection of concrete components
label | 3a333a4c-294d-588c-b59a-945a19de5f0b |  | note | Action: W
label | f38236d6-ce75-500c-858d-e7154e3d9564 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | cec8562d-e3d5-5603-8661-3b730d8021fd |  | note | Inspection / Test Method: Visual Inspection
label | 9bc4ae90-4ea0-53e1-bc60-79a9d65aa42d |  | note | Acceptance Criteria: No visible damage, especially around collars and joints
label | 435df944-a745-5ec2-b966-5e2d313d11eb |  | note | Record Documents: Contractor's site diary/Photos
label | ee07da0c-5ba4-583c-bea0-b7fd0e26d2a7 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.48 - Structures (manholes, head walls etc.)
label | 827db2d1-e230-59b3-8391-0585200b5d2a |  | note | Detail of Activity: Bedding
label | c2ada11b-2b33-521a-80df-4b41c1e17f07 |  | note | Action: M
label | b78c88f5-199d-5542-90d6-26531da2390b |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 9fe8985f-8c9b-5b42-9358-49fb71f6a3b8 |  | note | Inspection / Test Method: NZS 3725:2007
label | 2fae9a1c-fe38-59cc-ae2b-a2f78c66a299 |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | ef323d32-f279-5f9d-a8cd-b7f604c9b0cb |  | note | Record Documents: Contractor's site diary
label | 1d1e9277-f3f9-537c-9a6c-42d81a012b6e |  | note | Responsibility: Contractor
label | dd30a8bf-2891-585a-94a4-113d855f3f88 |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.49 - Structures (manholes, head walls etc.)
label | 388ce5d0-3f1e-5a43-8845-9ff857245b32 |  | note | Detail of Activity: Backfilling
label | 74ba4df9-40be-5b82-9c0e-b98b1f704a41 |  | note | Action: M
label | d440617d-6ce8-5f46-a145-081b38f9e98a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 29b16c2b-3024-5223-94fd-e0ee07a6ddad |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 60f39f31-1e06-53de-bbf9-d5a379857649 |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | 2aaa76a3-4177-5ce0-b9e5-1b8afe89bb5c |  | note | Record Documents: Contractor's site diary
label | e7281509-f9bf-58ae-8534-992ea64d8e32 |  | note | Responsibility: Contractor
label | 2c22ad5b-80fc-55c4-9640-68ccc27e0aa3 |  | note | Comments: Clean Pumice Fill to be used
checkpoint-group |  |  | section | Construction and Finishing - Stormwater Line 2 - Inlet 2-4 to Outlet 2-5 : Statehighway 30 (Ø1050mm)
checkpoint-status |  |  | checkpoint | 300.50 - Determine Subgrade Strength
label | dbdcda89-6382-5b4f-bc6a-7c369c072c0f |  | note | Detail of Activity: Determine bearing strength of subgrade
label | 32828512-21c1-5b1e-a9e7-e8e83d13067d |  | note | Action: H
label | 48a88cbb-6618-5236-bb25-d5c209f2ba94 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 7548ff3a-0962-516b-a790-8c6e1a72636a |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 8d5860c6-ae74-5675-bbaf-cb2b4ef4f031 |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | 2f75562d-4cde-53ee-b3ff-94d9fef96ce3 |  | note | Record Documents: Contractor's site diary
label | e9981e0c-6779-5c60-8513-17be04c74dfc |  | note | Responsibility: Contractor
label | 1e80823c-715d-597d-bb9b-92313d36312c |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.51 - Pipe bedding
label | 79f5e172-11da-5a72-a746-ca3e15647cf8 |  | note | Detail of Activity: Bedding
label | 7f00c230-f87d-5fa8-be84-9edd0d2b57b8 |  | note | Action: M
label | d8e07324-5e77-5e49-b646-49325e43bcb7 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench
label | 1415eb66-c87b-5459-b5df-82019070577c |  | note | Inspection / Test Method: NZS 3725:2007
label | f5b6ebda-f77a-5beb-8654-bcdbacdda33d |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | 4455ba10-bce8-5437-8990-e44b451cbc0f |  | note | Record Documents: Contractor's site diary
label | 3b29712f-2e45-5db8-855c-38d0dc6378b0 |  | note | Responsibility: Contractor
label | f2bc473a-99a4-5d0c-8a6e-66909c95c0da |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.52 - Jointing of pipes
label | 79711d62-b049-58bc-b650-ee39d3047c8f |  | note | Detail of Activity: Jointing
label | 2cb71cec-7181-5dba-929c-9cb65588f393 |  | note | Action: M
label | a7e29960-d337-5ed2-add7-22cfa70c8ab0 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Every Pipe Joint
label | 16a5808e-465c-59d8-a545-e0d690822bf3 |  | note | Inspection / Test Method: Visual Inspection
label | 54b25422-4590-514a-8eb3-e7bf43b6dc7f |  | note | Acceptance Criteria: In Accordance with section 5.2 of the Project Technical Spec.
label | 2c99e850-f584-55ab-abc2-fb24066d476c |  | note | Record Documents: Contractor's site diary
label | 7d33601d-0e7b-539a-a66e-bab0552ce2ad |  | note | Responsibility: Contractor
label | 51dfdc74-9320-564b-aa21-6173448944af |  | note | Comments: Rubber rings to be mounted evenly and lined up truly concentric with pipe. Gap between spigot and shoulder to of pipes to be even and between 5mm and 10mm.
checkpoint-status |  |  | checkpoint | 300.53 - Pipe haunching
label | 250613d3-20de-5853-a2eb-54a983a2405f |  | note | Detail of Activity: Haunching
label | 9eab8494-b99d-5d19-ae83-37e3ff786e35 |  | note | Action: M
label | 564b3876-424b-52be-a778-f7441b9b767a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench
label | a4eba41e-d097-5130-9510-8ddf4f2cb07d |  | note | Inspection / Test Method: NZS 3725:2007
label | 1e261869-af57-5f58-b335-371ffd97631d |  | note | Acceptance Criteria: In Accordance with HS2, Minimum haunching depth of 0.3D, CIV Value on compacted haunching >25 (CBR = 30).
label | 4f58d5a6-5c74-5760-9acf-c9884ae9fe40 |  | note | Record Documents: Contractor's site diary
label | 6ed477d5-e376-5a3d-9853-50cd9f281c22 |  | note | Responsibility: Contractor
label | f778a771-786c-5efc-8515-e65db40f91d3 |  | note | Comments: PAP 7 material to be used.
checkpoint-status |  |  | checkpoint | 300.54 - Trench backfill
label | 1f3bea28-9715-540f-a840-1b5df579caa9 |  | note | Detail of Activity: Backfilling
label | 2c3c7011-d8c5-5256-b262-fa3b61dbf9ac |  | note | Action: M
label | b4138d79-e646-536a-8640-0805efe02b9c |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 135d6687-9b27-5894-89c8-6e3c30cf80b1 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 44caec41-585f-5ed7-b3b3-67dcdef9b40c |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | 6e51abbc-c7fc-5961-b9ff-53c15b31e4b8 |  | note | Record Documents: Contractor's site diary
label | d7c55b88-dae5-5be2-8a25-d6a6e36a94c4 |  | note | Responsibility: Contractor
label | ef8fb887-9eca-5a08-a8c2-ec34190e49f4 |  | note | Comments: Clean Pumice Fill to be used
checkpoint-status |  |  | checkpoint | 300.55 - Visual Structural Inspection
label | fb23d105-45d6-5641-9231-42ee136fb67f |  | note | Detail of Activity: Visual inspection of concrete components
label | ae971849-fee4-5b07-9e23-7be2940bc16c |  | note | Action: W
label | f508f8b6-c7a9-5396-8978-a49f52e28f09 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | fa17e889-1c0c-52a7-81c9-f5659b70e092 |  | note | Inspection / Test Method: Visual Inspection
label | 434cfa88-d749-58a7-a280-04ad532ee394 |  | note | Acceptance Criteria: No visible damage, especially around collars and spiggots
label | dd48d700-a9e1-597a-a450-9e5d8642773c |  | note | Record Documents: Contractor's site diary/Photos
label | 2c536688-c43f-53ac-8005-f7ac4d569b65 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.56 - CCTV Inspection
label | cda20009-e9d1-57eb-ba01-5af349d40aaa |  | note | Detail of Activity: Visual record of Existing works
label | 99ad31fe-8f50-518d-9457-315aca1ac7fb |  | note | Action: W
label | 15a2a3a9-1753-5cae-a0ec-33418133721d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All drainage pipelines
label | 7b8feac7-9dae-5507-ae76-33f80171678c |  | note | Inspection / Test Method: CCTV Inspection
label | 10f0f7c9-5e12-5a96-b1fe-137a05504a8e |  | note | Acceptance Criteria: No significant cracks, level deformation, faulty joints
label | 06564585-6c59-51b9-ab14-6a51f964e7c1 |  | note | Record Documents: CCTV Footage
label | a1fdc620-c76a-5754-861b-c5af44e4bb23 |  | note | Responsibility: Contractor
label | 0ce25917-122b-5cf3-8660-932e680a8151 |  | note | Comments: CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practicle Completion
checkpoint-group |  |  | section | Construction and Finishing - Outlet 2-5 Precast headwall/wingwall : Statehighway 30 (Ø1050mm)
checkpoint-status |  |  | checkpoint | 300.57 - Determine Subgrade Strength
label | 43234a41-6338-5194-8901-cdf7c523b938 |  | note | Detail of Activity: Determine bearing strength of subgrade
label | 3692895c-4063-5600-84ac-0916cd01238d |  | note | Action: H
label | b844c143-3e58-5917-a7fb-520543345cb5 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 5638113d-21cc-5dcf-b92e-2328b094e1cf |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 1863b104-d398-5daf-88bf-d59e929d4eb5 |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | 76120239-ea2d-5b33-be0e-92b5c1c226bb |  | note | Record Documents: Contractor's site diary
label | d6142747-3670-5a7f-913f-a24c1eca0b00 |  | note | Responsibility: Contractor
label | c5a4f7aa-65b4-5535-baab-57fce8603363 |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.58 - Structures (manholes, head walls etc.)
label | 20ae46f3-8216-5923-add7-33bdc358bc4d |  | note | Detail of Activity: Visual inspection of concrete components
label | 6d047be5-755a-5264-b926-7e92a6dcc869 |  | note | Action: W
label | 716185a3-c342-5e7e-a5c7-c76a176540f7 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | 37ab3339-59df-5943-9ca3-da2b8cc4beff |  | note | Inspection / Test Method: Visual Inspection
label | 49e4baa9-18a6-5eb0-9ec1-a65fa89422ec |  | note | Acceptance Criteria: No visible damage, especially around collars and joints
label | 5fbfd90a-738a-5b57-a870-35324b4625fd |  | note | Record Documents: Contractor's site diary/Photos
label | 945b34b1-db0c-5186-aa13-a7f0aaa821c5 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.59 - Structures (manholes, head walls etc.)
label | 00231d93-eb5f-58d3-b73b-9078c23577f2 |  | note | Detail of Activity: Bedding
label | 8040a041-d85a-51b8-bb12-f18c2644972b |  | note | Action: M
label | 5e376528-ae4e-53b1-acd4-c807c646d97a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | f9c66b0a-5c63-59c0-98a0-0ae4cd41df82 |  | note | Inspection / Test Method: NZS 3725:2007
label | 2544b655-1132-5dfa-b1af-0da143b7b4d8 |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | a9a9f852-1baa-536c-9eea-0b61dc2d52a8 |  | note | Record Documents: Contractor's site diary
label | 140ed6c3-50ff-5953-ac05-7af3789a65ff |  | note | Responsibility: Contractor
label | 5fb3713a-58cf-56f1-acce-105764c38d57 |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.60 - Structures (manholes, head walls etc.)
label | 5fe83458-1721-5d3b-a2a5-fe2a2863561e |  | note | Detail of Activity: Backfilling
label | 784f37b2-e940-542b-801b-cc30bba97e39 |  | note | Action: M
label | 091a8ea1-ff01-5e84-ae53-59b52c13aba4 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 417ab375-d87c-5fc9-8ae8-b9e7c007e5fc |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | eb21f44c-df3c-56c4-a871-6545b1408ecf |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | e0ae6fae-d5f6-53a9-bcfd-f891a2df37a0 |  | note | Record Documents: Contractor's site diary
label | b8ef8fc2-c96a-55c6-b5d8-85490b763514 |  | note | Responsibility: Contractor
label | 547ed107-4c0b-545e-ba39-d0b67feeb587 |  | note | Comments: Clean Pumice Fill to be used
checkpoint-group |  |  | section | Construction and Finishing - Stormwater Line 3 : Inlet 3-1 to SD 3 -2 @ CH 410 Statehighway 30 (Ø750mm)
checkpoint-status |  |  | checkpoint | 300.61 - Determine Subgrade Strength
label | f02af9ab-85f1-5d89-ab81-789b74dcc926 |  | note | Detail of Activity: Determine bearing strength of subgrade
label | a95bd3eb-ee28-5952-9d81-fcc0464097bc |  | note | Action: H
label | 97af8504-f54a-5fbf-b8cc-9bd5258c5677 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | d85e7a95-f5d7-5815-ba87-48f0e79a6dd7 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | acaaaf51-bcc3-56e0-a3e4-10dcee156b09 |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | ae1e7e42-0dc3-50ca-84c5-bb4365d4b683 |  | note | Record Documents: Contractor's site diary
label | 4be51685-e92e-52d9-a0ee-0711b9705d61 |  | note | Responsibility: Contractor
label | 8883a3c4-70e3-525c-8c48-3aa66ea4a079 |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.62 - Pipe bedding
label | 1a044e55-324f-5886-927f-13b838eeafce |  | note | Detail of Activity: Bedding
label | 909aa130-50cf-5917-b77e-9d14c282da4d |  | note | Action: M
label | c88bb1e8-8923-5e2f-b73c-109482a1ea31 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench
label | b54d3900-a418-5156-a9d5-1fa0cfa81823 |  | note | Inspection / Test Method: NZS 3725:2007
label | ee010012-b141-5434-b386-5e5b03fb504b |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | a463e3e1-12ed-5629-a007-3f6a2fc1ea12 |  | note | Record Documents: Contractor's site diary
label | bb39d057-47eb-583a-b006-1727db549d1f |  | note | Responsibility: Contractor
label | 9a84e1a9-b515-55e6-b957-c7a56d819a5e |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.63 - Jointing of pipes
label | f87ba462-24ce-596c-be02-589653fad26f |  | note | Detail of Activity: Jointing
label | 68e87a6a-5b8e-525f-b342-a81f3c1267d5 |  | note | Action: M
label | 0c4cc371-d6bb-536c-ac3d-7bb8b2ae301f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Every Pipe Joint
label | 6a7229c8-528c-58b6-a166-b8f835fa9a76 |  | note | Inspection / Test Method: Visual Inspection
label | f290f9d2-4d4b-595b-a86b-09aca6dc4feb |  | note | Acceptance Criteria: In Accordance with section 5.2 of the Project Technical Spec.
label | b5739f1d-d0f8-5f07-90ce-594e00bd695a |  | note | Record Documents: Contractor's site diary
label | 34683dd5-b295-58d0-a152-3918d461a26f |  | note | Responsibility: Contractor
label | de711f17-9205-5417-b7e1-b61609e53f6f |  | note | Comments: Rubber rings to be mounted evenly and lined up truly concentric with pipe. Gap between spigot and shoulder to of pipes to be even and between 5mm and 10mm.
checkpoint-status |  |  | checkpoint | 300.64 - Pipe haunching
label | a4067e83-b6eb-5be3-a46a-05767bc020c6 |  | note | Detail of Activity: Haunching
label | e22c422a-c93e-5814-813a-e1b73787d1b1 |  | note | Action: M
label | 92c013ca-98ff-593e-b89a-0be5d571099e |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench
label | 11d2e6c7-9ff7-5e65-886e-77c9d5b4f5a1 |  | note | Inspection / Test Method: NZS 3725:2007
label | 75406d6d-4daf-5b0f-b7b3-0348c2fcb614 |  | note | Acceptance Criteria: In Accordance with HS2, Minimum haunching depth of 0.3D, CIV Value on compacted haunching >25 (CBR = 30).
label | 5b4c2077-1272-55c2-80a7-702e6f3bbde6 |  | note | Record Documents: Contractor's site diary
label | e29755fc-7067-5d52-8d6d-40bb094c985d |  | note | Responsibility: Contractor
label | da8af49a-2cf4-56b7-9b22-9d717fbfbb51 |  | note | Comments: PAP 7 material to be used.
checkpoint-status |  |  | checkpoint | 300.66 - Trench backfill
label | 658d96d9-6951-5b9d-94f1-98df864e8bd0 |  | note | Detail of Activity: Backfilling
label | 065fdebc-2ac8-5886-9ab8-8276fd914bee |  | note | Action: M
label | 62cf0f2e-8e89-58c1-b1a9-b1ea03d60bac |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | d8551f03-a86f-547e-a40e-0d2fd4a7c812 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 9192f0e4-229e-51e5-9c9b-485008c966dc |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | f4f1fa57-8edb-5560-a771-d2391e13d23a |  | note | Record Documents: Contractor's site diary
label | 8949a1f2-fc10-57f9-96fb-d4adfcb75e3e |  | note | Responsibility: Contractor
label | b2ec7d92-9c0d-55d5-85ba-704dc9c1b67c |  | note | Comments: Clean Pumice Fill to be used
checkpoint-status |  |  | checkpoint | 300.65 - Visual Structural Inspection
label | 9bb8111b-5421-5f9d-8260-230b600d65f4 |  | note | Detail of Activity: Visual inspection of concrete components
label | a2e2a2d2-7ee8-550f-94c9-5f7ca033a5d8 |  | note | Action: W
label | 658a3904-53ea-57b1-bc22-1efa73225913 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | 48525d7e-0d04-5cbd-8a9b-6c622a2abe13 |  | note | Inspection / Test Method: Visual Inspection
label | d888264e-d23c-5e65-bf92-5f0caf600690 |  | note | Acceptance Criteria: No visible damage, especially around collars and spiggots
label | 8e30f97a-1821-5f2a-a007-5003da60587a |  | note | Record Documents: Contractor's site diary/Photos
label | 8b35d61c-ae22-56a6-981d-6327ad4f11fc |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.67 - CCTV Inspection
label | 765e91b4-e146-5d87-8586-81e32e1b9c88 |  | note | Detail of Activity: Visual record of Existing works
label | 965a72e8-e2e8-5662-80ef-a9a1869b347d |  | note | Action: W
label | b2af7c33-17e4-51f6-81ae-f90d409697c9 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All drainage pipelines
label | 9ccf24eb-4fb8-55c9-9acd-b89b27bc0bce |  | note | Inspection / Test Method: CCTV Inspection
label | 99ce831a-b822-522a-9ac2-343a223f05b8 |  | note | Acceptance Criteria: No significant cracks, level deformation, faulty joints
label | 13670825-1c16-5f44-bb3c-32bb8a571b28 |  | note | Record Documents: CCTV Footage
label | 40e7fdf2-3c45-5aa8-8da0-657285a8e340 |  | note | Responsibility: Contractor
label | 39ab0faf-9a8f-5204-81ed-06f72d2aa196 |  | note | Comments: CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practicle Completion
checkpoint-group |  |  | section | Construction and Finishing - Inlet 3-1 : Precast headwall/wingwall - Statehiway 30 (Ø750mm)
checkpoint-status |  |  | checkpoint | 300.68 - Determine Subgrade Strength
label | 1f85c6e2-7340-5bc8-a759-6c2c51845bae |  | note | Detail of Activity: Determine bearing strength of subgrade
label | 152d781e-3014-54d2-8a04-f231deefa921 |  | note | Action: H
label | cd613f77-e999-5236-a7f3-dad63b0ac6f7 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 59b77435-a453-568b-b6bc-1ae432e6733f |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 0dcb7c39-8286-5c13-a7f5-f35367da74fc |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | aabd8924-19de-5803-9968-2ddd2d9ecd02 |  | note | Record Documents: Contractor's site diary
label | 9893f6a1-f9ab-505a-a958-d266b61ae1c4 |  | note | Responsibility: Contractor
label | 1401ab34-fd49-506f-b0b9-10fa2fe2ff19 |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.69 - Structures (manholes, head walls etc.)
label | 6d711332-1693-56a3-b592-71585501e049 |  | note | Detail of Activity: Visual inspection of concrete components
label | d72259c5-0676-55ad-8645-409f6a8130bb |  | note | Action: W
label | d9d61c5b-e766-51b7-b664-8131e1ac36bc |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | 27a9c469-7df5-5a58-840c-11ddeffae298 |  | note | Inspection / Test Method: Visual Inspection
label | 38eb582c-8a57-563c-9287-96614e491d5c |  | note | Acceptance Criteria: No visible damage, especially around collars and joints
label | e28ccef0-4b07-504d-acba-357157bb3d89 |  | note | Record Documents: Contractor's site diary/Photos
label | e0b755f0-cbe5-5267-bfa4-a837cc8ffa03 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.70 - Structures (manholes, head walls etc.)
label | 7ba90eab-e916-5549-99fc-4f00abb5d1fb |  | note | Detail of Activity: Bedding
label | 4acc660d-8e0b-55b0-bb7a-15b2dcd521f3 |  | note | Action: M
label | 7731b20d-0f1d-5388-b585-089ccb6a7f2c |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 30cbb894-60e5-5f58-a254-063e653f15ed |  | note | Inspection / Test Method: NZS 3725:2007
label | 0ea56efd-d166-5095-8a9e-449b4c3a99e9 |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | 80eef0dd-252a-50c2-a5ce-8965694b5078 |  | note | Record Documents: Contractor's site diary
label | e38ee671-fd77-5c5f-a9ec-d4e88c6f8a68 |  | note | Responsibility: Contractor
label | 6f903789-57b9-5509-b338-a7492c42d470 |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.71 - Structures (manholes, head walls etc.)
label | cc35ce38-eb23-56dc-823a-3e3d96f17638 |  | note | Detail of Activity: Backfilling
label | 8268c736-91e2-5491-9c2b-47dfe90f7dd2 |  | note | Action: M
label | d0d7e4a0-10e2-5a9c-a35a-14211233ded6 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 9326aa32-9032-5daa-96ee-598fdaf73882 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 7679c6eb-20e9-5412-b26b-2ad4ab4ab898 |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | 720d4d81-548e-53bd-8e50-c6a5f39b71e8 |  | note | Record Documents: Contractor's site diary
label | d8a417f3-ae1a-5a8f-822c-ac34761a306d |  | note | Responsibility: Contractor
label | 4cda4971-d535-5d51-a791-b2d8bbd1965f |  | note | Comments: Clean Pumice Fill to be used
checkpoint-group |  |  | section | Construction and Finishing - Outlet 3-2 Precast headwall/wingwall : Statehighway 30 (Ø750mm)
checkpoint-status |  |  | checkpoint | 300.72 - Determine Subgrade Strength
label | a214aeb4-0dd4-5d98-9d42-d64aa3c2f788 |  | note | Detail of Activity: Determine bearing strength of subgrade
label | 40679453-0217-5f2f-86bd-4139b851bd59 |  | note | Action: H
label | 4c1c19b6-8c05-5b39-bff7-086f4534f6ab |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 9307d4bf-29e2-580c-a142-0927ca20f5f0 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | f0df99ef-285b-5a91-b81a-d04db7317e9a |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | b5339ac1-6cdb-5046-9a79-63d7fa7cf505 |  | note | Record Documents: Contractor's site diary
label | a0b6923b-0f11-5801-9e16-97ed3bf93f7d |  | note | Responsibility: Contractor
label | adf4af1a-4d9d-5a66-bedc-61db13c0c137 |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.73 - Structures (manholes, head walls etc.)
label | 5e726772-05b2-56fc-83ed-4e63bb781283 |  | note | Detail of Activity: Visual inspection of concrete components
label | e54f927a-8f94-5486-b702-76f9e212da98 |  | note | Action: W
label | ea3876e2-c5ac-539a-b000-4758fbd2b462 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | 559d0472-e09b-5aae-9d2c-e960f3ae8151 |  | note | Inspection / Test Method: Visual Inspection
label | daa2bc24-912d-57e3-bcc1-e7bb4066c485 |  | note | Acceptance Criteria: No visible damage, especially around collars and joints
label | 57f175f2-783d-5d26-b8da-ba9bb2605aaf |  | note | Record Documents: Contractor's site diary/Photos
label | 51e3554c-fbbb-5c07-8774-9134ff068bf0 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.74 - Structures (manholes, head walls etc.)
label | 71a5fe0f-d1b6-53b5-a0d4-da8b2e58ef35 |  | note | Detail of Activity: Bedding
label | 3c38fdb6-f60e-52f2-83fe-9e859cb0e46a |  | note | Action: M
label | 96cc9214-e4ca-531f-998a-afe75fa8806d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | cc947161-a278-5f1d-a6bc-fb80f0dc93c7 |  | note | Inspection / Test Method: NZS 3725:2007
label | 07bc460f-3018-5a9f-912b-50be6d0e91bb |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | 20c596e3-9846-55e3-b756-382f4b2dff8d |  | note | Record Documents: Contractor's site diary
label | c3149165-7397-5704-888e-a4995638573f |  | note | Responsibility: Contractor
label | b15b1bcf-7add-5ff2-9446-d6f7c488e481 |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.75 - Structures (manholes, head walls etc.)
label | b53c71b1-5a6b-5b44-aaa7-0b6f35a04073 |  | note | Detail of Activity: Backfilling
label | b6b9eefe-d3c4-5377-8535-e9ea6d41989c |  | note | Action: M
label | aa768205-2d3b-5699-99eb-322664f232b8 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | a941b0a9-2215-5ea0-98b2-062e21942bcb |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 8f20df1c-190d-5b0a-8ae8-c39f6932ab3d |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | fd4322ad-dc07-5d72-bddf-2a7e0853e292 |  | note | Record Documents: Contractor's site diary
label | f322c3a8-870f-5516-83e1-4c43541cb75e |  | note | Responsibility: Contractor
label | 096a207c-4422-5735-aae9-e05f427dd44b |  | note | Comments: Clean Pumice Fill to be used
checkpoint-group |  |  | section | Construction and Finishing - Stormwater Line 4 : SD 4-1 to Outlet 4-2 - Culvert to Wetland Access Track (Ø750mm)
checkpoint-status |  |  | checkpoint | 300.76 - Determine Subgrade Strength
label | fd8d4dba-1e32-5f53-9208-33842c683685 |  | note | Detail of Activity: Determine bearing strength of subgrade
label | e85deb80-bb78-57c8-a63e-d173f30a9d33 |  | note | Action: H
label | 11a04578-7cfb-597f-b04d-668f7768049e |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 9b1926e8-6898-5031-a954-f682bc4b59ce |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 9920e738-d567-55eb-b71c-c7a640b2add4 |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | f0f311cf-03fe-57bd-a01a-cbd75763bc47 |  | note | Record Documents: Contractor's site diary
label | 6602bcc9-128a-54d6-a92b-d36eea280989 |  | note | Responsibility: Contractor
label | dda758d2-d212-53c9-9602-5aeb9dce06cb |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.77 - Pipe bedding
label | 87b59f6c-5e96-5201-b986-55dd93fee072 |  | note | Detail of Activity: Bedding
label | 2c9b966b-3e6f-51b0-bb30-86608013f3b5 |  | note | Action: M
label | 40e30c48-da02-5e48-a7db-6f16e5fc0390 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench
label | fd4840bc-802e-5357-a79c-387c462228d5 |  | note | Inspection / Test Method: NZS 3725:2007
label | 84e76fce-f450-5b4a-b790-303b1a44e299 |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | 1a0cb2e6-78b5-5c28-aee9-a67719f6235e |  | note | Record Documents: Contractor's site diary
label | 59297346-520f-5cfa-ae70-86423710490c |  | note | Responsibility: Contractor
label | cae505af-c822-5519-8f04-4b7874f73af8 |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.78 - Jointing of pipes
label | 9aac73cd-dc2c-5ac6-a19b-9754a8d6a8f1 |  | note | Detail of Activity: Jointing
label | 5daf5600-3aaa-52e9-8fa5-8ffb73c3ce24 |  | note | Action: M
label | f2f98ca5-fe59-5ea9-8d41-9aaaceca5b28 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Every Pipe Joint
label | 09ec3ce8-b5f6-53cc-abfe-5142ca12ca87 |  | note | Inspection / Test Method: Visual Inspection
label | 14412853-1469-5501-b0af-f59741a9bacc |  | note | Acceptance Criteria: In Accordance with section 5.2 of the Project Technical Spec.
label | 25b864d4-6e82-5bea-9e87-e9372ae55fd5 |  | note | Record Documents: Contractor's site diary
label | f8126818-d59f-5d54-a123-538e4c72a312 |  | note | Responsibility: Contractor
label | 0b493c92-fb9f-53d1-87c4-081c0d730a36 |  | note | Comments: Rubber rings to be mounted evenly and lined up truly concentric with pipe. Gap between spigot and shoulder to of pipes to be even and between 5mm and 10mm.
checkpoint-status |  |  | checkpoint | 300.79 - Pipe haunching
label | a5fc1110-24b7-580a-9158-4491f5b1ea9e |  | note | Detail of Activity: Haunching
label | fb0bad16-7e8e-5ba5-ab16-1235190172e7 |  | note | Action: M
label | dbebc92e-6f3c-5ccf-bc47-03d4ec885000 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench
label | f84cb065-96a3-5e5b-a4a7-5e0b526edc18 |  | note | Inspection / Test Method: NZS 3725:2007
label | e7d383f6-c5b8-5fe2-b17a-5ea902e18c7c |  | note | Acceptance Criteria: In Accordance with HS2, Minimum haunching depth of 0.3D, CIV Value on compacted haunching >25 (CBR = 30).
label | de0a5307-59d6-5183-a7b1-93d90c0a16f7 |  | note | Record Documents: Contractor's site diary
label | 129f0184-2437-5fa0-983f-a78f2581af51 |  | note | Responsibility: Contractor
label | 9e640109-6ab2-5027-a4a8-afe3601b9a15 |  | note | Comments: PAP 7 material to be used.
checkpoint-status |  |  | checkpoint | 300.80 - Trench backfill
label | 5198db1d-d9b2-5725-ab62-6a9b8774bd94 |  | note | Detail of Activity: Backfilling
label | d9547e86-48e9-5d15-a920-728313928c30 |  | note | Action: M
label | ba3176c1-0dcb-506d-bc0c-04f5a9fc77f1 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | e33fafb7-b26f-5d18-b4c9-461262e8c6c0 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | fb85812b-913f-5e78-b4fe-2370d4d79058 |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | bcba9816-eab7-515e-abc4-624f5036113e |  | note | Record Documents: Contractor's site diary
label | 51a0887d-6578-580a-b676-c248c6554b52 |  | note | Responsibility: Contractor
label | ed396a12-fd5a-5880-8166-a4ecf14aecb3 |  | note | Comments: Clean Pumice Fill to be used
checkpoint-status |  |  | checkpoint | 300.81 - Visual Structural Inspection
label | d9f9bd16-4f5a-5511-8c2f-7ffa91785390 |  | note | Detail of Activity: Visual inspection of concrete components
label | ba2a3b91-f6d3-5eb4-8c42-06ce2bd37e63 |  | note | Action: W
label | d9faddea-00ce-5945-9909-4287c1f3a76c |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | d0cdc50f-dcb4-53c3-9e41-b570ad3bd370 |  | note | Inspection / Test Method: Visual Inspection
label | 73ba994c-d2bf-5a62-9b3f-6b17d5a353f1 |  | note | Acceptance Criteria: No visible damage, especially around collars and spiggots
label | ff0481b6-1a52-5506-800e-8b496edef0a4 |  | note | Record Documents: Contractor's site diary/Photos
label | 82e930ae-06b2-5cea-a696-67cf41cfa1a8 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.82 - CCTV Inspection
label | 5d452432-fc36-5c16-afa1-26f1ca414171 |  | note | Detail of Activity: Visual record of Existing works
label | fd616468-c9c2-5e85-8888-ac432767a722 |  | note | Action: W
label | 5c5480ac-311a-5363-b94d-eda0e220fa8a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All drainage pipelines
label | 2a52603f-1b49-5594-9288-1743433c65d4 |  | note | Inspection / Test Method: CCTV Inspection
label | 34f0f60a-3fa5-5bb8-adbc-0475bdd5134b |  | note | Acceptance Criteria: No significant cracks, level deformation, faulty joints
label | 376097ae-e23c-5cb4-9171-086e08d1cea7 |  | note | Record Documents: CCTV Footage
label | 9817fe81-c13c-5b63-9f82-ad37f7181f11 |  | note | Responsibility: Contractor
label | c4d426a7-0ad8-5094-9a75-2960084bbb48 |  | note | Comments: CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practicle Completion
checkpoint-group |  |  | section | Construction and Finishing - SD 4-1 Manhole/Standpipe with Scruffy Dome ( Ø1400mm)
checkpoint-status |  |  | checkpoint | 300.83 - Determine Subgrade Strength
label | d0be59d1-d50c-52bd-8770-9ee680cdb11f |  | note | Detail of Activity: Determine bearing strength of subgrade
label | 4f3b2d38-460a-5989-aa2b-2d5cc9b5e98c |  | note | Action: H
label | 0c9ca33b-b57e-5f83-ac40-10698ff08485 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 2dac36b2-67ca-5c93-9026-66551037c747 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 3a7b72cb-9605-566f-ad8e-21cfdcc9d9f7 |  | note | Acceptance Criteria: No target - Engineer to advise undercut requirements prior to installation
label | 14f42eae-0fee-5c88-84f8-fc4e493d053a |  | note | Record Documents: Contractor's site diary
label | 621d191f-1856-58a2-a867-c3c6282df189 |  | note | Responsibility: Contractor
label | 53e13aa1-d5c7-569b-b92b-70ea7275a775 |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.84 - Structures (manholes, head walls etc.)
label | 2b6ff45f-b2de-5aec-b6a9-05765acfd495 |  | note | Detail of Activity: Visual inspection of concrete components
label | 96cd2f12-8942-5b39-8a79-5e9ef002b448 |  | note | Action: W
label | 67bbc882-b3e3-5dd3-855e-6189b8296ba2 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | 990c5f08-0e80-5065-933e-cb7b6f4fa98e |  | note | Inspection / Test Method: Visual Inspection
label | f3ab0c69-7e05-5b62-9030-2adc98dddff5 |  | note | Acceptance Criteria: No visible damage, especially around collars and joints
label | c4d3bc20-38f8-5a06-9b2a-323b8583f995 |  | note | Record Documents: Contractor's site diary/Photos
label | d9ad2742-5119-5b5a-9034-afe6eba96e5a |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.85 - Structures (manholes, head walls etc.)
label | c25c84d3-bcbd-5d98-be6b-ac20416dee49 |  | note | Detail of Activity: Bedding
label | 305e9e2e-0fb0-5eea-a20e-8495abfc0700 |  | note | Action: M
label | da9bae69-f014-5245-b191-ae2db49848bd |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 5d42c303-01b1-56c0-9674-3f2d5a2faf70 |  | note | Inspection / Test Method: NZS 3725:2007
label | f6d08267-891e-5337-9e18-20417a06c6ca |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >15 (CBR = 20).
label | bcfd7257-e768-50f3-9abd-7eba901ca226 |  | note | Record Documents: Contractor's site diary
label | 6fc3379a-e6f6-57aa-8b3f-6215970cf0e9 |  | note | Responsibility: Contractor
label | 8632e267-d51a-560b-ba66-7702b05fa340 |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.86 - Structures (manholes, head walls etc.)
label | d9a01a59-557d-52c4-8f80-8c5599f643cb |  | note | Detail of Activity: Backfilling
label | 97bfbc42-95a1-54af-8de8-7848de5639b6 |  | note | Action: M
label | 5ebd1a9f-0869-5e4f-ae84-ba0646cbc877 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | e76d6316-ede0-5f48-bddb-f12e646679ec |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 357a712b-3e8e-5074-814b-cc10a655715b |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | 54bae1fe-e96e-53ad-934f-598b9a5f2dd8 |  | note | Record Documents: Contractor's site diary
label | 475af32b-24c8-5ac3-9952-5c4eb5118582 |  | note | Responsibility: Contractor
label | 3678ec58-f475-5cf7-88c0-5b9b936c06a7 |  | note | Comments: Clean Pumice Fill to be used
checkpoint-group |  |  | section | Construction and Finishing - Outlet 4-2 Precast headwall/wingwall : Access Track (Ø750mm)
checkpoint-status |  |  | checkpoint | 300.87 - Determine Subgrade Strength
label | d1d60d37-a207-56a2-aaa5-31e90d67a1e5 |  | note | Detail of Activity: Determine bearing strength of subgrade
label | 7880b4d1-5d2c-577c-b71b-5699322d1351 |  | note | Action: H
label | ba9a74dc-7264-500d-a53f-e592e7083b9b |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 33d897d8-b6a4-5f2f-b175-86cee2772aad |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 25edaaa3-5422-5651-92fa-215c56e7d412 |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | 41944388-e06b-5fac-b6d2-99d1f73f677e |  | note | Record Documents: Contractor's site diary
label | b2a2050f-1eba-52f8-bb2f-cf7c00ac9491 |  | note | Responsibility: Contractor
label | 1a4e1068-ba06-58fd-8334-853a011cf9eb |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.88 - Structures (manholes, head walls etc.)
label | d4d43209-2b83-5024-9b47-4bb5c9fbf1ed |  | note | Detail of Activity: Visual inspection of concrete components
label | 985b63c3-2fa0-5464-bd73-2359b4814f48 |  | note | Action: W
label | 4c273dfc-431c-58bd-8794-27cbda925ccb |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | afe25c97-e990-5b02-ba81-089c3fd7a8fc |  | note | Inspection / Test Method: Visual Inspection
label | 15d6d147-0af2-59ef-a9a4-1020b561f3d3 |  | note | Acceptance Criteria: No visible damage, especially around collars and joints
label | 8700712c-24ac-5690-ac00-5c36741a2490 |  | note | Record Documents: Contractor's site diary/Photos
label | 00bbd3d3-2067-564a-93cf-8ea5ed6b76b5 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.89 - Structures (manholes, head walls etc.)
label | 1697bb38-41dc-5afe-81c1-fa445bdc684b |  | note | Detail of Activity: Bedding
label | c9122924-748f-597b-ad0b-399207631120 |  | note | Action: M
label | 15d93576-c503-50c5-adfd-83c816cf134b |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 7040b1ec-f6ba-5851-8ce3-1c1f19817ac2 |  | note | Inspection / Test Method: NZS 3725:2007
label | 693d3121-8335-50a4-b49b-900df300cf27 |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | fb302ef6-52f4-5738-9a63-e460f379d5db |  | note | Record Documents: Contractor's site diary
label | 35bd8321-86fe-5383-b517-2afd8cb7c6ac |  | note | Responsibility: Contractor
label | c8a3be88-2669-57b1-834c-653fabd1c323 |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.90 - Structures (manholes, head walls etc.)
label | da496a5e-5ae9-5990-bcc3-5664ee24466e |  | note | Detail of Activity: Backfilling
label | 1ea9bf27-620f-5a18-bee8-97713628258f |  | note | Action: M
label | 25881757-c894-5651-8610-da8da782c3e8 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | ac4f2f5c-51c7-52f8-b7b5-5d2249a24122 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 76176c7c-cb41-580e-bc41-77151d64f7d4 |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | ecb08540-a758-5ec8-a6ae-a124fe7dd897 |  | note | Record Documents: Contractor's site diary
label | 6857445a-69ca-5af8-aae5-464936f655a4 |  | note | Responsibility: Contractor
label | ca64987c-68f7-547c-b086-964fe1f91fe5 |  | note | Comments: Clean Pumice Fill to be used
checkpoint-group |  |  | section | Construction and Finishing - Stormwater Line 5 : SD 5-1 to Outlet 5-2 Culvet to SW Treatment Wetland (Ø600mm)
checkpoint-status |  |  | checkpoint | 300.91 - Determine Subgrade Strength
label | 7949bbb0-77aa-504b-af57-df60752d3efd |  | note | Detail of Activity: Determine bearing strength of subgrade
label | 84cc3564-a7cf-5b72-92fd-6d7185f078f9 |  | note | Action: H
label | a4c75da1-9514-5f77-92f8-2b07ce6bcd16 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 0d6414b8-b089-54db-b8ca-a0758c94cafd |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 4f2072b8-14b6-53d9-bf77-57296ef732bb |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | 8f1743bf-6b49-5d5e-b05a-b95dd199ccea |  | note | Record Documents: Contractor's site diary
label | 5890c0d2-efe7-507b-b662-a83d316dc968 |  | note | Responsibility: Contractor
label | 7e862fea-7657-5f67-a706-6f9972d28535 |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.92 - Pipe bedding
label | b047582f-959f-5bc0-ab27-140852ca75ef |  | note | Detail of Activity: Bedding
label | 8a5cd3d0-7429-558e-967f-e566f7e3ccc2 |  | note | Action: M
label | 2479752a-71ca-5d6d-b470-0904e4062d1f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench
label | 37ea76d0-d6cf-59a3-ad3c-153179c553cf |  | note | Inspection / Test Method: NZS 3725:2007
label | f35d7d10-1377-50e6-9825-27de32f2da8f |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | 6fdf3d57-0f70-5230-a3d0-5d20bac81d00 |  | note | Record Documents: Contractor's site diary
label | a81be3f5-7f44-5d46-82a2-717e76933865 |  | note | Responsibility: Contractor
label | 1ec26400-fbbb-5692-ae5e-f223d9740e6a |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.94 - Pipe haunching
label | cc0a06ad-26d4-5803-a896-c4a09e80a8e1 |  | note | Detail of Activity: Haunching
label | 1613dc9e-cfaf-5a57-8888-3bc1e26555ca |  | note | Action: M
label | dbbcb53b-f046-56bb-b81a-175002ce20d9 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench
label | 6654404a-90cc-5553-8317-71f2df79a5e7 |  | note | Inspection / Test Method: NZS 3725:2007
label | 4fe423c4-e8f7-5050-bfa6-9e26e33b5d2d |  | note | Acceptance Criteria: In Accordance with HS2, Minimum haunching depth of 0.3D, CIV Value on compacted haunching >25 (CBR = 30).
label | 207925bc-f734-5906-8797-fe980e1419ec |  | note | Record Documents: Contractor's site diary
label | 7368cee6-cda5-5c6b-869d-d7b7dea62424 |  | note | Responsibility: Contractor
label | 2b7dbd88-0aa3-5d8a-bcd4-c281b8541690 |  | note | Comments: PAP 7 material to be used.
checkpoint-status |  |  | checkpoint | 300.95 - Trench backfill
label | 79447b3e-9450-5a6b-9341-009cd4944be2 |  | note | Detail of Activity: Backfilling
label | 973affbd-dbf8-5eda-8c76-85c0c16982e3 |  | note | Action: M
label | 9f78ce67-1c6d-5cd2-a489-79d8f1b97a70 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 4d9cbfa1-a17c-5811-aa74-67569e3a512b |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | c486d077-4226-52ad-9805-ef43cc083e84 |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | 84e60b68-a037-5116-a18d-21440ca2f685 |  | note | Record Documents: Contractor's site diary
label | d7b8e1c0-9016-52af-82bd-ebd9205a95be |  | note | Responsibility: Contractor
label | 5bb36a27-7512-59e5-b15a-85324f762466 |  | note | Comments: Clean Pumice Fill to be used
checkpoint-status |  |  | checkpoint | 300.96 - Visual Structural Inspection
label | 85f04d32-7819-5ca0-b6cf-ddc703c42081 |  | note | Detail of Activity: Visual inspection of concrete components
label | 3fd0ee3b-8f18-5195-818a-81a316c3bfdd |  | note | Action: W
label | d4b4a62d-1450-555e-a0b7-c282e5863f9b |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | e7109cd3-dd82-55b4-8f45-e9d951c614c6 |  | note | Inspection / Test Method: Visual Inspection
label | 01a1f747-ed01-598e-a6eb-8b5b4f501d75 |  | note | Acceptance Criteria: No visible damage, especially around collars and spiggots
label | b19ddbfb-9cc3-5fb4-9eb6-280c54c7142a |  | note | Record Documents: Contractor's site diary/Photos
label | 1c162a57-7772-5000-8637-90341b9ab3db |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.97 - CCTV Inspection
label | ba26f38d-6b78-59fa-924b-4962e19b3a09 |  | note | Detail of Activity: Visual record of Existing works
label | 57dc2340-e1ad-5b4a-8de4-b0c0ceaec034 |  | note | Action: W
label | 78e5d61c-e041-52f0-a7fc-56ef8d5352f1 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All drainage pipelines
label | 6f959158-0c2d-5f2a-8ec4-b59202736e4c |  | note | Inspection / Test Method: CCTV Inspection
label | 4ed5c643-58b6-5138-8e01-7d9181c66853 |  | note | Acceptance Criteria: No significant cracks, level deformation, faulty joints
label | eae5deb4-9a1a-51df-a4ec-58ffe0630827 |  | note | Record Documents: CCTV Footage
label | 612c7840-46f7-58b9-add7-f1080b961b69 |  | note | Responsibility: Contractor
label | 083af908-7c08-5b46-aebb-e5b4fb4961d5 |  | note | Comments: CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practicle Completion
checkpoint-group |  |  | section | Construction and Finishing - SD 5-1 Manhole/Standpipe with Scruffy Dome ( Ø1400mm)
checkpoint-status |  |  | checkpoint | 300.98 - Determine Subgrade Strength
label | 1d0dbe60-cda7-5aba-a1a9-68599a16bf01 |  | note | Detail of Activity: Determine bearing strength of subgrade
label | 18a8f896-5743-55a6-9b85-b1b70387263a |  | note | Action: H
label | 595f512b-2945-5a7f-9b30-b048ffacfa48 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 86e9dbf6-7e7a-5010-8e9b-8f4df1da1db0 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 1449f41a-1cf5-5498-9386-3c7df1e5600a |  | note | Acceptance Criteria: No target - Engineer to advise undercut requirements prior to installation
label | 82a3ae94-7c04-5980-b4e9-d8b33c88e434 |  | note | Record Documents: Contractor's site diary
label | 74ed40c0-f85f-5c67-81d9-dfb790b0d617 |  | note | Responsibility: Contractor
label | fa1e8094-78a8-5ab5-8415-c58cf7398bab |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.99 - Structures (manholes, head walls etc.)
label | a6ee0cad-2fa6-53d3-b232-4b2981b7443c |  | note | Detail of Activity: Visual inspection of concrete components
label | 80dc56f3-ffc8-56da-92eb-d269e723f304 |  | note | Action: W
label | 28efd7f8-9d15-5cbf-8014-1da3fa593872 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | b11c2156-1ffb-5d23-9eea-47c17e1f2bd8 |  | note | Inspection / Test Method: Visual Inspection
label | bf1c6a90-04ba-5c43-a742-d023c93a1dcf |  | note | Acceptance Criteria: No visible damage, especially around collars and joints
label | 1b4415f3-2fe0-5611-b470-047246be7897 |  | note | Record Documents: Contractor's site diary/Photos
label | 122cdda4-5cd3-5b20-982f-24ca720753a3 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.100 - Structures (manholes, head walls etc.)
label | 9fd503a9-8878-5bad-b9e6-c0743bdc936b |  | note | Detail of Activity: Bedding
label | fd046982-4c9a-58ee-baa3-9fbfff0614a4 |  | note | Action: M
label | 3280647e-dc89-562d-b560-3c8dfb333a03 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | f0ed9b06-513d-5334-b242-2968dab69687 |  | note | Inspection / Test Method: NZS 3725:2007
label | a0e0b54a-e352-5f17-98fe-58ca49ca2509 |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >15 (CBR = 20).
label | 94237cfc-a31f-57d6-b0c6-421d42c148ff |  | note | Record Documents: Contractor's site diary
label | 35b2c7fb-1e1b-51f6-a5a1-393d44367da2 |  | note | Responsibility: Contractor
label | 10dae104-b643-533b-a631-9f0bd113339a |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.101 - Structures (manholes, head walls etc.)
label | b0914cc6-2e92-5b21-9142-7c8dae1d1912 |  | note | Detail of Activity: Backfilling
label | 80586d6a-55fb-5c71-9d3f-9de105f747c7 |  | note | Action: M
label | f6c609d1-1f8c-528f-8d9c-2ec361a1c712 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | d25f726b-2d1e-5e18-8f2c-f163524921bd |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 12d447bf-019a-5cd6-ae25-c9456511bf5d |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | 2b726b0e-ce4b-54b7-8a49-7901cd96b6ae |  | note | Record Documents: Contractor's site diary
label | fc467b56-117a-5275-a9d0-b77b0b939e7d |  | note | Responsibility: Contractor
label | 89282a9b-1fcf-5639-888b-b52fdd68044a |  | note | Comments: Clean Pumice Fill to be used
checkpoint-group |  |  | section | Construction and Finishing - Outlet 5-2 Precast headwall/wingwall : Swale line 1 (Ø600mm)
checkpoint-status |  |  | checkpoint | 300.102 - Determine Subgrade Strength
label | abca7ced-9bc0-56ee-ac3b-c5f1e43fcb53 |  | note | Detail of Activity: Determine bearing strength of subgrade
label | ed105f51-41a7-513d-a2f3-846abaa0cfdb |  | note | Action: H
label | 54a73bd4-e077-5115-b209-2bd082aa803e |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | e3117cd8-f47e-52b4-9c01-de61bd2f64a8 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | bc91ab93-a992-517b-be7d-15b743666ada |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | 5bab5140-36a6-5d26-8f11-9a36ed6e932d |  | note | Record Documents: Contractor's site diary
label | df4cfbe8-9828-5068-8676-fd7dab3b0b45 |  | note | Responsibility: Contractor
label | 3003be56-a5a4-597e-9c5c-866c9c493efc |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.103 - Structures (manholes, head walls etc.)
label | 57abef47-30a3-5134-adf5-41faa7a93470 |  | note | Detail of Activity: Visual inspection of concrete components
label | 1ac260d0-7c95-5f65-b7ab-e176d866c08c |  | note | Action: W
label | 14f24e12-e4ea-5fc1-96fa-a09870a1170d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | b19614fb-9bc0-54fe-83d0-56a6b607b4ab |  | note | Inspection / Test Method: Visual Inspection
label | d8df286f-5e8b-513e-8a70-58a60791069f |  | note | Acceptance Criteria: No visible damage, especially around collars and joints
label | 09dd7723-fbc7-554c-a46e-3ea2557f0ad7 |  | note | Record Documents: Contractor's site diary/Photos
label | 50d4fda1-3497-5af6-a88c-8442dd5bda85 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.104 - Structures (manholes, head walls etc.)
label | b9e0f72d-f5d8-54d5-8152-71b38fd56b29 |  | note | Detail of Activity: Bedding
label | dbd1cbf1-c1a9-5ec8-bd8c-356ed6a5e63b |  | note | Action: M
label | fa3a1bd0-20be-5c46-94fe-8727c59e54d1 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 3e029a7a-7664-5365-8e83-b9e1dfd381e7 |  | note | Inspection / Test Method: NZS 3725:2007
label | 0136a966-4ac5-582e-925c-97bc6ddedf4e |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | 27eee0ea-e74a-50f0-bbca-aaf0a313669d |  | note | Record Documents: Contractor's site diary
label | 6dd406e9-470f-50a5-8b71-e9f716a1c7cc |  | note | Responsibility: Contractor
label | 778871b8-5e85-55c7-9960-c09409f37608 |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.105 - Structures (manholes, head walls etc.)
label | 287d957a-feb4-52ef-bbb6-ebed71344377 |  | note | Detail of Activity: Backfilling
label | 8ed0384e-0220-5baf-880d-f923b711db6c |  | note | Action: M
label | e5893628-e67c-5a9d-8d7a-5598c8ea3ae9 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 61e30b47-46ab-5466-8682-6f7d41d8318f |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 2bd4dc1d-02f1-5d87-9d7b-7d6d87fa2daa |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | 573c8344-abee-5df9-bf79-017077f19fac |  | note | Record Documents: Contractor's site diary
label | beca671f-97cb-5439-a0c9-ffd2e0a93854 |  | note | Responsibility: Contractor
label | 876e198b-172d-5bbc-92af-8565235cb1a3 |  | note | Comments: Clean Pumice Fill to be used
checkpoint-group |  |  | section | Construction and Finishing - Peers Adams /Kiwirail Access Culvert : (Ø450mm)
checkpoint-status |  |  | checkpoint | 300.106 - Determine Subgrade Strength
label | 53166b21-a56a-59bc-ab12-7cb85a5ec11b |  | note | Detail of Activity: Determine bearing strength of subgrade
label | 2deb820c-509b-5210-8804-af9ee3702a39 |  | note | Action: H
label | f12e53a5-4a0e-53c2-aebe-67d17752b1a8 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | d11cadc9-a4d1-5e5e-ab9f-e7914f6ec94a |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | e6cb6b40-6a59-545e-8434-d670a44991f7 |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | 4a74fa7c-63bf-5ae8-96a8-f5b8ec9c42d2 |  | note | Record Documents: Contractor's site diary
label | 99a66da6-e081-5b66-930e-0761024a8298 |  | note | Responsibility: Contractor
label | e8b16ef1-aa5b-50fe-b8e8-614f191d468d |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.107 - Pipe bedding
label | e7606fcc-d33f-560e-921a-da5ca1c8b3fb |  | note | Detail of Activity: Bedding
label | 44ec0c23-da01-5379-9126-3a943d239409 |  | note | Action: M
label | 474c8547-a2e3-52c3-ad5d-31a2d1611247 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench
label | 084a7d77-40e6-5225-a992-d197086c738c |  | note | Inspection / Test Method: NZS 3725:2007
label | 85a14501-3203-5482-8a79-cfbb320df548 |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | e3133146-8bbc-5892-b128-8e787aba98c4 |  | note | Record Documents: Contractor's site diary
label | eec45036-7e82-55a2-a0e5-7a73636d9577 |  | note | Responsibility: Contractor
label | 36132039-40a1-5698-a6c0-259c46fe1327 |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.108 - Jointing of pipes
label | 3e50e489-57eb-5493-8065-14958c9fa8ed |  | note | Detail of Activity: Jointing
label | 26b3fa57-88bc-50e7-82b6-20cac00396fc |  | note | Action: M
label | eb550275-84b4-5c8e-8566-64dd3255ffe7 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Every Pipe Joint
label | 806454dc-a07b-5690-87bb-60a2cab3d88f |  | note | Inspection / Test Method: Visual Inspection
label | 0a273b0b-a0b2-570d-b834-5784fe8b097d |  | note | Acceptance Criteria: In Accordance with section 5.2 of the Project Technical Spec.
label | d6b1108e-e2d2-55a7-b78c-bdc2b94a73e6 |  | note | Record Documents: Contractor's site diary
label | 8f441060-07a4-5edc-b323-ed852108c856 |  | note | Responsibility: Contractor
label | 80df739a-78f5-57fe-87db-bf6dbe825ef8 |  | note | Comments: Rubber rings to be mounted evenly and lined up truly concentric with pipe. Gap between spigot and shoulder to of pipes to be even and between 5mm and 10mm.
checkpoint-status |  |  | checkpoint | 300.109 - Pipe haunching
label | da36e203-2311-5f5f-89f4-02a3f7b4b04c |  | note | Detail of Activity: Haunching
label | 8c69a82c-c9f8-58a5-bb74-696bc9febb8c |  | note | Action: M
label | e9b9d5e5-9767-5639-bccf-0b08031075b6 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench
label | 3759b4cf-0cfb-5ba4-9cc9-bb7d381b5a4a |  | note | Inspection / Test Method: NZS 3725:2007
label | ba16d2d5-ebef-5018-bd81-7ed4bb5e624d |  | note | Acceptance Criteria: In Accordance with HS2, Minimum haunching depth of 0.3D, CIV Value on compacted haunching >25 (CBR = 30).
label | c410ac7f-4d51-5a16-bb08-1d4ae71f7085 |  | note | Record Documents: Contractor's site diary
label | 0645d284-c88f-55b5-986a-099c107ebd4c |  | note | Responsibility: Contractor
label | f4933ada-f4fe-5440-94f0-e1524b0a1510 |  | note | Comments: PAP 7 material to be used.
checkpoint-status |  |  | checkpoint | 300.110 - Trench backfill
label | a3bdfec9-a0da-5bf0-bc5c-321cfa73d839 |  | note | Detail of Activity: Backfilling
label | 00533489-b301-572c-bc75-fad5f8f666bb |  | note | Action: M
label | 839d5e5f-8a9d-5ced-9a56-9a2b44fef400 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 8419c135-8b4d-5fca-848a-a575a1f193cb |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | e8c7e71f-90e2-5142-94ce-dbd1801ff9ac |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | 1add110c-8fd9-5409-ab0f-b6e85fb1aeb4 |  | note | Record Documents: Contractor's site diary
label | 3f764777-bee7-59e3-9708-a46c577a250b |  | note | Responsibility: Contractor
label | d1799d2c-3579-540d-a3fa-0a89c9115dc7 |  | note | Comments: Clean Pumice Fill to be used
checkpoint-status |  |  | checkpoint | 300.111 - Visual Structural Inspection
label | 537574fe-590a-5d8d-bb3b-8ee3baa1337a |  | note | Detail of Activity: Visual inspection of concrete components
label | 52b07492-b7da-5ce2-92dd-944556cb03b4 |  | note | Action: W
label | 6198d896-2d46-5f84-b51d-10f4203e556e |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | 3c0202d8-5b98-5732-b131-3b63caba022a |  | note | Inspection / Test Method: Visual Inspection
label | 0a7de16a-4a1a-5fc5-92e2-d282e98ca74f |  | note | Acceptance Criteria: No visible damage, especially around collars and spiggots
label | 52d128b8-bb44-515b-a82d-b53c277d690e |  | note | Record Documents: Contractor's site diary/Photos
label | e94ea371-4a0d-5fb9-831e-c61b84d923b3 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.112 - CCTV Inspection
label | e68e8695-e45b-56f3-9abc-1c3e3d69fd37 |  | note | Detail of Activity: Visual record of Existing works
label | f2887156-8368-5d05-bf91-1a54691e5a50 |  | note | Action: W
label | 78350bed-6d80-586e-8ccc-fc1bd451db4f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All drainage pipelines
label | 04e52377-0add-5f83-b507-aa6ac6d67c5b |  | note | Inspection / Test Method: CCTV Inspection
label | 688e0399-85c6-522d-913e-9c71796f0c23 |  | note | Acceptance Criteria: No significant cracks, level deformation, faulty joints
label | fac4301e-9dfe-510c-9492-8c6cb40a2c18 |  | note | Record Documents: CCTV Footage
label | 30b3301f-5313-50f7-b834-0e22849f835d |  | note | Responsibility: Contractor
label | b4848f2e-a934-5229-94cd-8b1fedc8fec7 |  | note | Comments: CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practicle Completion
checkpoint-group |  |  | section | Construction and Finishing - Intet : Precast headwall/wingwall unit for Ø450mm.
checkpoint-status |  |  | checkpoint | 300.113 - Determine Subgrade Strength
label | 4eeda5c3-f5a3-5898-b20d-f369f2cf73fa |  | note | Detail of Activity: Determine bearing strength of subgrade
label | a5b221f3-2ce6-51b9-bb15-a5f03aead663 |  | note | Action: H
label | 7f40bea8-edba-5581-9dcd-ced33e1ad788 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | 7523439e-eb76-5ad5-890a-e81a46abeed4 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 009e151d-2d83-5daf-8d43-560213ac64b2 |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | 1caaffa3-f2df-5082-8d8e-236ff4eeca7e |  | note | Record Documents: Contractor's site diary
label | fd12dfe4-ece0-56b8-8339-2fe1d532658b |  | note | Responsibility: Contractor
label | 94adf3c3-6fda-5b9f-922c-9faabd962778 |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.114 - Structures (manholes, head walls etc.)
label | eb57a559-0b22-5a98-8ddf-29bba562f1b3 |  | note | Detail of Activity: Visual inspection of concrete components
label | 473ed92f-5325-58d6-a713-046be3909f31 |  | note | Action: W
label | 47e0a33b-dc6c-5da5-867f-c7477636ee6b |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | 8eb33e42-781d-531b-bf34-009ada258d93 |  | note | Inspection / Test Method: Visual Inspection
label | 67336c53-004f-571e-a435-d9e639f88cb6 |  | note | Acceptance Criteria: No visible damage, especially around collars and joints
label | 2e878146-92d4-537f-8520-d56857d209e9 |  | note | Record Documents: Contractor's site diary/Photos
label | fb8237cb-f54a-586d-ab50-fc8aec0cca11 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.115 - Structures (manholes, head walls etc.)
label | bd868619-0412-56d4-9c98-8c41e9dc275a |  | note | Detail of Activity: Bedding
label | d974db16-30e8-5861-ba15-ce496bbf0785 |  | note | Action: M
label | 152c48f7-b7ad-5a66-9af4-7e7ac27fd5b0 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | d225e066-eb89-5814-8e84-67138a6382b8 |  | note | Inspection / Test Method: NZS 3725:2007
label | 6b5ec5b2-e0b8-528d-818a-1ea5b453fff6 |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | 6664d137-e057-5c2b-a81a-6af4f2768a5c |  | note | Record Documents: Contractor's site diary
label | f9ac3533-677f-54f3-9894-e0e152702294 |  | note | Responsibility: Contractor
label | 226fc02d-efdd-516f-b0d9-25bc5ece2db2 |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.116 - Structures (manholes, head walls etc.)
label | 7db1f143-483c-513f-a955-77a7c3081527 |  | note | Detail of Activity: Backfilling
label | 8ab21e75-48cf-54d5-ab81-6ecd660ee106 |  | note | Action: M
label | 79127a5a-8a27-5869-b636-7346bcfbe19e |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | dfd54a69-ba75-5df8-a790-2167d4a02bc7 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 5f0b2d5c-758d-5d6e-a54e-20038507078d |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | f64d9f7b-d8a5-50ed-942a-16ea46caf9d1 |  | note | Record Documents: Contractor's site diary
label | 9d4f0b1e-2bc2-5b62-a238-c89ff2f7edf0 |  | note | Responsibility: Contractor
label | eea4dba4-9a3f-5928-95f6-b84ae5d59f1f |  | note | Comments: Clean Pumice Fill to be used
checkpoint-group |  |  | section | Construction and Finishing - Outlet : Precast headwall/wingwall unit for Ø450mm.
checkpoint-status |  |  | checkpoint | 300.117 - Determine Subgrade Strength
label | 98ce840a-ddea-55a7-b940-57179bffd111 |  | note | Detail of Activity: Determine bearing strength of subgrade
label | 23decbed-cb94-5f22-8def-478ce1b070a4 |  | note | Action: H
label | 1d307f04-b40d-57c8-8ff3-b7f25a8989ad |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m length of trench base; or 1 per drainage structure
label | eb7fad40-d651-5a04-9dd6-ff0406f3d959 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 6a53ca11-eb13-50ca-9436-ef0e9ec11f44 |  | note | Acceptance Criteria: No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm.
label | 1dcd70c2-bdc3-51b7-ba84-c8d9cad72478 |  | note | Record Documents: Contractor's site diary
label | ff572c85-2c6b-50d3-9331-ece648b464d0 |  | note | Responsibility: Contractor
label | cff34cd8-454f-5e55-89cc-25833eeacbdf |  | note | Comments: Seek design subgrade strength prior to commencement so expected subgrade strength is known.
checkpoint-status |  |  | checkpoint | 300.118 - Structures (manholes, head walls etc.)
label | 8cc3333d-14b5-529d-8e29-9dfd809901d7 |  | note | Detail of Activity: Visual inspection of concrete components
label | 03a9be81-58ba-5190-a62f-80aa78ca4c9c |  | note | Action: W
label | 4ec2f929-7cfb-50b6-a545-8d6ce0169462 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | 646f8973-daf3-5514-b1d2-7c5b1ca7a3fb |  | note | Inspection / Test Method: Visual Inspection
label | f905ab25-54a0-547f-9332-75604d881ddc |  | note | Acceptance Criteria: No visible damage, especially around collars and joints
label | 7bc68ec8-be95-59a8-bdc2-3bc4b7e446e3 |  | note | Record Documents: Contractor's site diary/Photos
label | bf08e4b8-c8d8-5f24-8fdc-9b6256dad0d1 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 300.119 - Structures (manholes, head walls etc.)
label | 51b04a0f-4f95-5eb9-b8f5-c047a6207376 |  | note | Detail of Activity: Bedding
label | 4b54ca74-c045-51cc-9c97-8853db0925cd |  | note | Action: M
label | c7c3de51-0532-5840-8b26-b73ef5e96122 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 91dfdddf-276f-54a4-b321-a89d8ad5fa4b |  | note | Inspection / Test Method: NZS 3725:2007
label | daee94c7-f8ed-574a-a7ff-e150d179a75d |  | note | Acceptance Criteria: In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | 9ffc36d7-e226-5831-86b5-fa162781cdd9 |  | note | Record Documents: Contractor's site diary
label | 8f71cc33-9754-5e72-9756-db8fe1b5dd2b |  | note | Responsibility: Contractor
label | ab689edc-5b5b-507d-a2f8-2f5467cb7b80 |  | note | Comments: GAP 65 to be used with a leveling coarse of PAP 7.
checkpoint-status |  |  | checkpoint | 300.120 - Structures (manholes, head walls etc.)
label | 0926c65a-59a7-5fb3-8cf0-9e09c82ead68 |  | note | Detail of Activity: Backfilling
label | 278d7694-23aa-5b5c-b546-4892791a9387 |  | note | Action: M
label | ad721d11-6a39-545f-9448-aa2e6352da27 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per 5m trench per 1m lift
label | 2f90763d-abb4-5ef1-aa5c-590c8c6f41be |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2).
label | 3d28bae0-3a8a-5aaa-9846-061cb341a39f |  | note | Acceptance Criteria: In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15).
label | 8368a0ca-88d2-540b-adf3-23d41349e8d5 |  | note | Record Documents: Contractor's site diary
label | 490e7875-37e7-5a0b-b65b-c7ccaf54f055 |  | note | Responsibility: Contractor
label | bb9c8686-0d64-554e-9843-f58411bf21d0 |  | note | Comments: Clean Pumice Fill to be used
checkpoint-status |  |  | checkpoint | Final Sign Off
label | 8c9f8115-0604-5bab-8eaa-85d6213d7a89 |  | note | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 004fd0a8-304f-51f7-9f31-22afe9763c63 |  | textbox | Contractor's Rep Name:
text | cc6fe7ec-474c-5953-acc1-77374b048d7e |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Sign Off
checklist-sectioned |  |  | checklist | Concrete Pre-pour Inspection |  |  |  |  | Yes | Concrete Pre-pour Inspection | 2f23b2a1-fe32-4684-9227-7a53ed119223
checkpoint-group |  |  | section | Preliminary
checkpoint-status |  |  | checkpoint | Engineer notified of pour
text | 98ffea72-4951-5484-a1cb-4a448e1233c5 |  | textbox | Date
text | 7006f770-0251-5e19-ad15-3a83db9ada77 |  | textbox | Drawing Number and Revision
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Installed as per formwork design
checkpoint-status |  |  | checkpoint | Permit to load issued
checkpoint-status |  |  | checkpoint | Dimensions correct
checkpoint-status |  |  | checkpoint | Position and orientation correct
checkpoint-status |  |  | checkpoint | Forms vertical, plumb and true
checkpoint-status |  |  | checkpoint | Forms coated with release agent
checkpoint-status |  |  | checkpoint | Forms clean and clear of debris
checkpoint-status |  |  | checkpoint | Joints sealed
checkpoint-status |  |  | checkpoint | Pour level marks
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | Correct grade reinforcement
checkpoint-status |  |  | checkpoint | Correct bar size
checkpoint-status |  |  | checkpoint | Correct number of bars
checkpoint-status |  |  | checkpoint | Correct spacing
checkpoint-status |  |  | checkpoint | Starters bars included
checkpoint-status |  |  | checkpoint | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
checkpoint-status |  |  | checkpoint | Correct weld lengths (min 10 x bar diameter)
checkpoint-status |  |  | checkpoint | Correct lap length (min 50 x bar diamenter or as per drawing)
checkpoint-status |  |  | checkpoint | Correct lap position (staggered appropriately)
checkpoint-status |  |  | checkpoint | Longitudinal bars terminate with 90 or 180 deg hook)
checkpoint-status |  |  | checkpoint | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
checkpoint-status |  |  | checkpoint | Reinforcing adequately tied
checkpoint-status |  |  | checkpoint | Chairs or spacers fixed in place
checkpoint-group |  |  | section | Embedded items
checkpoint-status |  |  | checkpoint | Block-outs, ducts & cast in items installed
checkpoint-status |  |  | checkpoint | Correct position, level & alignment
checkpoint-status |  |  | checkpoint | Securely fixed in place
checkpoint-group |  |  | section | Construction Joints
checkpoint-status |  |  | checkpoint | Correct location
checkpoint-status |  |  | checkpoint | Adequately prepped
checkpoint-status |  |  | checkpoint | Joint board installed
checklist-sectioned |  |  | checklist | ITP 400 Rip Rap |  |  |  |  | Yes | ITP 400 Rip Rap | 348efe0d-f37b-4b3a-93b0-95b92fc338ab
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 400.1 - Mark out and approve
label | f7f7184a-2d13-52ef-a063-eaf39b5b186f |  | note | Detail of Activity: Set out and mark up of scour protection area
label | c8acce24-ce49-5ef8-a650-194d535b60dd |  | note | Action: H
label | 313d368d-897e-537c-bc43-7d49fd8fef4e |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All locations scour protection is required
label | 9ed33e02-e6e7-5203-a13e-a23c4cf9a933 |  | note | Inspection / Test Method: Visual Inspection
label | b5e74c41-3e7e-5d1f-b7d8-553f868f1982 |  | note | Acceptance Criteria: Engineer to confirm
label | d31fe4a5-e775-5766-a522-9b05a9db784d |  | note | Record Documents: Contractor's site diary
label | ad01b7d1-3f6d-5342-9944-5fba1d61931a |  | note | Responsibility: Contractor
label | d16d887d-a21f-598c-860b-10c2cdc250e3 |  | note | Comments: Treatment area marked up jointly by Contractor and Eng.Rep.
checkpoint-status |  |  | checkpoint | 400.2 - Confirm filter material
label | 7c089905-7b08-5b11-9e1f-ab8ff13d2e73 |  | note | Detail of Activity: Contractor to provide manufacturer's specificationfor proposed filter material
label | 23b6c469-eff1-5348-af9d-ebfcfd69fc84 |  | note | Action: H
label | b878de13-c08e-5982-a7d2-e3658ce90df2 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per material type
label | 164485b2-e5a9-54cd-939c-4cb74d06178d |  | note | Inspection / Test Method: N/A
label | 36471bd6-9666-58ba-9d9d-0d8fe7247b20 |  | note | Acceptance Criteria: Engineer to review and approve proposed material in accordance with Technical Specifications ( Section 7.1)
label | 90bafaa1-0fd4-5df5-9416-88f8903beab5 |  | note | Record Documents: NTC / Site instruction
label | 7e680972-50c8-5446-804d-1e6de1c909d0 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 400.3 - Confirm rip rap material
label | 341d08b2-fe03-504d-8af5-78073296e6d8 |  | note | Detail of Activity: Confirm the supply of grading results for proposed rip rap material
label | 2ac7ea54-d96e-55f3-9c03-5e8b4b60ed92 |  | note | Action: M
label | 6272d401-008f-5e16-b09c-2afdb60e91f9 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per material type
label | 0ff0ce6b-ac5f-5be8-acd8-4d3a8060b10e |  | note | Inspection / Test Method: N/A
label | be920eae-e659-5cdc-9042-3c7f7b212f05 |  | note | Acceptance Criteria: Engineer to review and approve proposed material in accordance with Project Technical Specification (Section 7.2)
label | 1fb17376-541e-505a-bc28-345ebaaf5994 |  | note | Record Documents: Laboratory Test Results
label | 669dfc4e-3555-52e0-981f-462caa505641 |  | note | Responsibility: Contractor
label | 7ce09ee5-4ebf-54df-a741-dce6afe74f6e |  | note | Comments: Laboratory test may be substitutes for a visual inspection (if instructed by the Engineer)
checkpoint-group |  |  | section | Construction and Finishing - Void Fill Rip-Rap Placement @ Stormwater Line 1 : SHEET 2126 (300mmx 14.5m)
checkpoint-status |  |  | checkpoint | 400.4 - Base Soil
label | ee6bbc9b-d5d8-55d4-8086-cfd4ef80d204 |  | note | Detail of Activity: Prepared slope or channel bottom
label | 38234e06-828b-50bd-8c19-b460ce0ae7d1 |  | note | Action: W
label | bc511825-a21b-59c4-9338-a22464f8823c |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All locations scour protection is required
label | 27b2db6d-5ac7-5bab-a0a8-81436c051bf1 |  | note | Inspection / Test Method: Visual Inspection
label | 768eb0f9-0017-5dc0-8af3-f71e29afa301 |  | note | Acceptance Criteria: No significant visual deformation
label | cab46569-23b6-5020-bc1b-9ded6f380f39 |  | note | Record Documents: Contractor's site diary
label | 2aaac579-38a7-51ee-9547-6db69a9318aa |  | note | Responsibility: Contractor
label | 93a5afc6-6a86-5ff8-b815-f713623da1a7 |  | note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint-status |  |  | checkpoint | 400.5 - Rip Rap Placement
label | 8fbd7cd4-88d8-5a1c-9011-1b8945ce14fc |  | note | Detail of Activity: Location - Excavation depth - assembly - Installed length
label | 6ad3d66c-3903-5ff1-abb6-69831712c6d3 |  | note | Action: H
label | 2cac4cbe-5d2e-5806-872e-8a4a0191fb0c |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 check per structure
label | a638cde8-6db1-5b26-b9ff-1cc337d9b11e |  | note | Inspection / Test Method: Visual Inspection
label | 7e7e1a83-7d14-5083-935d-f2919e254dee |  | note | Acceptance Criteria: Conform to Specification
label | 6ee4a200-9fd7-534c-987e-4666cf81c7f1 |  | note | Record Documents: Contractor's site diary
label | 700a4bd1-3172-5729-9797-c8f4a696ea70 |  | note | Responsibility: Contractor
label | da295bf0-012d-5acd-b822-062c92d5639f |  | note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint-group |  |  | section | Construction and Finishing - Void Fill Rip-Rap Placement @ Stormwater Line 1 : SHEET 2126 (300mmx 14.5m)
checkpoint-status |  |  | checkpoint | 400.6 - Visual Structural Inspection
label | cb29854b-86fa-56a5-9b34-4c6c6654821b |  | note | Detail of Activity: Visual inspection of Void Filled rip rap structure
label | 8e919017-41ff-5928-8961-f8f7ba268de4 |  | note | Action: W
label | c7fdb4ba-9e4f-5aa9-916e-0babf3374be4 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | bf766341-a8cb-50a4-943b-cffca4f709f6 |  | note | Inspection / Test Method: Visual Inspection
label | 9beabc20-71bf-5720-a9cf-9f7d4ebfb7cc |  | note | Acceptance Criteria: Conform to Approved Drawings & Specification
label | 2170c3c0-bc48-5f5f-8053-1013f3bf8f96 |  | note | Record Documents: Contractor's site diary/Photos
label | ce54e2ea-c94d-5aa9-ab0d-70070aeb8ffd |  | note | Responsibility: Contractor
label | fec41571-95a8-576e-9352-b150c8717fad |  | note | Comments:
checkpoint-status |  |  | checkpoint | 400.7 - Final Inspection
label | 02907d70-4c03-522b-83f7-65754b531869 |  | note | Detail of Activity: Engineer to inspect the final works
label | 11542c72-244b-5100-beab-ddd92522e427 |  | note | Action: H
label | a98a5c52-c408-50b2-bf3a-3e5a0cae22cd |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All locations scour protection is required
label | cd341d9e-957b-5eda-b638-a0a94c7d7e3d |  | note | Inspection / Test Method: Visual Inspection
label | 128b7976-398e-5663-a447-32e77834b744 |  | note | Acceptance Criteria: The final surface shall be thoroughly wetted for good compaction and smoothed and compacted by vibrating equipment
label | 9f02a36f-b49b-5a0b-b87e-65f4848dff81 |  | note | Record Documents: Contractor's site diary
label | 0f724cb6-4bd1-5b78-8035-0d91ed21d9ae |  | note | Responsibility: Contractor
label | db704c39-4e7e-58a2-960a-d1bb3ec9c051 |  | note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint-group |  |  | section | Construction and Finishing - Void Fill Rip-Rap Placement @ Stormwater Line 2 : SHEET 2128, 2129 and 2127
checkpoint-status |  |  | checkpoint | 400.4 - Base Soil
label | f3d15de2-a347-52b4-81ce-83a05cf2206c |  | note | Detail of Activity: Prepared slope or channel bottom
label | 884d7592-9f38-566f-abbb-3c11d7454eb7 |  | note | Action: W
label | d13a3a1c-b442-539b-bae3-3036d01c9061 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All locations scour protection is required
label | 212f8d43-8255-5eea-b2c2-5562d8614303 |  | note | Inspection / Test Method: Visual Inspection
label | 0e134457-f9d2-5150-89a9-79dd7ea192d3 |  | note | Acceptance Criteria: No significant visual deformation
label | 6009c3c9-1afe-5313-bdfd-1e7a3f644df6 |  | note | Record Documents: Contractor's site diary
label | e6ecb9bc-5a43-507c-b185-50e24dcfe779 |  | note | Responsibility: Contractor
label | 99594b6f-c316-5551-b244-dbf71827d2b7 |  | note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint-status |  |  | checkpoint | 400.4 - Rip Rap Placement
label | 73ac3375-9a65-519e-aa1a-ab5c299e8b17 |  | note | Detail of Activity: Location - Excavation depth - assembly - Installed length
label | 93363a3b-aa4e-52c6-bfdf-178bee9ab6d4 |  | note | Action: H
label | d8605467-7e39-5eac-bc62-ffe439759384 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 check per structure
label | a7a1e3d0-0dac-5e9d-8f38-081a57084df3 |  | note | Inspection / Test Method: Visual Inspection
label | a82f682d-7c24-536f-8393-89ba05c4cfc1 |  | note | Acceptance Criteria: Conform to Specification
label | f51f4a8c-e280-5205-91bc-45b6025fedb8 |  | note | Record Documents: Contractor's site diary
label | 7bc7e6b1-b1e4-5773-be6a-547549b8e6bd |  | note | Responsibility: Contractor
label | 2d46a919-bb4e-53fe-9675-145521e8b74a |  | note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint-status |  |  | checkpoint | 400.7 - Visual Structural Inspection
label | 391c6a66-9e3f-5b21-aa31-cd570516eb16 |  | note | Detail of Activity: Visual inspection of Void Filled rip rap structure
label | 8b5704cb-12de-5b00-9b11-99daf3aa071a |  | note | Action: W
label | 05a5f216-8e03-5e48-b795-502defd2126b |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | e9fb792a-3c7b-5641-a9f1-cae2044a2375 |  | note | Inspection / Test Method: Visual Inspection
label | 8e2f76d5-023b-577c-955a-c8e2ef728fc9 |  | note | Acceptance Criteria: Conform to Approved Drawings & Specification
label | dd0694eb-5a1c-5675-9ab7-861fea820a01 |  | note | Record Documents: Contractor's site diary/Photos
label | 0d944ab5-bd63-5a65-88c0-1611e4f43971 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 400.4 - Final Inspection
label | f942b7e3-f63c-5991-a87a-62c430872b7a |  | note | Detail of Activity: Engineer to inspect the final works
label | 93333ddd-920f-5977-a7c9-9b33bb93ef2d |  | note | Action: H
label | e56bb51b-3a12-5298-b9d5-9ee9b50433a0 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All locations scour protection is required
label | dc675a15-a389-51ce-88fa-8c1550c625d0 |  | note | Inspection / Test Method: Visual Inspection
label | adcfedb2-3947-586e-8bc4-918caebfb205 |  | note | Acceptance Criteria: The final surface shall be thoroughly wetted for good compaction and smoothed and compacted by vibrating equipment
label | 96c597fe-3cc0-51e1-b289-871759a4735b |  | note | Record Documents: Contractor's site diary
label | f508a724-7ade-5eaa-90b3-7c357fd56785 |  | note | Responsibility: Contractor
label | 298e21e8-3d05-5df4-bd60-fde1dfbb360c |  | note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint-group |  |  | section | Construction and Finishing - Void Fill Rip-Rap Placement @ Stormwater Line 3 : SHEET 2129
checkpoint-status |  |  | checkpoint | 400.4 - Base Soil
label | 213658ac-4fa1-5bae-a01e-370cd5cd5906 |  | note | Detail of Activity: Prepared slope or channel bottom
label | 2f083cc7-fdcc-5a61-9bb5-fd0a20058a3a |  | note | Action: W
label | baf78299-aba3-5162-826f-900401be63ef |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All locations scour protection is required
label | 5ea8e210-7dd1-5eb4-851c-d660b0216758 |  | note | Inspection / Test Method: Visual Inspection
label | e8fa57f9-e56d-5e6f-b5b4-11529bb2499b |  | note | Acceptance Criteria: No significant visual deformation
label | 6afbb82c-db99-5ba9-927d-7f65aac707d7 |  | note | Record Documents: Contractor's site diary
label | 454591af-a998-5a29-8ac7-0ab30c51ec3e |  | note | Responsibility: Contractor
label | ae2215b9-e935-538f-b884-21005593d49b |  | note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint-status |  |  | checkpoint | 400.4 - Rip Rap Placement
label | 84c19db9-b8ce-5ea2-b29d-231734e2fe2d |  | note | Detail of Activity: Location - Excavation depth - assembly - Installed length
label | 6c0b768e-46b3-5cae-a197-db9afde441b4 |  | note | Action: H
label | 6b00ef0e-e14c-5164-862c-7ced02cd8d5a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 check per structure
label | ab18a888-a707-576c-bdfa-2cb091e03298 |  | note | Inspection / Test Method: Visual Inspection
label | d4b768c9-5640-58f0-a4f0-353daf118316 |  | note | Acceptance Criteria: Conform to Specification
label | 26503328-d210-556a-9799-46896258ae43 |  | note | Record Documents: Contractor's site diary
label | 6d2e3e6d-fc95-52e4-ba5c-283376c58a21 |  | note | Responsibility: Contractor
label | 01ea9820-1a88-55dc-be18-6c2e97528b60 |  | note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint-status |  |  | checkpoint | 400.7 - Visual Structural Inspection
label | c3ca07ba-6a35-5118-9cf8-1130871727aa |  | note | Detail of Activity: Visual inspection of Void Filled rip rap structure
label | 98bbe820-8f61-5a12-aaa8-faca533e3331 |  | note | Action: W
label | 2437d679-fe47-5a7c-a6ef-bcd7d0185ea2 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | f85b8d5b-bdb0-50d4-bf76-97ea171ef569 |  | note | Inspection / Test Method: Visual Inspection
label | 5a177383-2d9a-5785-b2b6-a47872277767 |  | note | Acceptance Criteria: Conform to Approved Drawings & Specification
label | 63bdee86-3d89-5dbe-a92c-8a7ea9e73be9 |  | note | Record Documents: Contractor's site diary/Photos
label | 7ed263bd-50eb-5f71-9871-ca0ab6f05eea |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 400.4 - Final Inspection
label | 7c6b63dd-1d7a-59e1-bc62-ed4eb7bae78a |  | note | Detail of Activity: Engineer to inspect the final works
label | 65522255-e10d-5f13-b859-456c37a1dbc3 |  | note | Action: H
label | cfebb6c7-7145-5d69-9136-9e249e47031c |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All locations scour protection is required
label | 4bf9b1c4-df8e-57ee-833a-ee8e9d4a189d |  | note | Inspection / Test Method: Visual Inspection
label | 4e145670-6ae7-5f55-82fa-972489cf610b |  | note | Acceptance Criteria: The final surface shall be thoroughly wetted for good compaction and smoothed and compacted by vibrating equipment
label | 8a9287a7-557b-51de-a5f4-0662caf26394 |  | note | Record Documents: Contractor's site diary
label | e42e5868-f3f3-55af-b184-cd1bd0c73fb5 |  | note | Responsibility: Contractor
label | b9a71ed9-59ac-5b46-8def-08f5a2c1bf99 |  | note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint-group |  |  | section | Construction and Finishing - Void Fill Rip-Rap Placement @ Stormwater Line 5 : Swale 1: SHEET 2129
checkpoint-status |  |  | checkpoint | 400.4 - Base Soil
label | b10c6f4b-16ce-58ef-a515-5b7c2d54ef50 |  | note | Detail of Activity: Prepared slope or channel bottom
label | ca093dad-b516-50cf-981e-4c4fa5fd7aa9 |  | note | Action: W
label | f97007c7-6d52-5037-a9e0-6c10f5ab3df9 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All locations scour protection is required
label | d68c6cc1-2d27-5243-b9bc-3b482d791898 |  | note | Inspection / Test Method: Visual Inspection
label | eb8e0244-e75d-577e-9747-3e9881b756ff |  | note | Acceptance Criteria: No significant visual deformation
label | 10abc2af-1106-57fe-af93-6db38271f5bc |  | note | Record Documents: Contractor's site diary
label | ad59f19c-e6a5-5243-9a43-564f0b299a4e |  | note | Responsibility: Contractor
label | 27527bd7-163f-5d43-93bb-01fd18414031 |  | note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint-status |  |  | checkpoint | 400.4 - Rip Rap Placement
label | 1421f490-9c92-56e4-9908-f6c16d29c0f8 |  | note | Detail of Activity: Location - Excavation depth - assembly - Installed length
label | f4b74092-f865-542f-996f-ef9f17594f25 |  | note | Action: H
label | cfd0180c-5c7c-5e8f-b8ce-e859f7c72b36 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 check per structure
label | 87738018-9fc5-54ab-bb5c-016f66765d28 |  | note | Inspection / Test Method: Visual Inspection
label | c216af37-6dbd-515f-9af5-d721b3055507 |  | note | Acceptance Criteria: Conform to Specification
label | 1361460f-9e82-5a6b-b8c0-6db2969b55d7 |  | note | Record Documents: Contractor's site diary
label | 6e3942e8-4a8e-5ddd-a160-e61f11e050f9 |  | note | Responsibility: Contractor
label | 90aa6a77-3522-53ec-95cf-ce8171e34b51 |  | note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint-status |  |  | checkpoint | 400.7 - Visual Structural Inspection
label | 1a85843f-0a07-5629-bbf9-7defc4f97b70 |  | note | Detail of Activity: Visual inspection of Void Filled rip rap structure
label | f2fd72e6-2137-5a03-8a18-dbb9d2f16cee |  | note | Action: W
label | abeda4ab-9f90-50b6-9835-f4831b36ab1e |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per structure
label | 24a98e53-ab85-5976-a9ae-34f3f124c2d4 |  | note | Inspection / Test Method: Visual Inspection
label | 9df84fde-e732-5d9d-86d7-662333dacf8b |  | note | Acceptance Criteria: Conform to Approved Drawings & Specification
label | 87673813-1e01-5632-ab34-fe996fdd12ca |  | note | Record Documents: Contractor's site diary/Photos
label | f0ce129e-51ce-5876-9366-a3fbf6cb8226 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 400.4 - Final Inspection
label | 6045ed67-bc70-5906-9eb7-7b2b21d98161 |  | note | Detail of Activity: Engineer to inspect the final works
label | cd2e7042-11b1-5826-b98f-402ef66a0410 |  | note | Action: H
label | cf976424-bd11-511b-8128-ad6898bf39e4 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All locations scour protection is required
label | 79016b6c-0ecc-547e-9e45-e48a1861f4bd |  | note | Inspection / Test Method: Visual Inspection
label | 6e666577-e8f5-5e3c-b635-a8a59216d104 |  | note | Acceptance Criteria: The final surface shall be thoroughly wetted for good compaction and smoothed and compacted by vibrating equipment
label | fd585765-90c5-56b4-9a5a-f929ccb64b0f |  | note | Record Documents: Contractor's site diary
label | d5aa8235-c4e6-56da-a289-cf2a3f586df5 |  | note | Responsibility: Contractor
label | dd1003c0-0923-5391-9300-a59358645112 |  | note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint-status |  |  | checkpoint | Final Sign Off
label | 6b530282-aea5-5089-a79b-bc2be3ded7b0 |  | note | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 1308a6eb-0ae4-56d0-a749-bec5c4e3cd7b |  | textbox | Contractor's Rep Name:
text | 65254309-e6bc-54bf-9c74-d6ea92a6a6ef |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Sign Off
checklist-sectioned |  |  | checklist | ITP 500 Granular pavement |  |  |  |  | Yes | ITP 500 Granular pavement | 4736c723-e2c4-49c7-b9bd-604c242d2672
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 500.1 - Determine Embankment / Subgrade Strength (Shoulder Top-up)
label | b26792ea-7e73-58c3-940c-e6430608d9ca |  | note | Detail of Activity: Proof Roll the excavated area
label | 31657240-3ec0-5263-a403-780e2226c654 |  | note | Action: W
label | 123c5260-8e37-58a7-8453-e36d3a361b95 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All areas of shoulder top-up. 1 Lot < 300m long.
label | fd256845-20f3-5934-951b-037908869642 |  | note | Inspection / Test Method: NZS 4402.6.5.2
label | c1b15d88-542b-5e3d-8422-bd71a678a8f8 |  | note | Acceptance Criteria: No significant visual deformation under the wheel load CBR>10
label | d476b16c-67bf-53eb-9bde-5b580f8f488f |  | note | Record Documents: Contractor's site diary
label | 64b6fd5f-1c2d-520a-8348-adeee327a335 |  | note | Responsibility: Contractor
label | 3b379ee7-c22f-5655-ba47-e574780b20da |  | note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint-status |  |  | checkpoint | 500.2 - Determine Embankment / Subgrade Strength (Pavement Widening)
label | 48ac77d9-74fc-5107-b6b2-a3f414e28870 |  | note | Detail of Activity: Determine bearing strength of subgrade
label | bcf32447-08fc-5411-9131-551c0446222d |  | note | Action: W
label | cb278398-243f-5aee-a3dc-01e99545e116 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 Scala per 20m of shoulder or
label | 94477450-aab9-59f9-8478-2fb2c4838ded |  | note | Inspection / Test Method: NZS 4402.6.5.2
label | 1b028843-08f3-5b93-b77d-12cfdddeb1b3 |  | note | Acceptance Criteria: CBR >10 For design input
label | 63694c5b-fd26-506c-9067-e76cb4183855 |  | note | Record Documents: Contractor's site diary
label | 99201443-b2a9-52a5-919b-67a7895ce0fc |  | note | Responsibility: Contractor
label | 54e28f4a-9d72-50a8-95e4-441d88ae47a9 |  | note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint-status |  |  | checkpoint | 500.4 - Confirm SIL Material
label | bc96c7e3-09ea-58bc-b553-4eaffb2a8674 |  | note | Detail of Activity: SIL Aggregate
label | 03eef2f5-8b55-50ec-9e43-b68c6f5d5d29 |  | note | Action: M
label | 5ac5b872-866b-566d-8a48-11d29ae0f53f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Source properties: 1 test per source 4 weeks prior to use, repeat every 10,000m3 Production properties in stockpile: 0-1500m3 - 3 tests 1500-4000m3 - 4 tests >4000m3 1 test for every 1000m3
label | 6bd2fde4-19eb-588d-8197-6190b04f036d |  | note | Inspection / Test Method: Crushing Resistance MDD OMC CBR
label | 4bdfcc06-3082-52e3-922e-46134eb1c431 |  | note | Acceptance Criteria: Project Spec 2.2.10
label | 80cc285d-8b3a-59bb-90c7-cec4fb6627db |  | note | Record Documents: IANZ Report
label | df94f8ca-98f4-5935-b474-f2dc705031ff |  | note | Responsibility: Contractor
label | acfa77f3-0b9d-5f33-9779-6832bce4b963 |  | note | Comments: By IANZ accredited lab
checkpoint-status |  |  | checkpoint | 500.4 - Confirm Subbase Material
label | 71b77441-e471-5c0f-aeee-8349fac2fb5b |  | note | Detail of Activity: Subbase Aggregate
label | b70b9484-c8ff-5b2d-a5b4-968a37c0a11b |  | note | Action: M
label | 406b1f68-6252-5fee-8f99-9f9db351c745 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Source properties: 1 test per source 4 weeks prior to use, repeat every 10,000m3 Production properties in stockpile: 0-1500m3 - 3 tests 1500-4000m3 - 4 tests >4000m3 1 test for every 1000m3
label | b5d72ace-1c64-5536-b893-2ae0986b6144 |  | note | Inspection / Test Method: PSD, SE, CI, PI, Broken Faces Crushing Resistance Weathering Resistance MDD OMC CBR
label | a0a695ef-8da0-520c-bd3a-fa3fc3d66e4f |  | note | Acceptance Criteria: NZTA WHAP 65/ Project Spec 8.1.2
label | 03cb70c2-13d1-5840-9eab-fb75e43a751e |  | note | Record Documents: IANZ Report
label | cb16c307-9286-5115-a4b9-93fa6444419b |  | note | Responsibility: Contractor
label | 7bf80e1e-2e98-516d-9763-e283bcbb77ff |  | note | Comments: By IANZ accredited lab
checkpoint-status |  |  | checkpoint | 500.5 - Confirm Basecourse Material
label | 5ad628ae-ac7f-522e-baa6-95abedeea45d |  | note | Detail of Activity: Basecourse Aggregates
label | bcf22c77-f6f6-5bbf-9cb4-8730d262dc94 |  | note | Action: M
label | 97966ab1-a37b-5691-bd1f-cd46d8ec0ffe |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Source properties: 2 tests per source 4 weeks prior to use, repeat every 10,000m3 Production properties in stockpile: 0-1500m3 - 3 tests 1500-4000m3 - 4 tests >4000m3 1 test for every 1000m3
label | e255552d-7cac-56d5-9021-f5ae63830c9b |  | note | Inspection / Test Method: PSD, SE, CI, PI, Broken Faces Crushing Resistance Weathering Resistance MDD OMC CBR
label | 4cceb2d6-5c43-57da-b77e-f6b70cc6b709 |  | note | Acceptance Criteria: NZTA M4 / Project Spec
label | 6b327957-a421-54bd-8625-87c3ea4741ea |  | note | Record Documents: IANZ Report
label | 61ace645-44c0-5195-b1d9-fe002ef6135e |  | note | Responsibility: Contractor
label | 4fb652d4-234c-5be1-9d0c-2ac96a4f38d8 |  | note | Comments: By IANZ accredited lab
checkpoint-group |  |  | section | Construction and Finishing
checkpoint-status |  |  | checkpoint | 500.10. - SIL Layer Depth/Thickness
label | c9bb04a9-446d-5f30-a14c-7a6289c631d2 |  | note | Detail of Activity: Scala/Infered CBR of Subgrade
label | 56a755a4-d78b-5dd4-a22c-4c2251855b02 |  | note | Action: H
label | c1137665-749c-5862-8ee1-98b290a3a531 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All Subgrade Areas
label | 7028cdcf-f397-5a96-8408-8ff61e4e5768 |  | note | Inspection / Test Method: Scala @3 points across carriageway @ 20m spacings
label | 69fd2e3c-6c85-51ea-a380-28b40cdec732 |  | note | Acceptance Criteria: CBR<10 then SIL Layer = 600mm CBR <2 seek advice from engineer
label | 8c76799e-135d-52da-9f0c-055c7ff83ea3 |  | note | Record Documents: Scala Recording Sheet
label | 087e8e0a-6c46-5bba-a307-8f6d1d31771d |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 500.9 - Pavement - (SIL Construction)
label | 24d4004e-9e41-5f27-b85c-9264c5425fea |  | note | Detail of Activity: Maximum Dry Density
label | ec98dbf2-8be9-5ee6-a82d-784a7a698aae |  | note | Action: M
label | 6d0653a2-9f8d-5619-bda0-72070eb28115 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 5 per Lot (1,000 m2)
label | 8290e1c0-76f6-5aed-8130-c15058d5b419 |  | note | Inspection / Test Method: NZS 4402.4.1.3
label | 0aa2ce25-e5aa-5350-9f17-2863f0b93406 |  | note | Acceptance Criteria: For analysis of DoC
label | 7d667e81-1880-5862-a3c0-b62a22533ef8 |  | note | Record Documents: IANZ Report
label | 73bcb9ee-b52b-5548-ab14-7f421b92ea49 |  | note | Responsibility: Contractor
label | b6464f14-f1c8-51f4-9d09-cff952c6e21f |  | note | Comments: By Contractor with random Verification by IANZ accredited lab
checkpoint-status |  |  | checkpoint | 500.9 - Pavement - (SIL Construction)
label | 88eea24a-da91-550f-bae1-0731b555f655 |  | note | Detail of Activity: Degree of Compaction
label | 88bdd147-872e-59bb-b70d-1997699616f3 |  | note | Action: H
label | aa67733e-b21f-581a-8af8-5ddb14d1e1da |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 5 per Lot (1,000 m2)
label | faf75ef5-6fa3-5068-b4c5-4739f2d6ea26 |  | note | Inspection / Test Method: NZS 4407.4.2.1
label | 68922322-2d12-5246-9497-8b1066d7f074 |  | note | Acceptance Criteria: NZTA B02: DoC ≥ 95% with all >92%
label | 28adc177-ab41-5576-8f83-d2fada755e69 |  | note | Record Documents: IANZ Report
label | c871fecf-74a7-5d6f-97a1-ee0405954442 |  | note | Responsibility: Contractor
label | 13b52520-ee13-5225-841c-5d8d4a3315a0 |  | note | Comments: By Contractor with random Verification by IANZ accredited lab
checkpoint-status |  |  | checkpoint | 500.9 - Pavement - (Subbase Construction)
label | 911dacc7-71d5-5c14-97b7-0eddc6c50e94 |  | note | Detail of Activity: Maximum Dry Density
label | 8e3cc114-a9de-5143-a8a1-70afbf9ae273 |  | note | Action: M
label | 3f4ad5a1-ea67-5e26-b9f0-a60964da53b4 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 5 per Lot (1,000 m2)
label | 62c97cef-f74b-5635-87cc-e55d7ecacb6d |  | note | Inspection / Test Method: NZS 4402.4.1.3
label | 9b50bbf0-2aa5-5072-af01-8ccb9e937caf |  | note | Acceptance Criteria: For analysis of DoC
label | 0965a9d3-dddb-5d1e-b18b-6ec4fb812353 |  | note | Record Documents: IANZ Report
label | 465db4a4-93f6-502d-9db1-29f811890c2a |  | note | Responsibility: Contractor
label | 0f5cb778-4de3-5c96-aee3-c8fa36be6496 |  | note | Comments: By IANZ accredited lab
checkpoint-status |  |  | checkpoint | 500.9 - Pavement - (Subbase Construction)
label | aeeebcbe-13d7-5420-8514-8d4adb76b90a |  | note | Detail of Activity: Degree of Compaction
label | 017cc82f-651b-5a0a-aa78-b6ebe08c511f |  | note | Action: H
label | b5ace682-04fc-5d26-b96c-97ac82a8e3fb |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 5 per Lot (1,000 m2)
label | 67003d13-b63b-59dc-9e46-cf97f2f10b18 |  | note | Inspection / Test Method: NZS 4407.4.2.1
label | a79b237b-099a-5ad8-a322-e119b4a77dcd |  | note | Acceptance Criteria: NZTA B02: DoC ≥ 95%
label | e739c810-6014-5b94-a32f-06aab1499d88 |  | note | Record Documents: IANZ Report
label | f285b90a-a525-5fa2-a3aa-8fc823b167c3 |  | note | Responsibility: Contractor
label | 8de6c2c9-4b9d-5487-b28f-1de3f2e398ee |  | note | Comments: By IANZ accredited lab
checkpoint-status |  |  | checkpoint | 500.9 - Pavement - (Basecourse Construction)
label | 0c5e4c17-3c08-554e-ab51-3cc3f456913e |  | note | Detail of Activity: Maximum Dry Density
label | a15394be-5fb8-51aa-8fd7-13734f10056d |  | note | Action: M
label | 939fe3d2-7f1c-5f00-8c7a-17ab81565ce1 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 5 per Lot (1,000 m2)
label | 53eb1320-68d5-5fe6-9a82-55f8b1851f90 |  | note | Inspection / Test Method: NZS 4402.4.1.3
label | 123ef5cf-e2e5-58c6-882e-ea6e6e2d3cfb |  | note | Acceptance Criteria: For analysis of DoC
label | 5144926c-5e79-5899-83dc-fe4e2bce1b09 |  | note | Record Documents: IANZ Report
label | a05e6a6b-53c6-5eb0-9173-40748019ba8d |  | note | Responsibility: Contractor
label | 644399be-2318-544d-ac3e-79225e68bc02 |  | note | Comments: By IANZ accredited lab
checkpoint-status |  |  | checkpoint | 500.9 - Pavement - (Basecourse Construction)
label | 082e44c7-77b3-5efc-9656-78fff0f130aa |  | note | Detail of Activity: Degree of Compaction
label | 8aff97fb-4251-534d-85f8-56650117a755 |  | note | Action: H
label | fd6b970e-6b4d-56ce-8c05-48e033fd6293 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 5 per Lot (1,000 m2)
label | 3b0b5759-fb94-5ae1-8c79-8b7068da369f |  | note | Inspection / Test Method: NZS 4407.4.2.1
label | 783707c0-e18b-542c-aa66-7b6c6434211a |  | note | Acceptance Criteria: NZTA B02: DoC ≥ 98%
label | 811e5156-85f5-5964-a954-8e166d783663 |  | note | Record Documents: IANZ Report
label | cb6114e1-855d-576e-9fb0-ebe5b58e26bd |  | note | Responsibility: Contractor
label | a6858cbb-5dfd-5b1a-85c6-4ecf265e5b89 |  | note | Comments: By IANZ accredited lab
checkpoint-status |  |  | checkpoint | 500.10. - Surface Finishing Subbase
label | 2a874005-e38c-5652-8ca0-1f402ac1fb51 |  | note | Detail of Activity: Check geometry of the placed fill is in accordance with the design.
label | 74a86481-f791-5010-ac1c-eedc88f01c74 |  | note | Action: H
label | 4459b2a8-6a65-5694-8667-2e3a29ad39e9 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All Subbase Areas
label | c68e8e26-dab9-5506-85f5-61307e6b54e0 |  | note | Inspection / Test Method: Survey, Stringline dips @5 points across carriageway @ 20m spacings
label | d9c2c50d-913e-5067-84fc-4b1e34103235 |  | note | Acceptance Criteria: Geometry is in accordance with design drawings .
label | c73135a5-23f3-53bd-9a92-055d65793b13 |  | note | Record Documents: Stringline Report
label | d78d7c93-d6c3-5114-9a55-8ec3b3cc7f63 |  | note | Responsibility: Contractor
label | e31df5c5-11e8-5f54-9980-7071486e32d1 |  | note | Comments: Joint walkover between Contractor and Engineers Representative. All points to be within -25mm +5mm
checkpoint-status |  |  | checkpoint | 500.10. - Surface Finishing Basecoarse
label | 99e7b64c-2143-5231-a8de-ec367b2d9880 |  | note | Detail of Activity: Check geometry of the placed fill is in accordance with the design.
label | 54ac5944-dd47-5ada-a24e-bf0eb63ccc94 |  | note | Action: H
label | 7683538a-4307-50fc-b2ce-bd0e2560bc84 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All Basecoarse Areas
label | b5c1be60-24ed-5386-9967-1df387d14f01 |  | note | Inspection / Test Method: Survey, Stringline dips @5 points across carriageway @ 20m spacings
label | 56d5651e-d280-5817-ab31-75592ffedd25 |  | note | Acceptance Criteria: Geometry is in accordance with design drawings .
label | 4a32c26b-e65e-5d2b-a3ee-9dda54068760 |  | note | Record Documents: Stringline Report
label | 6a100605-90dc-574d-8037-d9a156521f36 |  | note | Responsibility: Contractor
label | 61136edf-fffd-57ee-a5d8-0c35ad9278ed |  | note | Comments: Joint walkover between Contractor and Engineers Representative. All points to be within -5mm +15mm
checkpoint-status |  |  | checkpoint | 500.10. - Surface Finishing
label | bc49a370-3787-58f3-83a4-656bd9c5a0a9 |  | note | Detail of Activity: Roughness Requirements
label | a0917096-82fe-5273-81dd-eb9174cd8f7f |  | note | Action: M
label | f39e3bb5-fd2a-50b7-9de6-ff38414fe45f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Finished Sealed Surface
label | 2636cd75-be27-549a-a4b8-cb96a7bfeb6e |  | note | Inspection / Test Method: NAASRA Counts
label | 9b838a3e-16e5-5878-ba2e-a6fafe8ce031 |  | note | Acceptance Criteria: Surface shape complies with Section 2 of NZTA TM7003.
label | ed1769cc-6d6d-5d21-9ff9-f27073cc774a |  | note | Record Documents: IANZ Report
label | c24278e7-839b-59f9-9772-7eaf6d3928ff |  | note | Responsibility: Contractor
label | 4fbabb01-cda0-5691-916e-78ad4ed8969f |  | note | Comments: Maximum NAASRA count of 70/100m with a target of 60/100m.
checkpoint-status |  |  | checkpoint | Final Sign Off
label | 290131f6-8823-59f5-a6fe-053fbd282564 |  | note | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | d0c50d29-aaf7-5330-83a5-28c72a510d55 |  | textbox | Contractor's Rep Name:
text | def2a8ef-2f9b-5d57-87b6-c1924c393d7e |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Sign Off
checklist-sectioned |  |  | checklist | ITP 800 Road Lighting |  |  |  |  | Yes | ITP 800 Road Lighting | 58e1d719-93d9-413f-a2da-5b3f271f40b8
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 800.1 - Mark out works
label | 5af7f7e2-9b87-57d2-94cb-a48285e7cacf |  | note | Detail of Activity: Set out fencing alignment and extents on site
label | ea0f2cb8-0c59-5c32-bf4b-16a4442f4ac3 |  | note | Action: H
label | 0929414e-081e-5fb7-a0bc-4fc94fefd18b |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All lighting columns and associated cabling
label | 8dcbf2b0-28ef-5229-ab24-e829d9f63398 |  | note | Inspection / Test Method: Visual Inspection
label | 07e579b9-eab9-5e56-a8cf-e0fcec4bd93d |  | note | Acceptance Criteria: N/A
label | 0554a838-9ed8-574c-a4c2-eafa8c3a7790 |  | note | Record Documents: Contractor's site diary
label | 707b39cd-4a39-5455-bae0-4b2a57636c8d |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 800.2 - Underground services
label | 2b36e2dc-66c2-5542-ac5c-49d94fa3670f |  | note | Detail of Activity: Identify and positively locate services
label | 39caccf5-0440-52fd-924b-8c87f033de5b |  | note | Action: H
label | 58f08b2d-f124-55b4-a17d-eb06cae8ce22 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All lighting columns and associated cabling
label | 64f7a982-9b83-5618-b447-65eb00254d14 |  | note | Inspection / Test Method: Hydoexcavation
label | 9f0fc9e0-3eb5-535c-a96c-0859b294c0ed |  | note | Acceptance Criteria: N/A
label | aaec9cc2-ac6d-550f-bffa-cd1891d8f57f |  | note | Record Documents: Drawings
label | e6841106-3ddb-5a0b-b79e-a18cd670c643 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 800.3 - Lighting Column Warranty Certificates
label | 99ec5f60-bb3f-5e75-9718-13aabd2ef7d5 |  | note | Detail of Activity: Contractor to provide design and warranty information for nominated lighting columns and luminares
label | b063b3e7-d94a-5bfc-86cc-7c798b537991 |  | note | Action: H
label | 8bec9205-97ab-50cb-9a59-42cbf4adddb1 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Prior to commencing works
label | a6b1753d-f997-53cc-9556-705fbc8b2d59 |  | note | Inspection / Test Method: N/A
label | 4d9cb24d-046a-52f4-9012-1f777ac9d4f8 |  | note | Acceptance Criteria: Engineer to review and approve proposed lighting columns and luminaries
label | 45d47521-89d7-53c1-a737-eb80a81e6cb1 |  | note | Record Documents: NTC / Site instruction
label | ac6f99e6-54c4-5492-a5a7-d42813add8f9 |  | note | Responsibility: Contractor
checkpoint-group |  |  | section | Construction and Finishing (W-Section Barriers)
checkpoint-status |  |  | checkpoint | 800.4 - Electrical Certificates
label | 3dd053e8-033e-564a-8c06-42b63c8cf681 |  | note | Detail of Activity: Contractor to provide electrical certification information for all electrical works installed
label | 2ed9ffb9-89c8-56c2-b899-a2de4ca0c8ec |  | note | Action: H
label | 3a578dc4-d6b5-533a-acf8-655e9a39d81f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All lighting columns and associated cabling
label | e74bcd77-dc0d-5cf1-afe3-db7b8b4b06c8 |  | note | Inspection / Test Method: TNZ M/20; TNZ M/7; TNZ M/24
label | 221908ed-c7e7-581a-8a56-a42cd18a02ca |  | note | Acceptance Criteria: Engineer to review and approve electrical certificates
label | 8f4c195d-c51d-5c11-bf85-23755f7dfc4d |  | note | Record Documents: NTC / Site instruction
label | 0f0551f7-1093-5ef0-b2c9-09dfb01038e2 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 800.5 - Completed road lights
label | ea3cd879-5ba5-5742-aa52-efc8319bd72e |  | note | Detail of Activity: Visual inspection of completed road lighting installations
label | ebff7bef-c557-507f-81af-c46711563289 |  | note | Action: H
label | f9a76750-9c6b-5ef4-9fe7-487fd4b5bc4d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All lighting columns and associated cabling
label | 4cde75dd-e626-5de6-8d34-175cc6536218 |  | note | Inspection / Test Method: TNZ M/20; TNZ M/7; TNZ M/24
label | 7a8bcd01-c498-5c2b-9a17-96ed837db086 |  | note | Acceptance Criteria: Compliance with project specifications
label | 023798ea-f394-5dac-9514-a281fba70c30 |  | note | Record Documents: NTC / Site instruction
label | 147e3e5c-928a-561c-ba0b-cba7fcc8f14f |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | Final Sign Off
label | 6e8d1a70-5a79-53f1-ae8d-d90a151016c7 |  | note | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 6c129784-46c2-5b98-b67a-21ec8e7f4770 |  | textbox | Contractor's Rep Name:
text | 5173b9b1-1ee2-5555-9aa6-a65c49dd0b4e |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Sign Off
checklist-sectioned |  |  | checklist | ITP 1 Soil Nails, Tecco Mesh | itp |  |  |  | Yes | ITP 001 Soil Nails, Tecco Mesh | 5b5019e2-7036-4f64-a63a-151d80e2ac35
checkpoint-group |  |  | section | A. Preliminary
checkpoint-status |  |  | checkpoint | A1
label | 3d8c4811-04ed-5a20-92e1-4cc680e17486 |  | note | Description - Ensure design is complete and "Issued For Construction" (IFC) drawings are accurate, complete, and approved by GSI Engineer & GSI Management
label | 5c9890dd-dec1-5a9c-9cc3-7d965fce4bc1 |  | note | Frequency - Before issue to site
label | f06c9909-ca78-5d5d-b6f4-9eb514af3598 |  | note | Specification Reference - Job pack
label | def81680-4d75-5462-8e10-ce44494c6134 |  | note | Responsible Person - GSI Project Manager
label | 165c89fa-3b73-55fc-8081-a218ac28a54b |  | note | Record Required - Job Pack
label | 3b589ec7-8cc8-5153-b546-7ecdac45e17e |  | note | Notes - Hard copies on site
checkpoint-status |  |  | checkpoint | A2
label | 4666c0e8-b33d-5824-85b1-ec402128f856 |  | note | Description - Confirm all material intended for use in the works comply with design specification, have been ordered, and will be available on site when required
label | b4b57ee4-5609-54ef-bb7c-ce171dd22081 |  | note | Frequency - Before site establishment
label | ab0f6f2a-05fb-5fb4-acd4-c0a9f809ec78 |  | note | Specification Reference - Job pack
label | 0bf463e3-8b8a-5e2a-a901-cbe359395a59 |  | note | Responsible Person - GSI Construction Manager / Site Engineer
label | 9c09d2fe-e21d-5820-ad0f-b709a796e8d3 |  | note | Record Required - Job pack
checkpoint-status |  |  | checkpoint | A3
label | ee4eac65-c589-5124-a37a-6d81dc755e46 |  | note | Description - Load test schedule, test locations and test sheets are reviewed and approved by GSI Engineer and Engineer to contract
label | 4e30b588-7aed-545f-91a3-d063d85bcabc |  | note | Frequency - Prior to start on site
label | 162a911d-164b-521b-b55f-21f5e0dc07c1 |  | note | Specification Reference - NZTA 2226 TS
label | c490f156-9b79-5062-b467-28ad4da2e8eb |  | note | Responsible Person - GSI Project Engineer
label | a2183d75-efbd-5294-aa22-d91a6fb99dbd |  | note | Record Required - Engineer to contract agreement in writing
label | b07f0274-4410-5ee2-b3d8-641bd19d2918 |  | note | Notes - Hard copy of standard held on site
checkpoint-status |  |  | checkpoint | A4
label | 07eea100-805a-5242-a3a8-afedb042648c |  | note | Description - Ensure load testing equipment is calibrated and calibration certificates supplied to Engineer to contract for review
label | 24983f4e-e5f9-5e26-88d9-74adb9b4f165 |  | note | Frequency - Prior to start on site
label | 9d4d3ebe-1116-5c35-bf3e-042203588642 |  | note | Specification Reference - NZTA 2226 TS
label | c804cc26-ab8f-54da-9dfb-09f02d9969ef |  | note | Responsible Person - GSI Project Engineer
label | 70d9d6d9-a118-5c62-8042-60f2f8b9dca9 |  | note | Record Required - Engineer to contract receipt
label | 7bc0c235-f47b-5820-88b4-5f2fa5b8b253 |  | note | Notes - Hard copy of standard held on site
checkpoint-status |  |  | checkpoint | A5
label | a5b40a30-2552-55bd-aea5-446f906f83e3 |  | note | Description - Slope assessment completed and reviewed by GSI Project Manager
label | 37c28c80-68e3-5c95-8dc0-2d2a1c629d09 |  | note | Frequency - Prior to start on site
label | 4cf6c7b0-e870-51b8-a8cc-49e755305775 |  | note | Specification Reference - N/A
label | 7d69a8b9-1f64-5336-8fc9-d2e83e79faf7 |  | note | Responsible Person - GSI Project Engineer
label | c131830a-c6fb-537b-b199-a226918e7d8a |  | note | Record Required - Slope assessment checksheet
label | 15a13f25-da91-5141-97d5-5ad703120c72 |  | note | Notes - Hard copy on site
checkpoint-status |  |  | checkpoint | A6
label | 2e0a8c58-b1e4-5e84-bd8a-2f2b856c501e |  | note | Description - Confirm site extents agreed with Engineer and aligns with general intent of the design
label | 77563eaf-ca6d-5b8f-bf76-ffc466b1d89b |  | note | Frequency - Prior to start on site
label | 6fa3e0fd-1ece-5b1c-b7d9-25492e11f86d |  | note | Specification Reference - N/A
label | 542dbd59-d1e0-5b9e-9dfc-cf4938939a7f |  | note | Responsible Person - GSI Project Engineer
label | 3e219578-c57a-5214-a275-c0609b209f59 |  | note | Record Required - Written confirmation to design team
checkpoint-status |  |  | checkpoint | A7
label | fe96e120-d250-5efc-8759-12799604208c |  | note | Description - Sacrificial test nail number and locations agreed and approved by GSI PDE/BBO/Earthtec
label | 79bc3aad-ff3f-5091-84da-0519c66511cb |  | note | Frequency - Prior to start on site
label | 9e9a62e8-b604-56b6-aced-c348bddacaf4 |  | note | Specification Reference - N/A
label | 417866bd-4f89-52fc-b2f7-802238982d1f |  | note | Responsible Person - GSI Project Manager
label | 63905eeb-dbe1-5b8d-bcf8-a02bcc3e8032 |  | note | Record Required - Engineer to contract agreement in writing
checkpoint-status |  |  | checkpoint | A8
label | 0828ce18-45c9-525c-9ec1-e82afbe3ce2d |  | note | Description - Pre-construction sign off - Subcontract agreement signed, TMP approved, all staff and subcontractors inducted, CMP reveiwed and in place
label | 1a75b3a5-81cf-5641-8076-635560a75eda |  | note | Frequency - Prior to start on site
label | 93c36bf4-3c8f-57a2-ad43-9942b91d2a97 |  | note | Specification Reference - N/A
label | 226328fb-e319-5ce1-8b7c-d348b52d9f9d |  | note | Responsible Person - GSI General Manager
label | 8613e892-ebf8-5781-be1a-2279cddfc0cf |  | note | Record Required - Job pack signed
label | 53c33663-960e-5c50-8471-82128a2a0d0b |  | note | Notes - Document reviewed and signed off by site staff and required management .
checkpoint-status |  |  | checkpoint | A9
label | 315b2885-95fc-5f61-b7b0-1a8f22797688 |  | note | Description - Permit to Work/Excavate - Confirm location and extent of works, notify service authorities, locate underground services where applicable, notify Worksafe of notifiable works
label | 885ab3ad-b824-51ae-9dbe-5b9116e6681f |  | note | Frequency - Before commencing work
label | 6258881b-710c-5076-9894-b5ec9302dab2 |  | note | Specification Reference - N/A
label | 7ddb3d54-ccab-579b-832a-08200563819c |  | note | Responsible Person - GSI Project Manager
label | 92c1c8a3-2bd6-5f6e-bee5-20e6164996bd |  | note | Record Required - Job pack signed
checkpoint-status |  |  | checkpoint | A10
label | 570b0f7b-c781-5357-bf6f-e36900fa7513 |  | note | Description - Plant - Ensure plant suitable for use on site and calibration up to date. Rig capable of reaching all anchor locations, sufficient wire rope and rig anchoring equipment
label | 36c9a8d4-c8b9-522d-bfe5-77d267e3fcaf |  | note | Frequency - Before commencing work
label | f3fef188-6236-5339-8f15-6894c24f68b3 |  | note | Specification Reference - N/A
label | 491e2740-f9a5-540b-a168-5239b169d078 |  | note | Responsible Person - Site supervisor
label | 05660d7f-042a-58b8-8088-b3b6fd337ede |  | note | Record Required - Job pack signed
checkpoint-status |  |  | checkpoint | A11 - HOLD POINT - NO WORK TO COMMENCE UNLESS THESE ARE COMPLETE
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | B. Site Establishment
checkpoint-status |  |  | checkpoint | B1
label | e198b58b-6625-5529-9c9b-0b1368986616 |  | note | Description - Check Erosion & Sediment Controls are in place and adequate
label | 7cec7037-a0bf-551f-93aa-944ebba246b3 |  | note | Frequency - Before commencing work
label | 5b52c200-5ef9-5024-9f0e-8bf65078bc87 |  | note | Specification Reference - Job pack
label | 99984e75-dcb4-5f9a-8b2a-8d0d7b1a0342 |  | note | Responsible Person - Site supervisor
label | 0abe51da-dc8b-5b2f-9044-a11e7958a24e |  | note | Record Required - Photos / drawings
label | 17323064-eaf8-512c-9f20-6456cb21b54c |  | note | Notes - Visual inspection
checkpoint-status |  |  | checkpoint | B2
label | e2a80bde-2a2b-541f-be8b-82267524d0df |  | note | Description - Establish lay down area and suitable protection of property (ply wood, tarps etc) and bunding around grout unit/refuelling areas as required
label | d6892db9-afd5-52a5-8721-0576479fb741 |  | note | Frequency - At time of establishment
label | 7f437f8d-fe02-58fa-9bae-ed6730676a1a |  | note | Specification Reference - N/A
label | 5c104c10-79f5-5d67-a998-6c4cf0aa2b96 |  | note | Responsible Person - Site Supervisor
label | 9265d100-3442-53b0-a6d4-95438cf6030a |  | note | Record Required - Photos. Note on Pre-Start form
label | 8eccbba7-87a3-5dec-b81f-81765a46aadd |  | note | Notes - Consider delivery of materials
checkpoint-status |  |  | checkpoint | B3
label | 59b3808a-019c-5378-9d7e-acba74727a22 |  | note | Description - Check slope stability, area is safe to work in for slope remediation crews (WAH permit in place)
label | 2b09c06c-ea44-590f-8517-bde5939312b8 |  | note | Frequency - Daily prior to accessing lower levels
label | 0d9cce01-9d1e-5d84-9c97-fa5fc6e4f072 |  | note | Specification Reference - N/A
label | e8358958-4d82-54f9-9c01-68aab7f85168 |  | note | Responsible Person - Site Supervisor
label | 4bfe6ee1-e8de-55ec-8748-b71062a77a4c |  | note | Record Required - Photos. Note on Pre-Start form
label | 40cad07a-a9d1-5e97-a55f-5cedecc6f68e |  | note | Notes - Install offset pegs
checkpoint-status |  |  | checkpoint | B4
label | 62986edd-81dd-59ef-bfd8-2e71c679323b |  | note | Description - Notify tenants / land users below work site of intended work and likely duration
label | 5d1cac1c-b2d8-58b9-a7b8-78db3e134da0 |  | note | Frequency - At time of establishment
label | 4d1c7e25-2f38-5252-ae22-a1fa900f0f89 |  | note | Specification Reference - N/A
label | a6c23093-c809-5c46-84b8-d9f8bf76ae27 |  | note | Responsible Person - Site Supervisor
label | 8104cfbb-7694-5bb9-abd9-7363d8eb2ba1 |  | note | Record Required - Note on Pre-Start form
label | 72135d2c-de06-53eb-b2a6-23d97b50b0f7 |  | note | Notes - Door knock and face to face discussion required.
checkpoint-status |  |  | checkpoint | B5
label | 45be4b31-223d-5aa7-a650-26a2a08c44e3 |  | note | Description - Completed installation of approved rope access anchor points as required
label | d851ff8a-c3bd-5bc9-b7cd-cd3a33caf94a |  | note | Frequency - At time of establishment
label | ba51f6e6-7e20-5aec-aa81-3dc624c58976 |  | note | Specification Reference - N/A
label | 641bc047-2b96-5b6e-975a-8bed632e6389 |  | note | Responsible Person - Site supervisor
label | 2496ae25-569b-5b98-8820-879e078aa76d |  | note | Record Required - Photos. Note on Pre-Start form
checkpoint-status |  |  | checkpoint | B6
label | 3ccd53cb-b673-535f-921e-068c5106e0ea |  | note | Description - Before You Dig completed. Identify and mark location of any existing services including probing, potholing and survey as required
label | b7df25d5-4195-58b0-b268-e89ec43dd1c0 |  | note | Frequency - At time of establishment
label | b79a28e1-1b83-52c5-9704-65253df62a67 |  | note | Specification Reference - N/A
label | 2d028262-5ea5-556d-926e-daa9d731802d |  | note | Responsible Person - Project Engineer and Site supervisor
label | 6c7841a5-81bc-5127-9c7c-a145b78fbf8e |  | note | Record Required - Written confirmation to client
label | ae81328c-eb5a-57a2-87e4-c74e699f0a93 |  | note | Notes - Install offset pegs, mark on drawings
checkpoint-status |  |  | checkpoint | B7
label | bd582b1c-bd86-5c30-89e5-dbce8edceb5a |  | note | Description - Site markout - GSI Engineer, GSI PDE and Engineer to contract to agree on nail and test nail set out plan
label | 2e4c7d70-d705-56ab-87f1-1ac3d09636fa |  | note | Frequency - Before commencing work
label | 29cae155-3959-54f2-96fc-67eddd9590b0 |  | note | Specification Reference - N/A
label | 8ca1e1ea-ac10-5ddb-bc83-fa15da99cd38 |  | note | Responsible Person - GSI Project Engineer & GSI PDE
label | 795405e1-7a61-5c65-9868-ebad4e2ac758 |  | note | Record Required - Engineer to contract agreement in writing
label | 79e67db1-dec0-5e8e-869b-98fb11dbcb76 |  | note | Notes - Install offset pegs, mark on drawings
checkpoint-status |  |  | checkpoint | B8 - HOLD POINT - NO WORK TO COMMENCE UNLESS THESE ARE COMPLETE
label | 6afc9dbd-fe1e-5c81-bc7a-0fed23043422 |  | note | Frequency - Before commencing work
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | C. Excavations/Slope trimming
checkpoint-status |  |  | checkpoint | C1
label | 98967a5a-99c0-59b4-a25e-803ee33706ea |  | note | Description - Valid Permit to Dig/SWMS
label | 989cfaec-a589-5306-836b-4a5920780cc6 |  | note | Frequency - Daily
label | 4e1f9fee-672e-57f2-b221-f6824da4bbc6 |  | note | Specification Reference - N/A
label | 711cd985-6798-5b3a-ace5-fefbab5dccba |  | note | Responsible Person - Project Engineer
label | fb1eb18b-1dfd-55f9-b173-5652428cfc61 |  | note | Record Required - Permit signed and valid
checkpoint-status |  |  | checkpoint | C2
label | 9d0c59b5-890b-5096-9c18-3304597da58c |  | note | Description - Pre-start check on equipment
label | b8628cbf-4041-5771-86f1-8810ea59ccac |  | note | Frequency - Daily
label | 58411aba-ade8-51b4-9424-3622b5e2e033 |  | note | Specification Reference - N/A
label | 1e608be8-92c7-5082-990f-bd705edf455a |  | note | Responsible Person - Site Supervisor
label | 7f49b992-9277-53fc-b59f-03c7e7e44ed1 |  | note | Record Required - Daily Equipment Pre-start form completed by operator
checkpoint-status |  |  | checkpoint | C3
label | fc70b82c-3006-53e6-9202-1269cba3945f |  | note | Description - Safety audit completed when trimming/scaling slope - not to impact people or property below slope
label | 92512543-e761-5fda-ac97-0d02d150fd69 |  | note | Frequency - Daily
label | 00945786-de53-5037-988e-7db6dc3ce0e3 |  | note | Specification Reference - N/A
label | 484caaf5-72ff-5e12-be1d-8ea4b87c0379 |  | note | Responsible Person - Site Supervisor
label | 5099f240-d0b8-54cd-b402-1ec9c6a19d15 |  | note | Record Required - Aduit results sent to PM
checkpoint-status |  |  | checkpoint | C4
label | 8beb3d18-5e0d-5a82-a85c-ba2e7468f3a2 |  | note | Description - Levels and extents of devegatation and slope trimming marked and checked
label | a9dbe529-d0b6-56fe-ab3a-85411d27ce16 |  | note | Frequency - Prior to excavating
label | 9afd1f7c-aa0d-5c9f-a0de-0000c70542cf |  | note | Specification Reference - Drawings
label | 0d1a8c48-8346-54d5-b9d0-5ad5a67a5955 |  | note | Responsible Person - Project engineer and site supervisor
label | 0719b0db-5e51-5788-9e94-320e8623711a |  | note | Record Required - Photo
checkpoint-status |  |  | checkpoint | C5
label | b15705eb-6696-5f13-b85b-7d190360505e |  | note | Description - GSI Engineer / GSI PM to sign off on completed vegatation and slope trimming
label | 10cd1a7c-49f5-5f91-9dc1-16ef129a53e3 |  | note | Frequency - At completion of earthworks
label | 90171439-5774-520d-b299-034a14cb538f |  | note | Specification Reference - N/A
label | e885a79d-41f4-5620-8484-ce8635a04b8a |  | note | Responsible Person - GSI PDE and GSI PM
label | a012bb0f-29b5-5673-9501-8ccfb1a80d5d |  | note | Record Required - Confirm with client
checkpoint-status |  |  | checkpoint | C6 - HOLD POINT - NO WORK TO COMMENCE UNLESS THESE ARE COMPLETE
label | d9ace11d-67d7-5c1a-8a3b-d3116da93955 |  | note | Description -
label | 6dfc836b-83f9-5ec3-bd5a-93af538f7680 |  | note | Frequency - Before commencing work
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | D. Soil Nails and Grouting
checkpoint-status |  |  | checkpoint | D1
label | 439531d7-640d-5568-a6ce-4b213cb777c7 |  | note | Description - Pre-start check on equipment
label | 40121578-328e-573a-a02a-3cfe873573af |  | note | Frequency - Daily
label | 136c8da7-3250-5846-ab52-04b990423c64 |  | note | Specification Reference - N/A
label | 40827b49-27d2-5460-a0a4-4157b3d1e7b4 |  | note | Responsible Person - Site Supervisor
label | d09f18ee-ad20-5367-908c-90e6fef1d7f3 |  | note | Record Required - Daily Equipment Pre-start form completed by operator
checkpoint-status |  |  | checkpoint | D2
label | fc90221f-914c-549b-8bc6-78bb8c49ea27 |  | note | Description - Valid Permit to Dig/SWMS
label | e8483b1c-0c47-5efa-8bfb-a60fafebe958 |  | note | Frequency - Daily
label | c2e6caa6-19bc-563c-979b-2e86f54bd709 |  | note | Specification Reference - N/A
label | 6fca2922-9195-55ae-98f2-00e927d7989a |  | note | Responsible Person - Site Supervisor
label | eddab83b-fa19-5016-bd18-6a6545412f5c |  | note | Record Required - Permit signed by operator and Site Superivisor and valid
checkpoint-status |  |  | checkpoint | D3
label | f23edb12-8107-5b7a-9632-bba14f03f938 |  | note | Description - Confirm cement/water mix ratio including number bags cement needed versus water capacity of mixer
label | 03dbc10c-584e-5387-8922-68cf098a5e0a |  | note | Frequency - Prior to drilling
label | 20667dca-143e-5f8f-9244-6f7e6e55aac3 |  | note | Specification Reference - Confirm ratio / IFC drawings / Specification
label | cd81edca-4597-5e7c-9e41-3497df3cc9d6 |  | note | Responsible Person - Site Supervisor
label | 52bd05ba-c456-5752-9b3c-c6d7b62eede0 |  | note | Record Required - Grout log
label | 31cb1057-07a2-534a-ab3c-7869e00e8f50 |  | note | Notes - Engineer to contract to confirm in writing
checkpoint-status |  |  | checkpoint | D4
label | e8f6d1e8-9c3c-5838-9824-ffd8fd664ce8 |  | note | Description - Drill methodology approved by GSI PDE/GSI Engineer and Engineer to contract confirmed following review of proof test results
label | ee0016f4-d045-5e69-b3cc-9de109359a29 |  | note | Frequency - Prior to production nail installation
label | cac33379-57dd-51ef-9ac7-70fab931d066 |  | note | Specification Reference - Engineer to contract
label | 61aec9f0-731f-5dcd-8369-a081efce9e1b |  | note | Responsible Person - Project Engineer
label | b261520f-527a-566c-994a-2ef0b16d21f9 |  | note | Record Required - Written confirmation designer
label | a96414de-ee4c-5f1d-8134-fad7a3879443 |  | note | Notes - Engineer to contract to confirm in writing
checkpoint-status |  |  | checkpoint | D5 - HOLD POINT - Ensure soil nail setout is in accordance with the drawings and approved by BBO/Earthtec
label | d2922641-74cd-5a3a-bb5d-ec60627b13b9 |  | note | Description -
label | b12d6092-96df-5193-9ad4-24101a344e74 |  | note | Frequency - Prior to drilling
label | e371f9fc-dfd0-5d51-8db0-8d43bfbe8b05 |  | note | Specification Reference - Drawings
label | 48b7ad66-6ecc-52f2-a17b-113693128238 |  | note | Responsible Person - Project Manager / GSI PDE
label | 52879c01-9460-5218-bf31-fa193be24f4a |  | note | Record Required - Written confirmation to client
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | D6
label | ba122c82-a17f-529d-9f09-fca0ffcd76cd |  | note | Description - Confirm drill depth, angle and orientation of soil nails - per IFC drawings
label | cf162305-7855-539b-adb5-27511cdf007b |  | note | Frequency - Each nail
label | 24e7fe3e-b2fc-5505-b858-42a2a93cb549 |  | note | Specification Reference - Drawings
label | 4bee7256-7077-5b47-9598-cb68e127e5da |  | note | Responsible Person - Site Supervisor
label | cc0a76e0-830b-5031-ba0d-cbca725442fe |  | note | Record Required - Drill log
label | 1306fe9d-f803-5710-b007-829b8735e3e9 |  | note | Notes - Mark on as-built drawings
checkpoint-status |  |  | checkpoint | D7
label | 3ba50fb7-fd68-5f82-bdbd-59f4a2dab70c |  | note | Description - Ensure grout sample cubes or cylinders are available and ready for use (4 per day of grouting)
label | 26da913f-7e59-5927-851a-124c78931ea6 |  | note | Frequency - Prior to drilling
label | dd46255b-cf78-533a-ba79-3509ab728d8d |  | note | Specification Reference - GSI grout sampling procedure
label | 60d2a693-0f11-5c24-9d10-245ae4923cb6 |  | note | Responsible Person - Site Supervisor
label | 0f70b77e-18b8-572b-8c87-1d4423076b8f |  | note | Record Required - Grout log
label | 6faf50c0-5abe-55d8-ba37-94066eba9ccd |  | note | Notes - All GSI staff to review updated Grout Samplign SOP prior to start of works
checkpoint-status |  |  | checkpoint | D8
label | 807420fd-ee5d-50db-8b62-fa6bb8029b47 |  | note | Description -
label | bef5f35b-f437-545c-babf-e567ec7dad90 |  | note | • Install sacrifical anchors: 1 x 9m anchor and 1 x 6m anchor with Grouted Bond Length of 4m ONLY.
label | c2e4b572-c1ae-56aa-953f-f2511124233a |  | note | • Anchors to be installed with 16mm tremmie line, with centralizers every 1.5m. Locations to be confirmed by GSI Engineer and Engineer to contract (per B7).
label | 4babbb61-7ede-5e38-b823-61d530b2ee8d |  | note | Frequency - During drilling
label | fa25d7f3-552c-5377-ac20-65b5bab65f0b |  | note | Specification Reference - NZTA 2226 TS (181220)
label | 1a6e8836-45e3-5059-90b3-a9cf49e29907 |  | note | Responsible Person - Project Engineer
label | 252dba0a-5d6c-5e38-b485-8bbe2686d623 |  | note | Record Required - Photo, Test result sheet
label | 43837594-6228-5930-b64e-02cec43a09cb |  | note | Notes - Results to be reviewed by GSI Engineer and Engineer to contract
checkpoint-status |  |  | checkpoint | D9
label | 3d7bbd7f-d822-5f66-b309-3c0e071f6215 |  | note | Description -
label | 6e9306dc-2670-5646-8089-54d5e1cb0ea5 |  | note | • Drill logs (fully) complete, including hole ID, diameter and length of hole drilled - as well as geology i.e. colour, type (rock/soil), moisture (i.e. dry, slightly moist, wet).
label | ee324c17-ac15-5d30-b897-cade31d367f0 |  | note | • Ensure to stipulate which holes are to be used for test anchors - based on B7.
label | 5d7cb462-7941-57d7-9a66-dffe08271a5b |  | note | Frequency - During drilling
label | ca031dee-3c35-56eb-b491-894478417c94 |  | note | Specification Reference - NZTA 2226 TS (181220)
label | 3221cf2c-9aa7-5d32-ba5f-d7bb742da7b5 |  | note | Responsible Person - Project Engineer
label | b3b4ec29-a377-573b-8996-ce6d2c1dda8b |  | note | Record Required - Photo, Test result sheet
label | faf3051b-69ad-56b4-a9a6-ed0bdba0530f |  | note | Notes - Results to be reviewed by GSI Engineer and Engineer to contract
checkpoint-status |  |  | checkpoint | D10
label | 0ac00bfd-d82f-5a1e-a674-2b506946ddc2 |  | note | Description -
label | 7114af73-bdb8-5a36-98fa-82915e0d6fd4 |  | note | • Anchor testing to follow NZTA 2226 TS test schedule at min 7 days after install. For both 6m and 9m anchors.
label | d27a2e79-90d4-56d9-99db-8a36490e5188 |  | note | • Pullout Creep test per NZTA 2226 TS test schedule i.e. 60 min creep test at 110kN. If pullout has not occurred at 150kN, proceed to next load. Do not exceed 250kN.
label | 25c1f1cf-d159-5f82-8552-e12d71aab25c |  | note | Frequency - During drilling
label | fba5ca8c-9f20-5427-82d9-b06ad3dbfe7b |  | note | Specification Reference - NZTA 2226 TS (181220)
label | 796a47fe-f391-5d2b-b337-7027aea20ad2 |  | note | Responsible Person - Project Engineer
label | e143bbcc-4a49-5682-a3a7-86b6869acfba |  | note | Record Required - Photo, Test result sheet
label | c6d4b71d-d1ec-5233-94bd-8f3a5d9200ed |  | note | Notes - Results to be reviewed by GSI Engineer and Engineer to contract
checkpoint-status |  |  | checkpoint | D11 - HOLD POINT - NO WORK TO COMMENCE UNTIL SACRIFICAL TEST RESULTS REVIEWED BY ENGINEER
label | 9dedf0ea-307c-5c9a-99c4-8050a8bee2ab |  | note | Frequency - Before commencing work
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | D12
label | fc1779d7-0c6a-52a9-aa53-446fba444740 |  | note | Description -
label | c36cb396-5d57-5a60-aa4b-0e115ea802b8 |  | note | • Install 78 no Anchors, in a top down methodology, 18 x 9m RB32 (top row) Anchors, 58 x 6m RB32 anchors. Anchors to be installed with 16mm tremmie line, with centralizers every 1.5m.
label | e61d8401-e6b3-5554-8d08-eb7b95c4e1ed |  | note | • Suitability testing on 5% of installed nails to 150% design working load. 2 x 9m and 3 x 6m suitability anchors to have 1m temporary debonded length for suitability testing. Locations to be confirmed by GSI Engineer and Engineer to contract (per B7).
label | e757857d-9d91-57d2-b740-b5545fbc200c |  | note | Frequency - During drilling
label | 0f578feb-af04-5042-b34b-cd8803a876f6 |  | note | Specification Reference - Drawings/NZTA 2226 TS
label | b3509b6c-2aca-56ed-b2d7-b8b6ee3e6430 |  | note | Responsible Person - Project Engineer
label | 0657aac0-3637-5197-93c7-4bbf029814ee |  | note | Record Required - Photo, Test result sheet
label | 220f8d25-965a-56bd-b3d1-7e44ac582514 |  | note | Notes - Results to be reviewed by GSI Engineer and Engineer to contract
checkpoint-status |  |  | checkpoint | D13 - HOLD POINT - NO WORK TO COMMENCE UNTIL SUITABILITY TEST RESULTS REVIEWED BY ENGINEER
label | 981c00e3-8ccb-5988-983f-b69b004023f2 |  | note | Frequency - Before commencing work
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | D14
label | 66745cca-efe7-51d6-aad9-02ac5bd7976e |  | note | Description - Acceptance testing on 25% of installed nails to 100% design working load
label | aabc67da-4f6a-52a3-8de5-61af785db0cb |  | note | Frequency - After Drilling
label | 0662f40a-924e-5d0b-b3cd-a8ffe847fc03 |  | note | Specification Reference - NZTA 2226 TS (181220)
label | fa417ff9-2592-591b-b054-45fd05f38804 |  | note | Responsible Person - Project Engineer
label | 460ef751-a6db-55ae-a952-02ab35b35841 |  | note | Record Required - Photo, Test result sheet
label | 96c1e4f8-e951-53de-9afa-235208178d1d |  | note | Notes - Results to be reviewed by Engineer to the contract and GSI Engineer
checkpoint-status |  |  | checkpoint | D15
label | b7729005-51fb-5acf-a3f0-36c4a3629d83 |  | note | Description -
label | 74c384fb-2df0-5662-ac47-9ae324df2515 |  | note | • Grout sampling to follow relevant SOP i.e. tamping down in 1/3 lifts, and stored in supplied chilly bin after initial 12 hours of curing.
label | 35baadbc-3ffe-5e49-b14e-f93d353d1371 |  | note | • Temperature in chilly bin is to remain as constant as practicable (avoid uneccesarily opening lid).
label | 0784cf6e-c571-55f4-8a1a-9568587d2746 |  | note | Frequency - During drilling
label | 44d0401b-47c7-51b5-9205-21146915329a |  | note | Specification Reference - GSI grout sampling procedures
label | 836d4700-70a9-5609-b456-eac3f7f94fdb |  | note | Responsible Person - Site Supervisor
label | 7f58091b-4c1a-5f78-8149-b735df5086d7 |  | note | Record Required - Grout log
checkpoint-status |  |  | checkpoint | D16
label | d99fd268-c3ec-51e2-89b9-38ad8448c8da |  | note | Description - Grout samples to be delivered to the lab within 2 days of sampling, where practicable, or as soon as possible thereafter.
label | 0e74fe93-8c63-54f9-9426-362b6fb0c4f8 |  | note | Frequency - During drilling
label | cb26d576-c68c-5356-9283-52e9d6915e8a |  | note | Specification Reference - GSI grout sampling procedures
label | 8e54ba1b-0777-5b99-98a4-33d32d204807 |  | note | Responsible Person - Site Supervisor
label | 8f8bd2be-fcd1-53ca-8b21-e625d0d0ff28 |  | note | Record Required - Grout log
checkpoint-status |  |  | checkpoint | D17
label | dfb4c9e9-df78-55c9-baed-a7c8bd1284aa |  | note | Description - Grout mud balance testing - per relevant SOP
label | 76f043f5-b469-5243-8539-47da9ae281cb |  | note | Frequency - Per hour during grouting session
label | 09497b3a-ae2d-5deb-a49a-4a8ca10eaa46 |  | note | Specification Reference - GSI grout sampling procedures
label | b23fc429-d606-5bda-b2fe-a2131d47f3f0 |  | note | Responsible Person - Site Supervisor
label | 2982e4cf-a074-58b0-b788-686bdaf022d2 |  | note | Record Required - Grout log
checkpoint-status |  |  | checkpoint | D18
label | 6d83f16d-67bd-5248-aa3c-508745c1d4fe |  | note | Description -
label | b76b2bd1-36d2-5a05-8e8c-a87967183522 |  | note | • Grout logs i.e. number of grout bags per hole and total.
label | 939e53d3-8ad2-5d50-8d39-556b0a16b671 |  | note | • Volumes to be recorded for each sol nail anchor.
label | 49721a37-e8d7-58cf-96cb-935d011cc962 |  | note | • Ensure nails are appropriately numbered with relevant ID.
label | 05e6a6f4-24d1-5673-9298-31596a74b014 |  | note | Frequency - Each grout session
label | ddc65f9f-6bef-5821-a1f3-eb80f7d1207c |  | note | Specification Reference - N/A
label | 5c9752b3-6de6-5dab-9b4d-1820c5d5ec6c |  | note | Responsible Person - Batching Operator and Project Engineer
label | 16c0e621-769f-55da-8f01-1de7344f1ace |  | note | Record Required - Grout log
checkpoint-status |  |  | checkpoint | D19
label | 6df3c366-56db-5b6d-8b76-9ad63f316244 |  | note | Description -
label | 7c31d42b-7b9f-5715-a3a3-027ddbeffca3 |  | note | • Grout top-up complete.
label | e9ecdc72-1fde-5fd0-9c92-b86d47509407 |  | note | • Where necessary, dry pack grout behind plates where grout not in contact with plate. Ensure temporary debonded sections of acceptance test nails are topped up.
label | 4c850b17-cc09-5fa9-a1db-607eefd0f06a |  | note | • Update grout logs with those test nails that have been topped up.
label | 64c6b9f3-2e54-53f6-ab0e-2df9594a30ef |  | note | Frequency - Each grout session
label | 3e2502d4-c58e-52a5-8a61-664bf536e2e5 |  | note | Specification Reference - N/A
label | 812055cb-be43-5ea1-ba40-2d1d69c2f8a6 |  | note | Responsible Person - Site Supervisor
label | 2837aa4b-fe6e-554d-ada1-5d713271b016 |  | note | Record Required - Photo
checkpoint-status |  |  | checkpoint | D20
label | 689b715d-67c1-569b-a3be-9f375c852e69 |  | note | Description - Soil nail sacrifical, suitability and acceptance tests complete (as above) - per IFC drawings/NZTA 2226 specification
label | d662ae97-3d6f-5d94-8d15-1092a88d8232 |  | note | Frequency - 2 nails, 5% of nails (or min. 5), and 25% of nails
label | 7b605741-ea4b-5740-b5a8-e2215ded930c |  | note | Specification Reference - Drawings
label | 156408c2-7d3e-5813-864e-54f4a1f34f1e |  | note | Responsible Person - Project Engineer
label | 853dba1a-9e74-5013-b533-30a3c52708e4 |  | note | Record Required - Test result sheets
checkpoint-status |  |  | checkpoint | D21 - HOLD POINT - NO WORK TO COMMENCE UNLESS THESE ARE COMPLETE
label | b0cba6bb-64db-5539-a6b4-adf59acb5ed0 |  | note | Frequency - Before commencing work
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | E. TECCO Mesh, Spider Plate and Bio Coir
checkpoint-status |  |  | checkpoint | E1
label | 855c5326-a150-587c-92f3-3b64308e4632 |  | note | Description - Confirm extents of mesh to be installed
label | 557e599d-07c6-5688-8788-8b69966d649f |  | note | Frequency - Prior to commencement
label | 34b838c8-e4a1-5d2c-bd82-8458f871148d |  | note | Specification Reference - Drawing
label | 16f96d4f-ab5e-5ec0-b7f6-3658abf492c0 |  | note | Responsible Person - GSI Project Engineer and Site Supervisor
label | 0ff474db-f706-583e-b980-025a8c7f3195 |  | note | Record Required - Email to PM
checkpoint-status |  |  | checkpoint | E2
label | 350daa1d-56ea-57b8-a092-4426b0ba46d8 |  | note | Description - Confirm that depressions for spike plates have been SUITABLY excavated around nail collars.
label | 1b0da37a-18f6-5ac5-ae20-3e24040465a0 |  | note | Frequency - Daily
label | f060d073-c6de-5d38-b188-830ad3fa31fc |  | note | Specification Reference - Manufacturers Guidelines
label | c153af35-6ddb-509f-ade0-07495fc3a570 |  | note | Responsible Person - Site Supervisor
label | ecedb5d0-02fe-596d-95c9-c81baf472b47 |  | note | Record Required - Photo
checkpoint-status |  |  | checkpoint | E3
label | 119a1d48-2c45-54ed-a030-742063300825 |  | note | Description - TECCO mesh installed as per manufacturers guidelines. Ensure wire ropes are installed on top and bottom edges of mesh and tensioned appropriately.
label | d85782cd-4637-5da7-8b64-5aeafd0b98bf |  | note | Frequency - Daily
label | c11482cc-2d18-5712-af09-835206b76170 |  | note | Specification Reference - Manufacturers Guidelines
label | 9b202403-a3ce-5214-9b64-e41d8f211450 |  | note | Responsible Person - Site Supervisor
label | d4bd0ef4-12dc-5ce0-9fcf-53055f4be123 |  | note | Record Required - Photo
checkpoint-status |  |  | checkpoint | E4
label | 1acbe70d-627d-5a33-bcf4-28389a3df5cc |  | note | Description - Cirtex Bio-Core installed as per manufacturers guidelines.
label | 2d71ed22-7d0c-5d8b-a13e-caf7fe8c6716 |  | note | Frequency - Daily
label | 04ddf039-4161-5b32-8a17-fadadab45d4c |  | note | Specification Reference - Manufacturers Guidelines
label | e8a15502-04a4-5044-82db-d7a4038e3f0b |  | note | Responsible Person - Site Supervisor
label | c678eae0-497d-597c-95f7-c3c98bbfe1ba |  | note | Record Required - Photo
checkpoint-status |  |  | checkpoint | E5 - HOLD POINT - NO WORK TO COMMENCE UNLESS THESE ARE COMPLETE
label | abcbb195-1aba-5521-bb4e-441cb1fce7c8 |  | note | Frequency - Before commencing work
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | G. Sign-Off and QA deliverables
checkpoint-status |  |  | checkpoint | G1
label | afada3a6-2dfc-5152-b40b-d8fa7d760f79 |  | note | Description - Drill and Grout logs
label | b801f456-be8e-5c27-914c-e31c796edddd |  | note | Frequency - Daily
label | f656f84d-0dbe-5c0f-b168-f80f3e7b006d |  | note | Specification Reference - N/A
label | 89a058cb-d1c7-55fc-ace4-13fba5ca7792 |  | note | Responsible Person - Site Supervisor
label | 6bd07228-9ce4-5106-bcb3-eeb11dbaa11f |  | note | Record Required - Drill and grout logs
checkpoint-status |  |  | checkpoint | G2
label | 176a0fb7-a321-5f1f-847d-0696f3426dab |  | note | Description - Sacrificial, Suitability and Acceptance test nails
label | 93daf170-9c36-53ff-bc5a-756cb1438d22 |  | note | Frequency - Per IFC drawings/NZTA 2226 TS
label | 60d7b814-f9f1-5a91-b168-511372e60e90 |  | note | Specification Reference - NZTA 2226 TS
label | b7e3a355-07a0-5d89-b917-2b8b1e225e64 |  | note | Responsible Person - Project Engineer
label | d6f5b3d7-efba-52cd-8b08-bcb08aca9b08 |  | note | Record Required - Test log sheets
checkpoint-status |  |  | checkpoint | G3
label | c560aa75-18e0-5669-86e4-2b223cff839c |  | note | Description - Grout crushing test
label | 879bf081-2cd3-5530-9451-ab1f17c511df |  | note | Frequency - 7, 14 and 28 day results
label | 8c7bea49-79f6-57d5-9322-1ff753b9ce0c |  | note | Specification Reference - 30MPa at 28 days
label | 3fe6c3d0-ab63-5615-a64b-8638da5e5390 |  | note | Responsible Person - Project Engineer
label | d251ff6c-2996-57fe-85e9-8bd1d6889af3 |  | note | Record Required - Test reults
label | 7771478c-0f0d-577c-b283-97f4898c1021 |  | note | Notes - 7 and 14 day results are indicative only
checkpoint-status |  |  | checkpoint | G4
label | cd9b6e4f-9de9-5eab-b661-29b7d448b057 |  | note | Description - Photo records
label | 2ecaebd7-4dc6-53ce-8d2a-330b4847b098 |  | note | Frequency - Daily
label | bde4cabc-0723-5a5a-842f-e80a12ce683c |  | note | Specification Reference - N/A
label | 63e97cc6-1420-53e9-b6e2-4db33e74fa88 |  | note | Responsible Person - Site Supervisor and Project Engineer
label | e1ab8f78-1956-5f92-91d9-8cbd7a21247a |  | note | Record Required - Photos
checkpoint-status |  |  | checkpoint | G5
label | 60ad3e87-2dc4-52d2-8818-da7abfa4522d |  | note | Description - As-Built Drawings
label | c8d462a7-1232-5a0b-8d24-6d43959aaac7 |  | note | Frequency - Project Completion
label | a2c903d5-c707-5ce2-b67d-059df1f8d617 |  | note | Specification Reference - N/A
label | 6d29216c-a985-5f39-9ab8-11d8d82278a3 |  | note | Responsible Person - Project Engineer
label | 907ec05f-bad8-5ee1-8dcd-9ff4546ffa16 |  | note | Record Required - Updated Drawings
checkpoint-status |  |  | checkpoint | Close out - Sign and Date When Action Complete
text | 5b86867a-820e-556c-a029-d2638cf18acf |  | textbox | Project Engineer:
text | 3531138b-6c91-519b-9d29-6423c072a11c |  | textbox | Project Manager:
text | 35695c44-db54-52e7-aa31-e0315a69be21 |  | textbox | Client:
text | 4d38dc7e-5283-5af3-81b9-57d22c74a981 |  | textbox | Supervisor:
text | cffedcbf-547e-56d0-a91b-9e2cdb016e2e |  | textbox | Construction Manager:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | Concrete Pour |  |  |  |  | Yes | Concrete Pour Checklist | 60b22bd4-47bd-4b4b-be40-343cf0f2ff78
checkpoint-group |  |  | section | Preliminary
checkpoint-status |  |  | checkpoint | Pour Details Correct
text | cfdba30e-13f6-592e-bee6-fe53f0d01a9d |  | textbox | Pour Date
text | 954867f4-18b1-5c62-b599-5c065a5e95bb |  | textbox | Pour Time
checkpoint-group |  |  | section | Concrete Ordered
checkpoint-status |  |  | checkpoint | Concrete Order Correct
text | f5f65755-6b29-51c8-aa0a-edd9587ca225 |  | textbox | Mix Type
text | 36658943-55cd-5aa1-9ecf-b880557cc840 |  | textbox | Volume
text | 4d567397-1982-5fce-a2c6-934302a5fd46 |  | textbox | Slump
text | 2a0b8d8d-6153-5304-9acd-f2087ce7dd56 |  | textbox | Additives
checkpoint-group |  |  | section | Concrete Received
checkpoint-status |  |  | checkpoint | Delivery docket received (upload photos)
checkpoint-status |  |  | checkpoint | Correct mix received
checkpoint-status |  |  | checkpoint | Slump test each truck (+- 30mm of design)
checkpoint-status |  |  | checkpoint | Concrete cylinders taken (1no tested at 7 days, 3no tested at 28 days)
checkpoint-group |  |  | section | Concrete Placement
checkpoint-status |  |  | checkpoint | Concrete Placement Correct
button | bc29fd44-6a91-5786-82bf-2e21bf59d1d5 | DataPoint is missing 'button' values | button | Placement method
checkpoint-status |  |  | checkpoint | Placed in layers
checkpoint-status |  |  | checkpoint | Concrete adequately vibrated
checkpoint-status |  |  | checkpoint | Placed to correct level
button | ff20de4f-fac7-5390-bb72-8537d80b5b0a | DataPoint is missing 'button' values | button | Surface finish
checkpoint-status |  |  | checkpoint | Rugasol applied to Type B joints
checklist-sectioned |  |  | checklist | ITP 014 Insitu Concrete Works | itp |  |  |  | Yes | ITP 014 Insitu Concrete Works | 80e991a8-a389-4bef-9887-07a4762eadee
checkpoint-group |  |  | section | Pre-construction
checkpoint-status |  |  | checkpoint | 1.1. Method Statement Development & Safety Analysis
label | 20be27d5-cbe0-5af2-a413-8496fffefa88 |  | note | Test Type: Document Review
label | 2ebdf9fb-1637-5c39-b995-abfcbd2057ce |  | note | Test Frequency: Prior to Construction
label | 3ee06a11-a0e8-5c2c-8d3f-6c7cc3a04543 |  | note | Conformance Criteria / Comments: Method Statement and JSEA Completed and signed by relevant authority
label | 609bcb92-0b9c-597b-bf2d-9ddda345e108 |  | note | QA Sheet Type: NA
label | 614ac37d-4639-5fe3-ac23-b528c8ae1bac |  | note | Hold/Witness Point or Review: HOLD
text | 5bc9ecac-f952-502e-acf0-68496ab48f30 |  | textbox | Site Initials - Project Engineer:
checkpoint-status |  |  | checkpoint | 1.2. Drawings and Specification
label | cc9fb383-87e9-5212-8c43-33b5cef581a3 |  | note | Test Type: Document Review
label | aef37759-4e0c-5be5-be98-75e728291296 |  | note | Test Frequency: Prior to construction
label | b14585a0-f5ce-5944-9abe-7a6163acc390 |  | note | Conformance Criteria / Comments: Drawings and Specification to be issued “For Construction”. Check InEight to ensure latest revision is used
label | cdf7dfb2-d6e4-5ad8-8112-610d8a022132 |  | note | QA Sheet Type: NA
label | 1193eaa5-dbd4-54e0-9e96-9ab07cddaf22 |  | note | Hold/Witness Point or Review: HOLD
text | 7ac747f7-94b3-5d49-95a4-93718df6eb70 |  | textbox | Site Initials - Project Engineer:
checkpoint-group |  |  | section | Temporary Works
checkpoint-status |  |  | checkpoint | 2.1. Complete Temporary works design and safety analysis
label | dd08b435-2fa1-5df4-a86b-46549a7b3b02 |  | note | Test Type: Document review
label | 386995a1-3b46-5eb5-9520-95781fc94ccf |  | note | Test Frequency: Prior to construction
label | af698729-b3f2-5b4b-b141-f45f90b7697a |  | note | Conformance Criteria / Comments: Drawings are completed and issued for construction. All elements signed off by Temporary works design engineer
label | ae585db5-63e0-55c9-b14e-3dde19fceae4 |  | note | QA Sheet Type: NA
label | ca650cd6-1768-5685-afd6-69361048abb4 |  | note | Hold/Witness Point or Review: HOLD
text | b3598d32-f2e6-5e3a-8087-2ba99ab9a01e |  | textbox | Site Initials - Project Engineer:
checkpoint-group |  |  | section | Material Acceptance
checkpoint-status |  |  | checkpoint | 3.1. Concrete
label | 1686b37c-de8e-5cec-ac12-91f2fa1eddcb |  | note | Test Type: Document review
label | afc47c35-aead-5ecc-b396-9dbdad26f1d1 |  | note | Test Frequency: Prior to construction
label | 820d7b26-eb87-5306-9eb9-3c8a74531eea |  | note | Conformance Criteria / Comments: Concrete Mix design meets requirements set out in specification:
label | dc389d33-d3e0-5244-abf7-dac9687f0f3c |  | note | In accordance with NZS 3109
label | 824daed3-8546-528f-b8e4-47a593bfbec4 |  | note | 40MPa, 19mm Aggregate
label | 023dc04d-ff94-5fc5-8e1c-de7780d79041 |  | note | Containing a shrinkage-compensating admixture
label | c92403d3-5a6c-5fab-a6f4-45cee4c93fa4 |  | note | Water/cement ratio no greater than 0.38
label | 91edf295-f407-5648-bec0-1d8ac68a4696 |  | note | QA Sheet Type: Mix Design
label | bcf2e326-5413-59cc-ae5e-1ee4912495b7 |  | note | Hold/Witness Point or Review: Review
text | edbd0cf2-c0bf-50e7-b23f-59d0adcf4582 |  | textbox | Site Initials - Project Engineer:
checkpoint-status |  |  | checkpoint | 3.2. Concrete
label | e027e74d-b031-52ab-b93c-60e12c1cc0f4 |  | note | Test Type: Document review
label | ee9c1e9d-fe9e-5755-a066-b702fb063fe5 |  | note | Test Frequency: Prior to construction
label | debf8b0f-f166-5662-b55e-13e2ab826119 |  | note | Conformance Criteria / Comments: BBO Concrete Checklist completed and submitted to Engineer for approval 5 days prior to intended production
label | d22ffcc6-d36c-5a8e-912d-922d30c124b5 |  | note | QA Sheet Type: BBO Checklist
label | fa1e3b6d-9ea1-51fc-89cc-1084459240f3 |  | note | Hold/Witness Point or Review: HOLD
text | 7474f583-5ec3-50ad-807b-487acc027dd4 |  | textbox | Site Initials - Project Engineer:
text | 093c025d-6b40-5a5e-9daf-ead11c482889 |  | textbox | Site Initials - BBO Engineer:
checkpoint-status |  |  | checkpoint | 3.3. Reinforcing
label | dc4977d6-4c27-5a32-acbe-2de1bbcbb879 |  | note | Test Type: Document review
label | cb28f4a9-08cc-5aec-8c6a-0a5ff98ea1bf |  | note | Test Frequency: Each batch of steel
label | 86a05be8-d23d-501f-951e-ba0430fcb47d |  | note | Conformance Criteria / Comments: Reinforcing to be Grade 500E manufactured using micro-alloyed process
label | d0b37599-374b-5ed6-97e9-e04eddb48470 |  | note | Reinforcing bending schedule checked against latest construction drawings.
label | 3cffdc41-0ec1-50a8-bd44-e7c88911ba8c |  | note | QA Sheet Type: Bending schedule
label | 1c9b0a29-99fb-52f2-b15d-5c3784baa21f |  | note | Hold/Witness Point or Review: Review
text | 8acf22ed-dba6-5fd8-9669-20b8acfc10fd |  | textbox | Site Initials - Project Engineer:
checkpoint-status |  |  | checkpoint | 3.4. Reinforcing
label | a3f01689-1860-589e-8293-6069754a44f8 |  | note | Test Type: Document review
label | 3acd973c-de66-56ac-9f01-6d6865081fab |  | note | Test Frequency: Each batch of steel
label | 4cc94dbf-757f-5df0-98e4-6fc390a2f030 |  | note | Conformance Criteria / Comments: Steel mill certificates and test reports provided to the engineer for each batch of reinforcement used.
label | 08ec83f6-16a5-5fb3-8d48-afbb9bd6c9a4 |  | note | QA Sheet Type: Mill certificate
label | fb2d8725-7e14-5094-924b-d669f895d604 |  | note | Hold/Witness Point or Review: Review
text | 9465495f-aedf-5837-8d0b-0ef5ef40d4e8 |  | textbox | Site Initials - Project Engineer:
text | 0c02d130-53f0-5551-8aa8-914a8feee469 |  | textbox | Site Initials - BBO Engineer:
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 4.1. Survey set out
label | 51ac15e0-1445-5057-a473-bfba3776133d |  | note | Test Type: Visual inspection
label | d8446182-3618-5893-aace-6b1c170c0536 |  | note | Test Frequency: All columns
label | e564bfbd-d9c9-5d77-975e-d6fd9e48933a |  | note | Conformance Criteria / Comments: Ensure all mark out including heights are completed prior to any works commencing. Surveyor to ensure latest data is being used.
label | 4ea85e5f-b27f-5a62-8858-14a534390b2a |  | note | QA Sheet Type: NA
label | bb205a6b-a275-580c-9597-3743e5469760 |  | note | Hold/Witness Point or Review: Witness
text | c55cf697-d51f-5835-aec8-d23e81e3ba16 |  | textbox | Site Initials - Project Engineer:
checkpoint-status |  |  | checkpoint | 4.2. Receipt of Reinforcement
label | 1ff7e8a6-9828-5012-8f01-5e66b1d1f80f |  | note | Test Type: Visual inspection
label | 70d668b0-69ec-5bbb-8b7f-0732b5373bb9 |  | note | Test Frequency: All deliveries
label | 797bad2a-75d3-5115-9387-8c0bd1a2fe08 |  | note | Conformance Criteria / Comments: Reinforcement checked against bending schedule. Bars correct length, size, shape, grade, and free of defects.
label | 2fb92ebb-d9b9-588f-96a1-930058ad35bd |  | note | QA Sheet Type: Photos / Dockets
label | 6ca0b45e-5424-5367-a1a7-b58e3575c67d |  | note | Hold/Witness Point or Review: Witness
text | 47d0e3a5-f340-5eb4-aede-cb8803293fed |  | textbox | Site Initials - Project Engineer:
checkpoint-status |  |  | checkpoint | 4.3. Pre-pour inspection
label | 44bde082-8c09-546f-a02d-dc3b916823f6 |  | note | Test Type: Inspection
label | af682c0f-9496-520b-a4af-249e00cfeccd |  | note | Test Frequency: Each pour
label | 8e89694a-c851-5799-b845-8a59b78b5c47 |  | note | Conformance Criteria / Comments: Pre-pour inspection checklist to be completed and signed prior to concrete pour commencing. At least 24 hours’ notice to be given to BBO Engineer for inspection
label | 4b7bb0eb-3674-5ef5-b34e-0a541b965539 |  | note | QA Sheet Type: Pre pour inspection checklist/ Photo Records
label | 5330627f-ef82-516f-a09a-85e9c0530fb2 |  | note | Hold/Witness Point or Review: HOLD
text | 41b4eeca-90f9-571b-a9cb-41f9e6287b06 |  | textbox | Site Initials - Project Engineer:
checkpoint-status |  |  | checkpoint | 4.4. Temporary works
label | bc45dc21-5b80-53f3-99b0-8891c86a14df |  | note | Test Type: Visual inspection
label | debd2c30-81e2-5f00-aec9-32c0b680ece4 |  | note | Test Frequency: All columns
label | e6e71831-f693-5705-b7ef-dc6e7470dc9c |  | note | Conformance Criteria / Comments: Temporary works to be installed as per design drawings. Permit to load to be issued by temporary works inspector prior to concrete pour
label | 395aad95-74ff-55d7-995c-906962e950bd |  | note | QA Sheet Type: Permit to load
label | 88bf3f9f-1b06-5df1-b2da-11bdc23802c0 |  | note | Hold/Witness Point or Review: HOLD
text | b66dca7e-9af0-547b-9a35-69d949690bae |  | textbox | Site Initials - Project Engineer:
checkpoint-status |  |  | checkpoint | 4.5. Concrete placement
label | 9bb2c699-2b6b-5741-ada6-166b0ff4dc7a |  | note | Test Type: Visual inspection
label | 9d437452-f723-576e-b905-f30820c55206 |  | note | Test Frequency: Each pour
label | 039a9ccc-883d-5d4a-8204-dd95279d9c10 |  | note | Conformance Criteria / Comments: Concrete pour checklist to be completed for each pour.
label | 73728d9a-0564-54d2-bd8f-f656a49a9e7c |  | note | QA Sheet Type: Concrete pour checklist/ Concrete dockets / Photo record
label | ec8390b3-31db-55ef-8090-8358ad95817d |  | note | Hold/Witness Point or Review: Witness
text | 33aed046-e85b-5179-bc64-903c5fcf7409 |  | textbox | Site Initials - Project Engineer:
checkpoint-status |  |  | checkpoint | 4.6. Concrete testing
label | 43364efc-fa30-5c3e-aa14-5882a88633b7 |  | note | Test Type: Laboratory Test
label | 50a12656-64fe-58aa-8d17-5cd90b25020e |  | note | Test Frequency: Each pour
label | 4418ea49-a171-5be6-97b4-d094a15c8d7b |  | note | Conformance Criteria / Comments: A minimum of 4 concrete cylinders taken and tested at the following intervals
label | 04c0b734-b748-5e0c-99c4-6c27d9a4c559 |  | note | 1 no 7 days
label | 8ec1f2f9-d51e-55a9-9b8e-8b2aaf6bebce |  | note | 3 no 28 days
label | 004c5fbe-653a-530a-b37f-ce39c7706230 |  | note | Test results show concrete meeting the required strength
label | 6b8c93a2-bded-5f64-ba5f-ace54689f24e |  | note | QA Sheet Type: Test report
label | 13324762-ecb9-5da3-bfff-4d3d8d9a3c9f |  | note | Hold/Witness Point or Review: Review
text | 0ba88ee6-4799-5c2f-8400-5d618c864551 |  | textbox | Site Initials - Project Engineer:
checkpoint-status |  |  | checkpoint | 4.7. Post-pour inspection
label | ca22f231-1f20-5268-90f7-7fac73bcf79e |  | note | Test Type: Visual inspection
label | e7ce5406-eb28-512d-b13e-a55203854cf5 |  | note | Test Frequency: Each pour
label | f3aae345-f0cb-53de-bee3-fbc199139a43 |  | note | Conformance Criteria / Comments: Post pour inspection undertaken following striking of shutters.
label | 88fe702b-69d1-5bac-afad-af5ec85b9bff |  | note | QA Sheet Type: Checksheet / Photo record
label | 8f37f555-a518-561e-9e8c-f784e3b88302 |  | note | Hold/Witness Point or Review: Hold
text | d6f13f6f-c6ee-57b5-8208-57b23ccb22ef |  | textbox | Site Initials - Project Engineer:
checklist-sectioned |  |  | checklist | ITP 700 Safety Barriers |  |  |  |  | Yes | ITP 700 Safety Barriers | aedc19ef-7257-4a85-b6f7-873c0829c574
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 700.1 - Seal Design
label | 172e9b64-f49a-5a16-9c0b-4bc7e1a35b83 |  | note | Detail of Activity: Seal design outling all design assumptions
label | 74790ce6-23cc-5f78-8c99-e544c5915f1d |  | note | Action: H
label | af84454f-0b8c-5778-a411-3a67b2a949de |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per seal application type
label | 352afb2c-4433-5afd-ae39-1a554ff21ecc |  | note | Inspection / Test Method: Review
label | c46ef4e1-3703-57a3-a391-2450159c8d0d |  | note | Acceptance Criteria: New Zealand Chip Sealing Handbook
label | c2a029bb-3e28-527a-923a-ba3f92c073cb |  | note | Record Documents: Seal design in contractor's site folder
label | f9354e33-bf45-5f35-8926-9985f166a876 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 700.2 - Leading and trailing treatments
label | b9748ebd-d830-52cd-a42a-a0ca82c796f9 |  | note | Detail of Activity: Start and End locations marked out and agreed with Engineer's rep.
label | 35a4e135-180a-52ed-a450-c16823702660 |  | note | Action: H
label | 06f33bb9-c213-5fa4-8382-7a6ff581601f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All barrier lengths
label | 5d265d26-82ea-5c2f-b863-51196543bcc0 |  | note | Inspection / Test Method: Visual Inspection
label | 99456980-46f6-5f18-8b30-43d1ba82871f |  | note | Acceptance Criteria: Positions in agreed marked out location
label | 3b31b1a0-314a-51a4-ab31-5899512af1cb |  | note | Record Documents: Check sheet
label | 27fcac0b-1d17-5bac-bab7-e04cfa387d46 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 700.3 - Leading and trailing treatments
label | e74f38bd-1cb2-547b-91f5-8ba8805ee0f4 |  | note | Detail of Activity: Correct type
label | 89c3bcb5-2b92-528d-8e23-57d34a9dfd52 |  | note | Action: H
label | 29a48c23-de80-5514-af5b-8e8ee2157784 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All barrier lengths
label | 02af03d3-fee0-5610-822c-fb59d91aa483 |  | note | Inspection / Test Method: Visual Inspection
label | 1c1043d2-0bb4-55c8-bac4-bd049312837a |  | note | Acceptance Criteria: Types as specified on drawings
label | 698fd9b1-1bf6-5e09-b2e4-c13c4356ecc4 |  | note | Record Documents: Check sheet
label | 18837e3a-63e7-5fcd-92c3-b3f21068b563 |  | note | Responsibility: Contractor
label | 6dee4655-b558-5d6a-b7ff-ca2dc3608aa4 |  | note | Comments: Engineer Rep to be aware of point where LON starts for terminal being used and account for it if possible.
checkpoint-group |  |  | section | Construction and Finishing (W-Section Barriers)
checkpoint-status |  |  | checkpoint | 700.4 - Ground conditions testing
label | 58a9efc4-6730-500f-b0e5-9d2a2c564f89 |  | note | Detail of Activity: Bearing strength of foundation depth
label | 4fafe110-9de3-5783-ae54-64945a14f3b6 |  | note | Action: H
label | abc48767-dfb9-5c5d-ab14-ca0de634d495 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 Scala every 20m - All leading and terminal ends Or as directed by the Engineer
label | 5ae0e366-3c99-5372-8e92-d17d64e602ad |  | note | Inspection / Test Method: NZS 4402.6.5.2
label | 09f3d11a-b3e9-5b54-8973-a9e97fcbd3ba |  | note | Acceptance Criteria: For design input
label | fa08c668-e3e8-55ac-8131-cb7745d63512 |  | note | Record Documents: Scalar test sheet / previous layer testing
label | cb8bf504-63c9-5206-8371-3e43f794fea2 |  | note | Responsibility: Contractor
label | 6cab19b3-78f8-5e8f-8810-6a8dc967ce84 |  | note | Comments: Test results provided to Eng.Rep. for analysis. BBo provides foundation size details
checkpoint-status |  |  | checkpoint | 700.5 - Pile position
label | 8b0a72cf-484f-5bfb-b702-c873a43b741e |  | note | Detail of Activity: Pile position
label | 05bd2741-3daf-5c5d-9f57-8bb443445555 |  | note | Action: M
label | 85440647-fc40-55c9-b5fe-444f837e200d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All piles
label | a1471183-967a-510a-8a3c-d3714a1c19e9 |  | note | Inspection / Test Method: Visual Inspection
label | 2e70a9de-148a-5b72-8162-d9a59cac9803 |  | note | Acceptance Criteria: Sufficient supporting slope outside the line of the posts in relation to pile size
label | 27b219af-5547-51f1-b9ee-bdbe8b51234f |  | note | Record Documents: Check sheet
label | c7af5ae6-446d-57b7-b11f-dfd0a7ae7cba |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 700.6 - Pile position
label | 358e6cc3-b7d4-51b3-b7a8-9cad3a79fbd4 |  | note | Detail of Activity: Pile spacing
label | a2811951-09d1-5c1a-a3e0-4cb51ad64296 |  | note | Action: M
label | 20e5e85f-2ff8-5f87-a53d-6986ab0da890 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All piles
label | 6f0531d8-88d6-5ae0-b23a-a5ecba5d222f |  | note | Inspection / Test Method: Visual Inspection
label | 5c94e6c7-5271-5ff6-a188-dcad705db326 |  | note | Acceptance Criteria: Post spacing's as per the Construction Drawings or NTCs
label | 40107751-fb40-5234-a11a-499ee7fd7e10 |  | note | Record Documents: Check sheet
label | f002727f-7900-5a97-bedd-1a3c552e8f3e |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 700.7 - Pile position
label | 40cc74d0-c937-51b6-a211-8af4836a7099 |  | note | Detail of Activity: Post orientation
label | 3a5f4378-8055-5a95-a675-983069851648 |  | note | Action: M
label | 767f2575-a384-5899-9f2d-e346d37b659e |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All piles
label | 0fc33158-9839-54f7-94ae-8f04498eecfc |  | note | Inspection / Test Method: Visual Inspection
label | c43e59c1-40f7-5a9e-abb5-397a4c592e5e |  | note | Acceptance Criteria: Slot orientation consistent for the entire length of the barrier
label | 982e7c9d-1343-575d-b715-1ca9b84107e6 |  | note | Record Documents: Check sheet
label | d8589922-937e-5190-8378-0a9a68fb06b0 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 700.8 - Installed WSB system
label | 93797d23-5d36-5e5e-ad5f-03f95a0a03ee |  | note | Detail of Activity: Barrier section at correct position as per manufacturer's installation manual
label | a84509b4-42d0-55f5-b458-2433e8c5f419 |  | note | Action: M
label | 12217efa-2d8b-5930-bab7-96b3962261fa |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All posts
label | aa9b723a-0fdd-590c-b292-70ad3c7f5771 |  | note | Inspection / Test Method: Visual Inspection
label | c9967d0a-abf3-5f46-9dfa-b78ff143f486 |  | note | Acceptance Criteria: Barrier is at correct height and secured correctly
label | 4f3e2f85-b910-517a-bd25-c33072593bc2 |  | note | Record Documents: Check sheet
label | 2f714339-a80c-5ffc-94fd-53d0c1767fdf |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 700.9 - Installed WSB system
label | e558ece8-11ff-51b8-b672-5278762b0fb5 |  | note | Detail of Activity: All cables are tensioned correctly
label | f0e09303-b9c5-52ff-9853-10a225e2b40f |  | note | Action: M
label | 68a3aede-c50e-5076-aec0-b673469e89ea |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All barrier lengths
label | e871b630-d2ae-5f21-b29d-ba5a27e9f728 |  | note | Inspection / Test Method: Visual Inspection
label | 1a265d05-c8fe-5fac-bb24-b7b5f1cb8932 |  | note | Acceptance Criteria: As per manufacturer's installation manual
label | 8d2b69d0-4267-5d8e-a8a9-58ca53b9b17c |  | note | Record Documents: Check sheet
label | 7b2f2663-1a53-5c88-b491-4d8923c8de56 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | Final Sign Off
label | 96278f54-4742-559e-aca8-df8cb6a261d0 |  | note | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | dc0e8bb8-05a8-5c8c-b3a3-3df8132ee770 |  | textbox | Contractor's Rep Name:
text | b600505e-8979-596a-a1c8-7833857e1e54 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Sign Off
checklist-sectioned |  |  | checklist | ITP 900 Fencing |  |  |  |  | Yes | ITP 900 Fencing | b82109c6-b63e-4007-bc54-77477759d05d
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 900.1 - Mark out works
label | 1f05a3f3-5294-5892-8b06-19292d78b1c7 |  | note | Detail of Activity: Set out fencing alignment and extents on site
label | fd4dce53-944b-5de7-827e-0be59786b4ae |  | note | Action: H
label | d31cc907-e717-5760-8420-d2f326d7a3ee |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All proposed fences
label | e4887286-ac5f-5808-a6fa-a9aaec69fd66 |  | note | Inspection / Test Method: Visual Inspection
label | 3b68d6e9-8bde-5b19-80d4-cb959eca3fad |  | note | Acceptance Criteria: N/A
label | 64dd88d6-1a86-516d-b977-0d3f728f2b95 |  | note | Record Documents: Contractor's site diary
label | e19a270d-707f-5ef8-9abc-a03b972f12a4 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 900.2 - Underground services
label | b0853207-a451-5054-ae71-5f8a066684f6 |  | note | Detail of Activity: Identify and positively locate services
label | d129ca21-7c82-5b51-832f-04ada18c95c9 |  | note | Action: H
label | 8eabf48a-e2e7-5103-950c-b8b8cf2dcf33 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All proposed fences
label | 96233167-e182-54ea-9190-418a082512eb |  | note | Inspection / Test Method: Hydro excavation
label | e45115bf-d625-5bfc-bf3c-171ccd5eb42c |  | note | Acceptance Criteria: N/A
label | a6dcd3f7-616b-5ee2-9488-f565e45a39f8 |  | note | Record Documents: Drawings
label | bf6f6262-eef9-51fb-95f4-5f9e407fdd58 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 900.3 - Confirm fencing Details
label | 8fe2860b-ba31-522f-b3e7-09dfcd79c7a8 |  | note | Detail of Activity: Contractor to confirm fencing details and nominated Supplier. Also confirm fencing meets the landowner agreement
label | 9b11681c-ec4e-522c-84c2-57202b3038ec |  | note | Action: H
label | bfbde98f-f9ed-5ca0-b1e4-d63f25227679 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Prior to commencing works
label | bfb898c8-0381-5c93-b13c-8e814784e9db |  | note | Inspection / Test Method: N/A
label | fd70be90-4188-5b0b-98b9-73efd2e7d1b3 |  | note | Acceptance Criteria: Engineer to review and approve proposed culvert supplier and methodology
label | 5505d5ab-ef82-5c8b-9771-f2f03d9629f7 |  | note | Record Documents: NTC / Site instruction
label | ce1dfd56-87d4-5741-8705-b87a98cf6dde |  | note | Responsibility: Contractor
label | eab8c98c-2f1c-5480-acc0-593887c5fb85 |  | note | Comments: This requirement confirms the Contractors fencing methodology and supply is in accordance with the performance specification and TNZ F4:1975
checkpoint-group |  |  | section | Construction and Finishing (W-Section Barriers)
checkpoint-status |  |  | checkpoint | 900.4 - Post and Wire Fence
label | b8c2ca66-8793-5787-b582-e9d1e7f8dc48 |  | note | Detail of Activity: Constructing new or relocating boundary fences
label | 0762db69-8ed5-57d5-bd6c-8a11b9ce807b |  | note | Action: H
label | 88f8fb0a-6942-5c12-843a-5420918dfbb6 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All proposed fences
label | 516ee099-ade9-5ddf-be85-9924de71582f |  | note | Inspection / Test Method:
label | f98a15c0-79f6-5b96-9ccf-9081317f32b4 |  | note | Acceptance Criteria: TNZ F4: 1975
label | 3fd4fd96-4dd1-5975-883f-af0f7a576776 |  | note | Record Documents: NTC / Site instruction
label | 7143635f-3ecd-546f-932d-e17ebea2ec94 |  | note | Responsibility: Contractor
label | 491c92db-0d1b-5837-9d71-fab293f79eb6 |  | note | Comments: As per the design drawings and specifications.
checkpoint-status |  |  | checkpoint | Final Sign Off
label | de9c180a-be54-56f5-9925-3e11f824f35c |  | note | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 2feafbe5-0e01-5524-b428-6d3c00ba86de |  | textbox | Contractor's Rep Name:
text | 91f1e236-51dd-5331-a811-86a2a159c034 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Sign Off
checklist-sectioned |  |  | checklist | ITP 600 Seal Coat |  |  |  |  | Yes | ITP 600 Seal Coat | d2ed3d76-1571-474b-97d1-d5c010cbec7d
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 600.1 - Seal Design
label | f6f22b8d-a8a3-5241-ad66-b2fcc774cb5e |  | note | Detail of Activity: Seal design outling all design assumptions
label | b22bc11a-19b2-5752-920e-bf9e7dd85de4 |  | note | Action: H
label | 2255e402-4f08-5b84-916b-aa52c6b00b85 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per seal application type
label | d96ec626-2c1c-599f-9b1d-292956ca987d |  | note | Inspection / Test Method: Review
label | ac6d6a05-d3db-57d7-bdb1-c64db48a3c79 |  | note | Acceptance Criteria: New Zealand Chip Sealing Handbook
label | 0e65fbfa-a947-54c0-bbb6-b696f2327bca |  | note | Record Documents: Seal design in contractor's site folder
label | 66265cfe-dc03-55e3-9ab5-ef13bb43c1ad |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 600.2 - Check raw materials
label | 231c8ba3-ac8d-5312-8e8d-adaf5971e4fe |  | note | Detail of Activity: Sealing Aggregates
label | 8ac92008-70f0-51c3-9624-d33da863417b |  | note | Action: M
label | 75e8a928-0871-5a94-b9f1-48d26e2c5071 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per source stockpile
label | 4af8d435-83b9-589c-8e8e-bcc513141bb1 |  | note | Inspection / Test Method: Source Properties
label | b504f263-7c8b-54cc-8c57-cfbf33a475ea |  | note | Acceptance Criteria: NZTA M06 / RNZ 9805:2009
label | 55f68749-f859-5c19-b325-c31ee384e753 |  | note | Record Documents: Certificate in contractor's site folder
label | b6714181-8a2a-5538-a929-04cb84444638 |  | note | Responsibility: Contractor
label | f0ceeef8-a853-54a3-b26e-dd7d82d7e6c7 |  | note | Comments: Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint-status |  |  | checkpoint | 600.3 - Check raw materials
label | 7ea9ec00-9b98-5622-b5e2-eb0cdbba748c |  | note | Detail of Activity: Sealing Aggregates
label | 0c835bb2-63b7-59b2-a44e-14794243fc4e |  | note | Action: M
label | 43d67298-12e1-5e72-a841-7395816983c6 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 1 per source stockpile
label | a22a5873-f04b-5dcb-beeb-b500c77aa0e9 |  | note | Inspection / Test Method: Production Properties
label | 11ca7bae-07c8-5f45-8baa-83adb8fb68a6 |  | note | Acceptance Criteria: NZTA M06 / RNZ 9805:2009
label | bc302fd0-47df-5c5a-a873-46ff1c72c5ec |  | note | Record Documents: Certificate in contractor's site folder
label | b56df955-324f-59a3-98b8-b60daa09a4c2 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 600.4 - Check raw materials
label | d601ace6-326a-51e0-82bb-f4d9eeadba43 |  | note | Detail of Activity: Adhesion Agents
label | dc82d462-1e8d-59a6-a68b-97d9b4003733 |  | note | Action: M
label | 966a3266-2073-526f-b26c-eb6cdf0d7d07 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Prior to use
label | 51b57b86-11e8-55e2-bda1-819f6ff5cade |  | note | Inspection / Test Method:
label | be934155-62da-5e47-8f0e-c828a01d5c41 |  | note | Acceptance Criteria: NZTA M06 / NZTA M13
label | 1f818f38-1a64-5482-9ba7-5f3e232f87dd |  | note | Record Documents: Certificate in contractor's site folder
label | 78d43449-9f88-5ae4-aeff-6269e19a8f11 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 600.5 - Check raw materials
label | e4b53032-7806-561f-a93a-3054fe0efa91 |  | note | Detail of Activity: Audit Samples
label | a910611a-2c38-5571-a0b9-14bb130a0237 |  | note | Action: M
label | 9d0c1cd7-c9c9-512e-96e6-04e79feae52e |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 20 kg per stockpile
label | 22c5ee2c-6568-5f25-8f97-44e8f0c4853d |  | note | Inspection / Test Method: TNZ M/20; TNZ M/7; TNZ M/24
label | 4f9d2e8a-cf90-557c-93ab-c091b7c4c91f |  | note | Acceptance Criteria: Stored in a sealed plastic bag in a covered environment
label | edb5f809-76f6-5a1b-a849-a6f3c5306529 |  | note | Record Documents: ITP
label | 3b775734-8614-511f-b2ae-8454d01caa3b |  | note | Responsibility: Contractor
label | 4911295f-61ca-5f73-ac82-db6cc9f9cdd6 |  | note | Comments: Retain for testing if required
checkpoint-status |  |  | checkpoint | 600.6 - Confirm sealing material
label | 1052f461-542e-56fd-8a8e-1a31607e4362 |  | note | Detail of Activity: Visual inspection of surface to be sealed
label | 76af3621-ad55-587a-aaff-93a3cc32aee7 |  | note | Action: W
label | 916b3dc5-5e60-52b0-bb4e-e396e8878867 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): per sealing schedule. 1 Lot = 1 day's production and < 1500m2
label | abfd355e-d114-537c-a552-2fe95fdfd7aa |  | note | Inspection / Test Method: TNZ M/20; TNZ M/7; TNZ M/24
label | 1019b0d9-f7a5-5700-b538-3012d6418837 |  | note | Acceptance Criteria: NZTA B02
label | b5baa08e-25a4-565f-b74e-e2cd0156f794 |  | note | Record Documents: Contractor's site diary
label | a8e0c7fa-309f-597c-9be8-5da14a2adc08 |  | note | Responsibility: Beca's Rep.
label | d5c961c8-60cb-5a19-a477-a25ed7e96f54 |  | note | Comments: The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing
checkpoint-status |  |  | checkpoint | 600.7 - Confirm sealing material
label | 9eae76e5-a928-5b87-ae79-81e34a6a7bf6 |  | note | Detail of Activity: Dry back Moisture Content
label | 76b62a9c-0fcc-5b52-adc0-fd66cd414079 |  | note | Action: H
label | 92ee2bb1-8d7b-5adf-a9c9-77b654a6fe85 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 9 per Lot
label | 988c9dc8-b884-5a19-bced-6c169258edba |  | note | Inspection / Test Method: NZS 4407.4.2.1
label | 6e69bc41-6d65-5a47-b355-3a9991daac9c |  | note | Acceptance Criteria: DOS ≤ 80% preferably ≤ 70%
label | a8ea13be-de28-5b68-a323-c95161c6fb46 |  | note | Record Documents: IANZ Report
label | 5e5d6858-36e7-5da3-a311-2e8b44bae7fe |  | note | Responsibility: Contractor
label | 4ec8678f-2623-587d-8857-065b5d495869 |  | note | Comments: DOS required for all pavement before surface is sealed.
checkpoint-group |  |  | section | Construction and Finishing
checkpoint-status |  |  | checkpoint | 600.8 - Sealing
label | e1d7a72b-abed-5eaf-8490-7023f0ed13a3 |  | note | Detail of Activity: Bitumen for Chip Sealing
label | e92607b3-25e8-585c-a5df-d07aafd23d19 |  | note | Action: M
label | c17dc6c7-1647-5111-833b-0e845299be70 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 2 samples per distributor
label | 80c91437-a4d2-5aae-8ebb-f13c936fc447 |  | note | Inspection / Test Method: Penetration grade testing
label | 651d7887-309f-529c-9f93-e6dcb2d17042 |  | note | Acceptance Criteria: NZTA M01 - Tables 1, 2, 3 and 5
label | 95a93ff2-25ed-570d-8962-88cb0baab140 |  | note | Record Documents: Certificate in contractor's site folder
label | 79c078c8-34a7-58fa-8951-2199b21a392c |  | note | Responsibility: Contractor
label | 5fb5822c-883b-5ffd-9dc6-3b74c10a688f |  | note | Comments: Sampling as per ASTM D140 or equivalent
checkpoint-status |  |  | checkpoint | 600.9 - Sealing
label | 964d8280-bcf8-5264-bc2c-4dd34f1c9e0a |  | note | Detail of Activity: Bitumen for Chip Sealing
label | 3c28e908-06a8-5f34-83cd-076136e1a880 |  | note | Action: M
label | 2c39ff83-b588-5ef3-9b8d-e0f3fda168c5 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2):
label | 07bb5a09-8609-50ae-910b-a513f62e137f |  | note | Inspection / Test Method: Durability
label | 9a19d1f7-b2ba-5ea1-9357-a71535fd8ef1 |  | note | Acceptance Criteria: NZTA M01 - Table 5
label | 21cfef28-a554-5cc7-81dc-96b42184f45e |  | note | Record Documents: Certificate in contractor's site folder
label | 27ac9ed1-e3fc-592d-b7a2-c05df6a6abe2 |  | note | Responsibility: Contractor
label | 6f1e00ef-b3d2-51d2-a5ad-9f9b2a3af7ca |  | note | Comments: Refer notes in clause 5 of NZTA M01
checkpoint-status |  |  | checkpoint | 600.10 - Sealing
label | a0d5906b-3c99-5142-b0b8-2f41e723cd9c |  | note | Detail of Activity: Spraying Temperature
label | 37a9835d-f7db-5cf8-894b-64053d958f14 |  | note | Action: W
label | 2e839fb9-b3ab-5e67-9e18-5645a48374b5 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Ongoing with non-going heat sensing gauge
label | 193f9e38-a3ee-5d86-a32b-4a1368231ea1 |  | note | Inspection / Test Method: Non-contact heat sensing gun
label | ec4e5880-e5e6-50ef-9d89-f6331829c972 |  | note | Acceptance Criteria: NZTA P03 - Table 2
label | 35cb9db9-a09f-5d24-a06d-1be965f8b6a8 |  | note | Record Documents: ITP
label | 1a7a7ac0-9742-5f65-8b88-5ff78fd8b836 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 600.11 - Sealing
label | 89bc4f0b-d2d0-503e-8a92-9444b8c65370 |  | note | Detail of Activity: Bitumen Application Rate
label | 313837bf-9d23-5ad3-a160-74a2e3c151fd |  | note | Action: W
label | 3c5bf4e0-11db-5d47-b7e7-15acfdbe9840 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Per Sprayer, per Site, per run
label | ce4ccecf-efb0-5da9-aaa5-c9504dde6caf |  | note | Inspection / Test Method: E/2 Certificate. Spray Sheets
label | 774359a5-7618-57e2-b267-b62b7f50f70a |  | note | Acceptance Criteria: Current E/2 Certificate per Spray Run of Seal Design
label | b6326b5e-4e44-5856-b3f8-cdfa0c17835a |  | note | Record Documents: E/2 Certificate. Spray Sheets
label | 627f0b1e-b152-5672-a60c-c1d8356e2b00 |  | note | Responsibility: Contractor
label | c7318c86-3598-5dff-9826-d8363dbf6a23 |  | note | Comments: Forms part of Quality Assurance requirements
checkpoint-status |  |  | checkpoint | Final Sign Off
label | e5b25ba2-90a5-5cf5-aceb-080e03e82435 |  | note | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 5b6abf96-4927-54d0-adf2-ff10a2caaca7 |  | textbox | Contractor's Rep Name:
text | b05caa8a-cce7-53b7-a757-96eae38985b5 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Sign Off
checklist-flat |  |  | checklist | Post Pour |  |  |  |  | Yes | Post Pour Checklist | e2ce5d4d-9d51-4463-b73a-a364229c23a1
checkpoint-status |  |  | checkpoint | Pour ready for Inspection
text | b8ad3abc-1400-5134-880c-a640be308a29 |  | textbox | Inspection Date
checkpoint-status |  |  | checkpoint | Formwork removed
checkpoint-status |  |  | checkpoint | Dimensionally correct
checkpoint-status |  |  | checkpoint | Correct level
checkpoint-status |  |  | checkpoint | Correct surface finish
checkpoint-status |  |  | checkpoint | Joints correct
checkpoint-status |  |  | checkpoint | Free from defects (upload photos if any)
checkpoint-status |  |  | checkpoint | Decfects made good
checklist-flat |  |  | checklist | ITP 100 General Contract |  |  |  |  | Yes | ITP 100 General Contract | e9627bc5-9530-4373-881e-9b9389e323cc
checkpoint-status |  |  | checkpoint | 100.1 - Physically located all utility locations
label | aca7c4e0-9474-45c1-be8c-c5b06d15bb67 |  | note | Detail of Activity: Permit to work around services (Gas, Power, Fibre, etc.)
label | fb2c8d47-d88c-40d4-8bd4-642471c092e1 |  | note | H
label | 1553c936-99bb-4b47-97bb-8cf2a582f794 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): as required per section of works
label | 298f37eb-f4ee-437e-b7ae-eaa413ec22d5 |  | note | Inspection / Test Method: Document Review
label | 36a5b0ca-ee96-4376-933c-2b601264db2c |  | note | Acceptance Criteria: All services physically located
label | 7205460a-2680-4841-ae94-9d767a3b566d |  | note | Record Documents: Permit attached or permit number noted
label | 991d92d8-49b6-474b-8a19-c7924a579fee |  | note | Responsibility: Contractor
label | 9af5a098-aa9f-4d09-866a-b210f05d7760 |  | note | Comments: Overhead power will be relocated by The Lines Company prior to possession of the Site for Separable Portion 2.
checkpoint-status |  |  | checkpoint | 100.2 - Contract Document Signed
label | fbc6177b-da00-406c-9f74-f9702512304e |  | note | Detail of Activity: Ensure Contract is signed
label | 99b645d4-72ca-4de8-88a1-4c85079da8bc |  | note | H
label | 6f9f260b-7a90-406b-8e54-3555e0d96358 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): at the Contract kickoff meeting
label | 1534ba34-34ca-47b8-b9e1-2ff6326f7946 |  | note | Inspection / Test Method: Document Issue
label | 09491af5-c658-4d4d-893b-3a4faf2d0350 |  | note | Acceptance Criteria: N/A
label | 83d85b64-d131-40cf-a6ec-3e21048632fd |  | note | Record Documents: Issued with a NTC
label | 62115bed-f1fb-43ed-b1ca-2397d9da8382 |  | note | Responsibility: Downer / BBO's Rep.
checkpoint-status |  |  | checkpoint | 100.3 - "For Construction" Drawings Issued
label | 7677fd20-3f71-48da-9109-2209cc1cb966 |  | note | Detail of Activity: Ensure "For Construction" drawings are issued
label | d733e5a6-2f01-4465-a37b-27a5bbd71bf0 |  | note | H
label | cbf6b132-6731-4379-beef-d749fdc84901 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): at the Contract kickoff meeting
label | 31149bd3-db7b-44b0-8dae-0aaf1abb9bbc |  | note | Inspection / Test Method: Document Issue
label | 1cbc11dd-5d37-4b95-9417-c23f3580085b |  | note | Acceptance Criteria: N/A
label | d2fdeeae-454c-4d3c-bd6b-532b31433b27 |  | note | Record Documents: Issued with a NTC
label | 1c183406-82c1-4334-b771-2cb02b294b01 |  | note | Responsibility: Downer/BBO's Rep.
checkpoint-status |  |  | checkpoint | 100.4 - Traffic Management Plan
label | 856ac5f5-f70a-481f-a446-ec7eb884439e |  | note | Detail of Activity: Ensure TMP is approved and check that the requirements are fully understood by the STMS
label | 657abb68-46b9-4b57-bed0-0bfad2c23247 |  | note | H
label | 44828d69-1adf-4720-83bb-8f33c8f37176 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): every morning and/or when the TMP changes
label | 7a6349b7-d4c4-4051-aea4-dc30652d8622 |  | note | Inspection / Test Method: Document and Physical works review
label | 988add93-a0ff-411c-be95-635a339bef39 |  | note | Acceptance Criteria: COPTTM
label | 1254c0c3-b631-4746-8e89-a076ef3bc9e3 |  | note | Record Documents: TMP from contractor
label | 24a3574f-e672-4103-8c08-c14990d75e77 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.5 - Design
label | afbed20c-bfdb-4e61-bc63-03266771bed7 |  | note | Detail of Activity: Ensure that Design is approved and Drawings are the latest version
label | 35024f2b-2555-4802-865f-f596fd7a8a39 |  | note | H
label | e9daced6-321d-410f-a1d6-e38596df6586 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Prior to commencement
label | d714d412-f515-46d7-81d7-8528910a5aa9 |  | note | Inspection / Test Method: TNZ M/20; TNZ M/7; TNZ M/24
label | 0fdf77ce-c8c5-42be-887b-a43d456041e3 |  | note | Acceptance Criteria:
label | 5972839a-bf34-4881-9a6e-cebc68452d41 |  | note | Record Documents: Check Drawing register
label | 20bcb06c-23e3-4784-8d54-f17fbba27076 |  | note | Responsibility: Contractor
label | 8ba16e5a-527c-4313-a4bb-982ce1f73748 |  | note | Comments: Drawing register maintained by BBO and e-mailed to contractor when revised drawings are issued
checkpoint-status |  |  | checkpoint | 100.6 - Approved Consents
label | 6d8d7184-8dab-4766-b121-4f1040c6a1c2 |  | note | Detail of Activity: Is a copy of approved consent(s) available on site
label | 7650d46a-164b-4d40-ba35-989b7101614a |  | note | H
label | 317c608a-8c67-4934-a6de-486d1c465f32 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Prior to commencement
label | f5ada3b9-4417-4dde-ac5d-5c2a5abe1d0c |  | note | Inspection / Test Method: Visual Inspection
label | c3b3076c-9ca4-4c55-bc21-606b50195048 |  | note | Acceptance Criteria:
label | dc9a6c41-19a2-4387-8d0f-eebf448ca33e |  | note | Record Documents: This ITP
label | d4bbe24b-684b-4c9d-9cb3-70a495b3128b |  | note | Responsibility: BBO's Rep.
checkpoint-status |  |  | checkpoint | 100.7 - Pre-start meeting
label | 25d956e2-5642-412b-9a8e-988dd96e5ff0 |  | note | Detail of Activity: Pre-start meeting to confirm work strategy and safety measures
label | 5af71579-f33f-491a-b7bb-f6f7b1d1c8c0 |  | note | H
label | 6e546a67-c704-4058-8d11-ca2f8519df34 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Before commencing work each day
label | 192f4fe4-e5b1-4449-919b-db7ed521bab3 |  | note | Inspection / Test Method: N/A
label | 194c36f3-5635-45de-8808-e044b03e72f9 |  | note | Acceptance Criteria: 100% attendance
label | b6a4be87-4ebb-4c92-9b11-82a1fdc34ca9 |  | note | Record Documents: Pre-start sign on register / site diary
label | 0e38f61d-5cf9-4db5-bd1e-7c0796def980 |  | note | Responsibility: BBO
checkpoint-status |  |  | checkpoint | 100.8 - Contractor's methodology
label | 10ea2228-1161-417d-9732-90e7a9a21179 |  | note | Detail of Activity: Approval of Contractor's methodology
label | 0a5293fa-0bb0-4951-b271-13fe6c444b85 |  | note | H
label | 050c6590-e1c8-4fda-b297-f83f002aac07 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Prior to commencement
label | 3e05347c-0282-48af-a62f-45d77d253878 |  | note | Inspection / Test Method: Document review
label | 43f0cfed-c521-4a8c-9f27-63eb15053719 |  | note | Acceptance Criteria: Methodology conforms with all relevant specifications
label | 742d92dc-b8aa-4bb5-a439-a4c113370796 |  | note | Record Documents: Methodology submitted via NTE
label | ab459fee-21a9-4707-8d1a-935586e4e004 |  | note | Responsibility: BBO's Rep.
label | acfc27f1-0bc8-4f55-98fb-852948015992 |  | note | Comments: Methodology submitted min. 7 working days and approval min. 3 working days prior to commencement
checkpoint-status |  |  | checkpoint | 100.9 - Laydown area / stockpile sites
label | 39591ddf-c3f2-4e21-9c3b-78efb2ad905e |  | note | Detail of Activity: Site inspection
label | 9ed00058-5e1a-4930-806a-6a13e607de07 |  | note | M
label | c5aaa159-ed6d-4b3c-8cf0-be24df577e58 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Prior to commencement
label | 91c44cff-8dad-41fd-8501-0a926b2ef80e |  | note | Inspection / Test Method: Visual Inspection
label | 194bd5c9-3def-4b65-b150-11e78f7e9a89 |  | note | Acceptance Criteria: Approved by NZTA
label | 5c796529-4a4f-4cd9-8cb0-86a54249ad54 |  | note | Record Documents: Request for approval (RFA) via NTE
label | dd4f97eb-1288-4edf-96c6-fa1feab60d15 |  | note | Responsibility: BBO's Rep.
label | 9eb9806a-125c-4713-a0b3-2c035f53b2e1 |  | note | Comments: RFA submitted min. 7 working days and approval min. 3 working days prior to commencement
checkpoint-status |  |  | checkpoint | 100.10 - Weather
label | c99bb2cd-b3b7-4a51-bb2f-1b0f3a474ae8 |  | note | Detail of Activity: Assessment of forecast
label | e3e554be-9eba-43e9-bbff-f2ebdcef8e3b |  | note | H
label | 836a02d0-8d42-4cfd-bb4b-d893f061abaa |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Daily prior to and during works
label | e632281a-206f-44d0-ae13-8711c9c97c7b |  | note | Inspection / Test Method: Check local and national weather forecast services
label | 2de8e2fb-0351-44b7-a050-e42e3ff27f03 |  | note | Acceptance Criteria: No imminent rain or adverse weather conditions. Consideration of wind and project location/environment
label | cd5b4752-13cc-48c6-8cd2-926a53a56ec5 |  | note | Record Documents: Contractor's site diary
label | 0d17b92f-c5fe-420a-93d6-6b4caa50dd84 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.11 - Environmental Protection
label | 51a2e7d4-a0e9-4ce5-8c62-75cf3ce7e343 |  | note | Detail of Activity: Site evaluation
label | 6fb75cdf-a819-4908-9a1f-ee2e87c97aec |  | note | M
label | 90596f1a-808b-488b-b07c-925b4162b85a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Prior to commencement
label | 308149b8-0d43-41ce-b6c1-e96313cc9bc5 |  | note | Inspection / Test Method: Inspection
label | fd58267b-3e16-4ee8-940a-0b08a5402eb8 |  | note | Acceptance Criteria: Supervisor assessment of conformance
label | 772f9090-5e94-427e-bf04-980a7c5e95c0 |  | note | Record Documents: Contractor's site diary
label | f80c524f-86e0-4f41-82d7-a3db63408260 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.12 - Precondition Survey
label | 6604c8f9-2fba-4c1b-a201-02b85f0bcfdf |  | note | Detail of Activity: Examine extent of the site
label | ad538454-4d30-432d-b8e8-90606c8c070e |  | note | M
label | 399c7776-2abe-413b-b288-9b8289b8dfe1 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Prior to commencement
label | 8bee615b-c2f1-4b62-84fb-36db2eabf992 |  | note | Inspection / Test Method: Inspection
label | 1af4695a-42cc-4649-8f78-77d5ca918a45 |  | note | Acceptance Criteria: Supervisor assessment of conformance
label | 11923d89-cf3f-4534-8b07-1925f6b8b669 |  | note | Record Documents: Contractor's site diary
label | 2096a8c9-392d-4455-b360-795b3f20e0d3 |  | note | Responsibility: Contractor
label | 2cbc39f5-b676-4708-b91b-b6ca052f3d06 |  | note | Comments: A precondition survey and report is to include, but is not limited to structures, road, rail, services, paved area, vegetation including weeds, fences, gates and farm paddocks condition generally within 10 metres of the extent of excavations, structural works or any laydown areas carried out by the Contractor on the Site and is specifically to include a survey of the State Highway 30 pavement, culverts and other structures and assets.
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | d91b2c2a-70a7-4397-8ce5-14ae69e2a66f |  | textbox | Contractor's Rep Name:
text | 26fb9391-dd14-417c-9e1a-5a76e8598882 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP 200 Earthworks |  |  |  |  | Yes | ITP 200 Earthworks | ee455941-155f-454c-b044-afa39abab2eb
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 200.1 - Earthworks methodology (prior to commencing site works)
label | a2019229-fd0b-54ab-a0c2-3b095241a987 |  | note | Detail of Activity: Prepare earthworks construction methodology suitable for site (eg access, working areas, proximity to slopes, traffic and other site hazards, construction stages proposed)
label | 33ce98ee-9498-517a-8a98-db374255e336 |  | note | Action: H
label | fcd9294c-26f6-5e73-8997-24929da90d9a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): NA
label | 7bf6b885-d8b9-56e7-a56a-d170a1468ae4 |  | note | Inspection / Test Method: NA
label | 41dca71b-086d-5fca-8c71-fd0d8945f2de |  | note | Acceptance Criteria: N/A
label | e8009757-6b2b-53d5-bda4-0f6f9bae5b88 |  | note | Record Documents: Methodology
label | fe8920e1-e913-576f-952b-a61c3d3e002c |  | note | Responsibility: Contractor
label | 1b54274d-6a31-5b08-af3a-1da4f6984a2b |  | note | Comments: Methodology to be provided to Engineer for review prior to commencing excavation on site.
checkpoint-status |  |  | checkpoint | 200.2 - Material suitability (prior to bringing fill to site)
label | 1ee0dc52-ccd1-5006-8b5a-d589aa6b24f4 |  | note | Detail of Activity: Confirm imported fill material suitability
label | 46c10731-2ee9-5c21-8ad5-eec5d09a6066 |  | note | Action: H
label | 28fc8909-488c-5fc0-8b57-d8a3235963c1 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): As per Drawings and Specification
label | 4c23e68c-fb01-5a2f-8058-659a269fc57a |  | note | Inspection / Test Method: As per Drawings and Specification
label | d5e8a002-a6d1-5061-b12f-ba7b76f6ee6a |  | note | Acceptance Criteria: As per Drawings and Specification
label | d4285396-9da1-5a36-8246-a65966248c66 |  | note | Record Documents: IANZ Report
label | d3adf7ba-7b1e-5787-a1ab-9a96fcf00795 |  | note | Responsibility: Contractor
label | 239d40c5-121f-5d39-8cc1-a56da9cb752d |  | note | Comments: Results to be provided to Engineers Geotechnical Representative for review prior to commencing excavation on site.
checkpoint-status |  |  | checkpoint | 200.3 - Mark out and approve
label | 97637b32-fa22-545e-bba6-b87a31be94d8 |  | note | Detail of Activity: Set out and mark up of extent of earthworks
label | 62e110c0-7a1a-5a94-b887-32e82c3b40a5 |  | note | Action: H
label | 49c4c26f-f0b9-587c-a182-637a810ec05e |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All earthworks areas
label | 6b851e48-9a9c-5832-a947-7c6411ea2a82 |  | note | Inspection / Test Method: Visual Inspection
label | 2bd7e54a-eb42-5cad-8fd3-13e2d042879f |  | note | Acceptance Criteria: N/A
label | 2f8c5e9c-498c-5d75-8e23-fa10e6d823a2 |  | note | Record Documents: Contractor's site diary
label | 76298d55-b7b8-57b3-8a51-26f0a21f370d |  | note | Responsibility: Contractor
label | 2f7035e4-1533-5e9c-9d5b-d2a3868a4f6b |  | note | Comments: Treatment area marked up jointly by Contractor and Eng.Rep. Approved by Designer
checkpoint-status |  |  | checkpoint | 200.4 - Excavation to formation level (prior to fill placement)
label | fb0da72f-5784-5dc7-b8b9-777e8f70a073 |  | note | Detail of Activity: Confirm excavations are suitably trimmed and benched.
label | feeb0524-16c4-5e26-9df4-61f7042833ab |  | note | Action: H
label | f25ec02a-eb5a-528a-946d-64a3154bc756 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All earthworks areas
label | ebd5fbd5-e801-58dc-b318-81302b63a4bb |  | note | Inspection / Test Method: TNZ F/1:1997
label | 06581174-538b-5836-9991-f5ce18c61971 |  | note | Acceptance Criteria: Formation materials in accordance with design assumptions.
label | 56be7626-e2c9-5b46-a46d-fb9102f5abe5 |  | note | Record Documents: Contractor's Site Diary
label | f61fbe40-d996-5370-9d6c-af637bc3115a |  | note | Responsibility: Contractor
label | 425a01c5-99ac-52e3-ae02-35bcc06fbf10 |  | note | Comments: Joint walkover with Contractor and Engineers Geotechnical Representative.
checkpoint-status |  |  | checkpoint | 200.5 - Suitability of excavation formation for compaction
label | fcb2e6cf-1949-5f61-a0b0-d22d0e2c61dd |  | note | Detail of Activity: Confirm the excavated soils are adequate to support construction plant and allow compaction of engineered fill.
label | a9e57b65-d415-5986-b929-3f6bedfbf488 |  | note | Action: H
label | 01f4216b-3b5d-53d5-8a77-175807bf7eb4 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Test on a on a 10m grid / maximum lineal distance between tests is 10m
label | f7b0de5c-939b-5cf1-aafc-6add1404a74d |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2) for cohesionless soil and shear vane test for cohesive soil.
label | 22d43e53-1a5a-5a53-ba87-c45859a8b935 |  | note | Acceptance Criteria: For approval by Engineer. Where forms Subgrade as per Pavement Design Drawings and ITP
label | 06e7bcc9-bcbc-5c70-8267-93bf2f3cb34e |  | note | Record Documents: Contractor's site diary
label | e9d1e198-49d3-559f-97cd-c6c82739058a |  | note | Responsibility: Contractor
label | 682e9d4d-eed3-5e7c-b6de-d60eeea71493 |  | note | Comments: Results to be provided to Engineers Geotechnical Representative for review prior to filling.
checkpoint-status |  |  | checkpoint | 200.6 - Suitability of excavation formation for compaction
label | 26678525-40d8-56b5-8db8-d85c23f1cdb7 |  | note | Detail of Activity: Confirm the excavated soils are adequate to support construction plant and allow compaction of engineered fill.
label | 726d94ae-950c-5326-be82-7334b306fe16 |  | note | Action: H
label | 57935868-85eb-50f7-8fbc-cab082109224 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All earthworks areas
label | e193012c-c5d2-5125-895a-4e7be37527fc |  | note | Inspection / Test Method: Proof roll or as agreed with Engineer
label | 9756f855-d900-5339-95cf-ef09626e768e |  | note | Acceptance Criteria: Formation soils do not heave and no significant visual deformation under wheel load
label | cc4034e3-528d-5178-9c15-7f3cf106d9de |  | note | Record Documents: Contractor's site diary
label | 8f2b3afa-96aa-5316-a1d9-3d78d192399c |  | note | Responsibility: Contractor
label | 713ba132-e4e1-5b5e-80f4-2eebabeec0f6 |  | note | Comments: Where the excavation formation soils are not adequate a working platform (SIL Layer) or undercut of unsuitable soils may be required.
checkpoint-status |  |  | checkpoint | 200.7 - Sediment Controls are in place for the particular section
label | 4a92d4d6-770c-53f3-87b4-2b53609bfd43 |  | note | Action: M
label | fd431dff-ee4e-5fa3-99c9-81fbccf3dcb9 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): once per section
label | 98240736-320d-559f-9157-1343a6294280 |  | note | Inspection / Test Method: Asbuilts completed
label | efc22aa5-284a-5821-a410-5737aa0925c5 |  | note | Acceptance Criteria: NA
label | 8cddb046-669b-5f1d-833a-ad5cb59b5c40 |  | note | Record Documents: Asbuilts
label | e4f2be19-303f-502f-8b24-e24ecb1a275f |  | note | Responsibility: Contractor
label | 99effcec-7775-5ac5-ab90-023a95446d0a |  | note | Comments: Forward asbuilts to Taranaki Regional Council
checkpoint-group |  |  | section | Construction and Finishing (Granular Fill)
checkpoint-status |  |  | checkpoint | 200.8 - Testing of placed material
label | 7fd9c795-13a8-5b13-8d44-e99a65da02f4 |  | note | Detail of Activity: Density of placed material
label | ef219dab-e9ca-506d-a6ab-8daf56aeb375 |  | note | Action: W
label | 3df95120-bfa0-5181-ba32-e3e9e367e770 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Unless otherwise in Specification or on Drawings, test every 300mm fill height on a 10m grid
label | 0ddbe9d5-6ebd-57a6-85bf-7fe4fbb995e3 |  | note | Inspection / Test Method: Nuclear Density Meter (NZS 4402:4.2.2 Heavy Compaction) or alternative agreed with Engineer
label | 1c659110-3c6a-5975-b4a1-a57f1db057f0 |  | note | Acceptance Criteria: Minimum field density of 90% of maximum dry density (MDD) obtained by static compaction for the first 500mm above thestripped and prepared ground surface.
label | 86fef790-5385-5769-8eb5-2c7758ea07b7 |  | note | Record Documents: IANZ Report & Contractors Report
label | 9abf811e-0a59-5ab6-a1e3-ba2faa1951eb |  | note | Responsibility: Contractor
label | f8256a39-6612-54fd-8138-2c7b2c95fcc7 |  | note | Comments: Test results to be provided to the Engineers Geotechnical Representative for review. Prelim tests in conjunction with IANZ Lab, compared to Contractors NDM Results, provided results are consistently within 1% of IANZ, acceptance for Contractor to Report NDM's thereafter on mutual agreement. On request by ER
checkpoint-status |  |  | checkpoint | 200.8.1 - Testing of placed material
label | 989e0f5a-c08b-5fe6-95f6-b3806d7a7799 |  | note | Detail of Activity: Density of placed material
label | 85fc7bed-bc8c-52d0-8ea3-d8182100ddcd |  | note | Action: W
label | b3a5395b-36a8-5cd5-8f22-fdef4bfdf1fe |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Unless otherwise in Specification or on Drawings, test every 300mm fill height on a 10m grid
label | e71c7886-9e19-5fcc-b056-6dd1cc5520bf |  | note | Inspection / Test Method: Nuclear Density Meter (NZS 4402:4.2.2 Heavy Compaction) or alternative agreed with Engineer
label | 35c16b95-da10-57e3-a8f9-3e7165c7f92f |  | note | Acceptance Criteria: Minimum field density of 98% of maximum dry density (MDD) obtained by vibrating compaction from 500mm above thestripped and prepared ground surface.
label | 4d98ba79-bb56-5744-925c-a4802693f615 |  | note | Record Documents: IANZ Report
label | a22f63b4-3479-5072-9d7b-62488df23fc8 |  | note | Responsibility: Contractor
label | 6262db92-d59a-5ba8-9dc0-fc8efce65872 |  | note | Comments: Test results to be provided to the Engineers Geotechnical Representative for review. Prelim tests in conjunction with IANZ Lab, compared to Contractors NDM Results, provided results are consistently within 1% of IANZ, acceptance for Contractor to Report NDM's thereafter on mutual agreement. On request by ER
checkpoint-status |  |  | checkpoint | 200.9 - Testing of placed material
label | 3f408cd4-e899-5223-8daf-f57b45b3ac19 |  | note | Detail of Activity: Density of placed material
label | 35717aad-6fcd-5a96-985f-0eef3c2f062b |  | note | Action: W
label | 7225e004-9486-5bab-930a-8c3d95e55076 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All Engineered Fill at 300mm lifts, 1 Test per 50m2/lift.
label | cf18b421-cfd8-572b-8c7c-b73fef9d0434 |  | note | Inspection / Test Method: Scala Penetrometer (NZS 4402.6.5.2) for cohesionless soil.
label | 87ded6b0-4e3f-5004-9a06-5a6a95435106 |  | note | Acceptance Criteria: Minimum CBR 10 as correlated against NDM's
label | be8c4f12-e83f-5615-ad62-bfece67d79d6 |  | note | Record Documents: Contractor's site diary
label | 07c5d4a5-306d-54dd-bead-6cf8fab5aa60 |  | note | Responsibility: Contractor
label | a5576cb5-fa14-5a79-8cc4-149a0bece8e2 |  | note | Comments: Correlated against NDM's by "in field testing" Witnessed by Engineers Representative and signed off in daily diary
checkpoint-status |  |  | checkpoint | 200.10. - Surface Finishing
label | 6675dab9-29c0-5542-893f-c91436431862 |  | note | Detail of Activity: Check geometry of the placed fill is in accordance with the design.
label | 693666be-7110-50ee-9cc2-0df29ab252b6 |  | note | Action: H
label | ee924d6b-f117-5dfc-a05f-3db845da3963 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All earthworks area
label | 810a53e8-7eb3-54af-96ec-117d59ce2dc5 |  | note | Inspection / Test Method: Survey, TNZ F/1 1997
label | 8ade1793-25b6-5095-b7ab-21701529fe9c |  | note | Acceptance Criteria: Geometry is in accordance with design drawings (fill surface and batter slope profile, removal of any excess fill). All points within 30mm of a 3m straight edge with no points above design level. No ponding of water.
label | d0afc307-d38e-518b-afb5-415d7ba101b8 |  | note | Record Documents: Survey, Stringline dips @5 points across carriageway @ 20m spacings
label | bf929d04-0b87-5965-8bd0-04df6f4d986b |  | note | Responsibility: Contractor
label | 24b44e23-f448-58d7-8ed4-fbd4e51fcd4e |  | note | Comments: Joint walkover between Contractor and Engineers Representative.
checkpoint-group |  |  | section | Construction and Finishing (GAP Hardfill)
checkpoint-status |  |  | checkpoint | 200.11 - Confirm GAP Hardfill Material
label | 09319e41-dbcd-5955-a3f6-8f005240e956 |  | note | Detail of Activity: Hardfill Aggregates
label | bf040272-b48b-5778-a907-9dfe3c92c9f2 |  | note | Action: M
label | 7e47276d-5a04-5b45-85a4-178f66955711 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): 3 per source stockpile
label | f67bff82-40c3-5f58-bbd6-6d1805685222 |  | note | Inspection / Test Method: PSD, Weathering Resistance, CBR, MDD OMC
label | 4a44ee33-8ebf-5847-b741-cebc194c4bda |  | note | Acceptance Criteria: NZTA Project Spec 2.2.10
label | 52b8cb92-b53e-5035-a024-b50e2de6c97a |  | note | Record Documents: Certificate in contractor's site folder
label | dc5e70e3-42d9-5c6e-9689-82e636670519 |  | note | Responsibility: Contractor
label | 04f95fc9-39d4-599b-8054-776060efdfb0 |  | note | Comments: Source properties: 1 test per source 4 weeks prior to use, repeat every 10,000m3 Production properties in stockpile: 0-1500m3 - 3 tests 1500-4000m3 - 4 tests >4000m3 1 test for every 1000m3
checkpoint-status |  |  | checkpoint | 200.12 - Confirm GAP Hardfill Material
label | 9601aa22-b253-5c85-bd9e-7e906d9f8dab |  | note | Detail of Activity: Density of placed material
label | a6e5a61e-8733-570c-8864-a72a96186e39 |  | note | Action: M
label | 9f7597e6-9e59-58a1-aa9d-2e2c4122351a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Unless otherwise in Specification or on Drawings, test every 300mm fill height on a 10m grid
label | 755dcba3-8378-5705-a7e2-8558004f439b |  | note | Inspection / Test Method: Nuclear Density Meter (NZS 4407:2015 4.3) or alternative agreed with Engineer
label | aa66bbd3-1cfc-5a48-ba7d-f93395dedb0d |  | note | Acceptance Criteria: Average field density of 92% of maximum dry density (MDD)with no readings below 90%.
label | 22f6fc5e-c915-5c77-a90c-28492c360788 |  | note | Record Documents: IANZ Report
label | 924d357b-4611-5dbc-8027-fbf495b22d8b |  | note | Responsibility: Contractor
label | f323e285-4be8-5319-b053-e2bb62a46c1a |  | note | Comments: By IANZ accredited lab
checkpoint-status |  |  | checkpoint | 200.13 - Surface Finishing
label | 02a2ee7f-3f2a-58ad-bddb-b0fad56ef8c6 |  | note | Detail of Activity: Check geometry of the placed fill is in accordance with the design.
label | 9563e2a7-c90d-59b1-9e62-d94353bbf7a4 |  | note | Action: H
label | 4887befc-a255-5018-97c6-652f440a417d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): All earthworks area
label | ef462e6e-3e3d-52e4-a7b4-35040c7e6d56 |  | note | Inspection / Test Method: Survey, Stringline dips @5 points across carriageway @ 20m spacings
label | a66d0513-c3ed-5d14-83fb-a8fed6eae394 |  | note | Acceptance Criteria: Geometry is in accordance with design drawings (fill surface and batter slope profile, removal of any excess fill). All points within 30mm of a 3m straight edge with no points above design level. No ponding of water.
label | 7b4b74ff-5ab7-5ce0-9dd1-de6c284847c1 |  | note | Record Documents: Stringline Report
label | 7edbed67-9c89-5e63-a2ad-1d0903c4281b |  | note | Responsibility: Contractor
label | 484e6e02-2bd9-5526-afbf-1291049bf328 |  | note | Comments: Joint walkover between Contractor and Engineers Representative.
checkpoint-group |  |  | section | Construction and Finishing (Surcharge)
checkpoint-status |  |  | checkpoint | 200.12 - Confirm Kopaki Cut to Waste Material
label | bb7bdb8f-caaf-55f8-b513-274f268f7ff2 |  | note | Detail of Activity: Density of placed material
label | 26a99f91-690b-547d-b438-9a66dea6d8dd |  | note | Action: M
label | cb1be31f-9712-5a64-8296-4a8dc0f68728 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Unless otherwise in Specification or on Drawings, test every 500mm fill height on a 10m grid
label | 679d38f7-1393-53f3-b1cb-7ea500f5ce08 |  | note | Inspection / Test Method: Nuclear Density Meter (NZS 4407:2015 4.3) or alternative agreed with Engineer
label | ed32e9fc-c53b-5b17-9408-d7e6607acd2c |  | note | Acceptance Criteria: Average field (wet) density recorded of each layer and used to calculate surcharge depth.
label | f04e25fe-c34a-53e3-94b8-727b2848661e |  | note | Record Documents: Contractors Report
label | 542ecfd3-a7eb-5104-b75b-bd9513c70355 |  | note | Responsibility: Contractor
label | ca8c45ad-484c-5348-9591-ca8ba810ea93 |  | note | Comments: By Contractor
checkpoint-status |  |  | checkpoint | 200.13 - Confirm Acceptance of Surcharge
label | 448d2033-1d06-5cc7-a896-c31874f4fe4f |  | note | Detail of Activity: Check density and depth of surcharge fill is in accordance with the design (40 Kpa)
label | d7002395-8dd1-5d50-addf-b3a70342d2f8 |  | note | Action: H
label | e0a50b36-6436-5997-9b8e-3bf6e3e1e6da |  | note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2): Field Density (wet) multiplied by depth of surcharge
label | 0ab5486b-8cb6-56d9-8c4b-b93e0af73178 |  | note | Inspection / Test Method: Survey, Stringline dips @3 points across carriageway @ 20m spacings
label | 5fe402cb-20cb-599f-9156-ac9884dca257 |  | note | Acceptance Criteria: 40Kpa (minimum) of exerted force from surcharge at each chainage and in place for 3 months
label | a9d0a951-32a6-5a89-83ef-d361899b3063 |  | note | Record Documents: Stringline Report
label | ac1e8ee2-dbdc-5351-b7c6-5bb034d4af82 |  | note | Responsibility: Contractor
label | f75132e3-dbf8-5a3b-82c3-510c16258dad |  | note | Comments: Contractor to supply spreadsheet of surcharge depths and densities at 3 points for each 20m chainage.
checkpoint-status |  |  | checkpoint | Final Sign Off
label | fc70f1c0-d944-5219-997c-8c30609c0ae8 |  | note | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | e2536ae8-ad4c-5854-850a-0c777f57974f |  | textbox | Contractor's Rep Name:
text | 755512c7-fdfd-5328-a322-7c962df6289f |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Sign Off