## Table 1
Item No. | ITEM | ACTIVITY TASK | ACCEPTANCE CRITERIA | FREQUENCY | Hold Point | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET | VERIFICATION SIGN OFFS
CRITICAL HOLD POINT AUTHORITY
0 | Pre-Construction Site Survey | Survey of Ex. Ground levels, boundary / Setout | As – Built data | Prior to commencing any works on site | W | N/A | Not Required
1 | EROSION AND SEDIMENT CONTROLS | Stripped Surface | Visual Inspection | Upon completion of surface stripping prior to further construction | W | N/A | Not Required
1.1 | EROSION AND SEDIMENT CONTROLS | Construct clean water diversion bund | Visual Inspection | Upon completion of bund construction | W | As per approved EMP / Drawing no. – 13182-C06-A | Not Required
1.2 | EROSION AND SEDIMENT CONTROLS | Construct Bund/Silt fence along stream | Visual Inspection | Upon completion of silt control install | W | As per approved EMP / Drawing no. – 13182-C06-A | Not Required
1.3 | EROSION AND SEDIMENT CONTROLS | Construct DEB/Swale | Visual Inspection | Upon completion construction. | W | As per approved EMP / Drawing no. – 13182-C06-A
1.4 | Granular storage zone | Excavation | Visual Inspection | Upon completion of Excavation work | W | As per IFC Drawings | H
1.4.1 | Granular storage zone | Construction of Pipe works | Visual Inspection / Drawing no. – 13182- C09/10-A 110mm slotted Novacoil, 150mm slotted pipe uppermost – 3mm wide slots@ 100mm C/C max, A29 geotextile or equivalent | Upon completion of each component installation (e.g. Geotextile, Pipe works) | H | As – Built data | H
1.4.2 | Granular storage zone | Install M/H component and backfill | Visual Inspection / Drawing no. – 13182- C09/10-A 100mm Upstand and outlet, Control chamber & Sump – AS 3996-E400, 64/40 Drainage metal, clean and washed = 38% voids by volume | During and After completion | H | As – Built Data / Photos of backfilling material, Discharge control verification | H
2 | EARTHWORKS | Strip topsoil and stockpile | Visual Inspection / Survey Stockpile volume | Upon completion of surface stripping prior to further construction | W | Survey data – Stoke pile volume | Not Required
2.1 | EARTHWORKS | Cut to Waste | Visual Inspection / As – Built subgrade level / test - As per site specification or engineer’s instruction Drawing no. – 13182- C01-A | Upon completion of cut to waste | H | As – Built data – Design Subgrade level / Dockets from approved landfill site Subgrade Verification | H
2.2 | EARTHWORKS | Install Geocells | Visual Inspection / Geoweb or similar – as per manufacturers guide | Upon completion of installation | W | Photos of installation | Not Required
2.3 | EARTHWORKS | Place topsoil over Geocells | Slop erosion protection with topsoil and planted pinned to slop 1V:2H / As-built final surface Drawing no. – 13182- C03/04-A | Upon completion of placing topsoil | W | As - Built Completed surface | Not Required
2.4 | EARTHWORKS | Construct aggregate Platform | Visual Inspection / As- built final surface / test - As per site specification or engineer’s instruction Drawing no. – 13182- C03-A | Upon completion of construction of aggregate platform | W | As – Built final completed surface | Not Required
2.5 | Rock Buttress | Cut to Subgrade level | Visual Inspection / As – Built subgrade level / test - As per site specification or engineer’s instruction Drawing no. – 13182- C03/04-A | Upon completion of cut to subgrade prior to commencing further construction | H | As – Built data – Design Subgrade level / Dockets from approved landfill site Subgrade + Basecourse verification | H
2.5.1 | Rock Buttress | Install Geotextile | Visual Inspection / AS410 Geocloth or similar Drawing no. – 13182- C03/04-A | Upon completion of placing geotextile | W | Photos of Installation | Not Required
2.5.2 | Rock Buttress | Place Revetment | Visual Inspection / As Built Slop 1V:1H 800 – 1200mm boulders void infilled with sub 100mm metal Drawing no. – 13182- C03/04-A | During and After completion of installation Inspect / Oversee Initial Sections | W | As – Built final surface | H
3 | INSTALL STEEL PILE | Delivery of piles on site | Visual Inspection 310UC137 & 310UC97 | Upon delivery of material on site | H | Delivery dockets and tags | Not Required
3.1 | INSTALL STEEL PILE | Setout piling locations | Visual Inspection Drawing No. – 24_089- 0000-DRG-S21.01-C | Prior to pile installation | W | N/A | Not Required
3.2 | INSTALL STEEL PILE | Driving piles | As per Drawing No. – 24_089-0000-DRG- S21.01-C & Geotech report. Refer to note as per drawing. – PDA testing & Case pile wave analysis program (CAPWAP). | During Pile installation | H | PDA test & CAPWAP results 2 X Piles – 1 for each pile depth before proceeding | Geotech. Engineer to review results prior commencing further construction.
3.3 | INSTALL STEEL PILE | Cut pile to suit | As per Drawing No. – 24_089-0000-DRG- S21.01-C - Section B & Geotech report. | Upon completion of driving | W | As – Built data to confirm final heights | Not Required
4 | RETAINING WALL | Excavate wall footprint | As per the design Dr. No. – 13182-C14-A | Upon completion of excavation | W | As – Built data – Design Subgrade level / Dockets from approved landfill site | Not Required
4.1 | RETAINING WALL | Gravel levelling pad | GAP20 X 150mm pad under the Magnumstone extender(610mm) & base block Dr. No. – 13182-C14-A | Prior installation of Magnumstone block | W | Visual Inspection | Not Required
4.2 | RETAINING WALL | Install Magnumstone wall | As per the Dr. No. – 13182-C14-A Blocks infilled with GAP 40/60 metal Slop 1H:20V | During & upon completion of installation | W | Installation photos / Visual Inspection | Not Required
4.3 | RETAINING WALL | Subsoil Drain | 100mm Perforated drain, discharge to low point F2 AP20 Drainage fines to backfill | During & upon completion of installation | W | As – Built subsoil drain / visual inspection | Not Required
4.4 | RETAINING WALL | Backfilling | Drainage metal 60/40 | Upon completion of backfilling | W | Material delivery dockets / As – Built final surface | Not Required
5 | As-Built Plans | Survey | Engineer to review and approve final As-built plans | Upon completion of the works | H | As-built plans | —