## Table 1
Item No. | ITEM | ACTIVITY TASK | ACCEPTANCE CRITERIA | FREQUENCY | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET | VERIFICATION SIGN OFFS
[6 empty] | INTERNAL VERIFICA TION AUTHORIT Y OR RESPONSI BILITY | CRITICAL HOLD POINT AUTHORIT Y
1 | Site Preparation | Site Clearance | Visual Inspection | Prior to excavation | As per Engineer’s acceptance | W | W
1.1 | Concrete Pipes and Pre-cast Structures | Delivery of Pipes and Pre- cast structures | Visual Inspection – as per WSP T-WES00012 Section 2.3 pg. no. 262 | Upon delivery on site | Delivery Dockets | R | W
1.2 | Fill Material | 65/40 Drainage metal | Clean and washed as per the drawings | Upon delivery on site | Delivery Dockets | R | W
2 | Initial Set Out | Setting out M/H locations and Trench Alignment | As per approved IFC drawings and design model provided | Prior to trench excavations | As per Engineer’s acceptance | H | W
3 | Excavation | Excavation | Visual Inspection – As per T- WES 00011 section 3.2.4 pg. no. 251 | During and after excavation works | Checksheet | H | W
3.1 | Geotextile | Bidim A29 or equivalent | As per drawings and specification | During and after excavation works | Checksheet | H | W
3.2 | Pipe General Bedding | Place Approved bedding, WDC EES Sheet 31 | Visual Inspection | Prior to pipe laying | Checksheet | W | W
3.3 | Pipe Laying | Laying and Jointing of the pipes | Visual Inspection - Lay and joint pipes in accordance with the manufacturer’s recommendations and | During and upon completion of laying | Checksheet, As-Built information – Invert level | H | W
3.4 | Slotted pipe | Laying and jointing of the pipe | Slotts as specified in the IFC drawings | During and upon completion of laying | Checksheet, As-Built information – Invert level | H | W
3.5 | Pipe Embedment | 65/40 Drainage metal | Bulk filled – 38% voids by volume | Upon completion of backfilling | Checksheet | H | W
4 | Subsoil Drain | Installation | 110mm slotted novacoil installed on top of granular storage | Prior to installation of subsoil drain | QF 007 Checksheet | R | R
4.1 | Trench Fill | Agreed or approved material | 300mm cover | Upon completion of the backfilling | Checksheet | H | W
5 | Manhole and Sump Construction | Pre-cast Manhole base and Standard Sump | Visual Inspection | Prior installation of Manhole/cesspit Base | Checksheet | R | W
5.1 | Manhole and Sump Construction | Manhole risers and components | As per IFC drawing and design model | During and after installation | Checksheet | R | W
5.2 | Manhole and Sump Construction | Standard sump 450x450x1200mm pcc, AS 3996 E400 grate and frame | As per IFC drawings and specification | For each Standard sump installation | Checksheet | R | W
6 | Enviropod filter | Install approved enviropod filters in sump | As per IFC drawings and specification | For each Standard sump installation | Checksheet | R | W
7 | Geotextile | Placing Bidim fabric around drainage aggregate | As per IF drawings and specification | Prior to backfilling | Checksheet | R | R
8 | As Built & Final Design Documentation | Supply As-built Plans | Engineer to review and accept as-built Drawings | For all completed works | Engineer’s acceptance of as-built drawings | H | H