## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP001 - E25-012 Rocket Lab - Earthwork & Construction | itp |  |  |  |  | ITP001 - E25-012 Rocket Lab - Earthwork & Construction
section | Earthwork & Construction
checkpoint | Pre-Construction Site Survey
label | ACTIVITY TASK - Survey of Ex. Ground levels, boundary / Setout
label | ACCEPTANCE CRITERIA - As – Built data
label | FREQUENCY - Prior to commencing any works on site
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - N/A
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 1 - EROSION AND SEDIMENT CONTROLS
label | ACTIVITY TASK - Stripped Surface
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Upon completion of surface stripping prior to further construction
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - N/A
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 1.1 - EROSION AND SEDIMENT CONTROLS
label | ACTIVITY TASK - Construct clean water diversion bund
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Upon completion of bund construction
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per approved EMP / Drawing no. – 13182-C06-A
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 1.2 - EROSION AND SEDIMENT CONTROLS
label | ACTIVITY TASK - Construct Bund/Silt fence along stream
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Upon completion of silt control install
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per approved EMP / Drawing no. – 13182-C06-A
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 1.3 - EROSION AND SEDIMENT CONTROLS
label | ACTIVITY TASK - Construct DEB/Swale
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Upon completion construction.
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per approved EMP / Drawing no. – 13182-C06-A
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY -
checkpoint | 1.4 - Granular storage zone
label | ACTIVITY TASK - Excavation
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Upon completion of Excavation work
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per IFC Drawings
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
checkpoint | 1.4.1 - Granular storage zone
label | ACTIVITY TASK - Construction of Pipe works
label | ACCEPTANCE CRITERIA - Visual Inspection / Drawing no. – 13182- C09/10-A
label | ○ 110mm slotted Novacoil,
label | ○ 150mm slotted pipe uppermost – 3mm wide slots@ 100mm C/C max,
label | ○ A29 geotextile or equivalent
label | FREQUENCY - Upon completion of each component installation (e.g. Geotextile, Pipe works)
label | HOLD POINT - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As – Built data
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | HOLD POINT
checkpoint | 1.4.2 - Granular storage zone
label | ACTIVITY TASK - Install M/H component and backfill
label | ACCEPTANCE CRITERIA - Visual Inspection / Drawing no. – 13182- C09/10-A
label | ○ 100mm Upstand and outlet,
label | ○ Control chamber & Sump – AS 3996-E400,
label | ○ 64/40 Drainage metal, clean and washed = 38% voids by volume
label | FREQUENCY - During and After completion
label | HOLD POINT - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As – Built Data / Photos of backfilling material, Discharge control verification
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | HOLD POINT
checkpoint | 2 - EARTHWORKS
label | ACTIVITY TASK - Strip topsoil and stockpile
label | ACCEPTANCE CRITERIA - Visual Inspection / Survey Stockpile volume
label | FREQUENCY - Upon completion of surface stripping prior to further construction
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Survey data – Stoke pile volume
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 2.1 - EARTHWORKS
label | ACTIVITY TASK - Cut to Waste
label | ACCEPTANCE CRITERIA - Visual Inspection / As – Built subgrade level / test
label | — As per site specification or engineer’s instruction
label | ○ Drawing no. – 13182- C01-A
label | FREQUENCY - Upon completion of cut to waste
label | HOLD POINT - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As – Built data – Design Subgrade level / Dockets from approved landfill site, Subgrade Verification
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | HOLD POINT
checkpoint | 2.2 - EARTHWORKS
label | ACTIVITY TASK - Install Geocells
label | ACCEPTANCE CRITERIA - Visual Inspection / Geoweb or similar – as per manufacturers guide
label | FREQUENCY - Upon completion of installation
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Photos of installation
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 2.3 - EARTHWORKS
label | ACTIVITY TASK - Place topsoil over Geocells
label | ACCEPTANCE CRITERIA - Slop erosion protection with topsoil and planted pinned to slop 1V:2H / As-built final surface
label | ○ Drawing no. – 13182- C03/04-A
label | FREQUENCY - Upon completion of placing topsoil
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As - Built Completed surface
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 2.4 - EARTHWORKS
label | ACTIVITY TASK - Construct aggregate Platform
label | ACCEPTANCE CRITERIA - Visual Inspection / As- built final surface / test - As per site specification or engineer’s instruction
label | ○ Drawing no. – 13182- C03-A
label | FREQUENCY - Upon completion of construction of aggregate platform
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As – Built final completed surface
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 2.5 - Rock Buttress
label | ACTIVITY TASK - Cut to Subgrade level
label | ACCEPTANCE CRITERIA - Visual Inspection / As – Built subgrade level / test
label | — As per site specification or engineer’s instruction
label | ○ Drawing no. – 13182- C03/04-A
label | FREQUENCY - Upon completion of cut to subgrade prior to commencing further construction
label | HOLD POINT - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As – Built data – Design Subgrade level / Dockets from approved landfill site, Subgrade + Basecourse verification
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | HOLD POINT
checkpoint | 2.5.1 - Rock Buttress
label | ACTIVITY TASK - Install Geotextile
label | ACCEPTANCE CRITERIA - Visual Inspection / AS410 Geocloth or similar
label | ○ Drawing no. – 13182- C03/04-A
label | FREQUENCY - Upon completion of placing geotextile
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Photos of Installation
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 2.5.2 - Rock Buttress
label | ACTIVITY TASK - Place Revetment
label | ACCEPTANCE CRITERIA - Visual Inspection / As Built
label | ○ Slop 1V:1H
label | ○ 800 – 1200mm boulders void infilled with sub 100mm metal
label | ○ Drawing no. – 13182- C03/04-A
label | FREQUENCY - During and After completion of installation, Inspect / Oversee Initial Sections
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As – Built final surface
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
checkpoint | 3 - INSTALL STEEL PILE
label | ACTIVITY TASK - Delivery of piles on site
label | ACCEPTANCE CRITERIA - Visual Inspection, 310UC137 & 310UC97
label | FREQUENCY - Upon delivery of material on site
label | HOLD POINT - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Delivery dockets and tags
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
holdpoint | HOLD POINT
checkpoint | 3.1 - INSTALL STEEL PILE
label | ACTIVITY TASK - Setout piling locations
label | ACCEPTANCE CRITERIA - Visual Inspection, Drawing No. – 24_089- 0000-DRG-S21.01-C
label | FREQUENCY - Prior to pile installation
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - N/A
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 3.2 - INSTALL STEEL PILE
label | ACTIVITY TASK - Driving piles
label | ACCEPTANCE CRITERIA - As per Drawing No. – 24_089-0000-DRG-S21.01-C & Geotech report.
label | ○ Refer to note as per drawing. – PDA testing & Case pile wave analysis program (CAPWAP).
label | FREQUENCY - During Pile installation
label | HOLD POINT - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - PDA test & CAPWAP results, 2 X Piles – 1 for each pile depth before proceeding
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Geotech. Engineer to review results prior commencing further construction.
holdpoint | HOLD POINT
checkpoint | 3.3 - INSTALL STEEL PILE
label | ACTIVITY TASK - Cut pile to suit
label | ACCEPTANCE CRITERIA - As per Drawing No. – 24_089-0000-DRG-S21.01-C - Section B & Geotech report.
label | FREQUENCY - Upon completion of driving
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As – Built data to confirm final heights
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 4 - RETAINING WALL
label | ACTIVITY TASK - Excavate wall footprint
label | ACCEPTANCE CRITERIA - As per the design
label | ○ Dr. No. – 13182-C14-A
label | FREQUENCY - Upon completion of excavation
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As – Built data – Design Subgrade level / Dockets from approved landfill site
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 4.1 - RETAINING WALL
label | ACTIVITY TASK - Gravel levelling pad
label | ACCEPTANCE CRITERIA - GAP20 X 150mm pad under the Magnumstone extender(610mm) & base block
label | ○ Dr. No. – 13182-C14-A
label | FREQUENCY - Prior installation of Magnumstone block
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 4.2 - RETAINING WALL
label | ACTIVITY TASK - Install Magnumstone wall
label | ACCEPTANCE CRITERIA - As per the Dr. No. – 13182-C14-A
label | ○ Blocks infilled with GAP 40/60 metal
label | ○ Slop 1H:20V
label | FREQUENCY - During & upon completion of installation
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Installation photos / Visual Inspection
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 4.3 - RETAINING WALL
label | ACTIVITY TASK - Subsoil Drain
label | ACCEPTANCE CRITERIA - 100mm Perforated drain, discharge to low point
label | ○ F2 AP20 Drainage fines to backfill
label | FREQUENCY - During & upon completion of installation
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As – Built subsoil drain / visual inspection
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 4.4 - RETAINING WALL
label | ACTIVITY TASK - Backfilling
label | ACCEPTANCE CRITERIA - Drainage metal 60/40
label | FREQUENCY - Upon completion of backfilling
label | HOLD POINT - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Material delivery dockets / As – Built final surface
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 5 - As-Built Plans
label | ACTIVITY TASK - Survey
label | ACCEPTANCE CRITERIA - Engineer to review and approve final As-built plans
label | FREQUENCY - Upon completion of the works
label | HOLD POINT - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As-built plans
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - —
holdpoint | HOLD POINT
checklist | ITP002 - E25-12 Rocket Lab - Reinforced Concrete Foundation | itp |  |  |  |  | ITP002 - E25-12 Rocket Lab - Reinforced Concrete Foundation
section | Materials
checkpoint | Concrete Mix Design
label | SPECIFICATION REFERENCE - Rocket Lab Neutron Separation Test Rig, Structural Specification clause 2.7 and 2.8.1
label | TEST REQUIRED - Ready Mix Test certificates accordance with NZS 3104 - supplier, 3X random test cylinders for each 75m3 placed on site NZS 3112, part2 , clause 3.
label | INSPECTION BY - UCCL, Engineer
label | TASK TIMING OR TASK FREQUENCY - Prior to work commencing on site
label | — Blinding / Site concrete 10 MPa
label | — Foundation pads 30 Mpa
label | ACCEPTANCE CRITERIA - Ready mix testing shall comply as per Structure specification clause 2.7 pg. no. 15. All other concrete shall be from an approved and fully audited Ready Mix plant clause 2.8.1 pg. 16. Calcium Chloride shall not be used.
label | ○ Maximum aggregate size shall generally be 19 mm.
label | ○ The aggregate used, and overall mix design (including the use of any additives) shall meet the provisions of section 2 of Alkali Aggregate Reaction (C&CA). Evidence may be required in support of this by the Engineer. Use of low alkali cements or aggregates from an alternative source may be required where the proposed aggregate contains deleterious material.
label | UCCL - H
label | Client - H
holdpoint | HOLD POINT
checkpoint | Reinforcement Steel
label | SPECIFICATION REFERENCE - Rocket Lab Neutron Separation Test Rig, Structural Specification clause 1.7
label | TEST REQUIRED - Manufacturer's certificates
label | INSPECTION BY - UCCL, Engineer
label | TASK TIMING OR TASK FREQUENCY - Prior to Ordering
label | ACCEPTANCE CRITERIA - All reinforcement shall be Grade 300E and 500E complying with AS/NZS 4671. Grade 500E reinforcement shall be manufactured by a micro-alloy process by an Pacific Steel.
label | ○ Coiled and re-straightened bar will not be accepted under any circumstances.
label | ○ Hard drawn steel wire reinforcing mesh shall be Grade L complying with AS/NZS 4671.
label | ○ Ductile 500 Mesh shall be Grade E complying with AS/NZS 4671.
label | ○ Mill certificates meeting New Zealand Standards must be provided to the Engineer for all reinforcing steel used on the project. Specification clause 1.10 pg. 8
label | UCCL - H
label | Client - H
holdpoint | HOLD POINT
checkpoint | Cast in Items - Nuts, Bolts and Anchor bars
label | SPECIFICATION REFERENCE - Rocket Lab Neutron Separation Test Rig, Structural Specification clause 3.6.8.4 pg.28
label | TEST REQUIRED - Supplier Documentation
label | INSPECTION BY - UCCL, Engineer
label | TASK TIMING OR TASK FREQUENCY - Prior to Ordering
label | ACCEPTANCE CRITERIA - Bolts, Nuts and Washers shall comply with AS/NZS 1252.1/2.
label | ○ All bolts shall be hot dip galvanized to AS/NZS 1214.
label | ○ Provide documentation demonstrating compliance to the relevant Standard (refer Section 5.3) prior to delivery of bolts to site.
label | UCCL - H
label | Client - H
holdpoint | HOLD POINT
section | Pre Construction Site works
checkpoint | Form work
label | SPECIFICATION REFERENCE - Rocket Lab Neutron Separation Test Rig, Structural Specification clause 2.8.5 pg.16
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - Prior and after being used
label | ACCEPTANCE CRITERIA - Fairface formwork shall be so constructed as to provide straight and true angles and so as to produce cast surfaces within a tolerance of ±5mm on the given dimensions.
label | ○ Plywood formwork shall be sealed with not less than two coats of polyurethane varnish on the concrete face. Diesel oil-based products are not permitted.
label | ○ Timber formwork which is not being used for the next seven days shall be cleaned, oiled and stored flat.
label | ○ It shall be protected against gross changes of moisture by use of a tarpaulin or similar waterproof cover enclosing the top and all four sides completely.
label | UCCL - W
label | Client - W
checkpoint | Reinforcing
label | SPECIFICATION REFERENCE - Rocket Lab Neutron Separation Test Rig, Structural Specification clause 2.8.5 pg.16 & Clause 1
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - UCCL, Engineer
label | TASK TIMING OR TASK FREQUENCY - Prior to pre-pour inspection
label | ACCEPTANCE CRITERIA - A copy of the completed pre-pour checklist is to be given to the Engineer prior to the Engineer observing the finished Section of work. 48 hours notice is considered a minimum. The Contractor shall furnish a fully completed Producer Statement. This certificate shall cover all work completed under this Section of the Specification.
label | UCCL - H
label | Client - W
holdpoint | HOLD POINT
checkpoint | Concrete Pouring and Curing
label | SPECIFICATION REFERENCE - Rocket Lab Neutron Separation Test Rig, Structural Specification clause 2.9 to 2.11 pg17
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - During and upon concrete pour
label | ACCEPTANCE CRITERIA - All concreting shall conform to NZS 3109, Section 7. Concrete shall not be pumped without the Engineer's approval. Where such approval is given, only a standard “structural” concrete mix design may be used. If it is found to have free fallen more than 1.5m, concrete will be rejected.
label | ○ Vibrators shall not come within 12mm of the face of the formwork.
label | ○ All concrete shall be cured as defined in NZS 3109, Clause 7.8. The use of a plastic curing compound shall be as agreed with the Engineer specifically for each occasion before it is used.
label | UCCL - H
label | Client - R
holdpoint | HOLD POINT
section | Prepour Inspection
checkpoint | Pre pour inspection
label | SPECIFICATION REFERENCE - Rocket Lab Neutron Separation Test Rig, Structural Specification clause 2.5 pg15
label | TEST REQUIRED - Pre pour inspection sheet
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - Prior to placing structural concrete
label | ACCEPTANCE CRITERIA - Pre pour inspection sheet to be completed prior to placing concrete. Engieeer to be notified of pours for inspection at least 48 hours prior to placing concrete.
label | UCCL - H
label | Client - H
holdpoint | HOLD POINT
section | Post Construction
checkpoint | As Built & Final Design Documentation
label | SPECIFICATION REFERENCE - Rocket Lab Neutron Separation Test Rig, Structural Specification clause 3.6.8.11 pg29
label | TEST REQUIRED - Surveying
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - For Each Foundation
label | ACCEPTANCE CRITERIA - Confirmation From Engineer on as built records. As-built HD bolts postion prior to pouring slab - as reqested by Engineer.
label | UCCL - H
label | Client - R
holdpoint | HOLD POINT
checkpoint | Completion Inspection inc. Construction Defects Report
label | SPECIFICATION REFERENCE - Rocket Lab Neutron Separation Test Rig, Structural Specification clause 2.24 to 2.26 pg21
label | TEST REQUIRED - Completion inspection on each foundation by Engineer
label | INSPECTION BY - Engineer/ UCCL
label | TASK TIMING OR TASK FREQUENCY - For Each Foundation
label | ACCEPTANCE CRITERIA - Provided a completed construction defect report that that details any remedial measures taken, & snag lists closed out
label | UCCL - H
label | Client - R
holdpoint | HOLD POINT
checklist | ITP003 - E25-012 Rocket Lab - Stormwater Network | itp |  |  |  |  | ITP003 - E25-012 Rocket Lab - Stormwater Network
section | Stormwater Network
checkpoint | 1 - Site Preparation
label | ACTIVITY TASK - Site Clearance
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Prior to excavation
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per Engineer’s acceptance
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - W
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 1.1 - Concrete Pipes and Pre-cast Structures
label | ACTIVITY TASK - Delivery of Pipes and Pre- cast structures
label | ACCEPTANCE CRITERIA - Visual Inspection – as per WSP T-WES00012 Section 2.3 pg. no. 262
label | FREQUENCY - Upon delivery on site
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Delivery Dockets
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 1.2 - Fill Material
label | ACTIVITY TASK - 65/40 Drainage metal
label | ACCEPTANCE CRITERIA - Clean and washed as per the drawings
label | FREQUENCY - Upon delivery on site
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Delivery Dockets
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 2 - Initial Set Out
label | ACTIVITY TASK - Setting out M/H locations and Trench Alignment
label | ACCEPTANCE CRITERIA - As per approved IFC drawings and design model provided
label | FREQUENCY - Prior to trench excavations
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per Engineer’s acceptance
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
holdpoint | HOLD POINT
checkpoint | 3 - Excavation
label | ACTIVITY TASK - Excavation
label | ACCEPTANCE CRITERIA - Visual Inspection – As per T- WES 00011 section 3.2.4 pg. no. 251
label | FREQUENCY - During and after excavation works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
holdpoint | HOLD POINT
checkpoint | 3.1 - Geotextile
label | ACTIVITY TASK - Bidim A29 or equivalent
label | ACCEPTANCE CRITERIA - As per drawings and specification
label | FREQUENCY - During and after excavation works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
holdpoint | HOLD POINT
checkpoint | 3.2 - Pipe General Bedding
label | ACTIVITY TASK - Place Approved bedding, WDC EES Sheet 31
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Prior to pipe laying
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - W
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 3.3 - Pipe Laying
label | ACTIVITY TASK - Laying and Jointing of the pipes
label | ACCEPTANCE CRITERIA - Visual Inspection - Lay and joint pipes in accordance with the manufacturer’s recommendations and
label | FREQUENCY - During and upon completion of laying
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet, As-Built information – Invert level
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
holdpoint | HOLD POINT
checkpoint | 3.4 - Slotted pipe
label | ACTIVITY TASK - Laying and jointing of the pipe
label | ACCEPTANCE CRITERIA - Slotts as specified in the IFC drawings
label | FREQUENCY - During and upon completion of laying
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet, As-Built information – Invert level
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
holdpoint | HOLD POINT
checkpoint | 3.5 - Pipe Embedment
label | ACTIVITY TASK - 65/40 Drainage metal
label | ACCEPTANCE CRITERIA - Bulk filled – 38% voids by volume
label | FREQUENCY - Upon completion of backfilling
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
holdpoint | HOLD POINT
checkpoint | 4 - Subsoil Drain
label | ACTIVITY TASK - Installation
label | ACCEPTANCE CRITERIA - 110mm slotted novacoil installed on top of granular storage
label | FREQUENCY - Prior to installation of subsoil drain
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - QF 007 Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 4.1 - Trench Fill
label | ACTIVITY TASK - Agreed or approved material
label | ACCEPTANCE CRITERIA - 300mm cover
label | FREQUENCY - Upon completion of the backfilling
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
holdpoint | HOLD POINT
checkpoint | 5 - Manhole and Sump Construction
label | ACTIVITY TASK - Pre-cast Manhole base and Standard Sump
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Prior installation of Manhole/cesspit Base
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 5.1 - Manhole and Sump Construction
label | ACTIVITY TASK - Manhole risers and components
label | ACCEPTANCE CRITERIA - As per IFC drawing and design model
label | FREQUENCY - During and after installation
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 5.2 - Manhole and Sump Construction
label | ACTIVITY TASK - Standard sump 450x450x1200mm pcc, AS 3996 E400 grate and frame
label | ACCEPTANCE CRITERIA - As per IFC drawings and specification
label | FREQUENCY - For each Standard sump installation
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 6 - Enviropod filter
label | ACTIVITY TASK - Install approved enviropod filters in sump
label | ACCEPTANCE CRITERIA - As per IFC drawings and specification
label | FREQUENCY - For each Standard sump installation
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 7 - Geotextile
label | ACTIVITY TASK - Placing Bidim fabric around drainage aggregate
label | ACCEPTANCE CRITERIA - As per IF drawings and specification
label | FREQUENCY - Prior to backfilling
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 8 - As Built & Final Design Documentation
label | ACTIVITY TASK - Supply As-built Plans
label | ACCEPTANCE CRITERIA - Engineer to review and accept as-built Drawings
label | FREQUENCY - For all completed works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Engineer’s acceptance of as-built drawings
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | HOLD POINT