## EnduroFlex
type | name | values | prefix | postfix | usage count
checklist-flat | EnduroFlex Insulated Roof Torch-On Installation
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | SOW description entered
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Substrate Acceptance
button | Substrate washed / cleaned & assessed for surface uniformity (photos attached below) | Yes,No
button | Substrate temperature is not less than 10*C and no greater then 35*C | Yes,No
button | Substrate free from pooling or ponding water (Moisture gauge photo attached below) | Yes,No
button | Adequate fall in substrate? | Yes,No
checkpoint | Vapour barrier installation
select | Vapour barrier type | Fully Adhered, Loose Laid
button | Primer installed to manufacturer's specification (Record batch and install photos) | Yes,No
button | Vapour barrier installed to manufacturer's specification (Record batch and install photos) | Yes,No
checkpoint | Insulation Installation
button | Vapour barrier free of pooling water? | Yes,No
select | Insulation installation method | Foam Adhesive,Mechanically Fixed
button | Insulation installed to fall (Record install photos) | Yes,No,N/A
checkpoint | Base Sheet Installation
button | Installation of fully adhered base sheet membrane to manufacturer's specification (Record batch and install photos) | Yes,No
button | Installation of drain droppers to manufacturer's specification (Record batch and install photos) | Yes,No
select | Cap sheet installation method | Fully Adhered,Torched
select | Cap sheet type | Unexposed,UV-Stable,Anti-Root
button | Installation of cap sheet membrane to manufacturer's specification (Record batch and install photos) | Yes,No
button | Installation of solar pedestals to manufacturer's specification (Record batch and install photos) | Yes,No,N/A
button | Termination pressure bar installed to manufacturer's specification (Record batch and install photos) | Yes,No
checkpoint | Area completed to manufacturer's specification? - photos attached below