## ITP Cover Page
Rain Garden Inspection and Test Plan
Project: Peacocke Whatukooruru Drive Stage 2A
Number and Revision: DN1205 - 119 - Rev B
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive Stage 2A |  |  |  |  | ITP Number: |  |  | 119
Project Number: |  |  | DN1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Rain Garden |  |  |  |  | Revision: | 1000 |  | B
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | 146000-002A-2195 REV7, 2151-2152 REV7, 3155 REV 4
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification, Appendices and GWS
Quality Specified: |  |  | TNZ F/5
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
B | Draft for Approval | 2024-03-19 | [7 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)
Note on A8: Callun Purchase:

## ITP Master Body
Rain Garden Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements
3.01.01 | Construction Pack | Methodology and ITP to be submitted to the Engineer and approved prior to works beginning | Downer | Construction Pack | Submit 10 days prior to commencement of works | HP | ENG
3.01.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
3.01.03 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE
3.01.04 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to Excavation | H | SE
3.01.05 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to Excavation | H | PE
3.01.06 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | Raind Garden Materials
4.01.01 | GCL Liner | GCL to be meet or exceed the test values of Bentosure NW4000. | Project Sechedule | Technical Datasheet | Atleast 2 days prior to placement | HP | ENG
4.01.02 | Geotextile | NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used to wrap 20/40 drainage aggregate. Confirm before placement | GWS 3.2.3 | Technical Datasheet Delivery Dockets or photos | Before placement | C | SE
4.01.03 | Drainage Aggregate | Drainage aggregate should be deep washed and in accordance with TNZ F/6 including gradings (40/20 aggregate). Open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1: App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification: Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate) Test Sieve Aperture (mm) Percentage Passing (%) 53 100 13.2 10 (max) | GWS 3.2.2 & 3.4 | PSD, CR | Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required. | C | SE
4.01.04 | Pipes and fittings | Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 110 mm diameter Class 200 complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer. | GWS 3.2.1 | Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class | Before placement | C | SE
4.01.05 | Graded Sand | (2A SAND) 10mm clean well graded sand transition layer with minimal fines, void ratio 0.3. | DWG 2195 REV1 | Verifying document to be copy of delivery dockets, photos of sand onsite | Every Delivery to Site | C | SE
4.01.06 | Filter Media | Filter/ Planting Media must follow the specification as per RITS 4.2.19. Seen below. | RITS 4.2.19 | Verifying documents Dockets | Every Delivery to Site | C | SE
4.01.07 | Scour Protection GAP 65 Rip Rap | Clean GAP65 to be used as Rip Rap. For soil filled scour protection a ratio of 30% topsoil, 70% GAP65. | BBO | Verifying document to be copy of delivery dockets, photos of mix | Every Rain Garden | C | SE | D50 = Gap 65 Riprap 200Mm Surrounding Manhole And 150Mm Deep
4.01.08 | Coconut (Coir) Matting | Biodegradable Erosion Mat (Coir Mat). Biodegradable mulching fabric 450 gsm | DWG 2195 REV1. Schedule SP2 4.3.7 | Verifying document to be copy of delivery dockets, photos of mat onsite | Every Delievery to Site | C | SE
SECTION 5 – CONSTRUCTION ACTIVITY
5.01 | SUB ACTIVITY
5.01.01 | Set-out | Check set-out prior to excavation of Rain Garden. | PS - 2.2.12 | Hold Point Release | Min 48h Notice | H | SUP
5.01.02 | Excavation | Excavations shall be completed in such manner that it is true to the drawings will allow novacoil to be laid true to the depths, grades and lines. | Downer | Survey Data, Photos | Prior to laying filter cloth | H | SV
5.01.03 | GCL Liner Fixing to Kerb | GCL Liner to be fixed to kerb as per manufacturers guidelines (Bentofix GCL 18.2, figure 14). Mechanical fasteners with stainless steel batten (connection bar) to be used to fix the liner to the kerb. Mechanical fasteners to be fixed 5 times ever meter of along the connection bar. | Manufacturers Guidelines 18.2 | Site Photos | Prior to backfill | I | SE
5.01.04 | GCL Sealing (Pipes) | GCL Liner to be sealed around pavement drains and stormwater lines which connect into rain garden. Sealing shall be completed as per manufacturers guidelines (Bentofix GCL 18.3 & 18.4 Figuire 15). GCL shall be cut with a sharp utility knife. For horizontal pipes, vertical laps of min 1m are required. Inside the rain garden a clamp shall be used anchor the GCL lap to the pipe. Bentonite paste shall be be used in the void between the main GCL and GCL lap to ensure a water tight seal. | Manufacturers Guidelines 18.3 & 18.4 | Site Photos | Prior to backfill | I | SE
5.01.05 | GCL Repair | GCL to be repaired as per manufacture's guidelnes (Bentofix PVB5100c). GCL becomes damaged, torn or punctured during installation, the affected area should be repaired. For damaged areas, a separate piece of GCL shall be used and extend past the comprimised section by 500mm in every direction. Bentonite shall be used to connect the seperate GCL to the main liner. | Manufacturers Guidelines 21 | Site Photos | Prior to backfill | I | SE
5.01.06 | GCL Inspection | GCL to be installed as per manufacturers guide and true to the drawings.The inspection should include overlaps, alignments, penetrations, connections, detections of any defects, including installation damage. Detected falsely installed areas shall be marked, repaired and the repairs shall be inspected and approved engineer. | Manufacturers Guidelines 22.2 | Site Photos | Prior to backfill | HP | ENG
5.01.07 | Geotextile Installation | All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. | GWS 3.2.3 | Site Photos | Prior to aggregate placement | I | SE
5.01.08 | Bedding | TNZ F/5 - Bedding thickness shall be no less than 100mm | TNZ F/5 | Photos, Sruvey Data | Prior to laying Novacoil | I | SE
5.01.09 | Joining Pipes | TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations | TNZ F/5 | Copy of delivery dockets, photos of joins onsite with tag showing class | Every join | I | SE
5.01.10 | Pipe Grade | Grade of subsoils must be falling in the correct direction based on the IFC Drawings and at the correct grade (greater than 1% based on TNZ F/5) | TNZ F/5 | AsBuilt | Every 10m | H | SV
5.01.11 | Pipe Cover | Pipe to have 100mm of drainage aggregate as top cover for pipe. | N/A | Site Photos | Every 10m | H | SV
5.01.12 | Sand Placement | Sand to be placed at a constant thickness of 100mm. Sand should be free of peaks and troughs. | N/A | Site Photos | Every Rain Garden | I | SE
5.01.13 | Filter Media | Filter media to be placed at a constant average thickness of 600mm, refer to drawing for detail. Filter media should be free of peaks and troughs. | N/A | Site Photos | Every Rain Garden | I | SE
5.01.14 | Coconut Matting | Mat shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. | GWS 3.2.3 | Site Photos | Every Rain Garden | I | SE
5.01.15 | Scour Protection GAP 65 Rip Rap | Scour protection shall be installed as per drawings around let downs, scruffy dome and the flush point end. | GWS 3.6 & BBO | Site Photos/ Survey Data | Every Rain Garden | I | SE
SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.01 | General
6.01.01 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | H | SE
6.01.02 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level | Downer | Records | As-builts taken every 10m prior to backfill | H | SV
6.01.03 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations | Downer | Redlines | Post construction | H | PE
6.01.04 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | H | PE
6.01.05 | Photos | Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill. | Downer | Photo Records | Post construction | H | SE