## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - 119 - Rain Garden Rev B | itp |  |  |  |  | ITP - 119 - Rain Garden Rev B
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Submit 10 days prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.02 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.01.03 - Service Location
label | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard / Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.04 - Internal Permits
label | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard / Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.05 - External Permits
label | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Standard / Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.06 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - GCL Liner
label | Acceptance / Conformance Criteria - GCL to be meet or exceed the test values of Bentosure NW4000.
label | Standard / Specification - Project Sechedule
label | Verifying Document - Technical Datasheet
label | Frequency - Atleast 2 days prior to placement
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.02 - Geotextile
label | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used to wrap 20/40 drainage aggregate. Confirm before placement
label | Standard / Specification - GWS 3.2.3
label | Verifying Document - Technical Datasheet Delivery Dockets or photos
label | Frequency - Before placement
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.01.03 - Drainage Aggregate
label | Acceptance / Conformance Criteria - Drainage aggregate should be deep washed and in accordance with TNZ F/6 including gradings (40/20 aggregate). Open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991
label | Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1:
label | App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification:
label | Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate)
label | Test Sieve Aperture (mm) Percentage Passing (%)
label | ○ 53 100
label | ○ 13.2 10 (max)
label | Standard / Specification - GWS 3.2.2 & 3.4
label | Verifying Document - PSD, CR
label | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.01.04 - Pipes and fittings
label | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 110 mm diameter Class 200 complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
label | Standard / Specification - GWS 3.2.1
label | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
label | Frequency - Before placement
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.01.05 - Graded Sand
label | Acceptance / Conformance Criteria - (2A SAND) 10mm clean well graded sand transition layer with minimal fines, void ratio 0.3.
label | Standard / Specification - DWG 2195 REV1
label | Verifying Document - Verifying document to be copy of delivery dockets, photos of sand onsite
label | Frequency - Every Delivery to Site
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.01.06 - Filter Media
label | Acceptance / Conformance Criteria - Filter/ Planting Media must follow the specification as per RITS 4.2.19. Seen below.
label | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | Planting media is to be as per RITS 4.2.19.
label | Planting Media
label | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | Raingarden media should meet the following specifications:
label | ○ Minimum depth 500mm.
label | ○ Saturated Hydraulic Conductivity: 50 to 300 mm hr^-1.
label | ○ Plant available water: 100 mm
label | ○ Organic matter: 10% – 30% by volume
label | ○ pH range: 6.5 – 7.5+
label | ○ Electrical Conductivity: < 2.5 dS m^-1
label | ○ Total Nitrogen: < 1,000 mg kg-1
label | ○ Total phosphorus: Leachate testing required if > 100mg kg^-1
label | ○ Total Copper: ≤ 80 mg kg^-1
label | ○ Total Zinc: ≤ 200 mg kg^-1
label | ○ Media sources: From a clean source (no waste products)
label | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | Standard / Specification - RITS 4.2.19
label | Verifying Document - Verifying documents Dockets
label | Frequency - Every Delivery to Site
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.01.07 - Scour Protection GAP 65 Rip Rap
label | Acceptance / Conformance Criteria - Clean GAP65 to be used as Rip Rap. For soil filled scour protection a ratio of 30% topsoil, 70% GAP65.
label | Standard / Specification - BBO
label | Verifying Document - Verifying document to be copy of delivery dockets, photos of mix
label | Frequency - Every Rain Garden
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.01.08 - Coconut (Coir) Matting
label | Acceptance / Conformance Criteria - Biodegradable Erosion
label | ○ Mat (Coir Mat). Biodegradable mulching fabric 450 gsm
label | Standard / Specification - DWG 2195 REV1. Schedule SP2 4.3.7
label | Verifying Document - Verifying document to be copy of delivery dockets, photos of mat onsite
label | Frequency - Every Delievery to Site
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint | 5.01.01 - Set-out
label | Acceptance / Conformance Criteria - Check set-out prior to excavation of Rain Garden.
label | Standard / Specification - PS - 2.2.12
label | Verifying Document - Hold Point Release
label | Frequency - Min 48h Notice
label | Verification Activity: Activity - H
label | Verification Activity: By - SUP
checkpoint | 5.01.02 - Excavation
label | Acceptance / Conformance Criteria - Excavations shall be completed in such manner that it is true to the drawings will allow novacoil to be laid true to the depths, grades and lines.
label | Standard / Specification - Downer
label | Verifying Document - Survey Data, Photos
label | Frequency - Prior to laying filter cloth
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 5.01.03 - GCL Liner Fixing to Kerb
label | Acceptance / Conformance Criteria - GCL Liner to be fixed to kerb as per manufacturers guidelines (Bentofix GCL 18.2, figure 14). Mechanical fasteners with stainless steel batten (connection bar) to be used to fix the liner to the kerb. Mechanical fasteners to be fixed 5 times ever meter of along the connection bar.
label | Standard / Specification - Manufacturers Guidelines 18.2
label | Verifying Document - Site Photos
label | Frequency - Prior to backfill
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.04 - GCL Sealing (Pipes)
label | Acceptance / Conformance Criteria - GCL Liner to be sealed around pavement drains and stormwater lines which connect into rain garden. Sealing shall be completed as per manufacturers guidelines (Bentofix GCL 18.3 & 18.4 Figuire 15). GCL shall be cut with a sharp utility knife. For horizontal pipes, vertical laps of min 1m are required. Inside the rain garden a clamp shall be used anchor the GCL lap to the pipe. Bentonite paste shall be be used in the void between the main GCL and GCL lap to ensure a water tight seal.
label | Standard / Specification - Manufacturers Guidelines 18.3 & 18.4
label | Verifying Document - Site Photos
label | Frequency - Prior to backfill
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.05 - GCL Repair
label | Acceptance / Conformance Criteria - GCL to be repaired as per manufacture's guidelnes (Bentofix PVB5100c). GCL becomes damaged, torn or punctured during installation, the affected area should be repaired. For damaged areas, a separate piece of GCL shall be used and extend past the comprimised section by 500mm in every direction. Bentonite shall be used to connect the seperate GCL to the main liner.
label | Standard / Specification - Manufacturers Guidelines 21
label | Verifying Document - Site Photos
label | Frequency - Prior to backfill
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.06 - GCL Inspection
label | Acceptance / Conformance Criteria - GCL to be installed as per manufacturers guide and true to the drawings.The inspection should include overlaps, alignments, penetrations, connections, detections of any defects, including installation damage.
label | ○ Detected falsely installed areas shall be marked, repaired and the repairs shall be inspected and approved engineer.
label | Standard / Specification - Manufacturers Guidelines 22.2
label | Verifying Document - Site Photos
label | Frequency - Prior to backfill
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.07 - Geotextile Installation
label | Acceptance / Conformance Criteria - All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
label | Standard / Specification - GWS 3.2.3
label | Verifying Document - Site Photos
label | Frequency - Prior to aggregate placement
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.08 - Bedding
label | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
label | Standard / Specification - TNZ F/5
label | Verifying Document - Photos, Sruvey Data
label | Frequency - Prior to laying Novacoil
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.09 - Joining Pipes
label | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
label | Standard / Specification - TNZ F/5
label | Verifying Document - Copy of delivery dockets, photos of joins onsite with tag showing class
label | Frequency - Every join
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.10 - Pipe Grade
label | Acceptance / Conformance Criteria - Grade of subsoils must be falling in the correct direction based on the IFC Drawings and at the correct grade (greater than 1% based on TNZ F/5)
label | Standard / Specification - TNZ F/5
label | Verifying Document - AsBuilt
label | Frequency - Every 10m
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 5.01.11 - Pipe Cover
label | Acceptance / Conformance Criteria - Pipe to have 100mm of drainage aggregate as top cover for pipe.
label | Standard / Specification - N/A
label | Verifying Document - Site Photos
label | Frequency - Every 10m
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 5.01.12 - Sand Placement
label | Acceptance / Conformance Criteria - Sand to be placed at a constant thickness of 100mm. Sand should be free of peaks and troughs.
label | Standard / Specification - N/A
label | Verifying Document - Site Photos
label | Frequency - Every Rain Garden
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.13 - Filter Media
label | Acceptance / Conformance Criteria - Filter media to be placed at a constant average thickness of 600mm, refer to drawing for detail. Filter media should be free of peaks and troughs.
label | Standard / Specification - N/A
label | Verifying Document - Site Photos
label | Frequency - Every Rain Garden
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.14 - Coconut Matting
label | Acceptance / Conformance Criteria - Mat shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
label | Standard / Specification - GWS 3.2.3
label | Verifying Document - Site Photos
label | Frequency - Every Rain Garden
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.15 - Scour Protection GAP 65 Rip Rap
label | Acceptance / Conformance Criteria - Scour protection shall be installed as per drawings around let downs, scruffy dome and the flush point end.
label | Standard / Specification - GWS 3.6 & BBO
label | Verifying Document - Site Photos/ Survey Data
label | Frequency - Every Rain Garden
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.01.01 - Construction Record Compilation
label | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.01.02 - Survey Records
label | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - As-builts taken every 10m prior to backfill
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 6.01.03 - Redline Drawings
label | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 6.01.04 - Defect, Snag and Punch List
label | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | Standard / Specification - Downer
label | Verifying Document - Register
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 6.01.05 - Photos
label | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
label | Standard / Specification - Downer
label | Verifying Document - Photo Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE