## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP 07 - Application of Waterproofing Template (Window Thresholds) | [5 empty] | ITP 07 - Application of Waterproofing Template (Window Thresholds)
section | Details
checkpoint | Obtain clearance to commence work.
checkpoint | Obtain approved shop drawings
checkpoint | Inspect and prepare substrate
label | Surfaces to be waterproofed must be sound, smooth and free from dust, loose matter, oil, grease or other contaminants.
checkpoint | Apply Epocote F100W epoxy primer
label | Apply one coat of Epocote F100W at a rate of 4m2/L
checkpoint | Apply Silcor LM PU. Detail internal corners, joints, turn-ups and penetrations to floor and wall
label | Minimum 15mm x 15mm fillet PU to all internal corners/turn-ups, joints and around penetrations.
checkpoint | Apply Silcor 140FB
label | Silcor 140FB acrylic to be applied by brush or roller in two coats at a combined thickness of 1.0mm (DFT).
checkpoint | Final QA review prior to sign off. Record and document.
holdpoint | Hold Point
checklist | ITP 08 - Application of Waterproofing Template (Podium) | [5 empty] | ITP 08 - Application of Waterproofing Template (Podium)
section | Details
checkpoint | Obtain clearance to commence work.
checkpoint | Obtain approved shop drawings
checkpoint | Prepare substrate.
label | Surfaces to be waterproofed must be sound, smooth and free from dust, loose matter, oil, grease or other contaminants.
checkpoint | Inspect prepared substrate.
label | Visual inspection.
label | Correct Falls 1:100
label | Moisture Meter ready under 5%
textbox | Moisture Meter Results:
holdpoint | Hold Point
checkpoint | Apply Primer BS
label | Apply one coat of Primer BS at 0.15kg/m2 approximately 5-7m2/L Allow to dry.
checkpoint | Apply Silcor LM PU. Detail internal corners, joints, turn-ups and penetrations to floor and wall
label | Minimum 15mm x 15mm fillet PU to all internal corners/turn-ups, joints and around penetrations.
checkpoint | Apply Silcor 575LB
label | Silcor 575LB polyurethane to be applied by brush or roller in one or two coats at a combined thickness of 1.5mm (DFT).
label | 1.75mm (WFT) Total
checkpoint | DFT Testing
label | Silcor 575LB polyurethane to be applied by brush or roller in one or two coats at a combined thickness of 1.5mm (DFT).
label | 1.75mm (WFT) Total
textbox | DFT testing results:
holdpoint | Hold Point
checkpoint | Holiday Testing – ELD (Electronic Leak Detection)
label | Pinhole testing
textbox | ELD testing results:
holdpoint | Hold Point
checkpoint | Final QA review prior to sign off. Record and document.
holdpoint | Hold Point