## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | First Fix - Communal space and corridor |  | First Fix - Communal space and corridor | 5ffdcd0f-130f-408a-8c95-5fd5065c119a
| checkpoint | All Pipe Work Secure:ie Cliping with Seismic
| checkpoint | Both Hose Tap feeds installed to waste room inside and out
| checkpoint | Incoming watermain connected to correct meter and on test
| checkpoint | Stack flood tested (attach photos)
| checkpoint | Inspection passed
| checklist | First Fix Plumbing - Services |  | First Fix Plumbing - Services | 712f4fee-2435-4142-9337-a46ea8bc32fa
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Floor grate installed in waste room and debirs clear (attach photos)
| checkpoint | CW booster room complete (attach photos)
| checkpoint | Fire main water feed installed as per plan (attach photos)
| checklist | First Fix Plumbing - Units & Multi Purpose |  | First Fix Plumbing - Units | e1e8c2a3-05dd-435b-b00e-dbdd6e848436
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Hot and cold pipe work installed to all plumbing fixtures (attach photos)
| checkpoint | Floor flanges installed
| checkpoint | All Pipe Work Secure:ie Cliping Silicone
| checkpoint | Hose Tap feed installed
| checkpoint | Incoming water connected
| checkpoint | Stack flood tested (attach photos)
| checkpoint | Inspection passed
| checkpoint | PVC Test plug removed , Cap closed and Hot cold pressure dropped and gauge removed.
| checklist | Second Fix - Services |  | Second Fix - Services | f2125f2d-865a-4ef4-9753-93bac0d5a186
| checkpoint | Hose taps are complete with Vacuum Breakers
| checkpoint | No debris in floor waste gully's
| checkpoint | All plumbing fittings and pipe removed from site
| checklist | Second Fix - Unit & Multi Purpose |  | Second Fix - Unit & Multi Purpose | 24afb054-fcd1-4010-97e8-7a9eb717988d
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | All plumbing fixtures installed commissioned and Leak free (attach photos)
| checkpoint | All fixtures siliconed in place where required
| checkpoint | Hose taps are complete with Vacuum Breakers
| checkpoint | White wall flanges installed to all plumbing penetrations
| checkpoint | Hot water cylinder installed to spec with Seismic restraints timber blocking and lagging (attach photo)
| checkpoint | Tempering valve set to required temperature (attach photo)
| checkpoint | No debris in floor waste gully's
| checkpoint | All plumbing fittings and pipe removed from site
| checklist | Underslab Plumbing - Fire main |  | Underslab Plumbing - Fire main | 3c6073a8-8b27-4a76-aa85-91b9b45026ca
| checkpoint | Correct location as per current plan - specify gridlines (attach photos)
| checkpoint | Pipe wrapped/protected (attach photos)
| checkpoint | Pressure tested to 1500KPa for 30mins (attach photos)
| checkpoint | Thrust blocks installed where required (attach photos)
| checkpoint | Flow test completed
| checklist | Underslab Plumbing - Gridlines 1-3 |  | Underslab Plumbing - Gridlines 1-3 | bf8a8bd0-512c-4f1a-a4d8-ef91821ce2f2
| checkpoint | Correct location as per current plan - specify gridlines (attach photos)
| checkpoint | Correct gradient (attach photos)
| checkpoint | Pipe wrapped/protected (attach photos)
| checkpoint | Flood test done (attach photos)
| checkpoint | Pipes capped or pretected from debris ingress (attach photos)
| checklist | Underslab Plumbing - Gridlines 3-5 |  | Underslab Plumbing - Gridlines 3-5 | e6da7c58-3dc1-4827-9720-c93dc8fc1d72
| checkpoint | Correct location as per current plan - specify gridlines (attach photos)
| checkpoint | Correct gradient (attach photos)
| checkpoint | Pipe wrapped/protected (attach photos)
| checkpoint | Flood test done (attach photos)
| checkpoint | Pipes capped or protected from debris ingress (attach photos)
| checkpoint | Watermain run as per plan
| checkpoint | Recycled watermain run as per plan
| checklist | Underslab Plumbing - Gridlines 5-7 |  | Underslab Plumbing - Gridlines 5-7 | 2220e847-ca09-41a4-83bb-2e0ee4daabef
| checkpoint | Correct location as per current plan - specify gridlines (attach photos)
| checkpoint | Correct gradient (attach photos)
| checkpoint | Pipe wrapped/protected (attach photos)
| checkpoint | Flood test done (attach photos)
| checkpoint | Pipes capped or protected from debris ingress (attach photos)
| checkpoint | Hot and cold pipe work installed as per plan (attach photos)