## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource ID
checklist | ITP-189-STR-PSDS-Precast Material Inspection | itp |  |  |  |  | ITP-189-STR-PSDS-Precast Material Inspection Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-189-STR-PSDS - Precast Material Inspection
label | ITP Description: PSDS - Precast Material Inspection
label | Discipline (e.g. CIV/STR/RAIL): 189-STR
label | Revision Number: 0
label | Revision Date: 30/07/2024
label | ITP created by: Dan O'Brien
label | ITP approved for use by: Victor Mira
section | Precast Deliveries
checkpoint | 1 - Delivery Details
textbox | Enter: Delivery Docket Number:
textbox | Enter: Delivery Date:
textbox | Enter: Element ID (s):
label | Attach: Delivery Docket and packaging Slip
label | METHOD: Document Review, Visual
label | FREQUENCY: Each Delivery
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 2 - Packaging Inspection-Quantity
label | ACCEPTANCE CRITERIA: Does the number of packages in the delivery match that listed on the freight list/packaging slip?
label | METHOD: Visual
label | FREQUENCY: Each Delivery
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 3 - Packaging Inspection-Delivery Contents
label | ACCEPTANCE CRITERIA: Have the correct precast elements been delivered? Check labels/markings, birth certificates and check actual dimensions against dwgs to make sure. Check that elements have the correct number of lifting points and hold-down brackets.
label | METHOD: Document Review, Visual
label | FREQUENCY: Each Delivery
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 4 - Packaging Inspection-Birth Certificate
label | ACCEPTANCE CRITERIA: Is the delivery accompanied by Precast items Birth Certificates?
label | ○ Precast components are to be marked on the birth certificate.
label | ○ Cast date and lot are to be marked on the birth certificate.
label | ATTACH: BIRTH CERTIFICATES
label | METHOD: Document Review
label | FREQUENCY: Each Precast item
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 5 - Packaging Inspection-Transport
label | ACCEPTANCE CRITERIA: Is the condition of packaging acceptable.
label | ○ Precast items are protected from damage during the transport. Check for cracking or damage around dunnage locations.
label | METHOD: Visual
label | FREQUENCY: Each Precast item
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 6 - Pre-Lift Inspection-Transport
label | ACCEPTANCE CRITERIA: Are the elements stacked in the correct way to allow for lifting per the approved lift plan? Check lifting points for damage to concrete or lifters. Is there safe access to lifting points and elements can be lifted without damaging the element.
label | METHOD: Visual
label | FREQUENCY: Each Precast item
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 7 - Fault IDs:
label | ACCEPTANCE CRITERIA: For each precast type delivered, check for the following:
label | 1 - Identification markings match the panel type
label | 2 - Element fabricated as per drawings
label | 3 - Cracks
label | 4 - Spalling/Damage to concrete surface
label | 5 - Exposed Reinforcement
label | 6 - Damage to Anti-Graffiti coating
label | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
label | 8 - Cast-in items incorrect or damaged inc bolts, hold-down brackets, conduits etc.
date | Date Completed:
checkpoint | 8 - Check for Faults - 1
label | REFERENCE: Item 7 on this Checklist
label | METHOD: Visual, Measure
label | FREQUENCY: Each precast type delivered
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 8 - Check for Faults - 2
label | REFERENCE: Item 7 on this Checklist
label | METHOD: Visual, Measure
label | FREQUENCY: Each precast type delivered
textbox | Enter: Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 8 - Check for Faults - 3
label | REFERENCE: Item 7 on this Checklist
label | METHOD: Visual, Measure
label | FREQUENCY: Each precast type delivered
textbox | Enter: Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 8 - Check for Faults - 4
label | REFERENCE: Item 7 on this Checklist
label | METHOD: Visual, Measure
label | FREQUENCY: Each precast type delivered
textbox | Enter: Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 8 - Check for Faults - 5
label | REFERENCE: Item 7 on this Checklist
label | METHOD: Visual, Measure
label | FREQUENCY: Each precast type delivered
textbox | Enter: Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | 8 - Check for Faults - 6
label | REFERENCE: Item 7 on this Checklist
label | METHOD: Visual, Measure
label | FREQUENCY: Each precast type delivered
textbox | Enter: Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This Checklist
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP