## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 01bb7add-157c-4745-a416-62c76b79e49c |  | checklist | Underslab QA |  |  |  |  | Yes | Underslab QA | 48165e4b-529e-49da-9f5c-e1ad0b5566aa
checkpoint-group | a3d6c376-e4d4-47dc-89e6-e13f62d46cb2 |  | section | Pipework
checkpoint-status | 94b811f8-a1cf-4bc3-8c71-8edfc375704f |  | checkpoint | Service
select | 59077681-6056-5cee-8cbd-d8261751616d |  | dropdown | Service being checked | Stormwater, Waste Water, Gas, Water supply, others
text | fd5b0906-39e4-557f-a004-7374999abec0 |  | textbox | If others
checkpoint-status | f00303c6-2ce8-46c0-b42e-d9a6925655bd |  | checkpoint | Pipework Material as specified/scheduled/drawn
checkpoint-status | b57d3980-5f26-4c3d-b008-af6d92270bf9 |  | checkpoint | Grid lines and fitting dimensions confirmed
checkpoint-status | da7dcb01-6ead-46ac-a91e-03dbf3a49144 |  | checkpoint | Drain invert checked
checkpoint-status | 73de1130-a587-4731-91f4-3003d0d456aa |  | checkpoint | Gully position checked
checkpoint-status | 5f18d272-a00d-4f40-a461-a9bbd4651c79 |  | checkpoint | Floor levels established
checkpoint-status | 58eb980e-3179-43bc-a3b4-52a3fec53c96 |  | checkpoint | Falls checked
checkpoint-status | 97fd7791-0a3c-48db-b228-00ed66e914e4 |  | checkpoint | Drainlayer/Plumber interface Points established
checkpoint-status | 4b806723-9472-4ec2-b69e-9292263af986 |  | checkpoint | Penetrations co-ordinated with main contractor
checkpoint-status | 8ccf2bd2-1822-4195-9bac-9667b8ab3a42 |  | checkpoint | Pipework backfilled correctly
checkpoint-status | 9ed7c7d6-2f19-4968-9180-273979ea4271 |  | checkpoint | Identification strip installed if required
checkpoint-status | bf265a6e-fd1b-4f0a-b440-82104373256e |  | checkpoint | Open ends of pipework capped off to prevent dirt ingress
checkpoint-status | 71c72632-cb55-457d-95c6-6a3a439a738e |  | checkpoint | Work completed and photos attached
checkpoint-group | 198ac627-e57f-4a08-89f3-52fb2ebdffc1 |  | section | Testing
checkpoint-status | d69af974-5a87-44b9-b4f3-7b297b21cbbd |  | checkpoint | Cold Water
text | 3b9b0a93-5293-552d-863d-c04a2e7b4442 |  | textbox | Specified to
text | dd21c393-426f-50ff-b02b-86cebeb6403a |  | textbox | Test Pressure
text | b5692aa0-df0c-5b68-88f7-f8edc8bde473 |  | textbox | Duration
checkpoint-status | 1edafe76-fbd7-4cb4-a163-b36351fd7c5c |  | checkpoint | Waste water
text | 779d6570-7195-5713-a218-a2d450ab0668 |  | textbox | Specified to
text | 00f14c5e-574b-55ad-8e4c-d9b0f0463a1e |  | textbox | Test Pressure
text | 33c73873-e67c-513b-a0f0-b26e19b4bda8 |  | textbox | Duration
checkpoint-status | 71de8a76-8cc6-4289-8a22-2e3db7adcc07 |  | checkpoint | Gas Services
text | df514b41-6ba5-50b7-81b9-5e3f10a2a253 |  | textbox | Specified to
text | ca5cbe1c-1710-54fa-a392-521a890fc01c |  | textbox | Test Pressure
text | a28f259f-dc88-5412-a53e-8ad0256cb710 |  | textbox | Duration
checkpoint-status | a6969dfd-18eb-4b13-ab5d-ada7550a9347 |  | checkpoint | Others
text | d958ddd3-fee4-5396-8a82-95a6238dc954 |  | textbox | Specified to
text | 0ec2f6a5-be31-565e-8741-9a3bd557a55b |  | textbox | Test Pressure
text | 3f600b98-b37a-56f8-9604-e01e35f5c72b |  | textbox | Duration
checkpoint-group | 240a152d-c6fc-464a-8f10-3c3b548e5a6f |  | section | Handover
checkpoint-status | de1fb8f2-7693-4f8b-8d73-64735851dc08 |  | checkpoint | Area left clean and tidy
checkpoint-status | 6dbcae18-f80d-4d7f-80a3-76cadce69702 |  | checkpoint | Local Authority Verification
label | fbfdcb98-7400-591b-9ff2-259a39327df8 |  | note | Plumbing inspection complete and passed as satisfactory
checkpoint-status | 310f1390-46de-4d17-8084-7d63ab45ce5a |  | checkpoint | DL Good Verification
label | ed288109-083a-5583-84a5-dd1e71cefc5e |  | note | Plumbing Complete and ready for backfill/ concrete pour
checkpoint-status | c0c5da22-3ed6-49d6-9e89-2d916732ee31 |  | checkpoint | Main Contractor verification
checklist-sectioned |  |  | checklist | Accident & Incident Investigation Report |  |  |  |  | Yes | H&S - Accident Report | 63162d14-115f-4bf2-9acf-acd2a38a3c85
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Completed
text | e9de5bfb-8771-4638-b38c-6460b4a51ce3 |  | textbox | Name of Investigator:
checkpoint-group |  |  | section | Particulars of Incident
checkpoint-status |  |  | checkpoint | Particulars of Incident Details Completed
select | 6b525f4e-f45b-4da7-8df5-23fe6bff84be |  | dropdown | Day of Incident: | Friday,Monday,Saturday,Sunday,Thursday,Tuesday,Wednesday
text | 7e5d562b-6c37-42a1-8dac-2df84d546b73 |  | textbox | Time:
text | 77139ee8-1724-49ec-b32f-6297f71fb24d |  | textbox | Project/Site:
text | a3d0113e-1792-4d2a-81a4-c196efecce04 |  | textbox | Date Reported:
checkpoint-group |  |  | section | Injured Person Details
checkpoint-status |  |  | checkpoint | Injured Person Details Completed
text | bcbcce61-cfa2-48bc-982c-c5b5e71a5820 |  | textbox | Name:
text | 557319b1-18ca-4e15-8145-bf19756ed742 |  | textbox | Age:
text | 17d87fda-3003-4f2f-800d-c104d51100a6 |  | textbox | Phone Number:
text | b250bb03-568c-46a4-930f-063d05523218 |  | textbox | Address:
text | 183cd7d2-02cd-4259-8bcf-687060e2ae22 |  | textbox | Reported date of incident:
text | cb2b501a-8ccb-408b-9bb5-195476e5b88e |  | textbox | Length of employment:
text | 9df08fae-8517-426e-a3fc-1ebb04a7daf1 |  | textbox | Time on job:
checkpoint-status |  |  | checkpoint | Type Of Injury:
boolean | 7ade6143-a0ba-43c7-94c8-17ffd8a461cb |  | tickbox | Strain/sprain
boolean | 5738b1fe-e0ff-4949-ba49-7c573b173ca4 |  | tickbox | Fracture
boolean | 6b4511fb-6c5c-4a9b-b2a1-9c48b3371cfa |  | tickbox | Laceration/cut
boolean | 24005c68-47eb-4552-ba5b-1dc0d9723144 |  | tickbox | Bruising
boolean | 769c2254-a4b9-40f7-8c98-a1b987acd4f0 |  | tickbox | Scratch/abrasion
boolean | 8e754d90-98ee-4346-8ef7-4e37d0cd0355 |  | tickbox | Amputation
boolean | 0f62ffbd-d654-4a44-b6ca-c8c5fd6bcf05 |  | tickbox | Burn scald
boolean | c8c5f313-eb09-4171-b9df-32520fffab31 |  | tickbox | Dislocation
boolean | 7e48ef93-56fc-4c31-8441-2b6734f61a1c |  | tickbox | Internal
boolean | 74f4e66e-8287-4131-ab3d-ea35d3e9e914 |  | tickbox | Foreign body
boolean | c0050bb4-329d-4731-b3b6-b00f4fe27d01 |  | tickbox | Chemical reaction
boolean | 4e1cd37b-f7a7-49d4-b988-e1a523b2d87e |  | tickbox | Other
text | 7e4b43c5-0b61-4b6b-ba7e-ec7748fc5de3 |  | textbox | If other please specify:
text | 18e138ea-f591-4403-a2ad-9bddb2e1f2f8 |  | textbox | Injured Part of Body:
checkpoint-group |  |  | section | Damaged Property
checkpoint-status |  |  | checkpoint | Damaged Property Details Completed
text | b40e64d9-5932-48a4-9420-88c8273d482f |  | textbox | Property/material damaged:
text | 7aa7cc35-9187-4c4d-96be-4b44ec4ab825 |  | textbox | Nature of damage:
text | 6eb6370f-545a-42cd-8129-fe259589d2bf |  | textbox | Object/substance inflicting damage:
checkpoint-group |  |  | section | Incident
checkpoint-status |  |  | checkpoint | Incident Details Complete
text | 4cd700c0-230d-460a-83f9-fd60b8704fb7 |  | textbox | Describe what happened (space overleaf for diagram – essential for all vehicle incidents):
checkpoint-group |  |  | section | Analysis
checkpoint-status |  |  | checkpoint | Analysis Details Completed
text | 04e074f8-e295-4677-856b-5c28255dd0ae |  | textbox | What were the causes (root and contributing causes) of the incident?
text | 1daea218-712c-4f70-9767-9a8134812e18 |  | textbox | Root causes – safety system failures:
text | c6818664-ec27-40a9-a8a7-26f7ef16536b |  | textbox | Contributing causes – unsafe acts and conditions:
checkpoint-group |  |  | section | Prevention
checkpoint-status |  |  | checkpoint | Prevention Details Completed
text | 68d803a6-e0f5-415b-a68d-026a47c8da2f |  | textbox | What action has or will be taken to prevent a recurrence? Tick items already actioned
boolean | bc67a7a4-86be-476f-be81-80038ecf4d50 |  | tickbox | Completed
text | bfa9b6c8-e5a0-4595-b25a-fe1bafc23161 |  | textbox | By Whom:
text | e03e6bef-8361-4a24-8eef-856453f85d7a |  | textbox | When:
checkpoint-group |  |  | section | Treatment and Investigation of Incident
checkpoint-status |  |  | checkpoint | Treatment and Investigation of Incident Details Completed
text | 659ceae3-0e40-4182-9989-845fda6a338f |  | textbox | Treatment and Investigation of Incident :
text | 0a690191-d11c-4abd-975b-a7dccd78628d |  | textbox | Name of person giving First Aid:
text | 26885b6b-063a-4c38-a2cc-5794f0204418 |  | textbox | Doctor/Hospital:
text | 1c479a88-1f1b-42c5-b9e7-6ce977689cb3 |  | textbox | Incident investigated by:
text | c19b857e-6fb6-4c5d-bb32-996e3a28f9fb |  | textbox | Date:
select | fc88a287-6242-4d70-8e73-0d2270065565 |  | dropdown | Worksafe NZ advised | No,Yes
text | 913c4a48-55ec-4ab0-aa2e-c6e004b75fe5 |  | textbox | Date:
checklist-sectioned | 79699b7f-ddaa-4892-9e41-fe1ddbe2aae6 |  | checklist | Plumbing Fitoff QA |  |  |  |  | Yes | Plumbing Fitoff QA | 6be0258b-e159-4803-a05f-3160a19b1f85
checkpoint-group | 389f538c-ba55-472c-af5c-2cd4d168682e |  | section | Wash Hand Basin
checkpoint-status | a5bbec99-2a3d-43d7-84a6-912c96515b55 |  | checkpoint | Basin level and secure
checkpoint-status | 7f159540-2394-4604-bf72-f0ab1b835900 |  | checkpoint | Waste connection watertight, plug supplied
checkpoint-status | 7c61a64c-0e70-4909-8552-c1fee8e4a228 |  | checkpoint | Water connection watertight, tap secure
checkpoint-status | 0f448c63-01bd-4b73-96c2-186221442006 |  | checkpoint | Hot & Cold waterflow satisfactory, no water hammer
checkpoint-group | 53c1a268-16dd-4334-9d32-14d442176aa8 |  | section | Toilet
checkpoint-status | d2751780-ac60-4cd2-bde8-2e8684d809f9 |  | checkpoint | Securely fixed, silicone at floor
checkpoint-status | 677889aa-c932-48c8-8848-53a2e48c7d8e |  | checkpoint | Flush and cistern fill operation checked
checkpoint-status | ce678bfc-fe5d-438e-bb57-f711884f167c |  | checkpoint | Water connection watertight – cold water
checkpoint-group | 89522b2f-108a-46bf-a42f-a114c1912725 |  | section | Shower
checkpoint-status | 2262605a-a87a-4054-9f44-d0f4348ae108 |  | checkpoint | Hot & Cold waterflow satisfactory, no water hammer
checkpoint-status | 374c9240-1570-4e79-88be-4dd10ce26c61 |  | checkpoint | Waste clear
checkpoint-status | 74b507a2-a556-4b6e-8efb-c9b98d85f860 |  | checkpoint | Cover plate fixed securely
checkpoint-group | 3ee82f91-a39f-4a3a-bc60-636dcb2ec3bf |  | section | Bath/Shower
checkpoint-status | 338de459-94de-463c-9dd7-79f4644fa01a |  | checkpoint | Waste clear, plug installed
checkpoint-status | 2f6a13d0-96c3-406a-a5df-8217d08b1005 |  | checkpoint | Divertor operation working (where applicable)
checkpoint-status | ba47021f-1f84-4708-866b-239506597acf |  | checkpoint | Hot & Cold waterflow satisfactory, no water hammer
checkpoint-status | fe3d8f70-cb81-4e2a-bebe-b7197df3726c |  | checkpoint | Cover plate/spout fixed securely
checkpoint-status | fe5356d5-6783-4036-9d49-7fd815bfce0e |  | checkpoint | FWG
checkpoint-status | 36d84eee-a87d-43de-aeb3-a9d420efb452 |  | checkpoint | Grate flush with floor or slightly below
checkpoint-status | ac7d1e40-21e4-4313-bb1f-03471d746029 |  | checkpoint | Waste clear of debris
checkpoint-group | b908d02d-4026-4737-9733-41b2f4725610 |  | section | Amenity Areas / Kitchens etc
checkpoint-status | 6679457a-5cad-4ca0-8775-26050b059364 |  | checkpoint | Hot & Cold waterflow satisfactory, no water hammer
checkpoint-status | 904154ec-9b86-44aa-97c1-6d53fa8849df |  | checkpoint | Water connection watertight, tap secure
checkpoint-status | 61e34489-b244-46f6-924d-ca664ee1e76c |  | checkpoint | Waste connection watertight
checkpoint-status | 7cd6eedf-c43b-4244-bda8-044bb5b18e3f |  | checkpoint | Dishwasher connection watertight
checkpoint-status | 4a542340-1acd-4e2f-99f9-f04cc707e85b |  | checkpoint | Wastemaster connection watertight
checkpoint-status | 2b17e2e7-a71f-4247-a708-c84162afab97 |  | checkpoint | Overflow connection watertight
checkpoint-status | bc68baa8-401a-4530-bce8-d8fda6d86fa3 |  | checkpoint | Waste clear, plug installed
checkpoint-group | f66a0014-e454-41f0-9dc2-2674acb92f3f |  | section | HWC
checkpoint-status | 7b47774c-37ce-489b-a6dd-ceb5d77d5bd8 |  | checkpoint | Seismic Restraints installed
checkpoint-status | e9851a11-0da2-4146-b9de-1001a95dbfc0 |  | checkpoint | Expansion valves operation checked
checkpoint-status | 8c542b63-2d8b-4ec9-b21a-ac29756d1c36 |  | checkpoint | Pipework securely fixed
checkpoint-status | ecbb2fe7-4d5f-49e5-aefe-a2f4467310cc |  | checkpoint | Waste connection watertight
checkpoint-status | 1b8e8f60-928e-401e-b9dc-86f63c18ff70 |  | checkpoint | Tempering valve set correctly – water temperature checked
checkpoint-group | 961bd70b-713a-4293-a509-0cf8b9d032a7 |  | section | Handover
checkpoint-status | 83bb1418-c3e2-4f65-b4d9-8698cbe7b639 |  | checkpoint | Area left clean and tidy
checkpoint-status | 7fe2ee7d-460f-4c1f-8187-7d813fc16a0f |  | checkpoint | DL Good Verification
holdpoint | f2d996d9-5628-4e0d-8361-2759e3c8dcc8 |  | signoff | Plumbing Complete and ready for lining
checkpoint-status | 3731a40b-5c44-4108-b228-26dcde801a86 |  | checkpoint | Main Contractor verification
holdpoint | 1b510de7-2d4d-4198-9259-e874ae555c8e |  | signoff | Plumbing Complete and ready for lining
checklist-sectioned |  |  | checklist | Toolbox Checklist |  |  |  |  | Yes | H&S - Toolbox Talks | 8f6b284f-1ba0-4dd9-8f4e-91a024ebe2c0
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Complete
text | 305f2185-4e3a-4417-ae95-885bb0b1de8a |  | textbox | Office location:
text | b2fd07dc-8f92-4010-8a71-46e71c03ff63 |  | textbox | Who is running this meeting:
text | 1d3d0b15-a56a-498c-b16b-2afa5f8e2573 |  | textbox | Company
text | 88e78785-0eea-4ad8-a896-1622379eacfc |  | textbox | Agenda items:
text | ce0224f5-54b8-47a5-b890-7a5416c69623 |  | textbox | Theme of the week (topic for focus):
checkpoint-group |  |  | section | Health and safety issues
checkpoint-status |  |  | checkpoint | 1.
text | 2ec0fc9e-b14f-43a5-bb60-4df5d5ab3ab4 |  | textbox | Issues raised from site safety inspection:
text | 1b5fcc97-f30c-4727-a783-29c22206fa41 |  | textbox | Actions:
text | b5107b7c-d991-4507-a1a9-6180db10057c |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 2.
text | 8978adff-e266-4646-b125-178fba33a0dd |  | textbox | Issues outstanding from previous briefings:
text | 507afe6b-4ee7-4485-bd4b-99698d8e8f47 |  | textbox | Actions:
text | 7d92f59d-ce24-4ec9-8428-a92c87f559e3 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 3.
text | 305b3039-3f3d-45b4-8536-fb028ee2010b |  | textbox | Employee-raised issues:
text | c98f50a5-1fb4-45b7-86e0-301132ec8b7c |  | textbox | Actions:
text | c250b53e-5070-459c-b01f-af8fcce5cdb7 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 4.
text | 26f6b1aa-3048-4106-a64b-dc4e2cf75ec3 |  | textbox | Positive safe-action observations:
text | dd2ab926-5b94-46f6-a93f-eed5fa00233e |  | textbox | Actions:
text | 464cc30b-c155-4299-b08c-242a1821bd72 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 5.
text | ba0166ff-1cef-49fe-a54e-fce60528feea |  | textbox | Incidents or injuries:
text | 8f9035d5-30e5-4ea2-9ec4-4d19df05b3fd |  | textbox | Actions:
text | 1a84fee3-7466-42bd-a3ff-39c2785201a3 |  | textbox | By who and when:
checkpoint-group |  |  | section | Job plans reviewed
checkpoint-status |  |  | checkpoint | Job/Task & Action/Outcome
text | cb9c1ca7-7b79-4c62-8f74-3a1d70af5886 |  | textbox | 1.
text | d396585a-1ce3-4d1e-b838-375ab4165dd0 |  | textbox | 2.
text | 4657beed-8141-41c2-926d-0d7204a497a2 |  | textbox | 3.
text | 1e162112-08ad-40c3-9d33-6c4bac52a906 |  | textbox | 4.
text | fd629f21-4050-47b3-b236-26daf8c94903 |  | textbox | 5.
text | a08ea05c-aa58-425b-9cb6-e2fa8951a414 |  | textbox | 6.
checkpoint-group |  |  | section | Operational issues
checkpoint-status |  |  | checkpoint | Issue & Action
text | 301f9ad4-6682-45c0-aa57-7b074b0e8a13 |  | textbox | 1.
text | 1373bee6-816f-408a-97a0-72f99b461b6e |  | textbox | 2.
text | c487e999-fa82-493c-b540-e056d94778fb |  | textbox | 3.
text | 5341a99d-52f8-4c86-8e11-6e8adfb0627e |  | textbox | 4.
text | 8e55092c-df52-43d0-b019-a8e67550ae09 |  | textbox | 5.
text | b87136a8-71c4-41f7-9cdb-74d4b55b5521 |  | textbox | 6.
checkpoint-group |  |  | section | Other business
checkpoint-status |  |  | checkpoint | Item & Action
text | 2e63def1-4462-4998-b972-d5125960181e |  | textbox | 1.
text | 044404a1-6065-4d33-8f96-7da9ab2eaf3a |  | textbox | 2.
text | 1e321545-4537-44dd-9443-3ae2c58d572b |  | textbox | 3.
text | e3214f18-5e4b-42bf-856b-435adffda167 |  | textbox | 4.
checkpoint-group |  |  | section | Attendees
checkpoint-status |  |  | checkpoint | Add name and Photo of attendees
checkpoint-group |  |  | section | Review by management
checkpoint-status |  |  | checkpoint | Reviewed and signed off
text | 054479d9-523d-4c50-88ce-626d6600059d |  | textbox | 1.
text | e1ea14ce-04e9-4c55-b0e6-131f75ee169d |  | textbox | 2.
checklist-sectioned |  |  | checklist | Site Inspection Checklist |  |  |  |  | Yes | H&S - Site Safety Inspection | bd120df7-c411-4082-aabf-b8aae3a06ced
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Complete
text | 8b03cbae-c408-4ae9-a756-cca7018dea83 |  | textbox | Site/Location :
text | 52914ecc-91b7-4603-9495-6a1e5ad3bd75 |  | textbox | Date
text | 8ff362f0-afb9-45ca-87d4-347265a7e11e |  | textbox | Name of Inspector :
checkpoint-group |  |  | section | Site Control
checkpoint-status |  |  | checkpoint | Hazard Board and signage up-to-date
checkpoint-status |  |  | checkpoint | Environmental plan - issues
text | cae0f94e-0878-4302-855f-50626b9940cc |  | textbox | Toolbox talk last date:
checkpoint-status |  |  | checkpoint | Safety inductions for all on-site
checkpoint-status |  |  | checkpoint | Safety notice board current
checkpoint-group |  |  | section | Site Facilities
checkpoint-status |  |  | checkpoint | Offices clean, adequate & good lighting
checkpoint-status |  |  | checkpoint | Smoko sheds - clean, portable water
checkpoint-status |  |  | checkpoint | Toilets - clean, washing water
checkpoint-status |  |  | checkpoint | Tool /equipment sheds adequate
checkpoint-group |  |  | section | General Site Tidiness and Access ways
checkpoint-status |  |  | checkpoint | Clear, safe access to work areas
checkpoint-status |  |  | checkpoint | Stairways and accessways clear
checkpoint-status |  |  | checkpoint | Hoardings /fence and gates secure
checkpoint-status |  |  | checkpoint | Loose materials secure from wind
checkpoint-group |  |  | section | Personal Safety Equipment
checkpoint-status |  |  | checkpoint | Signage displayed and legible
checkpoint-status |  |  | checkpoint | Hardhats being worn
checkpoint-status |  |  | checkpoint | Correct footwear being worn
checkpoint-status |  |  | checkpoint | Glasses /ear muffs /vests /masks used
checkpoint-group |  |  | section | First Aid/Fire Prevention
checkpoint-status |  |  | checkpoint | First Aid Box Available
checkpoint-status |  |  | checkpoint | Accident register
checkpoint-status |  |  | checkpoint | Fire Extinguishers
boolean | 12bab111-d5d2-4ba9-87f2-979c842a9df6 |  | tickbox | Available
boolean | 61ea2b23-6ac8-44f8-9d40-86c8daf1dd62 |  | tickbox | Current (12mth)
boolean | 3f3e012d-918a-4137-9689-dcced1049dcc |  | tickbox | Sufficient number
checkpoint-status |  |  | checkpoint | Evacuation
boolean | 7aa1d51b-82ee-46ea-a2d8-8922b951f5d1 |  | tickbox | Procedure current
boolean | 62e3bbb3-5108-4954-b02d-7071877274bd |  | tickbox | All emergencies incl
checkpoint-group |  |  | section | Cranes/hoist/lifting equipment
checkpoint-status |  |  | checkpoint | Proper lift assessment plan done
checkpoint-status |  |  | checkpoint | Crane certification current
checkpoint-status |  |  | checkpoint | Slings/chains certified
checkpoint-status |  |  | checkpoint | Operator procedures in place
checkpoint-status |  |  | checkpoint | Inspections being done
checkpoint-status |  |  | checkpoint | Man cage available
checkpoint-status |  |  | checkpoint | Emergency plan in place
checkpoint-group |  |  | section | Compressed air equipment
checkpoint-status |  |  | checkpoint | In good condition
checkpoint-status |  |  | checkpoint | Appropriate guards fitted
checkpoint-status |  |  | checkpoint | Trained user
checkpoint-group |  |  | section | Excavations
checkpoint-status |  |  | checkpoint | Correctly Shored
checkpoint-group |  |  | section | Welding/gas cutting
checkpoint-status |  |  | checkpoint | Hot work permits being issued
checkpoint-status |  |  | checkpoint | Fire extinguishers on hand
checkpoint-status |  |  | checkpoint | Operators using PPE
checkpoint-group |  |  | section | Electrical Equipment
checkpoint-status |  |  | checkpoint | Main board lockable /weatherproof
checkpoint-status |  |  | checkpoint | Current tagged and damage-free leads
checkpoint-status |  |  | checkpoint | Current tagged plant
checkpoint-status |  |  | checkpoint | Current tagged lifeguards
checkpoint-status |  |  | checkpoint | Leads safely placed
checkpoint-status |  |  | checkpoint | Equipment in good condition
checkpoint-status |  |  | checkpoint | Appropriate guards on equipment
checkpoint-status |  |  | checkpoint | Adequate temporary lighting
checkpoint-group |  |  | section | Chemicals
checkpoint-status |  |  | checkpoint | Correctly stored
checkpoint-status |  |  | checkpoint | Safety Data Sheet (SDS) available
checkpoint-status |  |  | checkpoint | Operators using PPE
checkpoint-group |  |  | section | Tools
checkpoint-status |  |  | checkpoint | PAT tool WoF current and secure
checkpoint-status |  |  | checkpoint | Staff trained in tool use (SWPS)
checkpoint-status |  |  | checkpoint | PAT signage on site
checkpoint-group |  |  | section | Scaffolding
checkpoint-status |  |  | checkpoint | Notifiable weekly Scaftag/current
checkpoint-status |  |  | checkpoint | Handrails/mid-rails
checkpoint-status |  |  | checkpoint | Toe boards
checkpoint-status |  |  | checkpoint | Platforms
checkpoint-status |  |  | checkpoint | Ladders/stairs
checkpoint-status |  |  | checkpoint | Base sound
checkpoint-status |  |  | checkpoint | Work platforms clear
checkpoint-status |  |  | checkpoint | Platforms trip free
checkpoint-status |  |  | checkpoint | Planks tied down
checkpoint-status |  |  | checkpoint | Headroom clear
checkpoint-status |  |  | checkpoint | Ties/bracing adequate
checkpoint-group |  |  | section | Ladders
checkpoint-status |  |  | checkpoint | Good condition
checkpoint-status |  |  | checkpoint | Secured top and bottom
checkpoint-status |  |  | checkpoint | Stays to step ladders
checkpoint-status |  |  | checkpoint | Working 2 steps down
checkpoint-group |  |  | section | Fall Hazards
checkpoint-status |  |  | checkpoint | Fall Hazards
checkpoint-status |  |  | checkpoint | Floor openings
checkpoint-status |  |  | checkpoint | Lift shafts
checkpoint-status |  |  | checkpoint | Stairs
checklist-flat |  |  | checklist | Variation Details - |  |  |  |  | Yes | Add Variation | ec9d7dcd-9b3a-4411-b2c3-3570562a1c54
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Reference/Drawing/Instruction Number
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Variation Area
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Materials & labour breakdown
holdpoint |  |  | signoff | Request Variation Acknowledgement
checkpoint-no-status |  |  | checkpoint | Staff & Time Details
text | bc9e0873-f032-484d-86a6-d3dfa4709a87 |  | textbox | Total number of staff involved
text | 994d6c3a-86bd-474a-ac6e-5f5b1ebbb2a6 |  | textbox | Total hours taken to do the work
label | 31a6bfbb-61f2-4a45-b21a-476d0cd8db83 |  | note | Once staff and time details are inputted above please attach client approval and signoff (click the paperclip below)
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  |  | signoff | Request Variation Signoff
checklist-sectioned | 42e13d6e-4e0c-48e1-a197-639c34945088 |  | checklist | Plumbing Preline QA |  |  |  |  | Yes | Plumbing Preline QA | f895c3c7-8f7d-46fc-be67-5f892c3eb30a
checkpoint-group | 28d0abeb-294a-4a58-b89f-d2368d62ac8a |  | section | Preline QA
checkpoint-status | c13d80db-36b4-49a9-ae2e-783ec47bec73 |  | checkpoint | Area Accessible
checkpoint-status | f3b77235-7666-41e7-aed8-7b4e28f62bdb |  | checkpoint | Service
select | fcef3941-4379-584c-b76e-411bd9552042 |  | dropdown | type | Hot Water, Gas Service, Vent, Condensate, Cold Water, Flushing Water, Soil/Waste, Other
text | 91e5390c-bbb8-59e7-ae81-11113f5e1fdc |  | textbox | If others
checkpoint-status | 202fb441-fa6d-4eb6-9ec2-6b8e8f7204d7 |  | checkpoint | Pipework securely clipped
checkpoint-status | 330a4927-08b8-41b1-8d8b-5a8f6d867fac |  | checkpoint | Lagging installed
checkpoint-status | d0acdc25-95dd-4596-8373-a2ba93f8dd3c |  | checkpoint | Seismic restraints installed
checkpoint-status | b908ad51-834f-4403-9384-1d67b0d257d3 |  | checkpoint | Fire collars fitted
checkpoint-status | c3850893-ad5e-43ef-93f9-30a57c1a54f1 |  | checkpoint | Penetrations sealed through floors
checkpoint-status | b59828fa-cd59-4fab-8181-666fc2fcf220 |  | checkpoint | Outlet positions checked for
boolean | fece330a-5d79-56ac-b815-69ecdf7c1388 |  | tickbox | Location
boolean | 3eded9b4-8a3c-561c-a1ce-0448f7114a4c |  | tickbox | Height
checkpoint-status | 164b7184-ac8f-420a-9015-0d32ec4f063a |  | checkpoint | Heights – Finished floor height verified with Main Contractor
text | f22dd6e0-a0ac-510a-8db0-d536bc11ba81 |  | textbox | mm
checkpoint-status | df0d0e52-0906-4f3c-9a04-6b166623e810 |  | checkpoint | Projection of valves, shower mixers and the like correct for second fix
checkpoint-status | 4e384930-0ab8-403c-b854-69096d154f5f |  | checkpoint | Nogs installed for second fix installation
checkpoint-status | 9c55d0c7-8672-47b4-b292-85787815cc35 |  | checkpoint | Pipework identification installed if required
checkpoint-group | ff00ac40-44a1-4519-a307-68bf409842a7 |  | section | Testing
checkpoint-status | 51e2de3e-b79f-4d0f-b4bd-89f4f8380dc2 |  | checkpoint | Hot Water
text | b9d66ecf-7f0f-59ee-a5c6-fcdc60745f13 |  | textbox | Specified to | Kpa
text | eaf0fe90-daeb-5316-bb41-34ce8b8510f9 |  | textbox | Test Pressure | Kpa
text | 2f88b9bc-6a82-5d7a-9de0-2ee239feca88 |  | textbox | Duration
checkpoint-status | a495de36-1912-4e82-9edb-b84df63f2444 |  | checkpoint | Cold Water
text | 9f76a64c-6a2f-5693-ad8f-d4d830bca695 |  | textbox | Specified to | Kpa
text | 46ec54c2-ceef-512f-89a6-cc6dd7a20126 |  | textbox | Test Pressure | Kpa
text | 7ca05e6e-06aa-5f16-a31d-a8b915edfcb8 |  | textbox | Duration
checkpoint-status | 63dc3d4e-877e-4585-8995-f2f1ad58facd |  | checkpoint | Soil/Waste Pipes
text | adba0dd2-0bed-5a57-9a0b-be5dcf2da626 |  | textbox | Specified to | Kpa
text | ef765e83-5a96-5520-8859-05d4028a752e |  | textbox | Test Pressure | Kpa
text | e2779f8c-e310-5cce-8e81-7c0c06a14e26 |  | textbox | Duration
checkpoint-status | 04c6938b-688b-4530-81ad-4641c1a1ac89 |  | checkpoint | Vent Pipes
text | 04d92435-a5b8-5125-a6a9-43a731c57bfa |  | textbox | Specified to | Kpa
text | c0d3bb5f-734e-5f40-a78f-acaf0dd31af2 |  | textbox | Test Pressure | Kpa
text | f6cf02a0-5642-589f-b845-28ee0b6832c0 |  | textbox | Duration
checkpoint-status | 8da223bc-8162-425f-af2c-cff2fd965fec |  | checkpoint | Gas Services
text | 58656f02-5d83-5b41-91c7-ab1d1e9f9414 |  | textbox | Specified to | Kpa
text | 9ae31007-84a0-5527-8d5d-eba6aa1c373c |  | textbox | Test Pressure | Kpa
text | 7c01b18c-4053-5aac-8289-cd84b56b85c6 |  | textbox | Duration
checkpoint-status | 0e4d7ceb-9e9a-4013-b56c-72375bd2f069 |  | checkpoint | Other
text | 53ce1a4c-bb4b-56c2-a34d-8264f6e5e621 |  | textbox | specify other
text | 2508d168-11e8-5f64-8270-f05fa3fc3a37 |  | textbox | Specified to | Kpa
text | 5eb47f69-a783-520d-83f2-b1be97c36a68 |  | textbox | Test Pressure | Kpa
text | bf5eefb7-ad10-58df-a1b9-67422ba0a0e0 |  | textbox | Duration
checkpoint-group | 8c6a12df-8399-47bd-8547-8ca443ff5564 |  | section | Handover
checkpoint-status | 2bbc5bfc-b135-421c-bb8a-7c7ec35cd43e |  | checkpoint | Area left clean and tidy
checkpoint-status | 771e8363-18c3-4878-bfb2-745a1e9c45b8 |  | checkpoint | Local Authority Verification
holdpoint | 8ade0fdb-1972-40ab-81d8-7239a3659ba1 |  | signoff | Plumbing inspection complete and passed as satisfactory
checkpoint-status | 03a42711-23c0-457b-a723-86c62131d186 |  | checkpoint | DL Good Verification
holdpoint | 74b343ba-53d7-482a-a6e0-86f099e11b57 |  | signoff | Plumbing Complete and ready for lining
checkpoint-status | 4d78030f-fe3d-4230-bd78-b4ed80ca28eb |  | checkpoint | Main Contractor verification
holdpoint | 722a665d-9074-4bc8-bcaf-9fd4773d1afe |  | signoff | Plumbing Complete and ready for lining