## Project Structure
Folder Structure |  |  |  | Checklists | #NAME?
Site QA
Switchboard's
Ground Floor
|  |  | Main Switchboard | Switchboards
Cable Tray
Ground Floor
|  |  | Warehouse | Cable Tray
First Fix
Ground Floor
|  |  | Stairwell | First Fix Electrical
|  |  | Office | First Fix Electrical
|  |  | Staff Room | First Fix Electrical
|  |  | Warehouse | First Fix Electrical
|  |  | Bathrooms | First Fix Electrical
Level 1
|  |  | Stairwell | First Fix Electrical
|  |  | Office | First Fix Electrical
|  |  | Staff Room | First Fix Electrical
|  |  | Bathrooms | First Fix Electrical
Second Fix
Ground Floor
|  |  | Stairwell | Second Fix
|  |  | Office | Second Fix
|  |  | Staff Room | Second Fix
|  |  | Warehouse | Second Fix
|  |  | Bathrooms | Second Fix
Level 1
|  |  | Stairwell | Second Fix
|  |  | Office | Second Fix
|  |  | Staff Room | Second Fix
|  |  | Bathrooms | Second Fix
FEL SM Weekly Site Checklist
| 2022-11-14 |  |  | FEL SM Weekly Site Checklist
| 2022-11-21 |  |  | FEL SM Weekly Site Checklist
| 2022-11-28 |  |  | FEL SM Weekly Site Checklist
| 2022-12-05 |  |  | FEL SM Weekly Site Checklist
| 2022-12-12 |  |  | FEL SM Weekly Site Checklist
| 2022-12-19 |  |  | FEL SM Weekly Site Checklist

## First Fix Electrical
type | name
checklist | QA - First Fix
section | Flush Boxes
checkpoint | Height as per plan
checkpoint | Location as per plan
checkpoint | Fire rated boxes installed where necessary
checkpoint | Acoustic boxes installed where necessary
section | Cabling
checkpoint | Power cables installed correctly
checkpoint | Lighting cables installed correctly
checkpoint | Power cables wired from correct RCD location
checkpoint | Circuits clearly labelled
checkpoint | Separation between Data and Power at 300mm or as specified
checkpoint | All cables secured via cable ties with ends cut
section | QA - Lights
checkpoint | Setout Correct
checkpoint | Cabling in correct location
checkpoint | Emergency/ Exit Lighting
checkpoint | Nogging installed for Electrical Services
section | Photos

## Cable Tray
Section | Cable Tray
Checkpoint | Unistrutt Filed & Painted
Checkpoint | Hangers Spaced as Specified
Checkpoint | Correct Size Cable Tray Installed
Checkpoint | Tray Joined Correctly
Checkpoint | Hangers Sceismicly Restrained / Under 400mm drop
Checkpoint | Tray Fastened to Hangers
Checkpoint | Correct Anchors used fixing to Ceiling / Walls
Checkpoint | Cable Tray Bonded
section | Photos

## Switchboards
section | Switchboard
checkpoint | Spatial certificate signed if required
checkpoint | Fixings installed in wall correctly if board is wall mounted
checkpoint | All clearances sighted to ensure location is compliant
checkpoint | All cables correctly installed in protection device and earth and neutral bars and fully secured
checkpoint | Cables neatly dressed
checkpoint | Phase tabs on chassy covered
checkpoint | All earths and neutrals labelled to match phase numbers
checkpoint | Switchboard is clean on the inside and outside
checkpoint | Masking blanks installed
checkpoint | DB legend installed
checkpoint | Feisst label on the door installed
section | Photos

## Second Fix Electrical
type | name | values
checklist | QA - Second fix
section | Power Outlets
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Outlet Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Switches
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Light switch Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Fixtures
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Tested for operation
checkpoint | Correctly installed with stainless screws & 90 / 45 angle
section | Photos

## SM Weekly Checklist
type | name
checklist | FEL SM Weekly Site Checklist
section | Monday
checkpoint | Prestart Meeting with Team
checkpoint | Health Check
checkpoint | Review Tasks for the week
checkpoint | Identify Targets Including Hours
checkpoint | Approve hours by 9AM for previous week
checkpoint | Sign off Subcontractor Hours & Submit
checkpoint | Review SWMS
checkpoint | Site Toolbox Meeting
checkpoint | SSSP in Order
section | Tuesday
checkpoint | Follow up outstanding RFI's with PM
section | Wednesday
checkpoint | Review Roadblocks & Follow Up if still unresolved
checkpoint | QAs up to date
section | Thursday
checkpoint | Weekly planner filled out for week ahead
checkpoint | Roadblocks identified and actioned
checkpoint | Materials organized for week ahead
checkpoint | Plans printed with any relevant notes added
section | Friday
checkpoint | Submit Toolbox minutes to main contractor and FEL office
checkpoint | Job Cards up to date and submitted
checkpoint | Team tasks for week ahead filled out on whiteboard