## PROJECT STRUCTURE
Folder Structure |  |  |  | Checklists
DRURY SCHOOL
EXTERIOR
SITE WORKS
|  |  | UNDERGROUND SERVICES | SITE WORKS - UNDERGROUND SERVICES
BUILDING
|  |  | LIGHTING | BUILDING - EXTERIOR LIGHTING AND POWER
| INTERIOR |  |  | FIRST FLOOR - CONDUIT CAST IN CONCRETE
CONTAINMENT
GROUND FLOOR
|  |  | G01a FLEXIBLE | CONTAINMENT - CABLE TRAY
CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G01b FLEXIBLE | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G01c FLEXIBLE | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G02 TEACHING RESOURCES | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G03 BREAK OUT | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G04 SMALL BREAK OUT | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G05 PROJECT/WET AREA | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G06 TOILET LOBBY | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G12 CLN | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G11 DB CUPBOARD | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G13 CIRCULATION | CONTAINMENT - CABLE TRAY
CONTAINMENT - CATNERY WIRE INSTALL
FIRST FLOOR
|  |  | LO1A FLEXIABLE | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | LO1C FLEXIABLE | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | LO1B FLEXIABLE | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | LO2 TRACHING RESOURCES | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | LO3 BREAKOUT | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | LO4 SMALL BREAK OUT | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | LO5 PROJECT/WET AREA | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | L13 CIRCULATION | CONTAINMENT - CABLE TRAY
|  |  | TOILETS | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | COMMS RISER | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | LIFT SHAFT | CONTAINMENT - CONDUIT INSTALL
CLASSROOM
GROUND FLOOR
|  |  | G01a FLEXIBLE | CLASSROOM - ROOM
|  |  | ROOM G01b FLEXIBLE | CLASSROOM - ROOM
|  |  | ROOM G01c FLEXIBLE | CLASSROOM - ROOM
|  |  | ROOM G02 TEACHING RESOURCES | CLASSROOM - ROOM
|  |  | ROOM G03 BREAK OUT | CLASSROOM - ROOM
|  |  | ROOM G04 SMALL BREAK OUT | CLASSROOM - ROOM
|  |  | ROOM G05 PROJECT/WET AREA | CLASSROOM - ROOM
|  |  | ROOM G06 TOILET LOBBY | CLASSROOM - ROOM
|  |  | ROOM G12 CLN | CLASSROOM - ROOM
|  |  | ROOM G11 DB CUPBOARD | CLASSROOM - ROOM
|  |  | ROOM G13 CIRCULATION | CLASSROOM - ROOM
FIRST FLOOR
|  |  | ROOM LO1A FLEXIABLE | CLASSROOM - ROOM
|  |  | ROOM LO1C FLEXIABLE | CLASSROOM - ROOM
|  |  | ROOM LO1B FLEXIABLE | CLASSROOM - ROOM
|  |  | ROOM LO2 TRACHING RESOURCES | CLASSROOM - ROOM
|  |  | ROOM LO3 BREAKOUT | CLASSROOM - ROOM
|  |  | ROOM LO4 SMALL BREAK OUT | CLASSROOM - ROOM
|  |  | ROOM LO5 PROJECT/WET AREA | CLASSROOM - ROOM
|  |  | ROOM L13 CIRCULATION | CLASSROOM - ROOM
|  |  | ROOM TOILETS | CLASSROOM - ROOM
|  |  | ROOM COMMS RISER | CLASSROOM - ROOM
BONDING
STRUCTURAL BONDING
BUILDING STRUCTURAL BONDING
DISTRIBUTION
DISTRIBUTION BOARD
DISTRIBUTION BOARD - MAIN SWITCHBOARD
DISTRIBUTION BOARD DB-A
COMMISSIONING
COMMISSIONIG - DISTRIBUTION BOARD
COMMISSIONING - DISTRIBUTION - MAIN SWITCHBOARD
COMMISSIONING - DISTRIBUTION BOARD DB-A

## CHECKPOINTS
TYPE | NAME
CHECKLIST | SITE WORKS - UNDERGROUND SERVICES
CHECKPOINT | POWER DUCTING INSTALLED INCL MAG SLAB AND DANGER TAPE
CHECKPOINT | COMMS DUCTING INSTALLED INCL DANGER TAPE
CHECKPOINT | UNDERGROUND PITS INSTALLED, LEVELLED AND DUCTING SEALED
CHECKPOINT | DRAW TAPE INSTALLED AS REQUIRED
CHEECK POINT | CORRECT QUANTITIES OF PIT INSTALLED AS PER UPDATED ELECTRICAL DRAWINGS
CHEECK POINT | CORRECT QUANTITIES OF DUCTING INSTALLED AS PER UPDATED ELECTRICAL DRAWINGS
CHEECK POINT | CORRECT QUANTITIES OF PIT INSTALLED AS PER UPDATED ELECTRICAL DRAWINGS
CHEECK POINT | CORRECT QUANTITIES OF DUCTING INSTALLED AS PER UPDATED ELECTRICAL DRAWINGS
CHECKPOINT | CORRECT DUCTING SIZE INSTALLED INTO BOXING FOR MSB PLINTH FOR MAINS CABLE
CHECKPOINT | CORRECT DUCTING SIZE INSTALLED INTO BOXING FOR MSB PLINTH FOR MAIN EARTHING
CHECKPOINT | CORRECT DUCTING SIZE FOR RELOCATED SUBMAINS INSTALLED INTO BOXING FOR MSB PLINTH
CHECKLIST | BUILDING - EXTERIOR LIGHTING AND POWER
CHECKLIST | DAYLIGHT SENSOR CABLED TO SUITABLE LOCATION
CHECKPOINT | EXTERIOR CLASSROOM WALL LIGHTING PREWIRED
CHECKPOINT | CABLE SEAL APPLIED PRE CLADDING
CHECKPOINT | EXTERIOR CLASSROOM WALL LIGHTING INSTALLED AND CONNECTED
CHECKPOINT | LIGHT FITTINGS CLEANED AND SEALED AGAINST WATER INGRESS
CHECKPOINT | POWER CABLING INSTALLED AND COMPLETED
CHECKPOINT | OUTDOOR OUTLETS INSTALLED AND COMPLETED
CHECKPOINT | SILCON COMPLETED AROUND OUTDOOR OUTLETS.
CHECKPOINT | LEVEL 1 BALCONY LIGHTS PREWIRED
CHECKPOINT | LEVEL 1 EXTERNAL STAIRCASE LIGHTS AND EMERGENCY LIGHTS PREWIRED
CHECKPOINT | LEVEL 1 EXTERNAL LIGHTS INSTALLED AND COMPLETED
CHECKPOINT | LEVEL 1 EXTERNAL EMERGENCY LIGHTS PREWIRED
CHECKPOINT | LEVEL 1 EMERGENCY LIGHTS INSTALLED AND COMPLETED.
CHECKLIST | FIRST FLOOR - CONDUIT CAST IN CONCRETE
CHECKLIST | 25MM CONDUIT CAST INTO CONCRETE AT CORRECT LOCATION
CHECKPOINT | CONDUIT LAID AS PER ARCHITECTURAL SET OUT
CHECKPOINT | END OF CONDUIT TO LIGHTS DUCT TAP AND FREE OF DEBRIE
CHECKPOINT | CONDUIT EITHER WELL SECURED BEFORE CONCRETE POUR
CHECKPOINT | TYPE B1 LIGHTS CABLED AND COMPLETED
CHECKPOINT | TYPE B1 LIGHTS INSTALLED AND COMPLETED.
CHECKLIST | CONTAINMENT - CATENERY WIRE INSTALL
CHECKPOINT | WOOD EYE ANCHORS INSTALLED AND CORRECTLY FIXED ONTO TIMBER WALLS
CHECKPOINT | SUFFICIENT CATENERY WIRE SUPPORTS INSTALLED AT APPROX 1.2M INTERVALS
CHECKPOINT | CATENRY WIRES INSTALLED AT HIGH LEVEL AND MEETS CLEARENCE FROM OTHER SERVICES
CHECKPOINT | TURNBUCKLES IS TIGHTENED AND CATENERY WIRE IS WELL SECURED
CHECKLIST | CONTAINMENT - CABLE TRAY
CHECKPOINT | CABLE TRAY DROPPERS INSTALLED IN CEILING
CHECKPOINT | SUFFICENT CABLE TRAY DROPPER SUPPORTS INSTALLED.
CHECKPOINT | CABLE TRAY UNISTRUT LEVELED AND PLUMBED
CHECKPOINT | CABLE TRAY RADIUS BEND HAS SUFFICIENT SUPPORTS
CHECKPOINT | BONDING COMPLETED AND CONNECTED WITH CORRECT EARTH SIZE
CHECKPOINT | SEISMIC INSTALLED WHERE REQUIRED
CHECKPOINT | BONDING COMPLETED AND CONNECTED WITH CORRECT SIZE
CHECKLIST | CONTAINMENT - LIFT CONDUIT INSTALL
CHECKPOINT | CONDUIT INSTALLED WITH SUFFICIENT SADDLE SUPPORT
CHECKPOINT | LIFT 3PHASE ISOLATOR INSTALLED AND COMPLETED
CHECKPOINT | LIFT POWER POINT INSTALLED AND COMPLETED
CHECKPOINT | LIFT LIGHTS INSTALLED AND COMPLETED
CHECKPOINT | LIFT BONDING CABLE INSTALLED AND COMPETED
CHECKLIST | BUILDING STRUCTURAL BONDING
CHECKPOINT | STRUCTURAL BONDING CABLE 1/3 SIZE OF DB-A SUB MAINS CABLE
CHECKPOINT | CORRECT SIZE EARTH CABLE INSTALLED
CHECKPOINT | CORRECT SIZE EARTH CABLE LUGGED AND BOLTED ONTO STRUCTURE
CHECKLIST | DISTRIBUTION BOARD - MAIN SWITCHBOARD
CHECKPOINT | NEW MAIN SWITCHBOARD INSTALLED AND SECURLY MOUNTED ON CONCRETE PAD
CHECKPOINT | NEW MAIN SWITCHBOARD LEVELLED.
CHECKPOINT | NEW UPGRADED MAINS INSTALLED AND TERMINATED.
CHECKPOINT | NEW MAIN EARTHING INSTALLED
CHECKPOINT | MEN LINK INSTALLED AND CONFIMRED
CHECKPOINT | SUFFICINET EARTH STAKE INSTALLED AND MAIN EARTH GROUND READING IS GOOD
CHECKPOINT | MAIN EARTH INSPECTION PIT INSTALLED
CHECKPOINT | STRUCTURAL BONDING CABLE TERMINATED AT SWITCHBOARD.
CHECKPOINT | DB SCHEDULE COMPLETED
CHECKPOINT | DISTRIBUTION BOARD TEST SHEET COMPLETED
CHECKPOINT | DB SCHEDULE INSTALLED
CHECKPOINT | CLEAN OF ALL DEBRI AND MARKS
CHECKLIST | COMMISSIONING - DISTRIBUTION - MAIN SWITCHBOARD
CHECKPOINT | MAIN SWITCHBOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | DB SCHEDULE COMPLETED, INSTALLED AND ADDED TO DROPBOX
CHECKPOINT | MAIN DISTRIBUTION BOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | DB SCHEDULE COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | MAIN SWITCHBOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | MAIN SWITHCBOARD DISTRIBUTION BOARD CHECK SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | MAIN EARTHING TEST SHEET COMPLETED
CHECKPOINT | MAIN EARTH PITS INSTALLED
CHECKPOINT | MEN LINK INSTALLATION CONFIRMED
CHECKPOINT | BOARD FREE FROM DEBRI, NO MARKS, ALL ACCESSORIES INSTALLED
CHECKPOINT | LABELLING COMPLETED ON ALL FIELD OUTLETS, SWITCHES AND ISOLATORS ETC
CHECKLIST | DISTRIBUTION BOARD - DB-A
CHECKPOINT | CABLE TRAY INSTALLED BELOW DB-A
CHECKPOINT | SUBMAINS CABLE CABLE TIED ONTO CABLE TRAY
CHECKPOINT | DISTRIBUTION BOARD INSTALLATION COMPLETED AND SECURELY MOUNTED
CHECKPOINT | SUBMAINS TERMINATED
CHECKPOINT | SUBCIRCUITS TERMINATED INCLUDING LABELLING/FERRULES TO ALL CORES
CHECKPOINT | EARTHING/BONDING TERMINATED
CHECKPOINTS | STRUCTURAL BONDING CABLE TERMINATED AT SWITCHBOARD.
CHECKPOINT | DB SCHEDULE COMPLETED
CHECKPOINT | DISTRIBUTION BOARD TEST SHEET COMPLETED
CHECKPOINT | DB SCHEDULE INSTALLED
CHECKPOINT | CLEAN OF ALL DEBRI AND MARKS
CHECKLIST | COMMISSIONING - SWITCHBOARD DB-A
CHECKPOINT | SWITCHBOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | DB SCHEDULE COMPLETED, INSTALLED INTO DB AND ADDED TO DROPBOX
CHECKPOINT | DISTRIBUTION BOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | SUBCIRCUIT COMMISSIONING RESULTS SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | DISTRIBUTION BOARD CHECK SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | EARTHING TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | EMERGENCY LIGHTING TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | TIMECLOCK TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | BOARD FREE FROM DEBRI, NO MARKS, ALL ACCESSORIES INSTALLED
CHECKPOINT | LABELLING COMPLETED ON ALL FIELD OUTLETS, SWITCHES AND ISOLATORS ETC
CHECKPOINT | EMERGENCY LIGHTING TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | SUBCIRCUIT COMMISSIONING RESULTS SHEET COMPLETED AND ADDED TO DROPBOX
CHECKLIST | CLASSROOM - ROOM
CHECKPOINT | SETOUT + FLUSHBOXES INSTALLED/COMPLETE
CHECKPOINT | LIGHTING PREWIRED
CHECKPOINT | LIGHTING INSTALLED AND CONNECTED
CHECKPOINT | LIGHTING CONTROLS PREWIRED AND COMPLETE
CHECKPOINT | EMERGENCY LIGHTING PREWIRED
CHECKPOINT | EMERGENCY LIGHTING INSTALLED AND COMPLETE
CHECKPOINT | EXIT LIGHTING PREWIRED
CHECKPOINT | EXIT LIGHT INSTALLED AND COMPLETE
CHECKPOINT | POWER CABLING INSTALLED
CHECKPOINT | POWER OUTLETS INSTALLED AND COMPLETE
CHECKPOINT | HAND DRYERS CABLLED IN BATHROOM
CHECKPOINT | HAND DRYER ISLOATOR INSTALLED AND COMPLETED
CHECKPOINT | HAND DRYER INSTALLED AND COMPLETED
CHECKPOINT | SUBCIRCUITS PREWIRED AND TIED ONTO CATENRERY WIRES BACK TO DB
CHECKPOINT | CONDUIT INSTALLED WHERE REQUIRED