## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Site - Pre-Install Checklist |  |  |  |  | Yes | Site - Pre-Install Checklist | 2c20c0d4-5b65-4109-93e3-54d1c8b7d88d
checkpoint-no-status |  |  | checkpoint | Work details
text | 00583f71-c47f-433e-85cb-33f2dbf18506 |  | textbox | Scope of work
text | 9f6840ec-a14f-4c1c-b1eb-a94232595335 |  | textbox | Expected start date
text | f21b9e08-30fe-49d5-a9c4-f6f491d14fe5 |  | textbox | How many guys are needed for install
checkpoint-status |  |  | checkpoint | Check heights concrete / RL
checkpoint-status |  |  | checkpoint | Check steel fits on pad or in location
checkpoint-status |  |  | checkpoint | Check cast in bolts height location - can nuts easily thread
checkpoint-status |  |  | checkpoint | Crane Access Requirements
checkpoint-status |  |  | checkpoint | EWP Access Requirements
checkpoint-status |  |  | checkpoint | Scaffolding Access Requirements
checkpoint-status |  |  | checkpoint | Hiab Access Requirements
checklist-flat |  |  | checklist | Site - Variation Checklist |  |  |  |  | Yes | Site - Variation Checklist | 51ebe556-76a5-43e6-8784-34ae616074f2
checkpoint-status |  |  | checkpoint | Variation logged into Sables VO system:
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 84fd102e-6da1-4a5e-a19b-831ebaa11813 |  | textbox | Reference/Drawing/Instruction Number
text | b2f94212-6e7b-4281-adc1-447b0301a8e1 |  | textbox | Variation Area
text | bcd1a583-300a-4dc4-b403-9094c56ef600 |  | textbox | Materials & labour breakdown
holdpoint |  |  | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  |  | signoff | Request Variation Signoff
checklist-sectioned |  |  | checklist | Site Erection |  |  |  |  | Yes | Site - Erection Checklist | a3059967-745b-41fb-94e5-46afc68e5455
checkpoint-group |  |  | section | Pre Start & Area Acceptance
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
text | 4acac22c-fdc3-5465-b8ee-e9e3da9909df |  | textbox | Input drawing/revision number
checkpoint-status |  |  | checkpoint | Work area acceptable
boolean | ad4dc7bc-b17d-5502-a176-c83c3e8ab74c |  | tickbox | Checked for set out and alignment
boolean | 54664d23-13bc-5d45-b652-734b103cfc8a |  | tickbox | Checked for Level and RL
boolean | f5f17f03-2f65-57f8-9867-82cb13d9abd4 |  | tickbox | Hold down bolts / cast-in items checked and approved (location and size)
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Correct orientation and grids identified and approved
text | dd3b149e-28a9-5ab6-b88b-4e20de174fed |  | textbox | Approved by
checkpoint-status |  |  | checkpoint | Relevant steel delivered, checked and correct
boolean | 863dcf24-312d-5c12-a57d-abc837832e23 |  | tickbox | Correct elements received
boolean | 2856dbb9-7a92-55bc-825f-3be2b0cb3f38 |  | tickbox | Coating condition acceptable
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Pre-erection checks
boolean | 8095afaf-0ed6-58e1-944b-d760da664d51 |  | tickbox | All steel tags match drawings marks numbers
boolean | 8e9632c8-4200-53b0-97d8-cb688375afd2 |  | tickbox | Sufficient steel on site for erection to proceed
checkpoint-status |  |  | checkpoint | Steel hoisted as per agreed lifting procedure
checkpoint-status |  |  | checkpoint | Soft slings used instead of chains, if required
checkpoint-status |  |  | checkpoint | Crane operated within rating chart capacity
checkpoint-group |  |  | section | Steel Erection QA
checkpoint-status |  |  | checkpoint | Steel erected level, plumb and correct pitch
checkpoint-status |  |  | checkpoint | All RLs of base plates after steel erection checked and correct
checkpoint-status |  |  | checkpoint | Temporary props, turfers, bracing etc. installed/removed
checkpoint-status |  |  | checkpoint | All fixings appropriately installed
checkpoint-status |  |  | checkpoint | Epoxy and mechanical anchors drilled to correct depths
checkpoint-status |  |  | checkpoint | Epoxy and mechanical anchors tightened
checkpoint-status |  |  | checkpoint | Taper wahers installed, if required
checkpoint-status |  |  | checkpoint | All bolts secure / correctly tensioned
checkpoint-status |  |  | checkpoint | Bolts tightened to snug
checkpoint-status |  |  | checkpoint | TB/ TF bolts tightened correctly
checkpoint-status |  |  | checkpoint | Bolts fully torqued correctly
checkpoint-status |  |  | checkpoint | All on-site welding completed correctly
checkpoint-status |  |  | checkpoint | Damaged coatings repaired / touched-up
checkpoint-status |  |  | checkpoint | General comments, observations
checklist-flat |  |  | checklist | Toolbox Safety Meeting Record |  |  |  |  | Yes | H&S - Toolbox Safety Meeting Record | a7662cfc-82de-4b0e-a101-88ae47674b19
checkpoint-no-status |  |  | checkpoint | Details
text | 40e6f6a8-202d-44dd-acf8-8b70c1c290d5 |  | textbox | Meeting chairperson
text | 9f8896e6-bbb6-4c81-8cc4-7000a9102a41 |  | textbox | Date
text | 6689d776-83c3-4bc2-adc9-4c3862e70f52 |  | textbox | Time
checkpoint-status |  |  | checkpoint | Attendees documented and signed on
checkpoint-status |  |  | checkpoint | Site Activities – Compulsory PPE required
label | c85f41db-3bff-422f-acdb-4118e49381d5 |  | note | Hard Hat
label | e3e03a8f-8c87-40ae-b888-98bbe3792959 |  | note | High Vis Vest
label | 2ae5b564-5c0f-4047-b19e-875bd58450fd |  | note | Steel Cap Boots
checkpoint-status |  |  | checkpoint | Site activities - job plans, work methods, incident investigations, etc. reviewed / discussed
boolean | 1e117465-513d-4f3e-9d7f-aacf3245b9fd |  | tickbox | Mark and set out steel.
boolean | b96b5fde-c3cb-4d14-81d2-3aaaf748b75c |  | tickbox | Pre drill holes in concrete using concrete drill.
boolean | be11e4b7-e3a9-4bf0-a983-24c1c46cdb4b |  | tickbox | Drill and bolt steel
boolean | 0f38526d-964f-43a2-bae4-0eeca17d7e23 |  | tickbox | Using crane to lift and erect steel.
boolean | 0d8c8d3c-552f-4ce6-a6f5-7d9945942514 |  | tickbox | Working off scaffolding.
boolean | fe9b9a83-d16a-4b4e-a0da-060860455afb |  | tickbox | Working off ladder.
boolean | 22bc0025-b26f-4b7d-9cb5-50ce97ea854c |  | tickbox | Knuckle boom being used.
boolean | 86f12aab-5290-40c1-8ec5-ba1a3cf57ec3 |  | tickbox | Fast bracing install
boolean | f3def2a4-9ad2-4a04-a3f9-6150654f5773 |  | tickbox | Cross bracing install
boolean | 7c48829c-f1a4-4c68-acd7-f441507ba436 |  | tickbox | Welding
boolean | 874c35da-8b00-4187-8277-ab923be90449 |  | tickbox | Scissor lift being used
boolean | 6b823416-6837-4de1-9875-6437f5c99b86 |  | tickbox | Other:
text | 2d9215ae-e73f-4e71-b162-1dcaeff4f65a |  | textbox
text | 9476be17-8837-4ae1-91cf-fe1d21260951 |  | textbox
text | 7a5460a3-36a4-41b4-aaa3-0b29afe88842 |  | textbox
text | 3ceec3f6-8fc6-44ed-be75-a830afba1946 |  | textbox
checkpoint-status |  |  | checkpoint | Employee issues raised
text | a8695f2f-0e19-469d-925e-dbc8c41f73d2 |  | textbox | 1
text | b95e0048-254e-4089-961f-392120724c6e |  | textbox | Date to be resolved
text | 19540728-1159-4606-a63a-1f6233944505 |  | textbox | 2
text | 2bdd13d7-0e85-4fdd-a801-a0a45f3e7cb9 |  | textbox | Date to be resolved
text | f7308d10-a824-4831-8c54-b74407f88c62 |  | textbox | 3
text | 7d5d1358-34ad-4367-b214-cfab42c6a7ff |  | textbox | Date to be resolved
text | 254c7801-6877-43ed-8df2-c401a7134e09 |  | textbox | 4
text | 9954efa4-8f1c-4474-a574-561966548cf1 |  | textbox | Date to be resolved
text | 0a7b4081-64f6-4d51-9d82-82d494a4cf90 |  | textbox | 5
text | 148950e1-d587-45e3-9292-610da7600098 |  | textbox | Date to be resolved
checkpoint-status |  |  | checkpoint | Safe observations reviewed / discussed
boolean | ae1131ae-0436-41b6-89c8-3ae4b5b01226 |  | tickbox | Be mindful of slips trips and falls onsite.
boolean | a8e40d86-df24-4ccc-8c45-e08bbe5e4164 |  | tickbox | Use of ladders and mobile scaffolding and ensure it is stable and erected correctly before using them.
boolean | d9671c37-d9a8-4a77-b70c-1b8ac6b6ea96 |  | tickbox | Ensure all handles are in place and you have a firm grip on the concrete drill at all times in case it kicks back.
boolean | 883c50c9-b5c2-4944-964e-95c9b28be8f1 |  | tickbox | Be mindful of pinching points when bolting up steel no walking under suspended loads alert any workers around the exclusion zone of lifts.
boolean | 9db98b5c-c302-44c2-84bf-2d1051a58f07 |  | tickbox | 8m Knuckle boom to be used competent drive and harnesses to be worn.
boolean | 24c24674-9783-402a-9ad6-816c058c3741 |  | tickbox | Weather is to be assessed throughout the day.
boolean | 20e61561-b07f-4cbe-86b0-eefee3adbb8e |  | tickbox | Log book to be filled out if operating a knuckle boom or scissor lift
boolean | f3ade78e-2e49-4365-aeef-b2883dc0e2b9 |  | tickbox | Other:
text | 9cc4795e-2fa7-4db8-b151-e56da1a6845e |  | textbox
text | 6d8f948a-8055-416b-8863-d443e664990c |  | textbox
text | 0f9287e2-bde6-468d-9e04-0d8e6fff19d6 |  | textbox
text | a12c3ce8-dd3f-44b4-99ee-791c7914327e |  | textbox
checkpoint-status |  |  | checkpoint | Task Specific PPE reviewed / discussed
boolean | d91d83a0-2b50-4b4c-b81d-23a2410ac7c1 |  | tickbox | Harness
boolean | ff312ae5-998a-43c3-acd9-177c026651b7 |  | tickbox | Long Sleeve Top
boolean | c5a38403-7483-42f1-84c8-f71dd9aa2aed |  | tickbox | Ear Protection
boolean | 845fa6fc-0136-4319-b6c3-2cb9e388489e |  | tickbox | Safety Glasses
boolean | 8298b54a-1208-4d85-8d0b-d2bcccd6c2db |  | tickbox | Gloves
boolean | f38b546b-69be-4b7d-8238-4ca1b2abd86a |  | tickbox | Dust Masks
boolean | bd1128c7-262a-4c76-b847-6e16bc13c9e0 |  | tickbox | Welding Helmet
checkpoint-status |  |  | checkpoint | This toolbox is inline with our current SSSP and TA’s are discussed
checklist-flat |  |  | checklist | Non-Conformance Item: |  |  |  |  | Yes | Add Non-Conformance Item Checklist | e0086616-4782-4c64-a5c5-5ce843850e1e
checkpoint-status |  |  | checkpoint | Observation / Remedial Status
text | 1056dbf5-0893-49d2-9ea8-c06aeaf34830 |  | textbox | Job Number:
button | f90ac5d5-a116-4733-b9c7-040696bd6574 |  | button | Item Type: | Rework,Non-Conformance
text | e8f3aa49-8b1e-48d4-a006-281a6994689a |  | textbox | Job Name / Location:
button | d973a8ed-14f7-47ca-ba7d-89c9d04d0a24 |  | button | Area: | Site, Workshop, Other
text | 278b57d8-7580-49a0-a0ec-fc5ccf0f7291 |  | textbox | Date:
text | edb2161b-c147-4333-a206-721af77ef4f0 |  | textbox | Report Generated By:
text | 107fe261-7132-454f-a648-6032f56ae0d0 |  | textbox | Site Description:
text | d80424a9-be9e-4a5a-9bc1-e2f1b903dc69 |  | textbox | Fabricator / Welder Name:
text | 4eec2ca0-1783-400e-9229-8b04cd3e8416 |  | textbox | Assembly No:
text | b50df880-8f34-4e24-8b08-b8392902e3fd |  | textbox | Description:
text | ac83b3b2-8325-4490-a3ca-33a8beebc339 |  | textbox | Investigation Results:
holdpoint |  |  | signoff | Request Review on Non-Conformance Item