## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - 118 - Hard Landscaping | itp |  |  |  |  | ITP - 118 - Hard Landscaping Rev D | 71c824d1-2ea4-446b-b65c-92dbab9ceb8e
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.02 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.01.03 - Service Location
label | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard / Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.04 - Internal Permits
label | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard / Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.05 - External Permits
label | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Standard / Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.06 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.07 - Previous Lots
label | Acceptance / Conformance Criteria - Landscaping works to only be carried out in sections where surrounding work that will cause rework has already been completed.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.08 - Subcontractors
label | Acceptance / Conformance Criteria - Ensure that subcontract and supplier agreements have been completed.
label | ○ All subcontractors have been inducted.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - Concrete
label | Acceptance / Conformance Criteria - Minimum 20MPa concrete to be used for landscaped structures.
label | Standard / Specification - Designer
label | Verifying Document - Concrete Delivery Dockets
label | Frequency - At delivery
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.01.02 - Timber
label | Acceptance / Conformance Criteria - Dimensions and grade as per drawings.No specific grade required unless noted otherwise.
label | Standard / Specification - Designer
label | Verifying Document - Site Record or Dockets
label | Frequency - At delivery
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.01.03 - Paint
label | Acceptance / Conformance Criteria - Dulux Weathershield x10 grade. Specific paint colours noted on drawings.
label | Standard / Specification - Designer
label | Verifying Document - Dockets
label | Frequency - At delivery
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.01.04 - Informal Path
label | Acceptance / Conformance Criteria - GAP40 to be used for the 100mm base layer of the informal path.
label | ○ Any clay is suitable for use in informal path capping mix. 80% GAP20 and 20% clay.
label | Standard / Specification - Designer
label | Verifying Document - Mix Approval Dockets
label | Frequency - At delivery
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.01.05 - Fixings
label | Acceptance / Conformance Criteria - Dimensions and grade as per drawings. No specific grade required unless noted otherwise.
label | Standard / Specification - Designer
label | Verifying Document - Site Record
label | Frequency - At delivery
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.01.06 - Steel Rebar
label | Acceptance / Conformance Criteria - Rebar for concrete play on the way items to be suitable.
label | Standard / Specification -
label | Verifying Document - Mill Certificates
label | Frequency - At delivery
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint | 5.01.01 - Climbing Trunk
label | Acceptance / Conformance Criteria - Tree trunks to be inspected and selected by suitable authority (BBO, HCC)
label | ○ Tree trunks from felled site tree. Bark to be removed. Retain side limbs for stability.
label | ○ Chamfer ends of branches. Minimum 100mm of mulch surrounding trunks.
label | Standard / Specification - Designer
label | Verifying Document - Inspection Record, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.02 - Post climb play unit
label | Acceptance / Conformance Criteria - Laser log climbing post with 100mm recessed bands and climbing foot holds.
label | ○ Painted in Dulux weathershield x10 in colours shown in detail.
label | ○ H5 painted post with chamfered top set into concrete footing.
label | ○ 150mm diametre climbing posts set into concrete footing.
label | ○ Concrete footing 600mm deep, 350mm wide.
label | ○ Posts to be spaced between 500mm to 650mm apart between centres.
label | ○ 125mm H5 laster log sanded smooth prior to painting. 10mm chamfer to top of posts.
label | Standard / Specification - Designer
label | Verifying Document - Subbase Material Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Photographs showing Dimensions
label | Frequency - Per Item
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.03 - Balance Stepping Log
label | Acceptance / Conformance Criteria - Logs buried 300mm below ground with well compacted crusher dust to stabilise.
label | ○ Logs stripped of bark and treated 2 coats of linseed oil prior to imbedding into crusher dust.
label | ○ Leading edges to be chamfered. 100x25 H4 timber edging to contain 100mm mulch surfacing.
label | ○ Use felled tree trunks for logs. Logs to vary in size and height.
label | Standard / Specification - Designer
label | Verifying Document - Subbase Material Delivery Docket, Log Dockets, Foundation Clegg Test, Concrete Delivery Docket, Photographs showing Dimensions
label | Frequency - Per Item
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.04 - Four Square Ball Play
label | Acceptance / Conformance Criteria - 150x25mm H4 timber edge set flush with grass.
label | ○ Coloured paint system over 100mm concrete base.
label | ○ Mask off squares prior to painting.
label | Standard / Specification - Designer
label | Verifying Document - Subbase Material Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.06 - Stepping Blocks
label | Acceptance / Conformance Criteria - Concrete has 10mm chamfer. 200x550mm concrete footing with toe 100mm either side.
label | ○ Lengths as shown in the drawings. D12 rebar at 250mm centres with c-links.
label | ○ Backfilled with 300mm topsoil and covered with 100mm mulch.
label | Standard / Specification - Designer
label | Verifying Document - Subbase Material Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Prepour Steel Inspection Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.07 - Concrete Balance Beam (straight)
label | Acceptance / Conformance Criteria - Dimensions and paint applied as per drawings. 200mm wide, 350mm deep, 6000mm length.
label | ○ Fair face finish.
label | Standard / Specification - Designer
label | Verifying Document - Subbase Material Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Prepour Steel Inspection Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.08 - Concrete Balance Beam (curved)
label | Acceptance / Conformance Criteria - Curvature as per drawings. 350mm deep footing, 200mm wide, 4000mm long. Fair face finish.
label | Standard / Specification - Designer
label | Verifying Document - Subbase Material Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Prepour Steel Inspection Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.09 - Timber Balance Beam
label | Acceptance / Conformance Criteria - Ensure correct beams are used in correct place. Beams to be embedded 500mm into concrete footing. Ensure correct nuts and bolts are installed as per drawings. 600mm deep concrete - 500mm embedment and minimum 100mm concrete beneath post. Posts to be covered with 100mm mulch.
label | Standard / Specification - Designer
label | Verifying Document - Concrete Delivery Docket, Prepour Inspection, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.10 - Stepping Stones
label | Acceptance / Conformance Criteria - 300mm topsoil surrounding boulder. 1/3 of boulder to be set in concrete.
label | ○ Boulder to be surrounding with 100mm mulch.
label | Standard / Specification - Designer
label | Verifying Document - Subbase Material Docket, Foundation Clegg Test, Concrete Delivery Docket, Prepour Inspection, Photographs with Dimensions
label | Frequency - Per Item
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.11 - Concrete Wall
label | Acceptance / Conformance Criteria - Concrete footing to be placed over well-compacted GAP40 subbase.
label | ○ D12 rebar located at 250mm centres.
label | ○ Leading edges to have 100mm chamfer with fair-faced concrete finish.
label | ○ To be painted with specified colours as shown in drawings.
label | Standard / Specification - Designer
label | Verifying Document - Subbase Material Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Prepour Steel Inspection Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.12 - Timber Stepping Logs
label | Acceptance / Conformance Criteria - Posts to be spaced about between 200-250mm.
label | ○ 600mm deep concrete; 500mm embedment and minimum 100mm concrete beneath post.
label | Standard / Specification - Designer
label | Verifying Document - Subbase Material Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Prepour Inspection, Photographs with Dimensions
label | Frequency - Per Item
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.02.01 - HCC Signage
label | Acceptance / Conformance Criteria - Signs to be confirmed with HCC Parks and Open Space.
label | ○ Signs to be concrete in 400x400x900mm concrete footing.
label | Standard / Specification - Designer
label | Verifying Document - Concrete Delivery Docket, Prepour Inspection, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.02 - Drinking Fountain A280
label | Acceptance / Conformance Criteria - 40mm diametre waster outlet pipe. Anchor bolt fixed to concrete base. 100mm thick concrete pad beneath table over 150mm thick compacted GAP40 subbase.
label | ○ Precast pit with locable cover and isolation valve on supply line.
label | ○ 50mm thick drainage layer with 15-20mm aggregate.
label | ○ Precast drain unit with steel drainage cover with surrounding 1:40 fall into drain.
label | Standard / Specification - Designer
label | Verifying Document - Subbase Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.03 - Type D Cycle Stand
label | Acceptance / Conformance Criteria - Mountain plates installed into 200mm thick 20MPa concrete path.
label | ○ Exposed aggregate concrete slab to be installed as per Engineer's requirements.
label | Standard / Specification - Designer
label | Verifying Document - Subbase Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.04 - Portland Picnic Set with Central Leg
label | Acceptance / Conformance Criteria - 400x400x1000mm concrete footing.
label | ○ 100mm thick concrete pad surrounding footing placed over 150mm well-compacted GAP40 subbase.
label | Standard / Specification - Designer
label | Verifying Document - Subbase Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.05 - Spinnaker Bin
label | Acceptance / Conformance Criteria - 100mm thick concrete pad beneath bin over 150mm well-compacted GAP40 subbase.
label | ○ HCC to confirm finish material (s/s electro polish, bead blast or ms galv powder coat).
label | Standard / Specification - Designer
label | Verifying Document - Subbase Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.06 - Surface Mounted Waihi Seat
label | Acceptance / Conformance Criteria - 1800x600mm Street Furniture seat with back and arm rests. Surface bolt mount to concrete footing. 20MPa concrete pad beneath seat over 150mm well compacted GAP40 subbase.
label | Standard / Specification - Designer
label | Verifying Document - Subbase Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03.01 - Ecological Tree Stump
label | Acceptance / Conformance Criteria - Tree stumps with dirt removed, laid on side and anchored to 100mm H4 Fence Post driven 500mm into ground. Wire achor to post. Ensure stump is stable position on ground to prevent rollover.
label | Standard / Specification - Designer
label | Verifying Document - Inspection, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.03.02 - Log Stack
label | Acceptance / Conformance Criteria - 100mm diametre H4 fence posts driven into ground 500mm to anchor log stacks. Logs from 100 to 200mm diametre from felled trees to be laid in stack up to min. 750mm unless otherwise advised by designer.
label | Standard / Specification - Designer
label | Verifying Document - Inspection, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.03.03 - Bird Song Post.
label | Acceptance / Conformance Criteria - 150mm diametre H5 posts with turned tops set in concrete footing within wetland areas.
label | ○ 450mm deep concrete footing, 100mm cover between base and post. 50mm soil coverage of post.
label | ○ Posts to be painted using Dulux Weathershield with colours as shown in detail.
label | Standard / Specification - Designer
label | Verifying Document - Inspection, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.03.04 - Lizard Refugia (Disc Pile)
label | Acceptance / Conformance Criteria - Wooden disks minimum 600mm daimetre, minimum 300mm thickness.
label | ○ 100mm nails on both sides for anchorage. Space disks between 5-10mm apart.
label | ○ Discs buried nomimally 300mm into soil.
label | Standard / Specification - Designer
label | Verifying Document - Inspection, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.04.01 - Base Layer
label | Acceptance / Conformance Criteria - Minimum 100mm of compacted GAP40.
label | Standard / Specification - Designer
label | Verifying Document - Inspection, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 5.04.02 - Capping layer
label | Acceptance / Conformance Criteria - 50mm compacted GAP20 with 20% clay content. Mixed prior to installation.
label | ○ Installed as a subtle slope for positive drainage.
label | Standard / Specification - Designer
label | Verifying Document - Inspection, Material Delivery Docket, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 5.04.03 - Geotextile
label | Acceptance / Conformance Criteria - Geotextile to be used if topsoil removal exceeds certain threshold. Designer to advise threshold.
label | Standard / Specification - Designer
label | Verifying Document - Inspection, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 5.04.04 - Soil Spread
label | Acceptance / Conformance Criteria - Topsoil to be feathered out beside edges of path. Should be laid in a way to prevent ponding.
label | ○ Can be placed in a mound if excessive quanties are encountered.
label | Standard / Specification - Designer
label | Verifying Document - Inspection, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 5.05.01 - Footpaths
label | Acceptance / Conformance Criteria - As per footpath construction ITP.
label | Standard / Specification -
label | Verifying Document -
label | Frequency -
label | Verification Activity: Activity -
label | Verification Activity: By -
checkpoint | 5.06.01 - Piles
label | Acceptance / Conformance Criteria - Piles installed as per drawings. 500mm encasement diametre. 900mm depth if installed in sandy soil, 1300mm depth if installed in clay-type soil.
label | Standard / Specification - Designer
label | Verifying Document - Inspection, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 5.06.02 - Fixings
label | Acceptance / Conformance Criteria - Installed in correct position as per drawings.
label | Standard / Specification - Designer
label | Verifying Document - Site Record
label | Frequency - Per Item
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 5.06.03 - Timber
label | Acceptance / Conformance Criteria - 150x50mm base rail coach screwed to post.
label | ○ 200x200mm post set in concrete as per Engineer's requirements.
label | ○ 50x50mm balustrade s/s screw fixed to rails.
label | ○ 150x50mm hand rail coach screwed to post.
label | ○ 200x50mm joists with bracket fixing using s/s screw fixings.
label | ○ 140x40 decking boards atatched to joints with s/s decking screws.
label | ○ 250x50(x2) bearings bolted to piled post.
label | Standard / Specification - Designer
label | Verifying Document - Inspection, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 5.06.04 - Bench
label | Acceptance / Conformance Criteria - Solid macrocarpa bench seats fixed with angle brackets.
label | Standard / Specification - Designer
label | Verifying Document - Inspection, Photographs
label | Frequency - Per Item
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 5.07.01 - Pou Tupua
label | Acceptance / Conformance Criteria - Designer to advise requirements for this item.
label | Standard / Specification - Designer
label | Verifying Document - As Required
label | Frequency - Each Item
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.07.02 - Pou Maumahara/Whenua
label | Acceptance / Conformance Criteria - Designer to advise requirements for this item.
label | Standard / Specification - Designer
label | Verifying Document - As Required
label | Frequency - Each Item
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.01.01 - Red-line Markup
label | Acceptance / Conformance Criteria - Provide red-line markups for items that have been moved, modified, etc.
label | Standard / Specification - Downer
label | Verifying Document - Red-line Markup to be include for every item that has needed to be changed from current IFC
label | Frequency - Upon Completion
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.01.02 - Checklists
label | Acceptance / Conformance Criteria - Provide Checklist for Each Item which shows each stage of QA and Inspections has been signed off
label | Standard / Specification - Downer
label | Verifying Document - For Each Item
label | Frequency - At Completion
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature