## Table 1
[8 empty] | Inspection and Test Plan - Control and Supervision of the Works | [11 empty] | Doc ID: FH-ZU2-QU-ITP033 Rev: 0
Client: Melbourne Airport (APAM) | [8 empty] | Contract No: CP14038 | [8 empty] | Prepared By: Jihad Barbar
Project: Taxiway Zulu 2.0 Project | [14 empty] | Reviewed By: Jamal Khodr | [5 empty] | Date: 06/01/2025
Construction Process: ALER 3 Unbound Pavements | [14 empty] | Approved By: Marco Poggenberg | [5 empty] | Date: 06/01/2025
Specifications: Drawings
Structure / Component: Asphalt Pavement, Crushed Rock Pavement (Type 1&2), Concrete Apron (Type 1&2)
Lot No: |  |  | Lot Details: | [8 empty] | Lot size/Quantity: |  |  |  | Date:
Item No. |  | Task/Activity Description |  |  | Inspection/Test | [10 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  | Responsibility | Checked by:
[5 empty] | Frequency |  | Acceptance Criteria |  |  | Reference Documents |  | Inspectio n/ Test Method |  | Record of conformity |  |  |  |  | Principal’s Representative |  |  | Fulton Hogan | Date
1 |  | Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
1.1 |  | The current revision drawings are being used including subcontractors copy. |  |  | Prior to commencing works |  | Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex |  |  | Aconex |  | Visual inspecti on |  | This signed ITP |  | HP* |  | Project/Site Engineer
1.2 |  | Implementation of all measures and controls. |  |  | Prior to commencing works |  | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP |  |  | PSP, EMP, TMP, WP SWMS |  | Visual inspecti on |  | This signed ITP |  | HP* |  | Project/Site Engineer Foreman
1.3 |  | Survey |  |  | Prior to commencing works |  | Area has been surveyed, highlighting any areas where excavations should not occur (e.g. exclusion zone). |  |  | PSP, EMP, TMP, WP SWMS |  | Verify |  | This ITP signed |  | HP* |  | Project/Site Engineer
1.6 |  | Material Test Certificates |  |  | Prior to commencing works |  | Source Rock shall comply with VicRoads Specification 801 Crushed Rock shall comply with VicRoads Specification 812. The contractor shall provide test certificates confirming that the supplied crushed rock meets this specification |  |  | Drawing 00201 P04 & P05 |  | Verify |  | This ITP signed Material Test Certificates |  | HP |  | Project/Site Engineer / Principals Representative
2 |  | Placement of Sub-basecourse and Basecourse
2.1 |  | Layer Placement |  |  | Every Lot |  |  Place in horizontal layers of approximately equal thickness. The loose thickness layer shall not exceed 300mm UNO, and in any case, shall not exceed the depth for which satisfactory compaction can be achieved |  |  | Drawing 00201 E32 |  | Verify |  | This ITP signed |  | IP |  | Project/Site Engineer
2.2 |  | Placement Checks |  |  | Every Lot |  | During placement of the material check;  Where engineered fill is used to construct permanent batters, it shall be overfilled, compacted, and cut back to the dimensions, levels and design grades to ensure that the final batters have the required compaction  Place in a manner such that handling and spreading of materials does not produce gradation of the materials  Place so that the surface is always self-draining  Engineered fill shall not be placed adjacent to concrete less than 7 days after final placement of the concrete UNO |  |  | Drawing 00201 |  | Verify |  | This ITP signed |  | IP |  | Project/Site Engineer
2.3 |  | Compaction Check |  |  | Every Lot |  | HOLD POINT  Engineered fill material shall be compacted by Tamping Rollers and methods approved by the superintendent.  In areas where access by such plant is not possible, it shall be compacted by a method approved by a qualified geotechnical engineer. |  |  | Drawings 00201 E37 |  | Verify |  | This ITP signed |  | HP |  | Project/Site Engineer / Principals Representative
2.4 |  | Services & Culverts |  |  | Every Lot |  | Check if any culverts or services are with the influence zone for compaction. A general rule, FH will seek advice from the Principles Representative if any culverts, duct banks or RCP pipe are identified closer than 1m from pavement layer surface. If identified, Fulton Hogan will maintain a 1m exclusion zone either side from centre of service for vibrating compaction activities. Hand held DPU’s/whacker plate to be used in lieu of rollers in restricted areas. |  |  | PSP, EMP, TMP, WP SWMS |  | Verify |  | This ITP signed |  | IP |  | Project/Site Engineer
2.5 |  | Protection of Layer |  |  | Every Lot |  | Protect area from undue deterioration by;  Section off area for at least 12 to 48 hours to allow material to dry back.  If unable to do so, keep traffic to a minimum  Or ensure any traffic that has to cross pavement layers, do not follow the same driving line. |  |  | FH Quality Process |  | Verify |  | This ITP signed |  | IP |  | Project/Site Engineer
2.6 |  | Proof Rolling |  |  | Every Lot |  | On Completion of Density Testing, Proof Roll with either: -20 tonne pneumatic tyred roller with individual tyre pressures of not less than 450kpa per tyre. -12 tonne static smooth wheeled roller with a load intensity on the wheels of not less than 6 tonne per metre width. |  |  | Drawing 00201 P07 |  | Verify |  | This ITP signed |  | HP |  | Project/Site Engineer / Principals Representative
3 |  | Testing, Lot Size and Compliance
3.1 |  | Surface Smoothness |  |  | Every Lot |  | No point on the surface of each base or subbase layer shall lie more than 10mm below a 3m straightedge laid parallel to the centreline of the pavement |  |  | Drawing 00201 P11 |  | Verify |  | Report |  | IP |  | Project/Site Engineer
3.2 |  | Layer Thickness |  |  | Every Lot |  | Pavement layers shall not be less than the design thickness. |  |  | Drawing 00201 P09 |  | Survey |  | Survey Report |  | SCP |  | Project/Site Engineer
3.3 |  | Field Dry Density Tests |  |  | Every Lot |  | The minimum frequency of field density tests shall be in accordance with VicRoads specification 304 and not less than:  Base each lot is 5,000 m2 or one day's production  Sub base each lot is 10,000 m2 or one day's production The minimum number of tests per lot shall be six. Field Dry Density Results shall satisfy the specified values as per the drawings |  |  | Drawing 00201 P06 |  | Test |  | Test Report |  | TP |  | Project/Site Engineer
Final Inspection On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract. Print Name: Position: Signature: Date: / /
Legend:
| HP |  |  | Hold Point |  | Work shall not proceed past the HP until released by the Principal’s Representative |  |  |  |  | IP |  | Inspection point |  |  |  | Formal Inspection to be done and recorded
| HP* |  |  | Fulton Hogan Hold Point |  | Work shall not proceed past the HP* until released by Fulton Hogan |  |  |  |  | TP |  | Test Point |  |  |  | Product compliance test to be undertaken and recorded/reported
| WP |  |  | Witness Point |  | An inspection which must be witnessed by the Principal’s Representative |  |  |  |  | SCP |  | Survey conformance point |  |  |  | A qualified surveyor to check product/section/structure and report
| AP |  |  | Approval Point |  | Written or verbal approval given by the Principal’s Representative
Notes: