## Table 1
[7 empty] | Inspection and Test Plan - Control and Supervision of the Works | [13 empty] | Doc ID: FH-ZU2-QU- ITP054 Rev: 0
Client: APAM (MELBOURNE AIRPORT) | [7 empty] | Contract No: CP14038 | [9 empty] | Prepared By: Jihad Barbar
Project: Taxiway Zulu 2.0 Project | [13 empty] | Reviewed By: Jamal Khodr | [7 empty] | Date: 13/01/2025
Construction Process: ALER 3 Fill Placement | [13 empty] | Approved By: Marco Poggenberg | [7 empty] | Date: 14/01/2025
Specifications: IFC Drawing Set-030
Structure / Component: Earthworks
Lot No: |  |  |  | Lot Details: | [6 empty] | Lot size/Quantity: |  |  |  | Date:
Item No. |  | Task/Activity Description |  |  |  | Inspection/Test | [10 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  | Responsibility | Checked by:
[6 empty] | Frequency | Acceptance Criteria |  | Reference Documents |  | Inspection/ Test Method |  | Record of conformity | [6 empty] | Principles Representative |  |  | Fulton Hogan | Date
1 |  | Preliminary Activities
1.1 |  | Check for correct documentation |  |  |  | Prior to works | Ensure that all employees and subcontractors are:  Using the correct and complete set of drawings.  All drawings are the latest revision |  | Aconex |  | Verify |  | This ITP signed |  |  |  | IP |  | Project/Site Engineer
1.2 |  | Implementation of all measures and controls |  |  |  | Prior to works | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS and WP. |  | PSP, EMP, TMP, SWMS, WP |  | Visual inspection |  | This ITP signed |  |  |  | IP |  | Project/Site Engineer
1.3 |  | Survey |  |  |  | Prior to works | Area has been surveyed, highlighting any areas where excavations should not occur (e.g. exclusion zone). |  | PSP, EMP, TMP, SWMS, WP |  | Visual inspection |  | This ITP signed |  |  |  | IP |  | Project/Site Engineer Surveyor
1.4 |  | Submission of Capping Layer material |  |  |  | Prior to works | HOLD POINT Submission of APAM supplied recycled crushed concrete 20MM Class 4 to VicRoads Section 812 and TN107 |  | FHPL- GCOR- 006781 |  | Test Report |  | This ITP signed Aconex Reference |  |  |  | HP |  | Project/Site Engineer Principles Rep
1.5 |  | Plant & Equipment |  |  |  | Prior to works | All plant inducted and inspected as per Fulton Hogan’s plant safety guidelines |  | FH Safety Policy |  | Verify |  | This ITP Signed |  |  |  | HP* |  | Project/Site Engineer
2 |  | Select Fill Works
2.1 |  | Select Fill Placement |  |  |  | Each Lot | Each Lot of fill must:  Not be greater than 300mm in loose layer thickness  Be placed in manner where handling and spreading does not produce gradation of the material  Surface is always self-draining  Where constructing Permanent batters, it shall be overfilled, compacted, and cut back to the dimensions, levels and design grades to ensure the final batters have the required compaction |  | Drawing 00201 E27- E34 |  | Verify |  | This ITP signed |  |  |  | IP |  | Project/Site Engineer Foreman
2.2 |  | Compaction |  |  |  | Each Lot | HOLD POINT  Engineered fill material shall be compacted by tamping rollers and methods approved by the Superintendent. In areas where access by such plant is not possible, it shall be compacted by a Method approved by a qualified geotechnical engineer.  Ensure each fill layer has adequate bonding between layers and is free of laminations and discontinuities |  | Drawing 00201 Notes E37, E38 |  | Visual Inspection & Verify |  | This ITP signed |  |  |  | HP |  | Project/Site Engineer Principles Rep
3 |  | Testing
3.1 |  | Compaction Testing |  |  |  | Each Lot |  Compact by rolling to achieve a Dry Density not less than the following: - Greater than 300mm below formation level to MIN 95% SMDD - Top 300mm below formation level to MIN 98% SMDD (Capping Layer)  The minimum frequency of field density tests shall be in accordance with AS 3798 TABLE 8.1 and not less than the following: - 1 test for each 500m³ volume of compacted fill distributed evenly (minimum 3)  Test Certificates to be provided 14 days after completion of each test to the principals representative |  | Drawing 00201 Note E33, E40, E43 AS1289 5.8.1 |  | Verify |  | Test results & This ITP signed |  |  |  | HP |  | Project/Site Engineer Principles Rep Foreman
3.2 |  | Proof Roll |  |  |  | Each Lot | On Completion of Density Testing, Proof Roll in accordance with AS3798 Section 5.5. |  | Drawing 00201 Note E41 AS3798 |  | Visual Inspection |  | This ITP Signed |  |  |  | HP |  | Project/Site Engineer Principles Rep
Final Inspection On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract. Print Name: Position: Signature: Date: / /
Legend:
| HP |  | Hold Point |  | Work shall not proceed past the HP until released by the Principal’s Representative |  |  |  |  | IP |  | Inspection point |  |  |  | Formal Inspection to be done and recorded
| HP* |  | Fulton Hogan Hold Point |  | Work shall not proceed past the HP* until released by Fulton Hogan |  |  |  |  | TP |  | Test Point |  |  |  | Product compliance test to be undertaken and recorded/reported
| WP |  | Witness Point |  | An inspection which must be witnessed by the Principal’s Representative |  |  |  |  | SCP |  | Survey conformance point |  |  |  | A qualified surveyor to check product/section/structure and report
| AP |  | Approval Point |  | Written or verbal approval given by the Principal’s Representative
Notes