## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP031 - ALER 3 Onsite Concrete | itp |  |  |  |  | FH-ZU2-QU-ITP031 - ALER 3 Onsite Concrete - Rev 1
section | 1.0 - Preliminaries
checkpoint | 1.1 - The current revision drawings are being used including subcontractors copy.
label | Frequency - Prior to Start
label | Acceptance Criteria - Current revision drawing is being used (including the subcontractors copy). Current revision to be obtained via Aconex or ACC
label | Reference Documents - Drawings and drawing registers
label | Inspection/Test Method - Verify
label | Record of conformity - Up to date drawing sets and this ITP signed
label | HP*
label | Responsibility - FH Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to Start
label | Acceptance Criteria - All necessary measures and controls being implemented, that is CEMP, TMP, SWMS, & WP
label | Reference Documents - CEMP, TMP, SWMS, & WP
label | Inspection/Test Method - Verify
label | Record of conformity - Site and office Inspection
label | HP*
label | Responsibility - FH Engineer
date | Date Completed:
checkpoint | 1.3 - Excavation Permit
label | Frequency - Prior to Start
label | Acceptance Criteria - Excavation Permit issued by APAM obtained prior to any excavation on site.
label | Reference Documents - APAM Excavation Permit
label | Inspection/Test Method - Verify
label | Record of conformity - Proof of & permit ITP sign
label | HP*
label | Responsibility - FH Engineer
date | Date Completed:
section | 2.0 - Supply of Materials
checkpoint | 2.1 - Reinforcement
label | Frequency - Pre- commencem ent
label | Acceptance Criteria - HOLD POINT
label | ○ Test Certificates demonstrating compliance of the reinforcement with the requirements of AS 3600
label | Reference Documents - Drawings and Specification
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | HP
label | Responsibility - FH Engineer / Principals Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Concrete Mix Designs
label | Frequency - Each Lot
label | Acceptance Criteria - HOLD POINT
label | ○ Mix design to be submitted to contract administrator for review and acceptance.
label | Reference Documents - Drawings
label | ○ ZULU-BECA- 014-DWG-00201
label | ○ ZULU-BECA- 030-DWG-20001
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | HP
label | Responsibility - FH Engineer / Principals Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Review of Curing Regime
label | Frequency - Each Lot
label | Acceptance Criteria - HOLD POINT
label | ○ Concrete curing regime to be reviewed and approved by the contract administrator prior to use
label | Reference Documents - ZULU-BECA- 030-DWG-20001
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | HP
label | Responsibility - FH Engineer / Principals Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 - Construction\Erection of Formwork
checkpoint | 3.1 - Setout
label | Frequency - Each Lot
label | Acceptance Criteria - Setout completed and conformance with Beca IFC Drawings.
label | Reference Documents - Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - Survey Report
label | SCP
label | Responsibility - FH Engineer Surveyor
date | Date Completed:
checkpoint | 3.2 - Excavate
label | Frequency - Each Lot
label | Acceptance Criteria - WITNESS POINT
label | ○ Excavation depth shall be as per specified or as shown on Drawings to accommodate structures.
label | ○ Principals representative to be notified for at the completion of excavations for inspection prior to any blinding being poured.
label | Reference Documents - Specifications as per Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - FH Engineer
date | Date Completed:
checkpoint | 3.3 - Confirm Ground
label | Frequency - Each lot
label | Acceptance Criteria - HOLD POINT
label | ○ Completion of excavation and inspection of subgrade materials.
label | ○ No soft spots, unsuitable material. Confirm ground bearing pressure
label | ○ Density Testing to be carried put at a minimum of 1 Test for each 100m2 area per layer of compacted excavations for footings & concrete works
label | Reference Documents - Drawing 00201 Note E40
label | Inspection/Test Method - Verify
label | Record of conformity - DCP Test Results
label | HP
label | Responsibility - FH Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Concrete Sub-Base
label | Frequency - Each Lot
label | Acceptance Criteria - Blinding layer is installed as per drawings
label | Reference Documents - Drawings
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Site Engineer / Foreman
date | Date Completed:
checkpoint | 3.5 - Formwork
label | Frequency - Each Lot
label | Acceptance Criteria - Formwork / Reverse Shall conform to shapes, lines, levels and dimensions of the concrete shown or indicated on the Drawings.
label | Reference Documents - Specifications as per Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - FH Engineer Surveyor
date | Date Completed:
checkpoint | 3.6 - Penetrations/Cast in items
label | Frequency - Each Lot
label | Acceptance Criteria - Penetrations/cast in items are present in the formwork.
label | Reference Documents - Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - FH Engineer Surveyor
date | Date Completed:
section | 4.0 - Reinforcement
checkpoint | 4.1 - Reinforcement installation
label | Frequency - Prior to concrete pour
label | Acceptance Criteria - Pre-Pour Checklist Completed:
label | ○ Position and spacing check and recorded.
label | ○ Cover checked and recorded.
label | ○ Reinforcing supports checked and recorded.
label | ○ Laps at required length.
label | ○ Penetrations/cast in items
label | Reference Documents - Specifications and drawings
label | Inspection/Test Method - Verify
label | Record of conformity - Pre-pour inspection List CLA31A
label | IP, HP*
label | Responsibility - FH Engineer
date | Date Completed:
section | 5.0 - Pre-pour Planning and Inspections and Placement (1st Pour)
checkpoint | 5.1 - Pre-pour Inspection
label | Frequency - Prior to concrete pour
label | Acceptance Criteria - HOLD POINT
label | ○ Superintendent or Engineer to conduct pre-pour inspection prior to concrete pour
label | ○ Principals representative to inspect formwork and steel fixing
label | Reference Documents - Specifications and Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - Pre-pour inspection List CLA31A
label | HP
label | Responsibility - FH Engineer / Principals Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Pour in-situ
label | Frequency - Each Lot
label | Acceptance Criteria - Concrete shall be placed within 90mins from batching.
label | ○ All concrete supplied for concrete structures shall be subject to project control testing in accordance with AS 1379.
label | Reference Documents - Specifications and drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - FH Engineer
date | Date Completed:
checkpoint | 5.3 - Concrete Testing – Compressive Tests
label | Frequency - Each Lot
label | Acceptance Criteria - Composite samples to be taken in accordance with AS 1012.1.
label | ○ 2 – 7 Day cylinder and 2 – 28 day cylinders to be taken.
label | ○ Frequency of testing shall be one sample taken either every 50m3 or once per day, whichever yields a higher frequency.
label | Reference Documents - Drawing 00201 Note 51. AS 1012.1, AS 1012.9
label | Inspection/Test Method - Verify
label | Record of conformity - Concrete Testers Sheet/Results
label | TP
label | Responsibility - FH Engineer
date | Date Completed:
checkpoint | 5.4 - Concrete Slump
label | Frequency - Each Truck
label | Acceptance Criteria - Slump test is required for each load per day
label | Reference Documents - Drawing 00201 Note 51.
label | Inspection/Test Method - Verify
label | Record of conformity - Concrete Testers Sheet/Results
label | TP
label | Responsibility - FH Engineer
date | Date Completed:
checkpoint | 5.5 - Finishing & Curing
label | Frequency - Each Lot
label | Acceptance Criteria - Concrete to be vibrated to ensure compaction and air voids removed. Screed finish required on exposed surfaces.
label | ○ Concrete shall be moist cured or coated by an approved curing compound for a period not less than seven days unless approved by the Superintendent.
label | Reference Documents - Specifications and drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This Signed ITP
label | IP
label | Responsibility - FH Engineer
date | Date Completed:
section | 6.0 - Post Pour Details and Inspections
checkpoint | 6.1 - Removal of Formwork
label | Frequency - Each Lot
label | Acceptance Criteria - Forms shall remain and be maintained firmly in place until the concrete has attained the necessary strength to support its own weight.
label | Reference Documents -
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - FH Engineer
date | Date Completed:
checkpoint | 6.2 - Review of Test Results
label | Frequency - Each Lot
label | Acceptance Criteria - Review of 7 day and 28 day test certificates
label | Reference Documents - Drawing 00201 Note 52.
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | HP
label | Responsibility - FH Engineer / Principals Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date:
checklist | ITP033 - ALER 3 Pavements | itp |  |  |  |  | FH-ZU2-QU-ITP033 - ALER 3 Pavements - Rev 0
section | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint | 1.1 - The current revision drawings are being used including subcontractors copy.
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy.
label | ○ Current Revision to be obtained via Aconex
label | Reference Documents - Aconex
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This signed ITP
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls.
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | Reference Documents - PSP, EMP, TMP, WP SWMS
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This signed ITP
label | HP*
label | Responsibility - Project/Site Engineer, Foreman
date | Date Completed:
checkpoint | 1.3 - Survey
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Area has been surveyed, highlighting any areas where excavations should not occur (e.g. exclusion zone).
label | Reference Documents - PSP, EMP, TMP, WP SWMS
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.6 - Material Test Certificates
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Source Rock shall comply with VicRoads Specification 801
label | ○ Crushed Rock shall comply with VicRoads Specification 812. The contractor shall provide test certificates confirming that the supplied crushed rock meets this specification
label | Reference Documents - Drawing 00201 P04 & P05
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed, Material Test Certificates
label | HP
label | Responsibility - Project/Site Engineer / Principals Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 - Placement of Sub-basecourse and Basecourse
checkpoint | 2.1 - Layer Placement
label | Frequency - Every Lot
label | Acceptance Criteria - Place in horizontal layers of approximately equal thickness. The loose thickness layer shall not exceed 300mm UNO, and in any case, shall not exceed the depth for which satisfactory compaction can be achieved
label | Reference Documents - Drawing 00201 E32
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.2 - Placement Checks
label | Frequency - Every Lot
label | Acceptance Criteria - During placement of the material check;
label | ○ Where engineered fill is used to construct permanent batters, it shall be overfilled, compacted, and cut back to the dimensions, levels and design grades to ensure that the final batters have the required compaction
label | ○ Place in a manner such that handling and spreading of materials does not produce gradation of the materials
label | ○ Place so that the surface is always self-draining
label | ○ Engineered fill shall not be placed adjacent to concrete less than 7 days after final placement of the concrete UNO
label | Reference Documents - Drawing 00201
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.3 - Compaction Check
label | Frequency - Every Lot
label | Acceptance Criteria - HOLD POINT
label | ○ Engineered fill material shall be compacted by Tamping Rollers and methods approved by the superintendent.
label | ○ In areas where access by such plant is not possible, it shall be compacted by a method approved by a qualified geotechnical engineer.
label | Reference Documents - Drawings 00201 E37
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project/Site Engineer / Principals Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Services & Culverts
label | Frequency - Every Lot
label | Acceptance Criteria - Check if any culverts or services are with the influence zone for compaction.
label | ○ A general rule, FH will seek advice from the Principles Representative if any culverts, duct banks or RCP pipe are identified closer than 1m from pavement layer surface. If identified, Fulton Hogan will maintain a 1m exclusion zone either side from centre of service for vibrating compaction activities. Hand held DPU’s/whacker plate to be used in lieu of rollers in restricted areas.
label | Reference Documents - PSP, EMP, TMP, WP SWMS
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.5 - Protection of Layer
label | Frequency - Every Lot
label | Acceptance Criteria - Protect area from undue deterioration by;
label | ○ Section off area for at least 12 to 48 hours to allow material to dry back.
label | ○ If unable to do so, keep traffic to a minimum
label | ○ Or ensure any traffic that has to cross pavement layers, do not follow the same driving line.
label | Reference Documents - FH Quality Process
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.6 - Proof Rolling
label | Frequency - Every Lot
label | Acceptance Criteria - On Completion of Density Testing, Proof Roll with either:
label | – 20 tonne pneumatic tyred roller with individual tyre pressures of not less than 450kpa per tyre.
label | – 12 tonne static smooth wheeled roller with a load intensity on the wheels of not less than 6 tonne per metre width.
label | Reference Documents - Drawing 00201 P07
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project/Site Engineer / Principals Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 - Testing, Lot Size and Compliance
checkpoint | 3.1 - Surface Smoothness
label | Frequency - Every Lot
label | Acceptance Criteria - No point on the surface of each base or subbase layer shall lie more than 10mm below a 3m straightedge laid parallel to the centreline of the pavement
label | Reference Documents - Drawing 00201 P11
label | Inspection/Test Method - Verify
label | Record of conformity - Report
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 3.2 - Layer Thickness
label | Frequency - Every Lot
label | Acceptance Criteria - Pavement layers shall not be less than the design thickness.
label | Reference Documents - Drawing 00201 P09
label | Inspection/Test Method - Survey
label | Record of conformity - Survey Report
label | SCP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 3.3 - Field Dry Density Tests
label | Frequency - Every Lot
label | Acceptance Criteria - The minimum frequency of field density tests shall be in accordance with VicRoads specification 304 and not less than:
label | — Base each lot is 5,000 m2 or one day's production
label | — Sub base each lot is 10,000 m2 or one day's production
label | ○ The minimum number of tests per lot shall be six.
label | ○ Field Dry Density Results shall satisfy the specified values as per the drawings
label | Reference Documents - Drawing 00201 P06
label | Inspection/Test Method - Test
label | Record of conformity - Test Report
label | TP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date:
checklist | ITP054 - ALER 3 Fill Placement | itp |  |  |  |  | FH-ZU2-QU-ITP054 - ALER 3 Fill Placement - Rev 0
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to works
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | ○ Using the correct and complete set of drawings.
label | ○ All drawings are the latest revision
label | Reference Documents - Aconex
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS and WP.
label | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.3 - Survey
label | Frequency - Prior to works
label | Acceptance Criteria - Area has been surveyed, highlighting any areas where excavations should not occur (e.g. exclusion zone).
label | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer, Surveyor
date | Date Completed:
checkpoint | 1.4 - Submission of Capping Layer material
label | Frequency - Prior to works
label | Acceptance Criteria - HOLD POINT
label | ○ Submission of APAM supplied recycled crushed concrete 20MM Class 4 to VicRoads Section 812 and TN107
label | Reference Documents - FHPL- GCOR- 006781
label | Inspection/Test Method - Test Report
label | Record of conformity - This ITP signed, Aconex Reference
label | HP
label | Responsibility - Project/Site Engineer, Principles Rep
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Plant & Equipment
label | Frequency - Prior to works
label | Acceptance Criteria - All plant inducted and inspected as per Fulton Hogan’s plant safety guidelines
label | Reference Documents - FH Safety Policy
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 2.0 - Select Fill Works
checkpoint | 2.1 - Select Fill Placement
label | Frequency - Each Lot
label | Acceptance Criteria - Each Lot of fill must:
label | ○ Not be greater than 300mm in loose layer thickness
label | ○ Be placed in manner where handling and spreading does not produce gradation of the material
label | ○ Surface is always self-draining
label | ○ Where constructing Permanent batters, it shall be overfilled, compacted, and cut back to the dimensions, levels and design grades to ensure the final batters have the required compaction
label | Reference Documents - Drawing 00201 E27- E34
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer, Foreman
date | Date Completed:
checkpoint | 2.2 - Compaction
label | Frequency - Each Lot
label | Acceptance Criteria - HOLD POINT
label | ○ Engineered fill material shall be compacted by tamping rollers and methods approved by the Superintendent. In areas where access by such plant is not possible, it shall be compacted by a Method approved by a qualified geotechnical engineer.
label | ○ Ensure each fill layer has adequate bonding between layers and is free of laminations and discontinuities
label | Reference Documents - Drawing 00201 Notes E37, E38
label | Inspection/Test Method - Visual Inspection & Verify
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project/Site Engineer, Principles Rep
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 - Testing
checkpoint | 3.1 - Compaction Testing
label | Frequency - Each Lot
label | Acceptance Criteria - Compact by rolling to achieve a Dry Density not less than the following:
label | — Greater than 300mm below formation level to MIN 95% SMDD
label | — Top 300mm below formation level to MIN 98% SMDD (Capping Layer)
label | ○ The minimum frequency of field density tests shall be in accordance with AS 3798 TABLE 8.1 and not less than the following:
label | — 1 test for each 500m³ volume of compacted fill distributed evenly (minimum 3)
label | ○ Test Certificates to be provided 14 days after completion of each test to the principals representative
label | Reference Documents - Drawing 00201 Note E33, E40, E43, AS1289 5.8.1
label | Inspection/Test Method - Verify
label | Record of conformity - Test results & This ITP signed
label | HP
label | Responsibility - Project/Site Engineer, Principles Rep Foreman
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Proof Roll
label | Frequency - Each Lot
label | Acceptance Criteria - On Completion of Density Testing, Proof Roll in accordance with AS3798 Section 5.5.
label | Reference Documents - Drawing 00201 Note E41, AS3798
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project/Site Engineer, Principles Rep
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: