## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP032 - ALER 3 Structure | itp |  |  |  |  | FH-ZU2-QU-ITP032 - ALER 3 Structure - Rev 0
section | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings.
label | – all drawings are the latest revision.
label | Reference Documents - Drawings / Aconex Register
label | Inspection/Test Method - Verify
label | Record of conformity - Drawings and drawing registers
label | HP*
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - All necessary measures and controls being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 1.3 - Survey Checks
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Check survey to be completed of all footing positions prior to placing any of the panels.
label | Reference Documents - Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed Survey Report
label | HP*
label | Responsibility - Project Engineer / Surveyor
date | Date Completed:
checkpoint | 1.4 - Submission & approval of precast shop drawings
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - HOLD POINT
label | ○ Submit precast wall panel shop drawings to the principal’s representative for approval prior to fabrication commencement.
label | Reference Documents - ZULU-BECA- 001-SPC-00005, 0321 cl 1.16, Drawing 20003 note PC7
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | HP
label | Responsibility - Project Engineer / Principals Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Submission & approval of structural steel shop drawings
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - HOLD POINT
label | ○ Submit structural steel shop drawings to the principal’s representative for approval prior to fabrication commencement.
label | Reference Documents - Drawings 20002, 20020, 20113, 20221
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | HP
label | Responsibility - Project Engineer / Principals Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Material Submissions
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - HOLD POINT
label | ○ Items to include but not limited to:
label | — Concrete Mix Design
label | — Element Casting Checklist
label | — Steel Reinforcement
label | — Precast Sample
label | — Bolts
label | — Ferrules
label | — Grout
label | — Incompressible filler
label | Reference Documents - ZULU-BECA- 001-SPC-00005 cl 1.16, Structural Drawing Set 030-20, AS/NZS 1252.2
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | HP
label | Responsibility - Project Engineer / Principals Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Welding Certification
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Submission & approval of the following:
label | – Welding Procedure Qualification
label | – Welding Procedure Specification
label | – Welder Qualification
label | – Approved Consumables
label | Reference Documents - AS1554.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed, Qualification Documents
label | HP*
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 1.8 - Temporary Works – Pre- Cast Concrete Panels
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Submission and approval of the following documentation by the FH Temp Works Coordinator (not limited to):
label | – Certification of Lifting Points
label | – Propping plan
label | – Erection sequence
label | – Lift plan
label | – Certification of Ground Platform for Lift
label | – Lifting inserts
label | Reference Documents - Structural Drawing Set 030-20
label | Inspection/Test Method - Verify
label | Record of conformity - Certification of lifting points, propping plan, erection sequence, lift study, Geo Report
label | HP*
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 1.9 - Temporary Works – Structural Steel Roof
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Submission and approval of the following documentation by the FH Temp Works Coordinator (not limited to):
label | – Certification of Lifting Points
label | – Installation sequence
label | – Lift plan
label | – Lifting Point calculation
label | – Certification of Ground Platform for Lift
label | Reference Documents - Structural Drawing Set 030-20
label | Inspection/Test Method - Verify
label | Record of conformity - Certification of lifting points, erection sequence, lift study, Geo Report
label | HP*
label | Responsibility - Project Engineer
date | Date Completed:
section | 2.0 - Construction - Precast Concrete Panel
checkpoint | 2.1 - Fabrication Inspections
label | Frequency - Each Lot
label | Acceptance Criteria - Inspection of the following prior to casting:
label | — Formwork dimensions & stability
label | — Edge details and penetrations
label | — Connection materials and inserts in place
label | — Reinforcement
label | — Concreting
label | ○ Inspection of the following after casting
label | — First precast element of each type at the earliest possible time before and immediately after stripping
label | — Stripping & storage
label | Reference Documents - ZULU-BECA- 001-SPC-00005, 0321 Shop Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed, Element Casting Checklist
label | WP
label | Responsibility - Project Engineer / Principals Representative
date | Date Completed:
checkpoint | 2.2 - Delivery of Precast Panels
label | Frequency - Each Lot
label | Acceptance Criteria - Complete inspection of precast panels whilst still loaded on the truck prior to accepting the delivery on site.
label | ○ Identify any damage/defects prior to unloading of the material and correct panel being delivered as per the sequence.
label | ○ Precast element identification is available on each panel
label | Reference Documents - FH Quality Process
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, Materials Inspection Checklist on Conqa
label | IP
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 2.3 - Erection Preparation
label | Frequency - Each Lot
label | Acceptance Criteria - Complete Pre-Lift/s Commencement Checklist
label | ○ Ensure erection drawings & propping plans available to the crew
label | Reference Documents - ZULU-BECA- 001-SPC-00005, 0321, AS 3850 cl 4.4.2
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - Pre-Lift/s Commencement Checklist, This ITP Signed
label | IP, SCP
label | Responsibility - Site Engineer / Foreman / Surveyor
date | Date Completed:
checkpoint | 2.4 - Panel Placement
label | Frequency - Each Lot
label | Acceptance Criteria - Levelling shims have been set correctly and gap between the footing & precast panel is not greater than 40mm
label | ○ Survey to confirm panel placement as per the design
label | Reference Documents - ZULU-BECA- 001-SPC-00005, 0321 Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | IP / SCP
label | Responsibility - Site Engineer / Surveyor
date | Date Completed:
checkpoint | 2.5 - Propping & supports
label | Frequency - Each Lot
label | Acceptance Criteria - Witness Point
label | ○ Propping plan is available for each precast panel
label | ○ Ensure propping is installed as per engineer’s design and/or conforms to AS 3850.2 Sections 5
label | ○ Inspection Notice provided for installed temporary bracing
label | Reference Documents - ZULU-BECA- 001-SPC-00005, 0321, AS 3850.2 Section 5
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, Building Engineering ITP
label | WP
label | Responsibility - Site Engineer / Foreman / Principals Representative
date | Date Completed:
checkpoint | 2.6 - Fixing & Welding on Precast Elements
label | Frequency - Each Lot
label | Acceptance Criteria - Install all fixings as per the drawings & engineers plan
label | ○ All welding shall be carried out in accordance with AS 1554.1 unless noted otherwise, all welds shall be 6 continuous fillet category SP using E49XX electrodes - butt welds shall be complete penetration butt welds, category SP.
label | Reference Documents - AS 1554.1, Drawing 20002
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed Welding Certificate
label | HP*
label | Responsibility - Site Engineer / Foreman
date | Date Completed:
checkpoint | 2.7 - Testing of Welding on Precast Elements (if required)
label | Frequency - Each Lot
label | Acceptance Criteria - A competent inspector shall inspect welding works as per the below table or as otherwise stated by the engineer:
label | – – – – – – – – –
label | WELD TYPE ¦¦ % OF WELDS TESTED ¦¦ TESTING PROCEDURE
label | – – – – – – – – –
label | ALL GP/SP ¦¦ 100% ¦¦ VISUALLY SCANNED
label | SP ¦¦ 20% ¦¦ VISUALL EXAMINED
label | SP BUTT ¦¦ 5% ¦¦ ULTRASONICALLY OR RADIOGRAPHICALLY
label | – – – – – – – – –
label | Reference Documents - Drawing 20002 Note S8
label | Inspection/Test Method - Verify
label | Record of conformity - This Signed ITP, Welding Test Certificate
label | HP*
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 2.8 - Grouting
label | Frequency - Each Lot
label | Acceptance Criteria - Grout to be used shall be non-shrink and have a 28 day characteristic strength of 40 MPA. Details of the proposed grout used to be submitted to the engineer for approval.
label | ○ Note: sealing of the panel vertical joints will be by the precast contractor.
label | Reference Documents - Drawing 20003 Note PC35
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed, Building Engineering ITP
label | IP
label | Responsibility - Site Engineer / Foreman
date | Date Completed:
checkpoint | 2.9 - Removal of Props and Inspection of Completed Precast Walls
label | Frequency - Each Lot
label | Acceptance Criteria - HOLD POINT
label | ○ Inspection Notice provided of the final structure before removal of temporary bracing
label | ○ All propping must remain in position until all structural elements (roof beams, bracing, struts and purlins) affecting stability are fully erected and braced, securely fixed to the panels and the panels have become an integral part of the structure. During construction the builder must ensure no panel props are disconnected by contractors other than the panel contractor.
label | ○ No propping is to be removed without the written consent of the engineer
label | Reference Documents - Approved Shop Drawings, Drawing 20003
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, Engineers Written Approval, Building Engineering ITP
label | HP*
label | Responsibility - Project Engineer / Principal’s Representative
date | Date Completed:
section | 3.0 - Construction - Structural Steel Roof
checkpoint | 3.1 - Delivery of Steel Sections
label | Frequency - Each Lot
label | Acceptance Criteria - Complete a materials inspection upon arrival of steel sections.
label | ○ Ensure correct components and sections have been sent
label | Reference Documents - FH Quality Process
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, Building Engineering ITP, Materials Inspection Checklist on Conqa
label | HP*
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 3.2 - Erection Preparation
label | Frequency - Each Lot
label | Acceptance Criteria - Complete Pre-Lift/s Commencement Checklist
label | ○ Lift sequence/arrangement of steel members available
label | ○ Adequate fall protection in place eg guard rails, safety mesh
label | Reference Documents - Drawing 20002
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed, Building Engineering ITP
label | HP*
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 3.3 - Erection of Steel Members
label | Frequency - Each Lot
label | Acceptance Criteria - Steel Members erected as per design layout and Steel Framing Schedule
label | Reference Documents - Erection Sequence
label | ○ Approved Shop Drawings
label | ○ Structural Drawing Set 030-20
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, Building Engineering ITP
label | IP
label | Responsibility - Site Engineer / Foreman
date | Date Completed:
checkpoint | 3.4 - Bolt installation
label | Frequency - Each Lot
label | Acceptance Criteria - Unless otherwise noted, all bolts shall be M20 Grade 8.8/S, all H/D bolts shall be grade 4.6/S.
label | ○ No connection shall have less than 2 bolts
label | ○ Bolts to be installed as per manufacturer/engineer specification
label | Reference Documents - Drawing 20002 Note S6
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Site Engineer / Foreman
date | Date Completed:
checkpoint | 3.5 - Welding on Steel Framing
label | Frequency - Each Lot
label | Acceptance Criteria - All welding shall be carried out in accordance with AS 1554.1 unless noted otherwise, all welds shall be 6 continuous fillet category SP using E49XX electrodes - butt welds shall be complete penetration butt welds, category SP.
label | Reference Documents - AS 1554.1, Drawing 20002
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed Welding Certificate
label | HP* IP
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 3.6 - Testing of Welding on Steel Framing
label | Frequency - Each Lot
label | Acceptance Criteria - A competent inspector shall inspect welding works as per the below table:
label | – – – – – – – – –
label | WELD TYPE ¦¦ % OF WELDS TESTED ¦¦ TESTING PROCEDURE
label | – – – – – – – – –
label | ALL GP/SP ¦¦ 100% ¦¦ VISUALLY SCANNED
label | SP ¦¦ 20% ¦¦ VISUALLY EXAMINED
label | SP BUTT ¦¦ 5% ¦¦ ULTRASONICALLY OR RADIOGRAPHICALLY
label | – – – – – – – – –
label | Reference Documents - Drawing 20002 Note
label | Inspection/Test Method - Verify
label | Record of conformity - This Signed ITP, Welding Test Certificate
label | HP*
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 3.7 - Inspection of Completed Steel Framing
label | Frequency - Each Lot
label | Acceptance Criteria - WITNESS POINT
label | ○ Provide notice for an inspection of the Steel Framing erected on site before installation of roofing sheets/lining.
label | Reference Documents - ZULU-BECA- 001-SPC-00005, 0342 cl 1.17
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, Building Engineering Structural Steel ITP
label | WP
label | Responsibility - Project Engineer / Principal’s Representative
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: