## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-240-CIV-Ferris-Under track crossing - Ausnet Gas and Telstra
ITP Description: |  | Under track crossing - Ausnet Gas and Telstra
Discipline (e.g. CIV/STR/RAIL) |  | 240-CIV
Revision Number: |  | 0
Revision Date: |  | 2025-02-04
ITP created by: |  | Joanthan Kogan
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Ferris only
Inspection & Test Plan - UTX Pipe Jacking (V/Line)
[9 empty] | Revision: | 0
[9 empty] | Date: | 2025-02-04
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.01 | Non Dependent | AS 4799-2000 Installation of underground utility services ad pipelines within railway boundaries | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.02 | Non Dependent | D/17/62901 Design Requirements & Guidelines - Civil Works on, under or over VicTrack Land | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.03 | Non Dependent | NIST 012.2 - Specification for Signalling Supply, Construction and Installation (V/Line) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.04 | Non Dependent | AS 4142 Fibre Ropes, installed and anchored in the pit | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.05 | Non Dependent | NIST 012.2.1 - Standard for Construction of Cable Route and Signalling Civil Works (V/Line) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.06 | Non Dependent | NIST-2706 - Inspection and Assessment Track Geometry (V/Line) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.07 | Non Dependent | VRIOGS 012.2.1. Settlement Monitoring during construction | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.08 | Non Dependent | VICTRACK STANDARD TS-SP-013 installation of the encasing pipe | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries
2.01 | Materials - Gas Jacking Pipe | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 | Confirm that the GRP pipes delivered to site meet the Pipe Specifications: - Internal Dia: 389mm - Outside Dia: 427mm - Material: GRP Pipe Specification & Grade: DM427 SN100,000 N/m²­­ - Wall Thickness: 19mm - Maximum Working Pressure: N/A - Joint Type: Stainless Steel Collar with EPDM Seal - Pipe Coating: N/A - Cathodic Protection: N/A | Document Review | Prior to Commencement | HP | SE | Material Compliance Certificate
2.02 | Materials - Comms Jacking Pipe | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0203 | Confirm that the GRP pipes delivered to site meet the Pipe Specifications: - Internal Dia: 389mm - Outside Dia: 427mm - Material: GRP Pipe Specification & Grade: DM427 SN100,000 N/m²­­ - Wall Thickness: 19mm - Joint Type: Stainless Steel Collar with EPDM Seal - Pipe Coating: No Coating - Electrically Continuous: N/A - Cathodic Protection: N/A | Document Review | Prior to Commencement | HP | SE | Material Compliance Certificate
2.03 | Materials - Draw ropes | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002 | All conduits must have minimum of one 6mm polypropylene draw rope to AS4142. | Document review/ Visual | Prior to commencement | HP | PE/SE | Material compliance certificate
2.04 | Materials - Comms Carrier conduits | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0203 | Conduit fittings shall be the same type and material as the conduit. Comms conduits to be: - Internal Dia: 93.3mm - Outside Dia: 110.5mm - Material: White PE100 Branded "TELSTRA" Specification & Grade: OD110 PE100 SDR13 - Wall Thickness: 8.6mm - Joint Type: Butt weld - Pipe Coating: N/A - Cathodic Protection: N/A | Document review/ Visual | Prior to commencement | HP | SE/PE/SPE | This ITP/ Material compliance certificate.
2.05 | Materials - Gas Encasing pipe | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 | Confirm that the Gas Encasing pipes delivered to site meet the Pipe Specifications: - Internal Dia: 256mm - Outside Dia: 315mm - Material: Polyethylene Specification & Grade: DN315 PE100 SDR11 - Wall Thickness: 28.6mm - Maximum Working Pressure: 700kPa - Joint Type: Burtt Weld - Pipe Coating: No Coating - Electrically Continuous: N/A - Cathodic Protection: N/A | Document review/ Visual | Prior to commencement | HP | SE/PE/SPE | This ITP/ Material compliance certificate.
2.06 | Materials - Gas Carrying pipe | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 | Confirm that the Gas Carrier pipes delivered to site meet the Pipe Specifications: - Internal Dia: 145mm - Outside Dia: 180mm - Material: Polyethyene Specification & Grade: DN180 PE100 SDR11 - Wall Thickness: 16.4mm - Maximimum Working Pressure: 700kPa Joint Type: Burtt Weld - Pipe Coating: No Coating - Electrically Condinuous: N/A - Cathodic Protection: N/A | Document review/ Visual | Prior to commencement | HP | SE/PE/SPE | This ITP/ Material compliance certificate.
2.07 | Materials - Grout | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 | Diameter of bored hole to jacking pipe shall not exceed diameter of encasing by more than 50mm. annulus to be grouted with an approve controlled low strength material (CLSM) of minimum 2MPa strength material | Document Review | Prior to Commencement | HP* | SE | Material Compliance Certificate and TDS
2.08 | Marker Post and Marker Plate | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203 AS4799-2000 cl 3.10 | Be of non-combustible material for the marker plates and of at least fire-resistant material for the pole. | Document Review | Prior to Commencement | WP | SE | Material Compliance Certificate
2.09 | Poly Welding Qualification (if applicable) | IFC Drawings | HDPE welder qualifications to be supplied | Document Review | Prior to Commencement | WP | SE | Welding Certificate
3 | Pre-construction Activities
3.01 | Survey Set-out | IFC Drawings: MRP-DPK-103-00-CUT-0065, MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203 | Set out line and level of drilling works. Survey to mark out existing services. Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON. GFRP must achieve a min. 1200mm vertical clearance to tracks and minimum 800mm to surface level. Check FSL of track and ground. | Measure Visual | Each element | IP | Surveyor SE/PE/SPE | This ITP
4 | Construction Activities
4.01 | Drill rig set out | NA | Location as per current Drill shot plans | Visual | Prior to commencement | VP | SE | This ITP
4.02 | Ground Conditions | IFC Design Report | Assumed ground conditions are as per site geotechnical report. Geotech Engineer to be immediately notified if the excavations encounter different materials than expected | Visual | Each lot | IP | SE/Site Supervisor | Photos Sign ITP
4.03 | Pilot Hole Drilling | IFC Drawings & SAP | Pilot hole to be drilled and fully supported at all times. | Visual | Each lot | IP | SE/Site Supervisor | Sign ITP
4.04 | Pipe Jacking Monitoring | IFC Drawings & SAP | Inclination and path to be monitored as per design alignment. Ensure bore hole blockage and fluid losses are detected and addressed by: Monitoring drilling fluid volumes, monitoring annular pressureand monitoring cutting returns. | Measure | Continuously through installation | WP | SE/Site Supervisor | Sign ITP
4.05 | Jacking Pipe installation | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203 D/17/62901 | DN427 GRP Jacking Pipe to be reamed, then immediately followed by pipe being pulled through. Bore should remain supported at all times. Diameter of bore is not to exceed diameter of pipe by more than 50mm. Pipes to be installed in straight sections with no excessive bending in the pipes | Visual and Measure | Each lot | IP | SE/Site Supervisor | Sign ITP
4.06 | ULX1 - Gas Encasing Pipe Installation | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 | Install thininsulators @ 1000mm centres between Encasing pipe and Jacking pipe to ensure centralisation | Visual | All Pipe | VP | SE | Sign ITP.
4.07 | ULX1 - Gas Carrier Pipe Installation | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203 | Min depth as per IFC drawings. Install thininsulators @ 1000mm centres between Encasing pipe and carrier pipe to ensure centralisation | Visual | All Pipe | VP | SE | Sign ITP.
4.08 | ULX2 - Conduit Installation and Trace Wire | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0203 | Min depth as per IFC drawings. All bored communications conduits shall include the installation of stainless steel 3mm trace wire. | Visual | All Pipe | VP | SE | Sign ITP.
4.09 | Track Monitoring and Ground Settlement | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002, MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203 NIST-2706 MRP-000-MRPA-PLN-XPM-0055 | Both tracks are to be monitored at 2m intervals either side of the centreline of the under bore for 10m either side of the bore centreline, with additional tilt sensors at 5m intervals up to 20m either side of the bore centreline. Settlement to be monitored with the escalation matrix on the monitoring plan to be followed. <5mm = no action. 5 to 9mm = notify v/line for inspection. 10 to 14mm = stop works and rectify. >14mm = halt train operations. | Measure and Visual | Continuously through installation | IP | SE/Site Supervisor/Survey | Sign ITP
4.10 | Conduit Welding | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203 | Joints are to be butt welded. Weld map to be supplied and identify unique joint numbers. Butt Welding records to be supplied. | Record and Review | All Joints | IP | SE/Site Supervisor/Survey | Sign ITP Butt Welding Records
4.11 | Vent Pipe Installation for ULX1 Gas | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 | DN50 PE Gas Ven to be installed by Asset owner (Downer) a minimum of 3m away from rail assets | Record and Review | All Pipe | HP* | SE/SPE | Sign ITP
4.12 | Grouting | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203 | Diameter of bored hole to jacking pipe shall not exceed diameter of encasing by more than 50mm. annulus to be grouted with an approve controlled low strength material (CLSM) of minimum 2MPa strength material | Review | Each lot | IP | SE/Site Supervisor | Sign ITP
4.13 | Draw rope | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002 | The draw rope shall be continuous for the complete length of the conduit run. All draw ropes must be continuous between pits and have 2m slack in the pit. Draw ropes to be restrained in each pit to prevent them from being inadvertently pulled into the conduits | Visual | All Pipe | VP | SE | Sign ITP.
4.14 | Mandrelling | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002 | Plug with 90% of the pipe diameter to be pulled through each conduit to ensure the conduit hasn't been compressed. | Record and Review | All Pipe | HP* | SE/SPE | Sign ITP
4.15 | Tracer Wire | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002 | All bored communication conduits shall include the installation of a stainless steel trace wire of 3mm diameter. | Record and Review | All Pipe | HP* | SE/SPE | Sign ITP
4.16 | Pipe Completion | IFC Drawings | End of encasing pipe to be sealed at each end as per IFC drawings | Review | Each end of pipe | IP | SE/Site Supervisor | Delivery dockets Sign ITP
4.17 | Reinstatement | IFC Drawings | Entry pits, exit pits and trenches to be backfilled using approved fine crushed rock material. Backfill material shall be compacted to the same density as adjacent material or as specified. | Review | Each lot | IP | SE/Site Supervisor VicTrack | Sign ITP
4.18 | Marker Post Installation | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203 AS4799-2000 | Marker posts to be installed at every 200m intervals, any change in direction and at the entry and exit points of VicTrack property. Marker Posts to be placed facing the rail tracks within VicTrack property 50mm x 8mm Galvanised Steel Plate Welded to 50mm Ø Galvanised Post with as Capped top protruding to the air and flatted end in concrete Marker plate riveted to post with 8mm insulated aluminium rivets. Post to be extend 500mm in ground and be concreted in a 300mm Ø footing, concrete to extend out of ground | Review | Entry and Exit Points | IP | SE/Site Supervisor | Sign ITP Delivery Dockets
5 | Post-construction Activities
5.01 | As-built Survey | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203 | Survey as built report to be compiled. Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON. Sleeve must achieve a min. 2000mm vertical clearance to tracks. | Document Review | Each element | IP | Surveyor SE/PE/SPE | Survey As Report
5.02 | Track Inspection and Maintenance | IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002, MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203 NIST-2706 MRP-000-MRPA-PLN-XPM-0055 | Once works are completed, survey to confirm settlement of the track and ground are within the predicted design settlement values. Not > 15mm To be provided to V/Line prior track hand back. Where track has been disturbed beyond the tolerances, realignment and/or maintenance is required by a qualified sub-contractor. Attach: Track Inspection & Maintenance plan Attach: Track Measuring Sheet | Document Review | Each element Where applicable, | IP | Surveyor SE/PE/SPE | Survey As Built Report
5.03 | Red-line / As-constructed IFC Drawings | MRPA Quality Management Plan | All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar. | Document Review | Once, after construction of the design package | WP | SE/PE/SPE | Red Line Drawing Pack
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /
Note on L45: RATHNAYAKE, Thilan: Correct - that’s the process we will be follwing. We will not be installing a tracer wire. In water pipes there are no tracer wires. Entry pits and exit pits location are not a quality related item so i dont thnk it need to be in the ITP. But I believe we have a dispensation for it. drawings are reviewd by victrack as well before it got to IFC.
Note on L50: RATHNAYAKE, Thilan: No requirements given in SEW specs