## Table 1
Project Name
INSPECTION TEST PLAN STRUCTURAL STEEL WORK
1A
| Rev # |  |  | Date |  |  | Prepared By |  |  |  |  | Reviewed By |  |  |  |  | Approved By |  |  |  | Remarks
| Revision |  |  |  | Revision History
| 1A |  |  |  | First Issue
Before Starting the Project, Ensure all relevant specifications are copied from tender drawings and attached to this ITP.
Page 1 of 7
[22 empty] | Client Name | [6 empty] | Project
INSPECTION TEST PLAN STRUCTURAL STEEL WORK
Prepared By | [13 empty] | Lee West |  |  |  |  | ITP No: | [5 empty] | TEG-007 | [5 empty] | Rev: No: | 1A
LEGEND: XXX – Fabrication Manager YYY – Technical / Project Manager R – REVIEW / S - SURVEILLANCE ZZZ – Independent Inspector W- WITNESS / H – HOLD POINT
No |  |  | Activity | [11 empty] | Inspection |  |  |  | Frequency |  |  |  |  | XXX In Charge |  |  | Acceptance Criteria |  |  |  |  | Verifying Documents
[15 empty] | XXX | YYY |  | ZZZ
1 |  |  | SHOP DRAWINGS
1a |  |  | Issued for Construction drawings received | [20 empty] | QS |  |  | IFC drawings received and reviewed against Tender Documents |  |  |  |  | IFC Drawings
1b |  |  | Shop drawings issued for Approval | [20 empty] | PM |  |  | In accordance to contract specs, design requirements, drawings |  |  |  |  | Issued for Approval Drawings
1c |  |  | Shop drawings issued for Fabrication | [20 empty] | PM |  |  | Should be complying with BOQ and tender conditions |  |  |  |  | Issued for Construction Drawings
2 |  |  | INCOMING MATERIALSa
2a |  |  | Steel profiles | [20 empty] | Fab | [7 empty] | Manufactures test certificates 3rd party test reports
2b |  |  | Plate | [20 empty] | Fab |  |  | Ordered as per BOQ, as per tender specifications and supplied mill certificates |  |  |  |  | Manufactures test certificates 3rd party test reports
2c |  |  | Purlins | [20 empty] | Fab |  |  | Ordered as per BOQ, as per tender specifications and supplied mill certificates |  |  |  |  | Manufactures test certificates 3rd party test reports
2d |  |  | Bolts & Fastenings | [20 empty] | Tech / PM |  |  | Ordered as per bolt list, as per tender specifications and supplied mill certificates |  |  |  |  | Manufactures test certificates 3rd party test reports
2e |  |  | Consumables | [20 empty] | Fab / Tech / PM |  |  | As per tender specifications and supplied mill certificates |  |  |  |  | Manufactures test certificates 3rd party test reports
3 |  |  | FABRICATION
3a |  |  | Fabricate to supplied approved drawings | [20 empty] | Fab |  |  | All pre-fabricated materials to be as per spec:, approved drawings and details and free from damages and rust. |  |  |  |  | Inspection, Checklist Individual QA Sheet
3b |  |  | Inspection complete | [20 empty] | Fab |  |  | Welding inspected in line with required procedures and standards |  |  |  |  | Inspection, Checklist Individual QA Sheet
3c |  |  | Galvanising | [20 empty] | Fab |  |  | Galvanising complete as per required specification |  |  |  |  | Galvanising Certificate Warranty
3d |  |  | Painting / Priming | [20 empty] | Fab |  |  | Galvanising complete as per required specification |  |  |  |  | Painting Certificate / Warranty
4 |  |  | PRE-ERECTION
4a |  |  | Check for bench marks | [20 empty] | Tech |  |  | Permanant bench mark for reference to be available. |  |  |  |  | Inspection, Checklist
4b |  |  | Check on foundations | [20 empty] | Tech |  |  | Foundations are to be cast as per approved drawings and in correct orientations |  |  |  |  | Inspection, Checklist
4c |  |  | Check on levels and distances of foundations | [20 empty] | Tech |  |  | Top level of the foundation wrt bench marks and centre to centre distance and diagonal distance are as per approved details. |  |  |  |  | Inspection, Checklist
5 |  |  | ERECTION IN PROGRESS
5a |  |  | Check on columns erection | [20 empty] | Tech |  |  | Interchanging and turning of columns by 180 degrees to be avoided. |  |  |  |  | Inspection, Checklist
5b |  |  | Check on alignment of columns | [20 empty] | Tech |  |  | Columns are to be properly oriented and centre line of base plate to be coincide with foundation pedestal axis. Foundation bolts to be properly tightened with lock nut |  |  |  |  | Inspection, Checklist
5c |  |  | Check for erection of horizontal beams, girders and vertical bracings | [20 empty] | Tech |  |  | First piece of all columns are to be erected and aligned first. Pieces which affects the movement of crane or other equipment to be erected only at appropriate time. |  |  |  |  | Inspection, Checklist
5d |  |  | Check on bolting | [20 empty] | Tech |  |  | Bolts to be of proper size and to be tightened properly as per bolt tightening procedure. |  |  |  |  | Inspection, Checklist
5e |  |  | Check on erection of interconnecting members | [20 empty] | Tech |  |  | All remaining members to be erected as per the drawing and details providing facility to movement of crane and other equipment. |  |  |  |  | Inspection, Checklist
5f |  |  | Check on welders | [20 empty] | Tech |  |  | All welders to be have qualified welder Certificate or to be approved by performing test at site. |  |  |  |  | Inspection, Checklist
5g |  |  | Check on welding materials | [20 empty] | Tech |  |  | All welding consumables to be available as per the approved details |  |  |  |  | Inspection, Checklist
5h |  |  | Check for pre heating | [20 empty] | Tech |  |  | All joints to be pre heated by approved method by maintaining uniform temperature |  |  |  |  | Inspection, Checklist
5i |  |  | Check for fit up of joints | [20 empty] | Tech |  |  | Minimum gap to be maintained for fillet welding. |  |  |  |  | Inspection, Checklist
5j |  |  | Check for assembly of welding parts | [20 empty] | Tech |  |  | All parts to be welded shall be arranged so as to fit properly on assembly. |  |  |  |  | Inspection, Checklist
5k |  |  | Check for post weld heat treatment | [20 empty] | Tech |  |  | To be done as applicable using appropriate heating method by maintaining uniform temperature. |  |  |  |  | Inspection, Checklist
6 |  |  | POST ERECTION
6a |  |  | Check on columns and other members | [20 empty] | PM |  |  | Total erected columns to be vertical within the tolerance as per spec All other members to be vertical or horizontal as the case may be within tolerance as per spec/standard |  |  |  |  | Inspection, Checklist
6b |  |  | Check on weld surface & Size | [20 empty] | PM |  |  | All welds to be cleaned, overlap / excess weld metal to be removed by grinding. Weld size not to be less than specified. |  |  |  |  | Inspection, Checklist
6c |  |  | Check on welding | [20 empty] | PM |  |  | All welding to be free from surface cracks, blow holes, infused welds, improper welding profile and misalignment of welded parts etc: |  |  |  |  | Inspection, Checklist
6d |  |  | Testing of welds | [20 empty] | PM |  |  | Tests to be done for required no.: of welds as per specification |  |  |  |  | Inspection, Checklist
6e |  |  | Check for repair of faulty welds | [20 empty] | PM |  |  | Defective weld to be removed up to the sound metal and parent metal is free from damage. |  |  |  |  | Inspection, Checklist
6f |  |  | Check for re weld and retest | [20 empty] | PM |  |  | To be done by using the same procedure and methods. |  |  |  |  | Inspection, Checklist
6g |  |  | Check on tolerances | [20 empty] | PM |  |  | All tolerance to be within the limit specified |  |  |  |  | Inspection, Checklist
6h |  |  | Check on grouting | [20 empty] | PM |  |  | After all erections are approved. Grouting to be done as per the approved method after cleaning and clearing of all dust, mud, water, oil and other unwanted material by using approved material. |  |  |  |  | Inspection, Checklist
6i |  |  | Check on painting | [20 empty] | PM |  |  | Painting to be carried out as per specifications |  |  |  |  | Inspection, Checklist
7 |  |  | CLOSEOUT
7a |  |  | Site diaries | [20 empty] | PM |  |  | All site diaries compiled in QA folder |  |  |  |  | Inspection, Checklist
7b |  |  | Internal Inspection reports | [20 empty] | PM |  |  | All internal reports including fabrication, surface treatment, and erection compiled in QA folder |  |  |  |  | Inspection, Checklist
7c |  |  | Independent Inspection reports | [20 empty] | PM |  |  | All Independent Weld Certificates compiled in QA folder |  |  |  |  | Inspection, Checklist
7d |  |  | Mill Certs | [20 empty] | PM |  |  | All Mill Certs compiled in QA folder |  |  |  |  | Inspection, Checklist
7e |  |  | As Built Drawings | [20 empty] | PM |  |  | Shop Drawings confirmed as acceptable and supplied to relevant parties |  |  |  |  | Inspection, Checklist
7f |  |  | Producer Statements | [20 empty] | PM |  |  | Producer Statements completed and in QA folder |  |  |  |  | Inspection, Checklist
7g |  |  | Client acceptance | [20 empty] | PM |  |  | Correspondence of acceptance compiled in QA folder |  |  |  |  | Inspection, Checklist
[15 empty] | Client |  |  | Project
INSPECTION CHECKLIST STRUCTURAL STEEL WORK-ERECTION
ITP | [5 empty] | Structural Steel |  |  |  | Inspection No. | [9 empty] | Location
Prepared by | [14 empty] | Applicable Drawing
# |  | Description | [6 empty] | Result |  | Date |  | Sign |  |  | # |  | Description | [5 empty] | Result |  | Date |  | Sign
[13 empty] | XXX |  | YYY | [12 empty] | XXX |  | YYY
3 |  | FABRICATION | [13 empty] | 6 |  | POST ERECTION
3a |  | Inspection complete | [13 empty] | 6a |  | Check on columns and other members
4 |  | PRE-ERECTION | [13 empty] | 6b |  | Check on weld surface & Size
4a |  | Check for bench marks | [13 empty] | 6c |  | Check on welding
4b |  | Check on foundations | [13 empty] | 6d |  | Testing of welds
4c |  | Check on levels and distances of foundations | [13 empty] | 6e |  | Check for repair of faulty welds
5 |  | ERECTION IN PROGRESS | [13 empty] | 6f |  | Check for re weld and retest
5a |  | Check on columns erection | [13 empty] | 6g |  | Check on tolerances
5b |  | Check on alignment of columns | [13 empty] | 6h |  | Check on grouting
5c |  | Check for erection of horizontal beams, girders and vertical bracings | [13 empty] | 6i |  | Check on painting
5d |  | Check on bolting | [13 empty] | 7 |  | CLOSEOUT
5e |  | Check on erection of interconnecting members | [13 empty] | 7a |  | Site Diaries
5f |  | Check on welders | [13 empty] | 7b |  | Internal Inspection reports
5g |  | Check on welding materials | [13 empty] | 7c |  | Independent Inspection reports
5h |  | Check for pre heating | [13 empty] | 7d |  | Mill Certs
5i |  | Check for fit up of joints | [13 empty] | 7e |  | As Built Drawings
5j |  | Check for assembly of welding parts | [13 empty] | 7f |  | Producer Statements
5k |  | Check for post weld heat treatment | [13 empty] | 7g |  | Client Acceptance
CONCLUSION | [7 empty] |  Accepted  Accepted with Comments  Rejected
COMMENTS
[8 empty] | XXX (Contractor) | [6 empty] | YYY (Consultant) | [7 empty] | Client
Name
Sign
Date