## Sheet1
1a | Issued for Construction drawings received | QS | IFC drawings received and reviewed against Tender Documents | IFC Drawings | 1a - Issued for Construction drawings received | XXX In Charge - QS | Acceptance Criteria - IFC drawings received and reviewed against Tender Documents | Verifying Documents - IFC Drawings | 1a - Issued for Construction drawings received | 3a | Inspection complete | 3a - Inspection complete | All Phases | Shop drawings issued in accordance with contract specification, design requirements and IFC drawings | Internal review against project specs. External review by Engineer / Architect | Approval of each phase | Engineer / Architect | All Phases | Specification - Shop drawings issued in accordance with contract specification, design requirements and IFC drawings | Acceptance Criteria - Internal review against project specs. External review by Engineer / Architect | Record - Approval of each phase | Inspected By - Engineer / Architect | All Phases
1b | Shop drawings issued for Approval | PM | In accordance to contract specs, design requirements, drawings | Issued for Approval Drawings | 1b - Shop drawings issued for Approval | XXX In Charge - PM | Acceptance Criteria - In accordance to contract specs, design requirements, drawings | Verifying Documents - Issued for Approval Drawings | XXX In Charge - QS | 4a | Check for bench marks | 4a - Check for bench marks | Steel Profiles | Various grades | Ordered as per BOQ, as per IFC specifications and supplied mill certificates | Mill Certs | Fabrication Manager | Steel Profiles | Specification - Various grades | Acceptance Criteria - Ordered as per BOQ, as per IFC specifications and supplied mill certificates | Record - Mill Certs | Inspected By - Fabrication Manager | Specification - Shop drawings issued in accordance with contract specification, design requirements and IFC drawings
1c | Shop drawings issued for Fabrication | PM | Should be complying with BOQ and tender conditions | Issued for Construction Drawings | 1c - Shop drawings issued for Fabrication | XXX In Charge - PM | Acceptance Criteria - Should be complying with BOQ and tender conditions | Verifying Documents - Issued for Construction Drawings | Acceptance Criteria - IFC drawings received and reviewed against Tender Documents | 4b | Check on foundations | 4b - Check on foundations | Purlins | Z275 Purlins. Z450 Fast Bracing | Ordered as per BOQ, as per IFC specifications and supplied mill certificates | Mill Certs | Fabrication Manager | Purlins | Specification - Z275 Purlins. Z450 Fast Bracing | Acceptance Criteria - Ordered as per BOQ, as per IFC specifications and supplied mill certificates | Record - Mill Certs | Inspected By - Fabrication Manager | Acceptance Criteria - Internal review against project specs. External review by Engineer / Architect
2a | Steel profiles | Fab |  | Manufactures test certificates 3rd party test reports | 2a - Steel profiles | XXX In Charge - Fab | Acceptance Criteria - | Verifying Documents - Manufactures test certificates 3rd party test reports | Verifying Documents - IFC Drawings | 4c | Check on levels and distances of foundations | 4c - Check on levels and distances of foundations | Bolts | Various | Ordered as per BOQ, as per IFC specifications and supplied mill certificates | Bolt / Mill Certs | Fabrication Manager | Bolts | Specification - Various | Acceptance Criteria - Ordered as per BOQ, as per IFC specifications and supplied mill certificates | Record - Bolt / Mill Certs | Inspected By - Fabrication Manager | Record - Approval of each phase
2b | Plate | Fab | Ordered as per BOQ, as per tender specifications and supplied mill certificates | Manufactures test certificates 3rd party test reports | 2b - Plate | XXX In Charge - Fab | Acceptance Criteria - Ordered as per BOQ, as per tender specifications and supplied mill certificates | Verifying Documents - Manufactures test certificates 3rd party test reports | 1b - Shop drawings issued for Approval | 5a | Check on columns erection | 5a - Check on columns erection | Internal Store Fitout | IZS2 | DFT Inspection Report and Supplier Certificate | Certificates from suppliers | Project Manager | Internal Store Fitout | Specification - IZS2 | Acceptance Criteria - DFT Inspection Report and Supplier Certificate | Record - Certificates from suppliers | Inspected By - Project Manager | Inspected By - Engineer / Architect
2c | Purlins | Fab | Ordered as per BOQ, as per tender specifications and supplied mill certificates | Manufactures test certificates 3rd party test reports | 2c - Purlins | XXX In Charge - Fab | Acceptance Criteria - Ordered as per BOQ, as per tender specifications and supplied mill certificates | Verifying Documents - Manufactures test certificates 3rd party test reports | XXX In Charge - PM | 5b | Check on alignment of columns | 5b - Check on alignment of columns | Internal Seismic | IZS2 | DFT Inspection Report and Supplier Certificate | Certificates from suppliers | Project Manager | Internal Seismic | Specification - IZS2 | Acceptance Criteria - DFT Inspection Report and Supplier Certificate | Record - Certificates from suppliers | Inspected By - Project Manager | Steel Profiles
2d | Bolts CHAR(AMP) Fastenings | Tech / PM | Ordered as per bolt list, as per tender specifications and supplied mill certificates | Manufactures test certificates 3rd party test reports | 2d - Bolts CHAR(AMP) Fastenings | XXX In Charge - Tech / PM | Acceptance Criteria - Ordered as per bolt list, as per tender specifications and supplied mill certificates | Verifying Documents - Manufactures test certificates 3rd party test reports | Acceptance Criteria - In accordance to contract specs, design requirements, drawings | 5c | Check for erection of horizontal beams, girders and vertical bracings | 5c - Check for erection of horizontal beams, girders and vertical bracings | Large Canopy | HDG600, PUR2 | DFT Inspection Report and Supplier Certificate | Certificates from suppliers | Project Manager | Large Canopy | Specification - HDG600, PUR2 | Acceptance Criteria - DFT Inspection Report and Supplier Certificate | Record - Certificates from suppliers | Inspected By - Project Manager | Specification - Various grades
2e | Consumables | Fab / Tech / PM | As per tender specifications and supplied mill certificates | Manufactures test certificates 3rd party test reports | 2e - Consumables | XXX In Charge - Fab / Tech / PM | Acceptance Criteria - As per tender specifications and supplied mill certificates | Verifying Documents - Manufactures test certificates 3rd party test reports | Verifying Documents - Issued for Approval Drawings | 5d | Check on bolting | 5d - Check on bolting | Small Canopy | HDG600, SHS topcoat only. | DFT Inspection Report and Supplier Certificate | Certificates from suppliers | Project Manager | Small Canopy | Specification - HDG600, SHS topcoat only. | Acceptance Criteria - DFT Inspection Report and Supplier Certificate | Record - Certificates from suppliers | Inspected By - Project Manager | Acceptance Criteria - Ordered as per BOQ, as per IFC specifications and supplied mill certificates
3a | Fabricate to supplied approved drawings | Fab | All pre-fabricated materials to be as per spec:, approved drawings and details and free from damages and rust. | Inspection, Checklist Individual QA Sheet | 3a - Fabricate to supplied approved drawings | XXX In Charge - Fab | Acceptance Criteria - All pre-fabricated materials to be as per spec:, approved drawings and details and free from damages and rust. | Verifying Documents - Inspection, Checklist Individual QA Sheet | 1c - Shop drawings issued for Fabrication | 5e | Check on erection of interconnecting members | 5e - Check on erection of interconnecting members | Plant Platform | HDG600 | DFT Inspection Report and Supplier Certificate | Certificates from suppliers | Project Manager | Plant Platform | Specification - HDG600 | Acceptance Criteria - DFT Inspection Report and Supplier Certificate | Record - Certificates from suppliers | Inspected By - Project Manager | Record - Mill Certs
3b | Inspection complete | Fab | Welding inspected in line with required procedures and standards | Inspection, Checklist Individual QA Sheet | 3b - Inspection complete | XXX In Charge - Fab | Acceptance Criteria - Welding inspected in line with required procedures and standards | Verifying Documents - Inspection, Checklist Individual QA Sheet | XXX In Charge - PM | 5f | Check on welders | 5f - Check on welders | Shop welding | CC2. NZS 3404 – Appendix D | 100% Visual Scanning 25% Visual Examination 10%UT for FSBW | Independent Welding Inspection Report | Fabrication Manager | Shop welding | Specification - CC2. NZS 3404 – Appendix D | Acceptance Criteria - 100% Visual Scanning 25% Visual Examination 10%UT for FSBW | Record - Independent Welding Inspection Report | Inspected By - Fabrication Manager | Inspected By - Fabrication Manager
3c | Galvanising | Fab | Galvanising complete as per required specification | Galvanising Certificate Warranty | 3c - Galvanising | XXX In Charge - Fab | Acceptance Criteria - Galvanising complete as per required specification | Verifying Documents - Galvanising Certificate Warranty | Acceptance Criteria - Should be complying with BOQ and tender conditions | 5g | Check on welding materials | 5g - Check on welding materials | [10 empty] | Purlins
3d | Painting / Priming | Fab | Galvanising complete as per required specification | Painting Certificate / Warranty | 3d - Painting / Priming | XXX In Charge - Fab | Acceptance Criteria - Galvanising complete as per required specification | Verifying Documents - Painting Certificate / Warranty | Verifying Documents - Issued for Construction Drawings | 5h | Check for pre heating | 5h - Check for pre heating | [10 empty] | Specification - Z275 Purlins. Z450 Fast Bracing
4a | Check for bench marks | Tech | Permanant bench mark for reference to be available. | Inspection, Checklist | 4a - Check for bench marks | XXX In Charge - Tech | Acceptance Criteria - Permanant bench mark for reference to be available. | Verifying Documents - Inspection, Checklist | 2a - Steel profiles | 5i | Check for fit up of joints | 5i - Check for fit up of joints | [10 empty] | Acceptance Criteria - Ordered as per BOQ, as per IFC specifications and supplied mill certificates
4b | Check on foundations | Tech | Foundations are to be cast as per approved drawings and in correct orientations | Inspection, Checklist | 4b - Check on foundations | XXX In Charge - Tech | Acceptance Criteria - Foundations are to be cast as per approved drawings and in correct orientations | Verifying Documents - Inspection, Checklist | XXX In Charge - Fab | 5j | Check for assembly of welding parts | 5j - Check for assembly of welding parts | [10 empty] | Record - Mill Certs
4c | Check on levels and distances of foundations | Tech | Top level of the foundation wrt bench marks and centre to centre distance and diagonal distance are as per approved details. | Inspection, Checklist | 4c - Check on levels and distances of foundations | XXX In Charge - Tech | Acceptance Criteria - Top level of the foundation wrt bench marks and centre to centre distance and diagonal distance are as per approved details. | Verifying Documents - Inspection, Checklist | Acceptance Criteria - | 5k | Check for post weld heat treatment | 5k - Check for post weld heat treatment | [10 empty] | Inspected By - Fabrication Manager
5a | Check on columns erection | Tech | Interchanging and turning of columns by 180 degrees to be avoided. | Inspection, Checklist | 5a - Check on columns erection | XXX In Charge - Tech | Acceptance Criteria - Interchanging and turning of columns by 180 degrees to be avoided. | Verifying Documents - Inspection, Checklist | Verifying Documents - Manufactures test certificates 3rd party test reports | 6a | Check on columns and other members | 6a - Check on columns and other members | [10 empty] | Bolts
5b | Check on alignment of columns | Tech | Columns are to be properly oriented and centre line of base plate to be coincide with foundation pedestal axis. Foundation bolts to be properly tightened with lock nut | Inspection, Checklist | 5b - Check on alignment of columns | XXX In Charge - Tech | Acceptance Criteria - Columns are to be properly oriented and centre line of base plate to be coincide with foundation pedestal axis. Foundation bolts to be properly tightened with lock nut | Verifying Documents - Inspection, Checklist | 2b - Plate | 6b | Check on weld surface & Size | 6b - Check on weld surface & Size | [10 empty] | Specification - Various
5c | Check for erection of horizontal beams, girders and vertical bracings | Tech | First piece of all columns are to be erected and aligned first. Pieces which affects the movement of crane or other equipment to be erected only at appropriate time. | Inspection, Checklist | 5c - Check for erection of horizontal beams, girders and vertical bracings | XXX In Charge - Tech | Acceptance Criteria - First piece of all columns are to be erected and aligned first. Pieces which affects the movement of crane or other equipment to be erected only at appropriate time. | Verifying Documents - Inspection, Checklist | XXX In Charge - Fab | 6c | Check on welding | 6c - Check on welding | [10 empty] | Acceptance Criteria - Ordered as per BOQ, as per IFC specifications and supplied mill certificates
5d | Check on bolting | Tech | Bolts to be of proper size and to be tightened properly as per bolt tightening procedure. | Inspection, Checklist | 5d - Check on bolting | XXX In Charge - Tech | Acceptance Criteria - Bolts to be of proper size and to be tightened properly as per bolt tightening procedure. | Verifying Documents - Inspection, Checklist | Acceptance Criteria - Ordered as per BOQ, as per tender specifications and supplied mill certificates | 6d | Testing of welds | 6d - Testing of welds | [10 empty] | Record - Bolt / Mill Certs
5e | Check on erection of interconnecting members | Tech | All remaining members to be erected as per the drawing and details providing facility to movement of crane and other equipment. | Inspection, Checklist | 5e - Check on erection of interconnecting members | XXX In Charge - Tech | Acceptance Criteria - All remaining members to be erected as per the drawing and details providing facility to movement of crane and other equipment. | Verifying Documents - Inspection, Checklist | Verifying Documents - Manufactures test certificates 3rd party test reports | 6e | Check for repair of faulty welds | 6e - Check for repair of faulty welds | [10 empty] | Inspected By - Fabrication Manager
5f | Check on welders | Tech | All welders to be have qualified welder Certificate or to be approved by performing test at site. | Inspection, Checklist | 5f - Check on welders | XXX In Charge - Tech | Acceptance Criteria - All welders to be have qualified welder Certificate or to be approved by performing test at site. | Verifying Documents - Inspection, Checklist | 2c - Purlins | 6f | Check for re weld and retest | 6f - Check for re weld and retest | [10 empty] | Internal Store Fitout
5g | Check on welding materials | Tech | All welding consumables to be available as per the approved details | Inspection, Checklist | 5g - Check on welding materials | XXX In Charge - Tech | Acceptance Criteria - All welding consumables to be available as per the approved details | Verifying Documents - Inspection, Checklist | XXX In Charge - Fab | 6g | Check on tolerances | 6g - Check on tolerances | [10 empty] | Specification - IZS2
5h | Check for pre heating | Tech | All joints to be pre heated by approved method by maintaining uniform temperature | Inspection, Checklist | 5h - Check for pre heating | XXX In Charge - Tech | Acceptance Criteria - All joints to be pre heated by approved method by maintaining uniform temperature | Verifying Documents - Inspection, Checklist | Acceptance Criteria - Ordered as per BOQ, as per tender specifications and supplied mill certificates | 6h | Check on grouting | 6h - Check on grouting | [10 empty] | Acceptance Criteria - DFT Inspection Report and Supplier Certificate
5i | Check for fit up of joints | Tech | Minimum gap to be maintained for fillet welding. | Inspection, Checklist | 5i - Check for fit up of joints | XXX In Charge - Tech | Acceptance Criteria - Minimum gap to be maintained for fillet welding. | Verifying Documents - Inspection, Checklist | Verifying Documents - Manufactures test certificates 3rd party test reports | 6i | Check on painting | 6i - Check on painting | [10 empty] | Record - Certificates from suppliers
5j | Check for assembly of welding parts | Tech | All parts to be welded shall be arranged so as to fit properly on assembly. | Inspection, Checklist | 5j - Check for assembly of welding parts | XXX In Charge - Tech | Acceptance Criteria - All parts to be welded shall be arranged so as to fit properly on assembly. | Verifying Documents - Inspection, Checklist | 2d - Bolts CHAR(AMP) Fastenings | 7a | Site Diaries | 7a - Site Diaries | [10 empty] | Inspected By - Project Manager
5k | Check for post weld heat treatment | Tech | To be done as applicable using appropriate heating method by maintaining uniform temperature. | Inspection, Checklist | 5k - Check for post weld heat treatment | XXX In Charge - Tech | Acceptance Criteria - To be done as applicable using appropriate heating method by maintaining uniform temperature. | Verifying Documents - Inspection, Checklist | XXX In Charge - Tech / PM | 7b | Internal Inspection reports | 7b - Internal Inspection reports | [10 empty] | Internal Seismic
6a | Check on columns and other members | PM | Total erected columns to be vertical within the tolerance as per spec All other members to be vertical or horizontal as the case may be within tolerance as per spec/standard | Inspection, Checklist | 6a - Check on columns and other members | XXX In Charge - PM | Acceptance Criteria - Total erected columns to be vertical within the tolerance as per spec All other members to be vertical or horizontal as the case may be within tolerance as per spec/standard | Verifying Documents - Inspection, Checklist | Acceptance Criteria - Ordered as per bolt list, as per tender specifications and supplied mill certificates | 7c | Independent Inspection reports | 7c - Independent Inspection reports | [10 empty] | Specification - IZS2
6b | Check on weld surface CHAR(AMP) Size | PM | All welds to be cleaned, overlap / excess weld metal to be removed by grinding. Weld size not to be less than specified. | Inspection, Checklist | 6b - Check on weld surface CHAR(AMP) Size | XXX In Charge - PM | Acceptance Criteria - All welds to be cleaned, overlap / excess weld metal to be removed by grinding. Weld size not to be less than specified. | Verifying Documents - Inspection, Checklist | Verifying Documents - Manufactures test certificates 3rd party test reports | 7d | Mill Certs | 7d - Mill Certs | [10 empty] | Acceptance Criteria - DFT Inspection Report and Supplier Certificate
6c | Check on welding | PM | All welding to be free from surface cracks, blow holes, infused welds, improper welding profile and misalignment of welded parts etc: | Inspection, Checklist | 6c - Check on welding | XXX In Charge - PM | Acceptance Criteria - All welding to be free from surface cracks, blow holes, infused welds, improper welding profile and misalignment of welded parts etc: | Verifying Documents - Inspection, Checklist | 2e - Consumables | 7e | As Built Drawings | 7e - As Built Drawings | [10 empty] | Record - Certificates from suppliers
6d | Testing of welds | PM | Tests to be done for required no.: of welds as per specification | Inspection, Checklist | 6d - Testing of welds | XXX In Charge - PM | Acceptance Criteria - Tests to be done for required no.: of welds as per specification | Verifying Documents - Inspection, Checklist | XXX In Charge - Fab / Tech / PM | 7f | Producer Statements | 7f - Producer Statements | [10 empty] | Inspected By - Project Manager
6e | Check for repair of faulty welds | PM | Defective weld to be removed up to the sound metal and parent metal is free from damage. | Inspection, Checklist | 6e - Check for repair of faulty welds | XXX In Charge - PM | Acceptance Criteria - Defective weld to be removed up to the sound metal and parent metal is free from damage. | Verifying Documents - Inspection, Checklist | Acceptance Criteria - As per tender specifications and supplied mill certificates | 7g | Client Acceptance | 7g - Client Acceptance | [10 empty] | Large Canopy
6f | Check for re weld and retest | PM | To be done by using the same procedure and methods. | Inspection, Checklist | 6f - Check for re weld and retest | XXX In Charge - PM | Acceptance Criteria - To be done by using the same procedure and methods. | Verifying Documents - Inspection, Checklist | Verifying Documents - Manufactures test certificates 3rd party test reports | [13 empty] | Specification - HDG600, PUR2
6g | Check on tolerances | PM | All tolerance to be within the limit specified | Inspection, Checklist | 6g - Check on tolerances | XXX In Charge - PM | Acceptance Criteria - All tolerance to be within the limit specified | Verifying Documents - Inspection, Checklist | 3a - Fabricate to supplied approved drawings | [13 empty] | Acceptance Criteria - DFT Inspection Report and Supplier Certificate
6h | Check on grouting | PM | After all erections are approved. Grouting to be done as per the approved method after cleaning and clearing of all dust, mud, water, oil and other unwanted material by using approved material. | Inspection, Checklist | 6h - Check on grouting | XXX In Charge - PM | Acceptance Criteria - After all erections are approved. Grouting to be done as per the approved method after cleaning and clearing of all dust, mud, water, oil and other unwanted material by using approved material. | Verifying Documents - Inspection, Checklist | XXX In Charge - Fab | [13 empty] | Record - Certificates from suppliers
6i | Check on painting | PM | Painting to be carried out as per specifications | Inspection, Checklist | 6i - Check on painting | XXX In Charge - PM | Acceptance Criteria - Painting to be carried out as per specifications | Verifying Documents - Inspection, Checklist | Acceptance Criteria - All pre-fabricated materials to be as per spec:, approved drawings and details and free from damages and rust. | [13 empty] | Inspected By - Project Manager
7a | Site diaries | PM | All site diaries compiled in QA folder | Inspection, Checklist | 7a - Site diaries | XXX In Charge - PM | Acceptance Criteria - All site diaries compiled in QA folder | Verifying Documents - Inspection, Checklist | Verifying Documents - Inspection, Checklist Individual QA Sheet | [13 empty] | Small Canopy
7b | Internal Inspection reports | PM | All internal reports including fabrication, surface treatment, and erection compiled in QA folder | Inspection, Checklist | 7b - Internal Inspection reports | XXX In Charge - PM | Acceptance Criteria - All internal reports including fabrication, surface treatment, and erection compiled in QA folder | Verifying Documents - Inspection, Checklist | 3b - Inspection complete | [13 empty] | Specification - HDG600, SHS topcoat only.
7c | Independent Inspection reports | PM | All Independent Weld Certificates compiled in QA folder | Inspection, Checklist | 7c - Independent Inspection reports | XXX In Charge - PM | Acceptance Criteria - All Independent Weld Certificates compiled in QA folder | Verifying Documents - Inspection, Checklist | XXX In Charge - Fab | [13 empty] | Acceptance Criteria - DFT Inspection Report and Supplier Certificate
7d | Mill Certs | PM | All Mill Certs compiled in QA folder | Inspection, Checklist | 7d - Mill Certs | XXX In Charge - PM | Acceptance Criteria - All Mill Certs compiled in QA folder | Verifying Documents - Inspection, Checklist | Acceptance Criteria - Welding inspected in line with required procedures and standards | [13 empty] | Record - Certificates from suppliers
7e | As Built Drawings | PM | Shop Drawings confirmed as acceptable and supplied to relevant parties | Inspection, Checklist | 7e - As Built Drawings | XXX In Charge - PM | Acceptance Criteria - Shop Drawings confirmed as acceptable and supplied to relevant parties | Verifying Documents - Inspection, Checklist | Verifying Documents - Inspection, Checklist Individual QA Sheet | [13 empty] | Inspected By - Project Manager
7f | Producer Statements | PM | Producer Statements completed and in QA folder | Inspection, Checklist | 7f - Producer Statements | XXX In Charge - PM | Acceptance Criteria - Producer Statements completed and in QA folder | Verifying Documents - Inspection, Checklist | 3c - Galvanising | [13 empty] | Plant Platform
7g | Client acceptance | PM | Correspondence of acceptance compiled in QA folder | Inspection, Checklist | 7g - Client acceptance | XXX In Charge - PM | Acceptance Criteria - Correspondence of acceptance compiled in QA folder | Verifying Documents - Inspection, Checklist | XXX In Charge - Fab | [13 empty] | Specification - HDG600
[9 empty] | Acceptance Criteria - Galvanising complete as per required specification | [13 empty] | Acceptance Criteria - DFT Inspection Report and Supplier Certificate
[9 empty] | Verifying Documents - Galvanising Certificate Warranty | [13 empty] | Record - Certificates from suppliers
[9 empty] | 3d - Painting / Priming | [13 empty] | Inspected By - Project Manager
[9 empty] | XXX In Charge - Fab | [13 empty] | Shop welding
[9 empty] | Acceptance Criteria - Galvanising complete as per required specification | [13 empty] | Specification - CC2. NZS 3404 – Appendix D
[9 empty] | Verifying Documents - Painting Certificate / Warranty | [13 empty] | Acceptance Criteria - 100% Visual Scanning 25% Visual Examination 10%UT for FSBW
[9 empty] | 4a - Check for bench marks | [13 empty] | Record - Independent Welding Inspection Report
[9 empty] | XXX In Charge - Tech | [13 empty] | Inspected By - Fabrication Manager
Acceptance Criteria - Permanant bench mark for reference to be available.
Verifying Documents - Inspection, Checklist
4b - Check on foundations
XXX In Charge - Tech
Acceptance Criteria - Foundations are to be cast as per approved drawings and in correct orientations
Verifying Documents - Inspection, Checklist
4c - Check on levels and distances of foundations
XXX In Charge - Tech
Acceptance Criteria - Top level of the foundation wrt bench marks and centre to centre distance and diagonal distance are as per approved details.
Verifying Documents - Inspection, Checklist
5a - Check on columns erection
XXX In Charge - Tech
Acceptance Criteria - Interchanging and turning of columns by 180 degrees to be avoided.
Verifying Documents - Inspection, Checklist
5b - Check on alignment of columns
XXX In Charge - Tech
Acceptance Criteria - Columns are to be properly oriented and centre line of base plate to be coincide with foundation pedestal axis. Foundation bolts to be properly tightened with lock nut
Verifying Documents - Inspection, Checklist
5c - Check for erection of horizontal beams, girders and vertical bracings
XXX In Charge - Tech
Acceptance Criteria - First piece of all columns are to be erected and aligned first. Pieces which affects the movement of crane or other equipment to be erected only at appropriate time.
Verifying Documents - Inspection, Checklist
5d - Check on bolting
XXX In Charge - Tech
Acceptance Criteria - Bolts to be of proper size and to be tightened properly as per bolt tightening procedure.
Verifying Documents - Inspection, Checklist
5e - Check on erection of interconnecting members
XXX In Charge - Tech
Acceptance Criteria - All remaining members to be erected as per the drawing and details providing facility to movement of crane and other equipment.
Verifying Documents - Inspection, Checklist
5f - Check on welders
XXX In Charge - Tech
Acceptance Criteria - All welders to be have qualified welder Certificate or to be approved by performing test at site.
Verifying Documents - Inspection, Checklist
5g - Check on welding materials
XXX In Charge - Tech
Acceptance Criteria - All welding consumables to be available as per the approved details
Verifying Documents - Inspection, Checklist
5h - Check for pre heating
XXX In Charge - Tech
Acceptance Criteria - All joints to be pre heated by approved method by maintaining uniform temperature
Verifying Documents - Inspection, Checklist
5i - Check for fit up of joints
XXX In Charge - Tech
Acceptance Criteria - Minimum gap to be maintained for fillet welding.
Verifying Documents - Inspection, Checklist
5j - Check for assembly of welding parts
XXX In Charge - Tech
Acceptance Criteria - All parts to be welded shall be arranged so as to fit properly on assembly.
Verifying Documents - Inspection, Checklist
5k - Check for post weld heat treatment
XXX In Charge - Tech
Acceptance Criteria - To be done as applicable using appropriate heating method by maintaining uniform temperature.
Verifying Documents - Inspection, Checklist
6a - Check on columns and other members
XXX In Charge - PM
Acceptance Criteria - Total erected columns to be vertical within the tolerance as per spec All other members to be vertical or horizontal as the case may be within tolerance as per spec/standard
Verifying Documents - Inspection, Checklist
6b - Check on weld surface CHAR(AMP) Size
XXX In Charge - PM
Acceptance Criteria - All welds to be cleaned, overlap / excess weld metal to be removed by grinding. Weld size not to be less than specified.
Verifying Documents - Inspection, Checklist
6c - Check on welding
XXX In Charge - PM
Acceptance Criteria - All welding to be free from surface cracks, blow holes, infused welds, improper welding profile and misalignment of welded parts etc:
Verifying Documents - Inspection, Checklist
6d - Testing of welds
XXX In Charge - PM
Acceptance Criteria - Tests to be done for required no.: of welds as per specification
Verifying Documents - Inspection, Checklist
6e - Check for repair of faulty welds
XXX In Charge - PM
Acceptance Criteria - Defective weld to be removed up to the sound metal and parent metal is free from damage.
Verifying Documents - Inspection, Checklist
6f - Check for re weld and retest
XXX In Charge - PM
Acceptance Criteria - To be done by using the same procedure and methods.
Verifying Documents - Inspection, Checklist
6g - Check on tolerances
XXX In Charge - PM
Acceptance Criteria - All tolerance to be within the limit specified
Verifying Documents - Inspection, Checklist
6h - Check on grouting
XXX In Charge - PM
Acceptance Criteria - After all erections are approved. Grouting to be done as per the approved method after cleaning and clearing of all dust, mud, water, oil and other unwanted material by using approved material.
Verifying Documents - Inspection, Checklist
6i - Check on painting
XXX In Charge - PM
Acceptance Criteria - Painting to be carried out as per specifications
Verifying Documents - Inspection, Checklist
7a - Site diaries
XXX In Charge - PM
Acceptance Criteria - All site diaries compiled in QA folder
Verifying Documents - Inspection, Checklist
7b - Internal Inspection reports
XXX In Charge - PM
Acceptance Criteria - All internal reports including fabrication, surface treatment, and erection compiled in QA folder
Verifying Documents - Inspection, Checklist
7c - Independent Inspection reports
XXX In Charge - PM
Acceptance Criteria - All Independent Weld Certificates compiled in QA folder
Verifying Documents - Inspection, Checklist
7d - Mill Certs
XXX In Charge - PM
Acceptance Criteria - All Mill Certs compiled in QA folder
Verifying Documents - Inspection, Checklist
7e - As Built Drawings
XXX In Charge - PM
Acceptance Criteria - Shop Drawings confirmed as acceptable and supplied to relevant parties
Verifying Documents - Inspection, Checklist
7f - Producer Statements
XXX In Charge - PM
Acceptance Criteria - Producer Statements completed and in QA folder
Verifying Documents - Inspection, Checklist
7g - Client acceptance
XXX In Charge - PM
Acceptance Criteria - Correspondence of acceptance compiled in QA folder
Verifying Documents - Inspection, Checklist