## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Structural Steel Work | itp |  |  |  |  | ITP - Structural Steel Work - Rev 1A
section | 1 - SHOP DRAWINGS
checkpoint | 1a - Issued for Construction drawings received
label | XXX In Charge - QS
label | Acceptance Criteria - IFC drawings received and reviewed against Tender Documents
label | Verifying Documents - IFC Drawings
checkpoint | 1b - Shop drawings issued for Approval
label | XXX In Charge - PM
label | Acceptance Criteria - In accordance to contract specs, design requirements, drawings
label | Verifying Documents - Issued for Approval Drawings
checkpoint | 1c - Shop drawings issued for Fabrication
label | XXX In Charge - PM
label | Acceptance Criteria - Should be complying with BOQ and tender conditions
label | Verifying Documents - Issued for Construction Drawings
section | 2 - INCOMING MATERIALS
checkpoint | 2a - Steel profiles
label | XXX In Charge - Fab
label | Acceptance Criteria -
label | Verifying Documents - Manufactures test certificates, 3rd party test reports
checkpoint | 2b - Plate
label | XXX In Charge - Fab
label | Acceptance Criteria - Ordered as per BOQ, as per tender specifications and supplied mill certificates
label | Verifying Documents - Manufactures test certificates, 3rd party test reports
checkpoint | 2c - Purlins
label | XXX In Charge - Fab
label | Acceptance Criteria - Ordered as per BOQ, as per tender specifications and supplied mill certificates
label | Verifying Documents - Manufactures test certificates, 3rd party test reports
checkpoint | 2d - Bolts & Fastenings
label | XXX In Charge - Tech / PM
label | Acceptance Criteria - Ordered as per bolt list, as per tender specifications and supplied mill certificates
label | Verifying Documents - Manufactures test certificates, 3rd party test reports
checkpoint | 2e - Consumables
label | XXX In Charge - Fab / Tech / PM
label | Acceptance Criteria - As per tender specifications and supplied mill certificates
label | Verifying Documents - Manufactures test certificates, 3rd party test reports
section | 3 - FABRICATION
checkpoint | 3a - Fabricate to supplied approved drawings
label | XXX In Charge - Fab
label | Acceptance Criteria - All pre-fabricated materials to be as per spec:, approved drawings and details and free from damages and rust.
label | Verifying Documents - Inspection, Checklist Individual QA Sheet
checkpoint | 3b - Inspection complete
label | XXX In Charge - Fab
label | Acceptance Criteria - Welding inspected in line with required procedures and standards
label | Verifying Documents - Inspection, Checklist Individual QA Sheet
checkpoint | 3c - Galvanising
label | XXX In Charge - Fab
label | Acceptance Criteria - Galvanising complete as per required specification
label | Verifying Documents - Galvanising Certificate Warranty
checkpoint | 3d - Painting / Priming
label | XXX In Charge - Fab
label | Acceptance Criteria - Galvanising complete as per required specification
label | Verifying Documents - Painting Certificate / Warranty
section | 4 - PRE-ERECTION
checkpoint | 4a - Check for bench marks
label | XXX In Charge - Tech
label | Acceptance Criteria - Permanant bench mark for reference to be available.
label | Verifying Documents - Inspection, Checklist
checkpoint | 4b - Check on foundations
label | XXX In Charge - Tech
label | Acceptance Criteria - Foundations are to be cast as per approved drawings and in correct orientations
label | Verifying Documents - Inspection, Checklist
checkpoint | 4c - Check on levels and distances of foundations
label | XXX In Charge - Tech
label | Acceptance Criteria - Top level of the foundation wrt bench marks and centre to centre distance and diagonal distance are as per approved details.
label | Verifying Documents - Inspection, Checklist
section | 5 - ERECTION IN PROGRESS
checkpoint | 5a - Check on columns erection
label | XXX In Charge - Tech
label | Acceptance Criteria - Interchanging and turning of columns by 180 degrees to be avoided.
label | Verifying Documents - Inspection, Checklist
checkpoint | 5b - Check on alignment of columns
label | XXX In Charge - Tech
label | Acceptance Criteria - Columns are to be properly oriented and centre line of base plate to be coincide with foundation pedestal axis.
label | ○ Foundation bolts to be properly tightened with lock nut
label | Verifying Documents - Inspection, Checklist
checkpoint | 5c - Check for erection of horizontal beams, girders and vertical bracings
label | XXX In Charge - Tech
label | Acceptance Criteria - First piece of all columns are to be erected and aligned first. Pieces which affects the movement of crane or other equipment to be erected only at appropriate time.
label | Verifying Documents - Inspection, Checklist
checkpoint | 5d - Check on bolting
label | XXX In Charge - Tech
label | Acceptance Criteria - Bolts to be of proper size and to be tightened properly as per bolt tightening procedure.
label | Verifying Documents - Inspection, Checklist
checkpoint | 5e - Check on erection of interconnecting members
label | XXX In Charge - Tech
label | Acceptance Criteria - All remaining members to be erected as per the drawing and details providing facility to movement of crane and other equipment.
label | Verifying Documents - Inspection, Checklist
checkpoint | 5f - Check on welders
label | XXX In Charge - Tech
label | Acceptance Criteria - All welders to be have qualified welder Certificate or to be approved by performing test at site.
label | Verifying Documents - Inspection, Checklist
checkpoint | 5g - Check on welding materials
label | XXX In Charge - Tech
label | Acceptance Criteria - All welding consumables to be available as per the approved details
label | Verifying Documents - Inspection, Checklist
checkpoint | 5h - Check for pre heating
label | XXX In Charge - Tech
label | Acceptance Criteria - All joints to be pre heated by approved method by maintaining uniform temperature
label | Verifying Documents - Inspection, Checklist
checkpoint | 5i - Check for fit up of joints
label | XXX In Charge - Tech
label | Acceptance Criteria - Minimum gap to be maintained for fillet welding.
label | Verifying Documents - Inspection, Checklist
checkpoint | 5j - Check for assembly of welding parts
label | XXX In Charge - Tech
label | Acceptance Criteria - All parts to be welded shall be arranged so as to fit properly on assembly.
label | Verifying Documents - Inspection, Checklist
checkpoint | 5k - Check for post weld heat treatment
label | XXX In Charge - Tech
label | Acceptance Criteria - To be done as applicable using appropriate heating method by maintaining uniform temperature.
label | Verifying Documents - Inspection, Checklist
section | 6 - POST ERECTION
checkpoint | 6a - Check on columns and other members
label | XXX In Charge - PM
label | Acceptance Criteria - Total erected columns to be vertical within the tolerance as per spec
label | ○ All other members to be vertical or horizontal as the case may be within tolerance as per spec/standard
label | Verifying Documents - Inspection, Checklist
checkpoint | 6b - Check on weld surface & Size
label | XXX In Charge - PM
label | Acceptance Criteria - All welds to be cleaned, overlap / excess weld metal to be removed by grinding.
label | ○ Weld size not to be less than specified.
label | Verifying Documents - Inspection, Checklist
checkpoint | 6c - Check on welding
label | XXX In Charge - PM
label | Acceptance Criteria - All welding to be free from surface cracks, blow holes, infused welds, improper welding profile and misalignment of welded parts etc:
label | Verifying Documents - Inspection, Checklist
checkpoint | 6d - Testing of welds
label | XXX In Charge - PM
label | Acceptance Criteria - Tests to be done for required no.: of welds as per specification
label | Verifying Documents - Inspection, Checklist
checkpoint | 6e - Check for repair of faulty welds
label | XXX In Charge - PM
label | Acceptance Criteria - Defective weld to be removed up to the sound metal and parent metal is free from damage.
label | Verifying Documents - Inspection, Checklist
checkpoint | 6f - Check for re weld and retest
label | XXX In Charge - PM
label | Acceptance Criteria - To be done by using the same procedure and methods.
label | Verifying Documents - Inspection, Checklist
checkpoint | 6g - Check on tolerances
label | XXX In Charge - PM
label | Acceptance Criteria - All tolerance to be within the limit specified
label | Verifying Documents - Inspection, Checklist
checkpoint | 6h - Check on grouting
label | XXX In Charge - PM
label | Acceptance Criteria - After all erections are approved.
label | ○ Grouting to be done as per the approved method after cleaning and clearing of all dust, mud, water, oil and other unwanted material by using approved material.
label | Verifying Documents - Inspection, Checklist
checkpoint | 6i - Check on painting
label | XXX In Charge - PM
label | Acceptance Criteria - Painting to be carried out as per specifications
label | Verifying Documents - Inspection, Checklist
section | 7 - CLOSEOUT
checkpoint | 7a - Site diaries
label | XXX In Charge - PM
label | Acceptance Criteria - All site diaries compiled in QA folder
label | Verifying Documents - Inspection, Checklist
checkpoint | 7b - Internal Inspection reports
label | XXX In Charge - PM
label | Acceptance Criteria - All internal reports including fabrication, surface treatment, and erection compiled in QA folder
label | Verifying Documents - Inspection, Checklist
checkpoint | 7c - Independent Inspection reports
label | XXX In Charge - PM
label | Acceptance Criteria - All Independent Weld Certificates compiled in QA folder
label | Verifying Documents - Inspection, Checklist
checkpoint | 7d - Mill Certs
label | XXX In Charge - PM
label | Acceptance Criteria - All Mill Certs compiled in QA folder
label | Verifying Documents - Inspection, Checklist
checkpoint | 7e - As Built Drawings
label | XXX In Charge - PM
label | Acceptance Criteria - Shop Drawings confirmed as acceptable and supplied to relevant parties
label | Verifying Documents - Inspection, Checklist
checkpoint | 7f - Producer Statements
label | XXX In Charge - PM
label | Acceptance Criteria - Producer Statements completed and in QA folder
label | Verifying Documents - Inspection, Checklist
checkpoint | 7g - Client acceptance
label | XXX In Charge - PM
label | Acceptance Criteria - Correspondence of acceptance compiled in QA folder
label | Verifying Documents - Inspection, Checklist
checklist | Inspection Checklist - Structural Steel Work-Erection | [5 empty] | Inspection Checklist - Structural Steel Work-Erection
section | 3 - FABRICATION
checkpoint | 3a - Inspection complete
section | 4 - PRE-ERECTION
checkpoint | 4a - Check for bench marks
checkpoint | 4b - Check on foundations
checkpoint | 4c - Check on levels and distances of foundations
section | 5 - ERECTION IN PROGRESS
checkpoint | 5a - Check on columns erection
checkpoint | 5b - Check on alignment of columns
checkpoint | 5c - Check for erection of horizontal beams, girders and vertical bracings
checkpoint | 5d - Check on bolting
checkpoint | 5e - Check on erection of interconnecting members
checkpoint | 5f - Check on welders
checkpoint | 5g - Check on welding materials
checkpoint | 5h - Check for pre heating
checkpoint | 5i - Check for fit up of joints
checkpoint | 5j - Check for assembly of welding parts
checkpoint | 5k - Check for post weld heat treatment
section | 6 - POST ERECTION
checkpoint | 6a - Check on columns and other members
checkpoint | 6b - Check on weld surface & Size
checkpoint | 6c - Check on welding
checkpoint | 6d - Testing of welds
checkpoint | 6e - Check for repair of faulty welds
checkpoint | 6f - Check for re weld and retest
checkpoint | 6g - Check on tolerances
checkpoint | 6h - Check on grouting
checkpoint | 6i - Check on painting
section | 7 - CLOSEOUT
checkpoint | 7a - Site Diaries
checkpoint | 7b - Internal Inspection reports
checkpoint | 7c - Independent Inspection reports
checkpoint | 7d - Mill Certs
checkpoint | 7e - As Built Drawings
checkpoint | 7f - Producer Statements
checkpoint | 7g - Client Acceptance
button | CONCLUSION | Accepted,Accepted with Comments,Rejected
holdpoint | Sign (Contractor/Consultant/Client)
checklist | ITP - Woolworths Pukekohe | itp |  |  |  |  | ITP - Woolworths Pukekohe
section | Shop Drawings
checkpoint | All Phases
label | Specification - Shop drawings issued in accordance with contract specification, design requirements and IFC drawings
label | Acceptance Criteria - Internal review against project specs. External review by Engineer / Architect
label | Record - Approval of each phase
label | Inspected By - Engineer / Architect
section | Materials
checkpoint | Steel Profiles
label | Specification - Various grades
label | Acceptance Criteria - Ordered as per BOQ, as per IFC specifications and supplied mill certificates
label | Record - Mill Certs
label | Inspected By - Fabrication Manager
checkpoint | Purlins
label | Specification - Z275 Purlins, Z450 Fast Bracing
label | Acceptance Criteria - Ordered as per BOQ, as per IFC specifications and supplied mill certificates
label | Record - Mill Certs
label | Inspected By - Fabrication Manager
checkpoint | Bolts
label | Specification - Various
label | Acceptance Criteria - Ordered as per BOQ, as per IFC specifications and supplied mill certificates
label | Record - Bolt / Mill Certs
label | Inspected By - Fabrication Manager
section | Coatings
checkpoint | Internal Store Fitout
label | Specification - IZS2
label | Acceptance Criteria - DFT Inspection Report and Supplier Certificate
label | Record - Certificates from suppliers
label | Inspected By - Project Manager
checkpoint | Internal Seismic
label | Specification - IZS2
label | Acceptance Criteria - DFT Inspection Report and Supplier Certificate
label | Record - Certificates from suppliers
label | Inspected By - Project Manager
checkpoint | Large Canopy
label | Specification - HDG600, PUR2
label | Acceptance Criteria - DFT Inspection Report and Supplier Certificate
label | Record - Certificates from suppliers
label | Inspected By - Project Manager
checkpoint | Small Canopy
label | Specification - HDG600, SHS topcoat only.
label | Acceptance Criteria - DFT Inspection Report and Supplier Certificate
label | Record - Certificates from suppliers
label | Inspected By - Project Manager
checkpoint | Plant Platform
label | Specification - HDG600
label | Acceptance Criteria - DFT Inspection Report and Supplier Certificate
label | Record - Certificates from suppliers
label | Inspected By - Project Manager
section | Welding Standard
checkpoint | Shop welding
label | Specification - CC2. NZS 3404 – Appendix D
label | Acceptance Criteria - 100% Visual Scanning
label | ○ 25% Visual Examination
label | ○ 10%UT for FSBW
label | Record - Independent Welding Inspection Report
label | Inspected By - Fabrication Manager
checkpoint | Site Welding
label | Specification - CC2. NZS 3404 – Appendix D
label | Acceptance Criteria - 100% Visual Scanning
label | ○ 25% Visual Examination
label | ○ 10%UT for FSBW
label | Record - Independent Welding Inspection Report
label | Inspected By - Technical Manager
section | Consumables
checkpoint | Various
label | Specification - CC2
label | Acceptance Criteria - As per IFC specifications
label | Record - Mill / Supplier Certifications
label | Inspected By - Project Manager
section | Closeout
checkpoint | Site Diaries
label | Record - Site Diaries saved in project folder
label | Inspected By - Project Manager
checkpoint | Internal Inspection Reports
label | Record - All internal reports including fabrication, surface treatment, and erection saved to project folder
label | Inspected By - Project Manager
checkpoint | Independent Inspection Reports
label | Record - All reports saved to project folder
label | Inspected By - Project Manager
checkpoint | Mill Certificates
label | Record - All mill certs saved to project folder
label | Inspected By - Project Manager
checkpoint | AS Built Drawings
label | Record - Shop Drawings confirmed as acceptable and supplied to Contractor
label | Inspected By - Project Manager
checkpoint | Producer Statements
label | Record - PS3 completed and issued to Contractor
label | Inspected By - Project Manager
checkpoint | Supplier Warranties
label | Record - Warranties completed and issued to Contractor
label | Inspected By - Project Manager
section | Client Acceptance
checkpoint | Client Acceptance
label | Record - Communication of acceptance received
label | Inspected By - Project Manager