## Structure
Id | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Checklist Template

## Checklists
Id | Project | Location | Checklist Name | Status | Checklist Template | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6

## Checkpoints
Checklist Id | Project | Location | Checklist Name | Section Name | Checkpoint Name | Checkpoint Status | Signoff Status | Checklist Template | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Usage Count | Resource Id
8394e415-15e3-4b05-9bbc-55440890702f/1 | checklist | 202579S02 Rev1 - Stormwater Pond CQA Plan Checklist | itp | 202579S02 Rev1 - Stormwater Pond CQA Plan Checklist | 0 | e7361695-33fd-4582-9eb9-389bb897e625
a571aabe-8219-48c6-89c3-eb2c6739d3d1 | section | 1.1 - Site Preparation and Earthworks Inspection and Test Plan Checklist
4fc637b6-6817-453c-aa31-f8b7b661c29f | checkpoint | SE1 - Contractor to provide WHS Plan and SEDMP
c608bf17-eea2-5eac-9a9d-3b6022b08402 | note | Specification Clause - 1.6, 1.9.2.2
f3e50ab5-e757-5fcc-9f2a-17acd76ea5ca | note | Frequency - Once
2dbec0d6-720d-51e0-9f68-8a4c0fb7a050 | note | Timing - At least 10 days prior to commencing the works
b0f50fbd-05be-5ca2-91b7-521ff16afa42 | note | Acceptance Criteria - Meeting specification requirements
931c8671-86b8-56d2-a754-9ee76f140551 | note | Reporting Form - Documents:
c973bd68-9bd2-545e-8159-f21563f6d831 | note | ○ WHS Plan
ffde35bf-6679-539c-abfe-6abd384d6b2c | note | ○ SEDMP
73b7d252-3946-480a-b4f3-fbfd3160a8d8 | checkpoint | SE2 - Superintendent to review WHS Plan and SEDMP (HOLD POINT H-SE1)
25473bec-e562-5954-b761-76eee49e22d9 | note | Specification Clause - 2.4.4
56ee407f-01c6-59b6-8bb6-f7ca0cd14285 | note | Frequency - Once
0ff0c21e-48aa-5358-b7a5-976c151b748e | note | Timing - Prior to commencing works
f3810cb8-96db-54db-8dc2-edba84d8a992 | note | Acceptance Criteria - Superintendent’s acceptance
6760d5e5-9ac6-55cf-9db6-421a583b0558 | note | Reporting Form - Written confirmation of acceptance
e17a70a0-2734-4a1b-89d8-3752c3f9e55a | signoff | HOLD POINT H-SE1
9e0cd569-0ef1-4a8c-894a-37d855f5a29a | checkpoint | SE3 - GTA’s approval of Subgrade Fill materials proposed to be used in the works (HOLD POINT H-SE2)
59a16363-27ea-5a5d-bf92-bd9f3d8cd445 | note | Specification Clause - 2.2.2, 2.4.4
a2d3faaa-5b32-5f69-9d9c-c946baa1b735 | note | Frequency - As required
57da84c7-d6d4-5889-88e1-62beb8c629a3 | note | Timing - Prior to placement
134781fd-8cac-527c-b2d7-f0738472ca50 | note | Acceptance Criteria - Meeting GTA’s approval
91efab23-c1bf-5fc2-9548-eae3377fd17b | note | Reporting Form - Document, Written Approval
f5ed71d3-dbd0-4847-b6a4-f339a617b93a | checkpoint | SE4 - Environmental Consultant to approve of imported subgrade fill materials (if applicable)
546a9661-137b-5e8a-845f-bb12adda149b | note | Specification Clause - 2.2.3
509d3bfe-1188-5a70-80a5-334bf46e1332 | note | Frequency - As required
49c629b2-ab0b-56c4-9f72-907acf04b4a4 | note | Timing - Prior to subgrade filling works
5b4f818e-a06c-5ced-b8c2-f222b132f5c5 | note | Acceptance Criteria - Meeting Environmental Consultants approval
88ab29c6-1c80-5027-94a6-fe0e5ad920a6 | note | Reporting Form - Document, Written Approval
2596df4a-adaf-47a3-9421-a948b2aaffb4 | checkpoint | SE5 - Proof rolling of existing subgrade surface areas (HOLD POINT H-SE3)
4c31d6c9-51bd-54f3-b3da-c9482a8c37cd | note | Specification Clause - 2.4.3, 2.4.4
806826a3-08a5-5c43-ad4a-351d8ded6117 | note | Frequency - As required
702f0831-edc5-5773-b2e0-aa6143a45cc3 | note | Timing - Prior to commencement of filling
9ee8cfbf-8e49-5fd6-a6a7-b4b7640f155f | note | Acceptance Criteria - Meeting GTA’s approval
d43d4db9-21a5-54ea-aa9e-3abfe1cc08ca | note | Reporting Form - Written confirmation of acceptance
43a68c38-901f-4079-a872-22a1f38157ae | signoff | HOLD POINT H-SE3
5aff3467-c26c-4bd0-ac99-6900df30facf | checkpoint | SE6 - All subgrade testing shall be performed at a rate determined by the GTA in accordance with the Specification.
aa79200a-13b4-50d5-a436-441061d35dad | note | Specification Clause - 2.4.3
fc2b8a65-afa0-5fc5-8c62-474c7248ef6e | note | Frequency - Testing as required
68f06360-1b0a-5b27-8446-c9c2950075f3 | note | Timing - Throughout the works
c5a1f1c8-9479-5a55-ba96-9c34f5f56b19 | note | Acceptance Criteria - Meeting GTA’s approval
863b6bb0-6cb1-59a4-a1da-576d16edc8f8 | note | Reporting Form - GTA test and inspection documentation
9ff08b59-35ed-42e1-bb79-498a15ee22cd | checkpoint | SE7 - Survey of subgrade levels
b9b1d49b-ef0b-5f13-87f4-930c89896646 | note | Specification Clause - 2.4.5
ae5f0dae-32e7-55f3-a063-39737dc3cb48 | note | Frequency - After placement and compaction
85cfda3a-db7d-589b-8435-4caeee3fe25e | note | Timing - Meeting specification requirements
de4719f2-045d-5282-8967-a74fa65f269e | note | Acceptance Criteria - Meeting specification requirements
0e4449f1-9745-5fa6-8014-b2ccaffc73f5 | note | Reporting Form - As constructed documentation
b929c2d1-4a0c-4b34-8a46-353ebef4ed2a | checkpoint | SE8 - CQA Engineer to review and approve as constructed information (HOLD POINT H-SE4)
de81cfea-8dd5-5f4c-a4cf-f658b1b11ac8 | note | Specification Clause - 2.4.4
b64ded37-92df-5d69-9df8-b1723c1015d1 | note | Frequency - Once
83be8831-19d9-501b-8edb-a1a134c8dcc0 | note | Timing - Prior to placement of subsequent layers
fa921904-32e9-5b87-b03a-8a3c7c0a2ec6 | note | Acceptance Criteria - CQA Engineer’s acceptance
7ec360d3-c3bc-5edd-b172-93f4fa54f271 | note | Reporting Form - Written confirmation of acceptance
df64b4b9-87ed-4df2-8a45-80f3000a44f9 | signoff | HOLD POINT H-SE4