## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 202579S02 Rev1 - Stormwater Pond CQA Plan Checklist | itp |  |  |  |  | 202579S02 Rev1 - Stormwater Pond CQA Plan Checklist
section | 1.1 - Site Preparation and Earthworks Inspection and Test Plan Checklist
checkpoint | SE1 - Contractor to provide WHS Plan and SEDMP
label | Specification Clause - 1.6, 1.9.2.2
label | Frequency - Once
label | Timing - At least 10 days prior to commencing the works
label | Acceptance Criteria - Meeting specification requirements
label | Reporting Form - Documents:
label | ○ WHS Plan
label | ○ SEDMP
checkpoint | SE2 - Superintendent to review WHS Plan and SEDMP (HOLD POINT H-SE1)
label | Specification Clause - 2.4.4
label | Frequency - Once
label | Timing - Prior to commencing works
label | Acceptance Criteria - Superintendent’s acceptance
label | Reporting Form - Written confirmation of acceptance
holdpoint | HOLD POINT H-SE1
checkpoint | SE3 - GTA’s approval of Subgrade Fill materials proposed to be used in the works (HOLD POINT H-SE2)
label | Specification Clause - 2.2.2, 2.4.4
label | Frequency - As required
label | Timing - Prior to placement
label | Acceptance Criteria - Meeting GTA’s approval
label | Reporting Form - Document, Written Approval
checkpoint | SE4 - Environmental Consultant to approve of imported subgrade fill materials (if applicable)
label | Specification Clause - 2.2.3
label | Frequency - As required
label | Timing - Prior to subgrade filling works
label | Acceptance Criteria - Meeting Environmental Consultants approval
label | Reporting Form - Document, Written Approval
checkpoint | SE5 - Proof rolling of existing subgrade surface areas (HOLD POINT H-SE3)
label | Specification Clause - 2.4.3, 2.4.4
label | Frequency - As required
label | Timing - Prior to commencement of filling
label | Acceptance Criteria - Meeting GTA’s approval
label | Reporting Form - Written confirmation of acceptance
holdpoint | HOLD POINT H-SE3
checkpoint | SE6 - All subgrade testing shall be performed at a rate determined by the GTA in accordance with the Specification.
label | Specification Clause - 2.4.3
label | Frequency - Testing as required
label | Timing - Throughout the works
label | Acceptance Criteria - Meeting GTA’s approval
label | Reporting Form - GTA test and inspection documentation
checkpoint | SE7 - Survey of subgrade levels
label | Specification Clause - 2.4.5
label | Frequency - After placement and compaction
label | Timing - Meeting specification requirements
label | Acceptance Criteria - Meeting specification requirements
label | Reporting Form - As constructed documentation
checkpoint | SE8 - CQA Engineer to review and approve as constructed information (HOLD POINT H-SE4)
label | Specification Clause - 2.4.4
label | Frequency - Once
label | Timing - Prior to placement of subsequent layers
label | Acceptance Criteria - CQA Engineer’s acceptance
label | Reporting Form - Written confirmation of acceptance
holdpoint | HOLD POINT H-SE4