## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: Solar Farm J#43687 - Large Room
| step |  |  | Tier 2: Toolbox Meetings
Toolbox Meeting | checklist |  |  | Tier 3: Daily Toolbox meetings - Site Installation
| step |  |  | Tier 2: Room Construction
Sign Off | checklist |  |  | Tier 3: Room Construction Checklist
Sign Off | checklist |  |  | Tier 3: QA Documentation
| step |  |  | Tier 2: Frame Construction
Sign Off | checklist |  |  | Tier 3: Frame Construction Checklist
Sign Off | checklist |  |  | Tier 3: Coastal Services QA Documentation
| step |  |  | Tier 2: Floor, Duct Penetrations
| step |  |  | Tier 3: Flooring, Penetrations Checklist
| step |  |  | Tier 4: Floor Cable Penetrations
| step |  |  | Tier 4: Floor Covering
| step |  |  | Tier 2: Cable Supports
| step |  |  | Tier 3: Cable Support Checklists
ITR-E-02B Cable Supports Above Ground | checklist |  |  | Tier 4: Cable Ladder
ITR-E-02B Cable Supports Above Ground | checklist |  |  | Tier 4: Uni Tray
| step |  |  | Tier 2: LV Lighting, Power, DATA & Accessories
| step |  |  | Tier 3: MV Room
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Internal 5ft Emergency Light 01
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Internal 5ft LED Light 02
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: 2 Way Light Switch 01
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: 2 Way Light Switch 02
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Exterior Flood Light 03
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Emergency Exit Light 04
| step |  |  | Tier 3: Control Room
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Internal 5ft LED Light 05
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Internal 5ft LED Light 06
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Internal 5ft LED Light 07
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Internal 5ft Emergency Light 08
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: 2 Way Light Switch 03
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: 2 Way Light Switch 04
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Emergency Exit Light 09
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: Double Socket Outlet GPO01
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: Daylight Sensor 01
| step |  |  | Tier 3: Office
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Internal 5ft LED Light 10
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Internal 5ft Emergency Light 11
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: 2 Way Light Switch 05
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: 2 Way Light Switch 06
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: Double Socket Outlet GPO02
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: Double Socket Outlet GPO03
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: Double Socket Outlet GPO04
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Emergency Exit Light 12
| step |  |  | Tier 3: Smoko Room
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Internal 5ft LED Light 13
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Internal 5ft Emergency Light 14
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: 2 Way Light Switch 07
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: 2 Way Light Switch 08
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Emergency Exit Light 15
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Exterior Flood Light 16
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: Double Socket Outlet GPO05
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: Double Socket Outlet GPO06
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: Double Socket Outlet GPO07
| step |  |  | Tier 3: Toilet
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Internal LED round light 17
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: 1 Way Light Switch 09
| step |  |  | Tier 2: HVAC
| step |  |  | Tier 3: AC01
ITR-E-55 HVAC System | checklist |  |  | Tier 4: Indoor Unit
ITR-E-55 HVAC System | checklist |  |  | Tier 4: Outdoor Unit
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: AC Controller
| step |  |  | Tier 3: AC02
ITR-E-55 HVAC System | checklist |  |  | Tier 4: Indoor Unit
ITR-E-55 HVAC System | checklist |  |  | Tier 4: Outdoor Unit
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: AC Controller
| step |  |  | Tier 2: Equipment and Installation
| step |  |  | Tier 3: Panels
ITR-E-34A Low Voltage Switch Board | checklist |  |  | Tier 4: TCE LV AC Distribution Board
ITR-E-10 Electrical Equipment Package | checklist |  |  | Tier 4: 33KV RMU Siemens 8DJH
ITR-E-06 Control Panel | checklist |  |  | Tier 4: SCADA / Comms panel
ITR-E-15 UPS Installation | checklist |  |  | Tier 4: No1 UPS Cabinet
ITR-E-15 UPS Installation | checklist |  |  | Tier 4: No2 UPS Cabinet
ITR-E-06 Control Panel | checklist |  |  | Tier 4: Fire Panel
ITR-E-06 Control Panel | checklist |  |  | Tier 4: Revenue Metering Panel
ITR-E-06 Control Panel | checklist |  |  | Tier 4: Meteo Control Panel
| step |  |  | Tier 3: Pressurization Unit
ITR-E-10 Electrical Equipment Package | checklist |  |  | Tier 4: Pressurization Unit
| step |  |  | Tier 3: Earth Bar
ITR-E-40A Bus Bar | checklist |  |  | Tier 4: Switchroom Earth bar
| step |  |  | Tier 2: Cable Installation
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: A01; Tier 4: 6.0mm 4C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: A02; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: A03; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: A04; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: U01; Tier 4: 1.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: U02; Tier 4: 1.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: U03; Tier 4: 1.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: D01; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: D02; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: D03; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: D04; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: D05; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: D06; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: D07; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: F01; Tier 4: SM 0S2
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: C01; Tier 4: CAT6
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: C02; Tier 4: CAT6
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: C03; Tier 4: CAT6
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: C04; Tier 4: CAT6
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 3: T01; Tier 4: 2.5mm 12C Firstflex CTP12/2.5
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 3: T02; Tier 4: 2.5mm 12C Firstflex CTP12/2.6
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 3: T03; Tier 4: 2.5mm 12C Firstflex CTP12/2.7
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 3: T04; Tier 4: 2.5mm 12C Firstflex CTP12/2.8
| step |  |  | Tier 2: Building Access
Sign Off | checklist |  |  | Tier 3: Stairs
Sign Off | checklist |  |  | Tier 3: Platform
| step |  |  | Tier 2: COC, ESC
Certificate of compliance (COC) | checklist |  |  | Tier 3: COC
Electrical Safety Ceritificate (ESC) | checklist |  |  | Tier 3: ESC
Test Equipment Details | checklist |  |  | Tier 3: Test Equipment
Sign Off | checklist |  |  | Tier 2: Punchlist Walkdown
Sign Off | checklist |  |  | Tier 2: Punchlist work Complete Acceptance
| step |  |  | Tier 2: Switchroom Complete
ITR-E-09 Electrical Switch Rooms | checklist |  |  | Tier 3: Entec Project Engineer
| step |  |  | Tier 2: As Built Drawings Complete
Sign Off | checklist |  |  | Tier 3: Entec Supervisor
| step |  |  | Tier 2: Workpack Completion Sign Off
Sign Off | checklist |  |  | Tier 3: Entec Project Engineer
Sign Off | checklist |  |  | Tier 3: Chint Client representative
| step |  |  | Tier 1: North Power J#45005 - Small Room
| step |  |  | Tier 2: Toolbox Meetings
Toolbox Meeting | checklist |  |  | Tier 3: Daily Toolbox meetings - Site Installation
| step |  |  | Tier 2: Room Construction
Sign Off | checklist |  |  | Tier 3: Room Construction Checklist
Sign Off | checklist |  |  | Tier 3: QA Documentation
| step |  |  | Tier 2: Frame Construction
Sign Off | checklist |  |  | Tier 3: Frame Construction Checklist
Sign Off | checklist |  |  | Tier 3: Coastal Services QA Documentation
| step |  |  | Tier 2: Floor, Duct Penetrations
| step |  |  | Tier 3: Flooring, Penetrations Checklist
| step |  |  | Tier 4: Floor Cable Penetrations
| step |  |  | Tier 4: Floor Covering
| step |  |  | Tier 2: Cable Supports
| step |  |  | Tier 3: Cable Support Checklists
ITR-E-02B Cable Supports Above Ground | checklist |  |  | Tier 4: Cable Ladder
ITR-E-02B Cable Supports Above Ground | checklist |  |  | Tier 4: Uni Tray
| step |  |  | Tier 2: LV Lighting, Power, DATA & Accessories
| step |  |  | Tier 3: Lighting Checklist
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Internal 5ft Emergency Light 01
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Internal 5ft LED Light 02
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: 2 Way Light Switch 01
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: 2 Way Light Switch 02
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Emergency Exit Light 03
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Emergency Exit Light 04
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Exterior Flood Light 05
ITR-E-64 General Lighting | checklist |  |  | Tier 4: Exterior Flood Light 06
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: Daylight Sensor 01
| step |  |  | Tier 3: Power Checklist
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: Double Socket Outlet GPO01
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: Double Socket Outlet GPO02
| step |  |  | Tier 2: Fire and Security
| step |  |  | Tier 3: Fire System
ITR-I-01 Fire and Gas Detection Alarms | checklist |  |  | Tier 4: Manual Call Point 01
ITR-I-01 Fire and Gas Detection Alarms | checklist |  |  | Tier 4: Manual Call Point 02
ITR-I-01 Fire and Gas Detection Alarms | checklist |  |  | Tier 4: Exterior Becon Sounder 01
ITR-I-01 Fire and Gas Detection Alarms | checklist |  |  | Tier 4: Exterior Becon Sounder 02
ITR-I-01 Fire and Gas Detection Alarms | checklist |  |  | Tier 4: Smoke Heat detector 01
ITR-I-01 Fire and Gas Detection Alarms | checklist |  |  | Tier 4: Smoke Heat detector 02
| step |  |  | Tier 3: Security System
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: PIR Sensor 01
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: PIR Sensor 02
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: Electronic door lock 01
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: Electronic door lock 02
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: Swipe Card Reader 01
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: Swipe Card Reader 02
| step |  |  | Tier 2: Equipment and Installation
| step |  |  | Tier 3: Panels
ITR-E-06 Control Panel | checklist |  |  | Tier 4: SCADA / Comms panel
ITR-E-06 Control Panel | checklist |  |  | Tier 4: Cardex Panel
ITR-E-34A Low Voltage Switch Board | checklist |  |  | Tier 4: AC LV DB
ITR-E-06 Control Panel | checklist |  |  | Tier 4: DC Panel
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: 110V DC Battery Rack
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: 24V DC Battery Rack
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: 33KV Protection Panel
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: Generator Connection Box
| step |  |  | Tier 2: HVAC
| step |  |  | Tier 3: AC01
ITR-E-55 HVAC System | checklist |  |  | Tier 4: Indoor Unit
ITR-E-55 HVAC System | checklist |  |  | Tier 4: Outdoor Unit
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 4: AC Controller
| step |  |  | Tier 2: Cable Installation
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: L-001; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: L-002; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: L-003; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: L-004; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: L-005; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: L-006; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: L-007; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: L-008; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: L-009; Tier 4: 1.5mm 3C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-001; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-002; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-003; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-004; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-005; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-006; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-007; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-008; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-009; Tier 4: 2.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-010; Tier 4: 1.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-011; Tier 4: 1.5mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: P-012; Tier 4: 25mm 4C&E PVC/PVC TPS 90C 0.6/1KV
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 3: C-005; Tier 4: 1.5mm 1 PR
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 3: W575; Tier 4: 1.5mm 1 PR
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 3: W576; Tier 4: 1.5mm 1 PR
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: W405; Tier 4: 6mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: W311; Tier 4: 6mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: W380; Tier 4: 16mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 3: W381; Tier 4: 25mm 2C&E PVC/PVC TPS 90C 0.6/1KV
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 3: W391; Tier 4: 0.5mm 1 PR
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 3: W392; Tier 4: 0.5mm 1 PR
| step |  |  | Tier 3: Earth / Bonding Cables
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 4: 25mm 1c GRN/Y Cardex Panel
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 4: 25mm 1c GRN/Y 110VDC Battery Rack
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 4: 25mm 1c GRN/Y 110VDC Battery Rack
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 4: 25mm 1c GRN/Y Rear Entrance Stairs
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 4: 25mm 1c GRN/Y 33KV Protection Panel
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 4: 25mm 1c GRN/Y DC Panel
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 4: 25mm 1c GRN/Y SCADA/COMMS Panel
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 4: 25mm 1c GRN/Y ACDB
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 4: 25mm 1c GRN/Y Cable Ladders
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 4: 25mm 1c GRN/Y Main Entrance Stairs
ITR-E-05 - Low Voltage Cable | checklist |  |  | Tier 4: 25mm 1c GRN/Y Structural Steel
| step |  |  | Tier 2: Building Access
Sign Off | checklist |  |  | Tier 3: Stairs
Sign Off | checklist |  |  | Tier 3: Platform
| step |  |  | Tier 2: COC, ESC
Certificate of compliance (COC) | checklist |  |  | Tier 3: COC
Electrical Safety Ceritificate (ESC) | checklist |  |  | Tier 3: ESC
Test Equipment Details | checklist |  |  | Tier 3: Test Equipment
Sign Off | checklist |  |  | Tier 2: Punchlist Walkdown
Sign Off | checklist |  |  | Tier 2: Punchlist work Complete Acceptance
| step |  |  | Tier 2: Switchroom Complete
ITR-E-09 Electrical Switch Rooms | checklist |  |  | Tier 3: Entec Project Engineer
| step |  |  | Tier 2: As Built Drawings Complete
Sign Off | checklist |  |  | Tier 3: Entec Supervisor
| step |  |  | Tier 2: Workpack Completion Sign Off
Sign Off | checklist |  |  | Tier 3: Entec Project Engineer
Sign Off | checklist |  |  | Tier 3: TOP Energy Client representative