## Repair Checklist
checklist-sectioned | checklist | Defects Repair Checklist |  | Yes | Concrete Slabs Checklist | 9baf8102-41c7-45ba-8a51-d1c81c74b091
checkpoint-group | section | Details of Defects
checkpoint-no-status | checkpoint | Details and Attached Mark-Up Drawings
label | note | Type of Defects:
boolean | tickbox | Cracking
boolean | tickbox | Delamination
boolean | tickbox | Crazing
boolean | tickbox | Blisters
boolean | tickbox | Curling
boolean | tickbox | Discoloration
boolean | tickbox | Dusting
boolean | tickbox | Low Spots
boolean | tickbox | Pop-outs
boolean | tickbox | Scaling
boolean | tickbox | Spalling
checkpoint-no-status | checkpoint | Methodology
boolean | tickbox | Injection
boolean | tickbox | Patching
checkpoint-group | section | Injection Method: Roadware 10-Minute Mender
checkpoint-no-status | checkpoint | Location Details of the Defects (Attached Photo)
select | dropdown | Severity of the defects | Minor, Moderate, Severe
checkpoint-no-status | checkpoint | Surface Preparation
checkpoint-status | checkpoint | Inspect the crack surface for oil, grease, and other contaminants that could affect adhesion.
checkpoint-status | checkpoint | Check for any corrosion or rust on nearby reinforcing steel that could compromise the repair.
checkpoint-status | checkpoint | Ensure that the crack edges are clean, sound, and free from loose material.
checkpoint-status | checkpoint | Verify that the crack has been properly opened (if necessary) to allow proper epoxy penetration.
checkpoint-status | checkpoint | Check for moisture in the crack, as excessive moisture can affect epoxy adhesion.
checkpoint-no-status | checkpoint | Injection Process
checkpoint-status | checkpoint | Inspect the injection equipment to ensure it's in proper working condition.
checkpoint-status | checkpoint | Monitor the epoxy flow rate during injection to ensure consistent and proper filling.
checkpoint-status | checkpoint | Check for any leaks or seepage of epoxy from the crack or nearby areas.
checkpoint-status | checkpoint | Verify that epoxy is penetrating through the entire depth and length of the crack.
checkpoint-status | checkpoint | Inspect for the appearance of epoxy at adjacent surfaces, indicating proper penetration.
checkpoint-no-status | checkpoint | Finishing and Curing
checkpoint-status | checkpoint | Inspect the cured epoxy surface for uniform color and texture.
checkpoint-status | checkpoint | Check for any raised areas, excess epoxy, or irregularities on the surface.
checkpoint-status | checkpoint | Verify that the epoxy has properly adhered to the crack edges and surrounding concrete.
checkpoint-status | checkpoint | Inspect for any discoloration or blemishes on the surrounding concrete caused by epoxy spillage.
checkpoint-group | section | Patching Method: FasTrac
checkpoint-no-status | checkpoint | Location Details of the Defects (Attached Photo)
select | dropdown | Severity of the defects | Minor, Moderate, Severe
checkpoint-no-status | checkpoint | Surface Preparation
checkpoint-status | checkpoint | Inspect the delaminated area for loose concrete, dust, debris, and contaminants.
checkpoint-status | checkpoint | Verify that the area has been thoroughly cleaned using appropriate tools.
checkpoint-status | checkpoint | Confirm that any remaining loose material has been removed from the area.
checkpoint-status | checkpoint | Ensure that the prepared surface is smooth and free from obstructions.
checkpoint-no-status | checkpoint | Patching Application
checkpoint-status | checkpoint | Inspect the mixing process of the patching material according to manufacturer guidelines.
checkpoint-status | checkpoint | Check that the mixed material is consistent in color and texture.
checkpoint-status | checkpoint | Verify that the application of the patching material is even and uniform across the damaged area.
checkpoint-status | checkpoint | Inspect for proper coverage and that the patching material is applied to the required thickness. (Attached Photo)
checkpoint-no-status | checkpoint | Finishing and Curing
checkpoint-status | checkpoint | Verify that the patched area is flush and doesn't create any tripping hazards.
checkpoint-status | checkpoint | Confirm that the edges of the patch blend seamlessly into the adjacent concrete.
checkpoint-status | checkpoint | Verify that the epoxy has properly adhered to the crack edges and surrounding concrete.
checkpoint-status | checkpoint | Confirm that the patch material is curing as intended.
checkpoint-no-status | checkpoint | Safety Data Sheets