## Data Population
Area | Location | Lot Type | Description | Responsible Engineer | Pay Items | Doval Access | Client Access
Woodlands Drive | Chainage From | Concrete Works |  | Daniel Reid | See Pay Items Tab | David Reid
Underwood Road | Chainage To | Installation of Insitu Stormwater Structures |  | Mark Theron |  | Mark Theron
| Offset | Installation of Precast Pits |  |  |  | Daniel Reid
| Control Line | Linemarking |  |  |  | Sam Carrington
Minor Concrete Works (Kerb)
Stormwater Pipe Installation
Unbound Granular Pavements
Landscaping
Reinforcement

## Pay Items - Woodlands
Item | Description | Unit
00 | ESTABLISHMENT
00.05 | Project Specific Management Plans and Approvals
00.05.05 | Provide and implement Traffic Management Plan and Guidance Schemes | item
00.05.10 | Provide and implement Work Health and Safety Management Plan | item
00.05.15 | Provide and implement Environmental Management Plan | item
00.05.20 | Provide and implement Aboriginal Cultural Heritage Plan | item
00.05.25 | Recycling and Sustainability Plan | item
00.05.30 | Provide and implement Public Utility Plant Protection & Safety Plan | item
00.10 | Site Establishment
00.10.05 | Mobilisation and Demobilisation | item
00.10.10 | Dilapidation reports (pre / post construction) | item
00.10.15 | Underground Service Location | item
00.10.20 | Implement Environmental Management Plan | item
00.10.25 | Prepare and Submit As-Constructed Drawings | item
00.15 | Site Monitoring
00.15.05 | Dust Monitoring | item
00.15.10 | Noise Monitoring | item
00.15.15 | Water Quality Monitoring | item
00.15.20 | Vibration Monitoring | item
05 | TRAFFIC MANAGEMENT
05.05 | Traffic Management
05.05.05 | Traffic Management | item
10 | TEMPORARY WORKS
10.05 | Protection
10.05.05 | Protection of Services | item
10.05.10 | Protection of Private Property | item
10.10 | Access
10.10.05 | Temporary Pavements | item
10.10.10 | Temporary Line Marking | item
10.10.15 | Temporary Bus Stops | item
10.10.20 | Temporary Pedestrian Facilities | item
10.10.25 | Temporary Fencing | item
15 | CLEARING, DEMOLITION AND SITE PREPARATION
15.05 | Vegetation
15.05.05 | Arborist and Fauna management report (pre and post clearing report) | item
15.05.10 | Clearing and Grubbing | item
15.05.15 | Removal of Trees | No.
15.10 | Pavement
15.10.05 | Remove Existing Asphalt to Spoil | m2
15.15 | General
15.15.05 | Breakout and dispose existing K&C structures | m
15.15.10 | Breakout and dispose existing gully traps | No.
15.15.15 | Breakout and dispose existing MH | No.
15.15.20 | Blank off stormwater drainlines | No.
15.15.25 | Recover and remove existing RC pipes to stockpile (diameter 300-450mm) | m
15.15.30 | Recover and remove existing RC pipes to stockpile (diameter 525-750mm) | m
15.20 | Other Structures
15.20.05 | Relocation of sheds/structures on/near drainage easement including slab construction | no.
20 | PUBLIC UTILITY PLANT WORKS
20.05 | Water Services
20.05.05 | Water - Coordinate and Oversee Service Authority Works as Principal Contractor | item
20.10 | Sewer Services
20.10.05 | Sewer - Coordinate and Oversee Service Authority Works as Principal Contractor | item
20.15 | Communications
20.15.05 | Communications - Coordinate and Oversee Service Authority Works as Principal Contractor | item
20.20 | Electricity
20.20.05 | Electrical - Coordinate and Oversee Service Authority Works as Principal Contractor | item
25 | DRAINAGE
25.05 | General
25.05.05 | Connect into Existing Stormwater Drains, Pits & Manholes | item
25.05.10 | Supply and Install House Kerb Outlet - Provisional (If Ordered) | item
25.10 | Pipe Culvert
25.10.05 | Supply/excavate/lay/backfill Reinforced Concrete Pipe, 375mm | m
25.10.10 | Supply/excavate/lay/backfill Reinforced Concrete Pipe, 450mm | m
25.10.15 | Supply/excavate/lay/backfill Reinforced Concrete Pipe, 525mm | m
25.10.20 | Supply/excavate/lay/backfill Reinforced Concrete Pipe, 600mm | m
25.10.25 | Supply/excavate/lay/backfill Reinforced Concrete Pipe, 675mm | m
25.10.30 | Supply/excavate/lay/backfill Reinforced Concrete Pipe, 750mm | m
25.10.35 | Supply/excavate/lay/backfill Reinforced Concrete Pipe, 825mm | m
25.10.40 | Supply/excavate/lay/backfill Reinforced Concrete Pipe, 900mm | m
25.10.45 | Supply/excavate/lay/backfill Reinforced Concrete Pipe, 1050mm | m
25.15 | Pits and Manholes
25.15.05 | Supply/excavate/lay/backfill Side Entry Pit Type 1C1T including Chamber | each
25.15.10 | Supply/excavate/lay/backfillSide Entry Pit Type 1C2T including Chamber | each
25.15.15 | Supply/excavate/lay/backfillSide Entry Pit Type 1C3T including Chamber | each
25.15.20 | Supply/excavate/lay/backfill Precast RGU, Grate and 1.2m Side Entry | each
25.15.25 | Supply/excavate/lay/backfill Precast RGU, Grate and 2.4m Side Entry | each
25.15.30 | Supply/excavate/lay/backfill Manhole/Chamber 1050mm | each
25.15.35 | Supply/excavate/lay/backfill Manhole/Chamber 1200mm | each
25.15.40 | Supply/excavate/lay/backfill Manhole/Chamber 1350mm | each
25.15.45 | Supply/excavate/lay/backfill Manhole/Chamber 1500mm | each
25.15.50 | Supply/excavate/lay/backfill Manhole/Chamber 2100mm | each
25.15.55 | Supply/excavate/lay/backfill 835x960 Chamber | each
25.15.60 | Manhole Extension Elongated [2000 x 1500]mm ID | each
30 | CONCRETE WORKS
30.05 | Kerb
30.05.05 | Concrete Kerb & Channel (Wet Mix) Barrier Kerb (to Gully Pits) | m
30.05.10 | Concrete Kerb & Channel (Wet Mix) Mountable Kerb (M3) | m
30.05.15 | Concrete Kerb & Channel (Wet Mix) Mountable Kerb (Type B1) | m
30.10 | Footpath
30.10.05 | Concrete Footpath 1.2m | m
30.15 | Driveways
30.15.05 | Remove and Reconstruct Concrete Driveways - Residential (125mm) - Provisional (If Ordered) | m2
30.20 | Concrete Infill
30.20.05 | Concrete Infill to medians | m2
35 | PAVEMENT & SURFACING
35.05 | Unbound Pavement
35.05.05 | Class 2.1 Unbound Pavement | m3
35.05.10 | Class 2.3 Unbound Pavement | m3
35.05.15 | Class 2.5 Unbound Pavement | m3
35.10 | Primerseal
35.10.05 | Primerseal - Emulsion 10mm | m2
35.15 | Asphalt
35.15.05 | Asphalt 35mm, Dense Graded | tonne
35.15.10 | Asphalt 50mm, Dense Graded | tonne
35.20 | Signs
35.20.05 | Project Signs | item
35.25 | Pavement Markings
35.25.05 | Pavement Markings - linemarking | item
35.25.10 | R.R.P. Markers in place | no.
35.30 | Fencing & Bollards
35.30.05 | Weldmesh fencing - Lot 245 RP130556 | m
35.30.10 | Fence - brick base & post with grille fence - Lot 143 RP179799 | item
40 | LANDSCAPING AND FINISHES
75.05 | Topsoil
75.05.05 | Topsoil Placement from Stockpile | m2
75.05.10 | Topsoil Placement - Imported | m2
75.10 | Turf
75.10.05 | Turfing | m2
40.05 | Landscaping
40.05.05 | Landscaping - Reinstating Easement | m2
40.10 | Trees and Plants
40.10.05 | Trees and plants for 116 Woodlands Drive | item

## Precast Stormwater Structures
| checklist | Installation ofPrecast Access Chambers / Gully Pits
| section | Details
| checkpoint | Lot Boundaries
1376a992-2035-59e3-9f08-b77fb9676dc1 | note | Lot Size: Each Stormwater Structure
ebbc9dee-5700-51e5-9f2a-0fcca4486b43 | note | Check Item - Check & Verify
ba075458-f427-5f71-9cb6-7b1e27a7747d | note
| checkpoint | Setout
bb5c926d-6283-55a1-915b-02abfc64aecc | note | Acceptance Criteria and Frequency (Project Specific) - Stormwater structures set out in accordance with the details shown in the drawing.
02f7a40a-4dfe-5743-b5b6-fb1b01189eb8 | note | Check Item - Check & Verify
39c03caa-aa22-5c1a-b200-7558f7d18c04 | note | Reference - Standard specification No. 3 Cl3.1
| checkpoint | Excavation
357b8562-a039-5ace-ad0f-98efdd040c6a | note | Acceptance Criteria and Frequency (Project Specific) - Excavation constructed to the shapes, alignment, and level shown on the drawings. Where in situ material at the bottom of excavations is other than rock, the material has been compacted to not less than 95 percent standard compaction as determined by AS 1289.1-2000 Methods of testing soils for engineering purposes - General requirements and list of methods. Compaction Testing: 1 test per structure foundation
96779f64-f840-5f44-9ba7-4e2d08bbf17b | note | Check Item - Check & Verify
d82bd16c-14ff-5f0e-b8c0-3799d11d0184 | note | Reference - Standard specification No. 3 Cl3.1
| checkpoint | Foundation
e23c44b5-d67c-569a-82bf-c3be85b7729a | note | Acceptance Criteria and Frequency (Project Specific) - Trench Foundation inspected prior to placing of Structure. Hold Point If poor trench conditions exist, the pipe, or structure shall be supported by rock ballast which is • sound igneous or metamorphic material that does not disintegrate in water; • of a 50mm nominal size; • completely wrapped in a non-woven geotextile fabric 1.9mm minimum thickness; • tamped into place.
a01a6610-8bff-552b-b325-293977d67b91 | note | Check Item - Hold Point
c81fa987-7e4e-5ae3-8e4f-8aa0753f3245 | note | Reference - RID/15/2018 Cl 7.0 & Standard specification No. 3 Cl3.3
c81fa987-7e4e-5ae3-8e4f-8aa0753f3245 | Sign Off | Hold Point
| checkpoint | Installation Precast Base
70a31081-b2d1-537f-83b1-3ca3e34c720b | note | Acceptance Criteria and Frequency (Project Specific) - Precast base installed in the location and levels shown in drawing within the following tolerances: o invert levels–±50mm; o manhole locations–within 1,000mm of design; o gully locations–within 300mm of design
48e43fca-992a-51dd-9d37-2b1be68cf6d2 | note | Check Item - Check and Verify
52154140-4539-52ff-bbd3-b3cb1e8c6b5a | note | Reference - Standard specification No. 3 Cl3.2
| checkpoint | Concrete Benching
4a8d3a5e-f757-55ba-9e34-6608ef560750 | note | Acceptance Criteria and Frequency (Project Specific) - Concrete benching has been provided to manholes, gullies and inlet pits and is shaped to the shapes specified and has smooth, even surfaces and neat edges
2049b3f8-76c7-5a48-b8ed-069b3e9db02d | note | Check Item - Check and Verify
5431d770-4f91-5635-b35c-d8c7dce79387 | note | Reference - Standard specification No. 3 Cl6.3
| checkpoint | Joining of Precast Sections
6f817abc-6633-5835-8698-fede051418d4 | note | Acceptance Criteria and Frequency (Project Specific) - Where Pre-cast systems are constructed by lowering the precast shaft section onto a precast base and a converter slab onto the precast shaft. In accordance with manufacturers' instructions, an Epoxy resin has be applied to both joint surfaces prior to joining.
e482be51-a17b-567b-84c4-7020f009e2f8 |  | #VALUE!
89cf0708-62b4-50d6-b243-b846ebb5e6ed | note | Check Item - Check and Verify
89cf0708-62b4-50d6-b243-b846ebb5e6ed | note | Reference - Humes Installation instructions
| checkpoint | Pipe Penetration Cut Outs
6f817abc-6633-5835-8698-fede051418d4 | note | Acceptance Criteria and Frequency (Project Specific) - Cut outs for pipe penetrations have been made using concrete saws or drills in such a manner as to minimise damage to the pre-cast units. Precast concrete shaft sections joints have been made watertight using an epoxy compound or using cement mortar and the joints have been be finished to provide smooth surfaces, uniform with the inner surfaces of the structures
e482be51-a17b-567b-84c4-7020f009e2f8 | note | Check Item - Check and Verify
89cf0708-62b4-50d6-b243-b846ebb5e6ed | note | Reference - Standard specification No. 3 Cl7.3
| checkpoint | Concrete Top Slab/Entry Units
6f817abc-6633-5835-8698-fede051418d4 | note | Acceptance Criteria and Frequency (Project Specific) - Concrete top slabs, inlet units and converter slabs shall be joined to the access champers/gully pits using cement mortar or epoxy mortar.
e482be51-a17b-567b-84c4-7020f009e2f8 | note | Check Item - Check and Verify
89cf0708-62b4-50d6-b243-b846ebb5e6ed | note | Reference - Standard specification No. 3 Cl6.3
| checkpoint | Backfilling
6f817abc-6633-5835-8698-fede051418d4 | note | Acceptance Criteria and Frequency (Project Specific) - Backfilling has been completed in accordance with Stormwater Pipe Installation - ITP
e482be51-a17b-567b-84c4-7020f009e2f8 | note | Check Item - Check and Verify
89cf0708-62b4-50d6-b243-b846ebb5e6ed | note | Reference - Stormwater Pipe Installation ITP
| checkpoint | Final Verification
5bb1bcd6-6a7d-5cdf-9a8b-f6b39da6fb5f | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
29eccf8b-c4b4-57da-9586-9cab3c249118 | textbox | Print Name:
0af1bfb1-9ba9-5eca-911c-9e849be2df12 | date | Date:
b9c17899-0ee7-561b-a4a1-8879a6ad98ab | note | Client Verify that the Above has been Constructed according to Specification
9be73287-be93-5b90-a88a-298b55bc8bc9 | textbox | Print Name:
214cfb75-7d8a-5839-9092-11176ae46b87 | date | Date:
| signoff | Signature

## Insitu Stormwater Structures
| checklist | Installation of Insitu Stormwater Structures
| section | Details
| checkpoint | Lot Boundaries
1376a992-2035-59e3-9f08-b77fb9676dc1 | note | Lot Size: Each Stormwater Structures
ebbc9dee-5700-51e5-9f2a-0fcca4486b43 | note | Check Item - Check & Verify
ba075458-f427-5f71-9cb6-7b1e27a7747d | note
| checkpoint | Setout
bb5c926d-6283-55a1-915b-02abfc64aecc | note | Acceptance Criteria and Frequency (Project Specific) - Stormwater structures set out in accordance with the details shown in the drawing and within the following tolerances: o invert levels – ±50mm; o manhole locations – within 1,000mm of design;
02f7a40a-4dfe-5743-b5b6-fb1b01189eb8 | note | Check Item - Check & Verify
39c03caa-aa22-5c1a-b200-7558f7d18c04 | note | Reference - Standard specification No. 3 Cl3.1
| checkpoint | Excavation
357b8562-a039-5ace-ad0f-98efdd040c6a | note | Acceptance Criteria and Frequency (Project Specific) - Excavation constructed to the shapes, alignment, and level shown on the drawings. Where in situ material at the bottom of excavations is other than rock, the material has been compacted to not less than 95 percent standard compaction as determined by AS 1289.1-2000 Methods of testing soils for engineering purposes - General requirements and list of methods. Compaction Testing: 1 test per structure foundation
96779f64-f840-5f44-9ba7-4e2d08bbf17b | note | Check Item - Check and Verify
d82bd16c-14ff-5f0e-b8c0-3799d11d0184 | note | Reference - Standard specification No. 3 Cl3.1
| checkpoint | Foundation
e23c44b5-d67c-569a-82bf-c3be85b7729a | note | Acceptance Criteria and Frequency (Project Specific) - Trench Foundation inspected prior to placing of Structure. Hold Point If poor trench conditions exist, the pipe, or structure shall be supported by rock ballast which is • sound igneous or metamorphic material that does not disintegrate in water; • of a 50mm nominal size; • completely wrapped in a non-woven geotextile fabric 1.9mm minimum thickness; • tamped into place.
a01a6610-8bff-552b-b325-293977d67b91 | note | Check Item - Hold Point
a01a6610-8bff-552b-b325-293977d67b91 | note | Reference - RID/15/2018 Cl 7.0 & Standard specification No. 3 Cl3.3
c81fa987-7e4e-5ae3-8e4f-8aa0753f3245 | Signoff | Hold Point
| checkpoint | Formwork Walls
70a31081-b2d1-537f-83b1-3ca3e34c720b | note | Acceptance Criteria and Frequency (Project Specific) - Where the sides of excavations are in solid ground, the manhole shafts may be constructed without the use of backforms. Where concrete is placed without the use of backforms, the specified wall thicknesses is increased by not less than 50mm
48e43fca-992a-51dd-9d37-2b1be68cf6d2 | note | Check Item - Check & Verify
52154140-4539-52ff-bbd3-b3cb1e8c6b5a | note | Reference - Standard specification No. 6 Cl6.3
| checkpoint | Access Chamber/Gully Pit Walls
4a8d3a5e-f757-55ba-9e34-6608ef560750 | note | Acceptance Criteria and Frequency (Project Specific) - The walls of gullies and manholes are constructed so the thickness is nowhere less than the minimum shown on the plans nor greater than 300mm above the design thickness.
2049b3f8-76c7-5a48-b8ed-069b3e9db02d | note | Check Item - Check & Verify
5431d770-4f91-5635-b35c-d8c7dce79387 | note | Reference - Standard specification No. 3 Cl6.3
| checkpoint | Concrete Batching
6f817abc-6633-5835-8698-fede051418d4 | note | Acceptance Criteria and Frequency (Project Specific) - Ready mixed concrete is supplied by a manufacturer: (a) approved by the local government; (b) which has an accredited quality assurance system.
e482be51-a17b-567b-84c4-7020f009e2f8 | note | Check Item - Check and Verify
89cf0708-62b4-50d6-b243-b846ebb5e6ed | note | Reference - Standard specification No. 8 Cl2.5
| checkpoint | Concrete Testing
6f817abc-6633-5835-8698-fede051418d4 | note | Acceptance Criteria and Frequency (Project Specific) - The frequency of sampling and testing to be in accordance with the Department of Transport and Main Roads – MRTS070 Concrete Technical Specification – Sampling Frequencies per Lot for 28 Day Strength Tests.
e482be51-a17b-567b-84c4-7020f009e2f8 |  | #VALUE!
89cf0708-62b4-50d6-b243-b846ebb5e6ed | note | Check Item - Test Results
89cf0708-62b4-50d6-b243-b846ebb5e6ed | note | Reference - Quotation Notes Cl25.0
| checkpoint | Concrete Slump
6f817abc-6633-5835-8698-fede051418d4 | note | Acceptance Criteria and Frequency (Project Specific) - The consistency and workability of concrete shall be such that it complies with the Slump limits specified in Table 2.4.1 below. Any extra water that is added to concrete on site shall be measured and recorded and the concrete shall be thoroughly remixed and reslumped.
e482be51-a17b-567b-84c4-7020f009e2f8 |  | #VALUE!
e482be51-a17b-567b-84c4-7020f009e2f8 | note | Check Item - Check & Verify
89cf0708-62b4-50d6-b243-b846ebb5e6ed | note | Reference - Standard specification No. 7 Cl2.4
| checkpoint | Approval to place concrete
6f817abc-6633-5835-8698-fede051418d4 | note | Acceptance Criteria and Frequency (Project Specific) - All concrete is placed in dry conditions and no concrete is placed until the formwork, falsework, and reinforcing materials have been inspected and approved by the Inspector. Hold Point
e482be51-a17b-567b-84c4-7020f009e2f8 | note | Check Item - Hold Point
e482be51-a17b-567b-84c4-7020f009e2f8 | note | Reference - Standard specification No. 8 Cl4.1
89cf0708-62b4-50d6-b243-b846ebb5e6ed | Signoff | Hold Point
| checkpoint | Placing time limit
6f817abc-6633-5835-8698-fede051418d4 | note | Acceptance Criteria and Frequency (Project Specific) - Ready mixed concrete is placed and compacted within 1 hour 15 minutes of charging the mixer for concrete temperatures up to 30°C and within 30 minutes of charging the mixer. No concrete with a temperature higher than 30°C is placed unless otherwise approved by the local government.
e482be51-a17b-567b-84c4-7020f009e2f8 | note | Check Item - Check & Verify
89cf0708-62b4-50d6-b243-b846ebb5e6ed | note | Reference - Standard specification No. 8 Cl4.3
| checkpoint | Removal of Forms/Falsework
6f817abc-6633-5835-8698-fede051418d4 | note | Acceptance Criteria and Frequency (Project Specific) - Forms/Falswork shall not be removed from the concrete until the times specified the table below are met:
e482be51-a17b-567b-84c4-7020f009e2f8 |  | #VALUE!
e482be51-a17b-567b-84c4-7020f009e2f8 | note | Check Item - Check & Verify
89cf0708-62b4-50d6-b243-b846ebb5e6ed | note | Reference - Standard specification No. 8 Cl6.2
| checkpoint | Concrete Benching
6f817abc-6633-5835-8698-fede051418d4 | note | Acceptance Criteria and Frequency (Project Specific) - Concrete benching is provided to manholes, gullies and inlet pits and is shaped to the shape specified and has smooth, even surfaces and neat edges.
e482be51-a17b-567b-84c4-7020f009e2f8 | note | Check Item - Check & Verify
89cf0708-62b4-50d6-b243-b846ebb5e6ed | note | Reference - Standard specification No. 3 Cl6.3
| checkpoint | Pipe Joint
6f817abc-6633-5835-8698-fede051418d4 | note | Acceptance Criteria and Frequency (Project Specific) - The joints between access chambers/gully pits and pipes shall be made water tight using cement mortar and shall be finished to provide smooth surfaces, uniform with the inner surfaces of the chamber/pits.
e482be51-a17b-567b-84c4-7020f009e2f8 | note | Check Item - Check & Verify
89cf0708-62b4-50d6-b243-b846ebb5e6ed | note | Reference - Standard specification No. 3 Cl6.3
| checkpoint | Concrete Top Slab/Entry Units
6f817abc-6633-5835-8698-fede051418d4 | note | Acceptance Criteria and Frequency (Project Specific) - Concrete top slabs, inlet units and converter slabs shall be joined to the access champers/gully pits using cement mortar or epoxy mortar.
e482be51-a17b-567b-84c4-7020f009e2f8 | note | Check ItemCheck & Verify
89cf0708-62b4-50d6-b243-b846ebb5e6ed | note | Reference - Standard specification No. 3 Cl6.3
| checkpoint | Backfilling
6f817abc-6633-5835-8698-fede051418d4 | note | Acceptance Criteria and Frequency (Project Specific) - Backfilling has been completed in accordance with Stormwater Pipe Installation - ITP
e482be51-a17b-567b-84c4-7020f009e2f8 | note | Check Item - Check & Verify
89cf0708-62b4-50d6-b243-b846ebb5e6ed | note | Reference - Stormwater Pipe Installation ITP
| checkpoint | Final Verification
5bb1bcd6-6a7d-5cdf-9a8b-f6b39da6fb5f | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
29eccf8b-c4b4-57da-9586-9cab3c249118 | textbox | Print Name:
0af1bfb1-9ba9-5eca-911c-9e849be2df12 | date | Date:
b9c17899-0ee7-561b-a4a1-8879a6ad98ab | note | Client Verify that the Above has been Constructed according to Specification
9be73287-be93-5b90-a88a-298b55bc8bc9 | textbox | Print Name:
214cfb75-7d8a-5839-9092-11176ae46b87 | date | Date:
| signoff | Signature

## Culverts RCPs
| checklist | 03.02 - Supply and Installation of Precast Concrete Pipe
| section | Details
| checkpoint | Lot Boundaries
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Check & Verify
| checkpoint | Materials
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - Bed Zone Material: 5mm or 10mm screenings. Embedment Zone Material: 5mm or 10mm screenings Backfill Material: Granular fill comprising rock (75mm maximum size, non plastic open graded material) or crusher run recycled concrete.
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Check Item
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - Note 2 IPEA STD DRW DS-030
| checkpoint | Geometric Tolerances
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - Pipes are laid from the discharge end upstream to the following tolerances: o invert levels–±50mm; o manhole locations–within 1,000mm of design; o gully locations–within 300mm of design.
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Check & Verify
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - Standard specification No. 3 Cl4.2
| checkpoint | Excavation
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - • Drainage lines and structures shall set out in accordance with the details shown in the Drawings • Excavation constructed to the shapes, alignment, and level shown on the drawings bottom of excavations shall be trimmed to the tolerances specified • Where excavation is carried out in asphalt pavement, the pavement has been cut 150mm beyond the limits of the trench excavation width • Trench not excavated wider than the trench width shown on the approved drawings. • All excavations are made in a careful manner to ensure they are rendered secure and safe by sheeting or other means
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Check & Verify
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - Standard specification No. 3 Cl3.1
| checkpoint | Trench Foundation
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - Trench Foundation Inspected prior to placing of bedding material. Hold Point
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Hold Point
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - RID/14/2018 & RID/15/2018 Cl 7.0
| signoff | Hold Point
| checkpoint | Unsuitable Trench Foundation
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - Where the excavation encounters ground water or other poor ground conditions at foundation, the depth of the bedding and surround material is to be increased to provide adequate support for the pipe as approved by the local government. Hold Point
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Hold Point
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - Standard specification No. 3 Cl3.3
| signoff | Hold Point
| checkpoint | Drainage of Bedding Material
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - Upstream of each headwall, manhole, or gully (other than an end of line gully), a 3.0 metre length of 100mm diameter sub-soil drainage pipe has been laid in the bedding material.
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Check & Verify
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - Standard specification No. 3 Cl3.2
| checkpoint | Pipe Laying
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - • Pipes are laid true to line and grade, and are free draining and firmly bedded. • Circular pipes with elliptical reinforcement supplied with marked “Top” and “Bottom” to indicate the correct position when laid and such pipes are laid correctly according to the marking. • For pipes up to and including 600mm diameter, the socketed end of the pipe is laid upstream and a shallow excavation is made under the socket of each pipe so that the pipe fully rests for its full length of barrel upon the bedding material in the trench. • Elastomeric ring joints are carefully made ensuring the spigot and socket are clean, and the rubber ring is rolled evenly into place and elastomeric ring lubricant is used for fibre reinforced concrete pipes. • For concrete pipes greater than 600mm diameter, internal interlocking joints may be used and the pipes are laid generally as specified in section 4.2 (Pipe laying) of this standard specification. • Externally the pipe joint is sealed with an approved proprietary manufactured natural rubber jointing band. • Lifting holes in all pipes are plugged by a method approved by the local government.
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Check & Verify
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - Standard specification No. 3 Cl4.2
| checkpoint | Jointing Pipes - Spigot and Socket
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - Where specified, spigot and socket pipes are joined by elastomeric ring joints which is in accordance with AS 1646–2007 Elastomeric seals for waterworks purposes–General requirements.
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Check & Verify
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - Standard specification No. 3 Cl4.3
| checkpoint | Jointing Pipes - Flush Joint
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - When a flush jointed pipe is used: • the first pipe (downstream) is bedded to established line and grade with the groove upstream; • the external band is installed after the joint is made, in accordance with manufacturer’s recommendations.
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Check & Verify
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - Standard specification No. 3 Cl4.3
| checkpoint | Pipe Backfill
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - Backfill is not placed until the Culvert pipe has been inspected and approved
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Hold Point
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - Standard specification No. 3 Cl5.1
| signoff | Hold Point
| checkpoint | Pipe Backfill - Road Reserve
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - Where stormwater pipe is laid in a drainage easement or property other than the road reserve, backfill material may comply to the requirements of general fill providing that a minimum CBR of 5 is evidenced. 5 or 10mm drainage screenings are to be fully wrapped in A34 geofabric for all stormwater trenches located within a property easement or park land Compaction Testing: 1 test per 100 m³, 2 per Lot.
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Check & Verify
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - RID/14/2018 & RID/15/2018 Cl 26.0
| checkpoint | Pipe Backfill - Drainage Easement
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - Where stormwater pipe is laid in a drainage easement or property other than the road reserve, backfill material may comply to the requirements of general fill providing that a minimum CBR of 5 is evidenced. 5 or 10mm drainage screenings are to be fully wrapped in A34 geofabric for all stormwater trenches located within a property easement or park land Compaction Testing: 1 test per 100 m³, 2 per Lot.
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Check & Verify
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - RID/14/2018 & RID/15/2018 Cl 26.0
| checkpoint | Final Verification
f498f173-10f8-5d3d-9e8d-220444c354b2 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
1125a7a9-6adc-5b33-8c12-73bcec1ef178 | textbox | Print Name:
28cdb289-42a4-54ce-afc0-14a13cf4a8f1 | date | Date:
9acd3400-a965-5190-91fb-1dadb52d11ce | note | Client Verify that the Above has been Constructed according to Specification
db266d05-69b6-56a9-b7a3-33f4b1500364 | textbox | Print Name:
5ac97e2d-4838-5d59-b83b-4c813aab909f | date | Date:
| signoff | Signature

## Pavements
| checklist | Unbound Granula Pavements
| section | Details
| checkpoint | Materials
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - Subgrade Replacement - Type 2.5 CBR > 15 Sub-Base Course - Type 2.3 CBR > 45 Base Course - Type 2.1 CBR > 60 Equivalent unbound gravel materials for road pavements as per MRTS05 are considered acceptable for use in this project, should the Contractor determine materials adhering to MRTS05, are more readily available. Contractor is to advise the Superintendent of MRTS05 materials proposed including grading envelopes, prior to use in the contract.
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Check Item
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - Quotation Notes Cl 57.0
| checkpoint | Submission of material Testing
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - Pavement material compliance testing is carried out by a NATA registered or equivalent accredited soils testing laboratory. Prior to the use of road base material, the developer is to submit current certified evidence obtained within the last twelve months
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Material Submission
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - Standard specification No. 1 Cl3.1
| checkpoint | Layer Placement Thickness
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - Where the required compacted thickness of any pavement course is 200mm or less, the pavement material is spread and compacted in one layer. Where the required compacted thickness of any pavement course is more than 200mm, the pavement material is compacted in two or more layers each not less than 75mm compacted thickness and not greater than 150mm compacted thickness.
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Check & Verify
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - Standard specification No. 6 Cl4.2
| checkpoint | Compaction
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - On all transverse stormwater road crossings, field density testing must be carried out at a frequency of one test per layer of granular pavement material over each section of new pipeline. On all subsequent roads, field density tests must be carried out at a frequency of one test per layer every 50m of new pipeline unless directed otherwise by the Superintendent Transverse Lines: 1 test per Stormwater Section Longitudinal Lines: 1 test per 50m of pipeline
a0a4483b-e995-5844-9f64-74a884ebea70 |  | #VALUE!
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Test Results
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - Standard specification No. 6 Cl6.1
| checkpoint | Geometrics
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - The finished pavement complies with the alignment and dimensions shown on the approved drawings or within the tolerances specified in Table 5.1.1 - Tolerance on the alignment, grade and crossfall of this standard specification.
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | #VALUE!
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Survey
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - Standard specification No. 6 Cl5.1
| checkpoint | Proof Roll
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - Proof rolling of the base course layer prior to placement of Asphaltic Concrete(AC) or Concrete kerb and channel shall constitute a Hold Point Proof rolling of all other intermediate layers of pavement materials shall constitute a Witness Point
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Hold Point / Witness point
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - Quotation Notes Cl 59.0
| signoff | Hold Point / Witness Point
| checkpoint | Approval to Place Subsequent Layer
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - No subsequent pavement course shall be placed until the previous course, that is the subgrade, sub-base, base or existing pavement, has been inspected by the local government.
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Hold Point
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - Standard specification No. 6 Cl4.2
| signoff | Hold Point
| checkpoint | Final Verification
bfbcc263-c8fa-5be7-a5fb-2499e5339c94 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
9be776d2-402a-5123-970b-7034cd968c5c | textbox | Print Name:
380f812e-044f-5987-87f9-a6c37d13e3dc | date | Date:
ee1aa6cb-7a6b-5a9f-a060-eed6faf29c4e | note | Client Verify that the Above has been Constructed according to Specification
5a431bef-2d6b-5252-8cd5-330ba275561d | textbox | Print Name:
42fa8ffc-22da-5fe4-b7ad-10889565d113 | date | Date:
| signoff | Signature

## Concrete
| checklist | Concrete Works
| section | Details
| checkpoint | Concrete batching
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Ready mixed concrete shall be supplied by a manufacturer: (a) approved by the local government; (b) which has an accredited quality assurance system.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 7 Cl2.5
| checkpoint | Concrete testing
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - The frequency of sampling and testing to be in accordance with the Department of Transport and Main Roads – MRTS070 Concrete Technical Specification – Sampling Frequencies per Lot for 28 Day Strength Tests. However, For concrete footpath and driveway slab construction, the frequency of testing is to be reduced to one (1) batch per day. Testing is to provide one (1) 7 day test result and two (2) 28 day test results.
20fed177-faf7-5996-8a48-703ffc349cbd |  | #VALUE!
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Test Results
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Quotation Notes Cl25. & Cl40.
| checkpoint | Concrete Slump
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - The consistency and workability of concrete shall be such that it complies with the Slump limits specified in Table 2.4.1 below. Any extra water that is added to concrete on site shall be measured and recorded and the concrete shall be thoroughly remixed and reslumped.
20fed177-faf7-5996-8a48-703ffc349cbd |  | #VALUE!
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 7 Cl2.4
| checkpoint | Approval to place concrete
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - All concrete is placed in dry conditions and no concrete is placed until the formwork, falsework, and reinforcing materials have been inspected and approved by the Inspector. Hold Point
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 7 Cl4.1
| signoff | HOLD POINT
| checkpoint | Placing time limit
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Ready mixed concrete is placed and compacted within 1 hour 15 minutes of charging the mixer for concrete temperatures up to 30°C and within 30 minutes of charging the mixer. No concrete with a temperature higher than 30°C is placed unless otherwise approved by the local government.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 7 Cl4.3
| checkpoint | Finishing of concrete
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - All surfaces of concrete that are exposed to view in the completed structure are finished such that: (a) immediately after the removal of forms, all fins and other projections are ground off, all pockets and honeycombs are cleaned and filled with a stiff cement mortar having the same proportion of cement and sand as the original concrete, and the surface of the patch is ground flush; (b) decks are roughened slightly by brooming or other approved method before initial set; (c) kerb and channel, invert crossings, vehicle crossings and industrial crossings are finished with an approved steel finishing tool; (d) footpaths and pram ramps are finished with a wooden float and broomed.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check 7 Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 7 Cl6.1
| checkpoint | Curing of concrete
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Curing shall be commenced immediately on completion of the finishing of exposed surfaces or within 30 minutes of removal of the forms from other surfaces and shall be completed using either of the following method: (a) Spraying and approved curing compound; or (b) Using water sprays or wet sand in which case the surfaces are kept moist 24 hours a day for the full period specified
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 7 Cl6.3
| signoff | HOLD POINT
| checkpoint | Removal of Forms / Falsework
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Forms/Falsework shall not be removed from the concrete until the times specified the table below are met:
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 7 Cl6.2
| checkpoint | Final Verification
b153a008-efe3-53d7-86a7-e72d4ec9c408 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
ba9c0c4e-96be-5de2-a3ac-9fbc1e1f8304 | textbox | Print Name:
00d2598d-065f-53bc-95f7-973eddfc6049 | date | Date:
15b7bcfe-9323-5005-86ea-096816430239 | note | Client Verify that the Above has been Constructed according to Specification
67f4372c-079a-5353-9dfa-06790b0eb74d | textbox | Print Name:
260fe1c7-94f5-50be-b433-e6cb474e1b17 | date | Date:
| signoff | Signature

## Kerb & Channel
| checklist | Minor Concrete Works (Kerb & Channel)
| section | Details
| checkpoint | Kerb and channel
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - kerb and channel rehabilitation works, the kerb and channel are to be constructed in accordance to the LCC Supplementary Specification for Kerb & Channel Rehabilitation Projects
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Quotation Notes Cl41.
| checkpoint | Pavement under kerb and channel
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Where pavement thickness exceeds 175mm in depth, the pavement shall extends under the kerb. Where the pavement thickness does not exceed 175mm in depth, the kerb and channel shall be firmly bedded on 100mm road base aggregate compacted to 95 percent modified dry density
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 8 Cl6.2
| checkpoint | Machine placed kerb and channel
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - 1. Where a kerb and channel machine is used to place the replacement kerb and channel, a 20MPa kerb mix with maximum aggregate size of between 5mm and 10mm shall be used. 2. A minimum slump of 12mm shall be adopted for this mix. The concrete shall be fully compacted and finished with a high strength sand/cement slurry to the profile as specified
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 8 Cl6.4.1
| checkpoint | Hand placed kerb and channel
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - 1. Where the replacement kerb and channel is placed and finished by "hand" an N25/20 grade concrete shall be used with a minimum 40mm and maximum 80mm slump. 2. The concrete shall be fully compacted with vibratory equipment, shaped and trowel finished to match the profile of the adjoining kerb and channel or to a profile as otherwise specified. 3. Transitions between different kerb types shall be done over a distance of at least 2.0 metres.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 8 Cl6.4.2
| checkpoint | Backfill behind kerb & channel
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - When suitably cured, the kerb and channel shall be backfilled with a suitable granular material, compacted and finished with 50mm of topsoil and turfed with a minimum 'B' grade couch turf. Excavated pavement material may be reused as kerb backfill.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 8 Cl6.5.1
| signoff | HOLD POINT
| checkpoint | Final Verification
b153a008-efe3-53d7-86a7-e72d4ec9c408 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
ba9c0c4e-96be-5de2-a3ac-9fbc1e1f8304 | textbox | Print Name:
00d2598d-065f-53bc-95f7-973eddfc6049 | date | Date:
15b7bcfe-9323-5005-86ea-096816430239 | note | Client Verify that the Above has been Constructed according to Specification
67f4372c-079a-5353-9dfa-06790b0eb74d | textbox | Print Name:
260fe1c7-94f5-50be-b433-e6cb474e1b17 | date | Date:
| signoff | Signature

## Linemarking
| checklist | Linemarking
| section | Details
| checkpoint | Linemarking Accordance
06e5d28b-f267-50b7-a9df-798a879cfcb0 | note | Acceptance Criteria and Frequency (Project Specific) - All Linemarking shall be in accordance with manual of uniform traffic control devices. Surplus pavement markings shall be removed by a method approved Council
2d07c1b4-9995-5a87-8b31-f9f03dd2856e | note | Check Item - Check & verify
2d07c1b4-9995-5a87-8b31-f9f03dd2856e | note | Reference - Project Drawings General Notes Cl11.
| checkpoint | Minimum Placement Period between Operations
280bef65-91de-5ec7-b2b3-b7ca6a82fe00 | note | Acceptance Criteria and Frequency (Project Specific) - The Contractor to ensure that there is a minimum period of 72 hours between the placement of asphalt wearing course/spray seal surfacing and line marking installation.
095baebd-5d80-5f30-b88f-f0f65e0128e9 | note | Check Item - Check & Verify
095baebd-5d80-5f30-b88f-f0f65e0128e9 | note | Reference - Quotation Notes Cl63.
| checkpoint | Application of Linemarking | d
db77e0d2-7e74-5fb0-9bad-71740d85fd47 | note | Acceptance Criteria and Frequency (Project Specific) - Linemarking (excluding thermoplastic) shall be marked at an application rate of 0.375 litres/m2 +/- 0.025 litres/m2. All transverse Linemarking and arrows are to be placed in Thermoplastic unless otherwise directed by the Superintendent.
f879c085-dc8a-5b2f-81cf-7ff13a0ce7d1 | note | Check Item - Check & Verify
f879c085-dc8a-5b2f-81cf-7ff13a0ce7d1 | note | Reference - Operations Specification Cl31.
| checkpoint | Final Verification
b7fd5ec4-a2aa-5567-a654-4e9ce96b8601 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
0587223c-d2e1-5767-b904-2b1dacea5cb9 | textbox | Print Name:
8dfa17c5-d4b4-5d6c-a200-a25789a71406 | date | Date:
1d9eaa3e-b9ae-5c3d-b076-8a99bca2fc6f | note | Client Verify that the Above has been Constructed according to Specification
63abdbb3-30c1-5f4b-99a8-c5231588a2e4 | textbox | Print Name:
e6c44da6-c50d-55f0-8cac-271d03fe02bd | date | Date:
| signoff | Signature

## Landscaping
| checklist | Landscaping
| section | Details
| checkpoint | Landscaping Materials
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Materials and workmanship comply with the relevant Australian Standards. Manufactured items used in accordance with manufacturer's specification. All landscape materials (soil, plants and mulch) free from fire ants, certificate or legislation.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 3 Cl2.1
| checkpoint | Landscaping Commencement
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Prior to landscaping works commencement, the Contractor shall liase with LCC Site Representative to confirm locations / spacing of plants.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Hold Point
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Quotation Note No. 85
| signoff | HOLD POINT
| checkpoint | Plant Management
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Plant protection, works near trees, damage, maintenance, removal and weed eradication to be in accordance with Standard Specification No. 3 Cl 3.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 3 Cl 3
| checkpoint | Earthworks
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Erosion and sediment control, clearing and grubbing, stockpiles, softworks grades and earth mounds to be in accordance with Standard Specification No. 3 Cl 4. The maximum grade for a garden bed is 1 in 3. The maximum grade for a garden bed is 1 in 4.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 3 Cl 4
| checkpoint | Hardworks
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Edges to garden areas, outdoor furniture, play areas, and bollards to be in accordance with Standard specification No. 3 Cl 5
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 3 Cl 5
| checkpoint | Softworks
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Cultivation, soil, fertiliser, plant material, tree planting, transplanting, plant size, mulch, organic stabilisation matting, turfing and grassing and rehabilitation planting to be in accordance with Standard Specification No. 3 Cl6
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 3 Cl 6
| checkpoint | Maintenance
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Maintenance works and spraying of plants to be in accordance with Standard specification No. 3, Cl 7.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Maintenance works and spraying of plants to be in accordance with Standard specification No. 3, Cl 7.
| checkpoint | Revegetation (Topsoil)
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - All embankment batters are to be topsoiles with a minimum 75mm of topsoil. Prior to topsoil being placed, the batters shall be lightly tyned to a depth of 75mm.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Operations Specification RID/14/2018 and RID/15/2018 Civil Construction Services Part 32.
| checkpoint | Revegetation (Grassing)
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Unless directed otherwise by the Superintendent, grassing shall be rolled turfed (not seed or hydromulched products). Sufficient allowance made by Contractor to maintain turf with watering such that turf does not brown off and until such time that turf has taken root in topsoil and is not able to be lifted away from the ground by hand.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Operations Specification RID/14/2018 and RID/15/2018 Civil Construction Services Part 32.
| checkpoint | Contractual Provisions
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - The Contractor must obtain written approval of the Superintendent before ordering alternative materials.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Hold Point
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard specification No. 8 Cl8
| signoff | HOLD POINT
| checkpoint | Final Verification
3451aa62-d848-576d-aed2-4d878fd3b7c8 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
654f9b20-a7a0-5bf8-9267-75805919d172 | textbox | Print Name:
7212e641-ec40-537d-8f8b-b05fd9186a10 | date | Date:
4df799a0-8551-57d4-b5ef-3630232d5e5f | note | Client Verify that the Above has been Constructed according to Specification
ad2b022d-d6ac-556d-89cb-33c04441c94c | textbox | Print Name:
b28d5a62-f70f-533f-a115-b98a413793b5 | date | Date:
| signoff | Signature

## Reinforcement
| checklist | Reinforcement for Drainage Structures
| section | Details
| checkpoint | Material for Reinforcement
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - All materials for reinforcement comply with the relevant Australian Standards as per Standard Specification No. 9 Cl 2.1
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - All materials for reinforcement comply with the relevant Australian Standards as per Standard Specification No. 9 Cl 2.1
| checkpoint | Protection
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Reinforcement is to be protected from damage at all times. Reinforcement is stacked in racks or on timber above ground, kept clear of contamination and cleaned if accidental contamination occurs.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard Specification No. 9 Cl 3.1
| checkpoint | Cutting & Bending
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Approval to hot bend reinforcement on site.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Hold Point
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard Specification No. 9 Cl 4.1
a40d8616-88f1-522d-a01a-69680485dc7d | Signoff | Hold Point
| checkpoint | Cutting & Bending
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Reinforcment is fabricated to the shape and dimensions shown on the approved drawings and within the following tolerances: (a) on any overall dimension for bars and fabric except where used as a fitment (i) length up to 600mm, 25mm, +0; or (ii) length over 600mm, 40mm, +0; or (b) on any overall dimension of bars or fabric used as a fitment: (i) for deformed bars and fabric, 15mm, +0; or (ii) for plain round bars and wire, 10mm, +0; or (c) on the overall offset dimension of a cranked column bar -0, +10mm; or (d) for the sawn or machined end of a straight bar intended for use as an end-bearing splice, the angular deviation from the square measured in relation to the end 300mm is within 2 degrees.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard Specification No. 9 Cl 4.1
| checkpoint | Surface Condition of Reinforcement
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Reinforcement projecting from a previous concreting operation is cleaned free of adhering concrete or loose slurry prior to any further embedment.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard Specification No. 9 Cl 5
| checkpoint | Placing & Fixing
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Reinforcement is placed in position as shown in the approved drawings
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard Specification No. 9 Cl 6
| checkpoint | Tolerance on Position of Reinforcement
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - The deviation from the specified position of reinforcement and densons do not exceed: (a) for positions controlled by cover: (i) in beams, girders, slabs, columns and walls, -5mm and +10mm; (ii) in slabs-on-ground including foorings of walls and culverts, -10mm and +20mm; (iii) in footings cast in the ground where the depth of the footing is 500mm or more, -20mm and +40mm; (b) for positions not controlled by cover: (i) the location of reinforcement on a profile, 10mm; (ii) the position of the ends of reinforcement along the line of the bar, 50mm; (iii) the spacing of bars in walls and slabs and of fitments in beams and columns, whichever is the greater of: (A) 10 percent of the specified spacing; or (B) 15mm, whichever is the greater.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Check & Verify
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard Specification No. 9 Cl 7.1
| checkpoint | Splicing
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - The splicing of reinforcement occurs only in the locations shown in the approved drawings.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Hold Point
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard Specification No. 9 Cl 8.1
a40d8616-88f1-522d-a01a-69680485dc7d | Signoff | Hold Point
| checkpoint | Substitution
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Approval for the substitution of reinforcement.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Hold Point
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard Specification No. 9 Cl 9.1
a40d8616-88f1-522d-a01a-69680485dc7d | Signoff | Hold Point
| checkpoint | Fibre Reinforcement
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Approval to incorporate fibre reinforcement into the works.
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Hold Point
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - Standard Specification No. 9 Cl 10.1
a40d8616-88f1-522d-a01a-69680485dc7d | Signoff | Hold Point
| checkpoint | Final Verification
53534733-c5d2-526d-bb03-3538b57de3f8 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
e83f7e7a-6a61-5bea-855c-e6c73d66b4f0 | textbox | Print Name:
e53cf56f-54a8-598b-90a5-cd2a1c0ceb2b | date | Date:
cb12f9b9-2267-5b12-9e5b-c0dc56ba152a | note | Client Verify that the Above has been Constructed according to Specification
1bf0baa9-9145-54ff-8e54-cee7090fa564 | textbox | Print Name:
edcd39a6-4824-5973-90b7-2d08efed6d04 | date | Date:
| signoff | Signature