## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | ITP - Chipseal Rev 0 | itp | ITP - Chipseal | 6aaca462-f4e3-49f0-867c-664e6c25c141
| section | Design
| checkpoint | 1 - Treatment Selection
8c8594da-6af8-5f58-ac8b-47786c4a2d04 | note | Verification Activity - Physical / Site video/photographic record
363258c0-aa1d-539c-b37b-8cb853b851c7 | note | Methods or Reference - Asset Team - Base Preservation
4605c89f-a749-5eb0-8e15-b1899d96f3d9 | note | Frequency - Annually Pre-reseal
0690ea7e-7d71-58ff-a5cc-df717e41231f | note | Acceptance Criteria - Documented approval from at time of Tender -Team/Client
ad9ca390-cec5-526f-97fe-8da5c922e867 | note | Hold / Witness Point - Mandatory HOLD POINT - Client Approval
e0ad7bbf-75fb-5ae2-bef0-ee1bd76cdb92 | note | Records - Approved Seal Designs
04e2df52-d24e-59ac-9339-5d0aba9c964c | note | Responsible Person - Sealing Contract Manager / Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Chipseal Design
21cc6101-c692-5b4a-ab48-48ea98e33d80 | note | Verification Activity - Peer review by Authorised Seal Design Approver
f79ca6ff-d241-5e3e-b4c5-b73e48345a7e | note | Methods or Reference - Chipsealing in NZ
f61c2fcf-6b67-503c-8fd8-f43c54bab3dc | note | Frequency - One per design prior to commencing onsite
d6fc83d3-15f6-5631-8b3d-ee8513d1eac7 | note | Acceptance Criteria - Design meets requirements of P17
33f7bfc6-4035-5500-b475-022f399b75b8 | note | Hold / Witness Point - Mandatory HOLD POINT - Seal Design peer Reviwer - Client Approval
d4ab7a59-00d3-56c2-96ad-3d16f4f8384a | note | Records - Peer Reviewed Seal Designs
a118de6c-c1d7-5c54-abbc-01dc3ac1e2cf | note | Responsible Person - Sealing Contract Manager / Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials Testing
| checkpoint | 1 - Size (Grades 2-5) & Shape (Grades 2-4)
a9880745-584d-5cec-9fca-0e8bd2611dbd | note | Verification Activity - Lab Test
e0239544-b439-510c-9a6c-248f9527d84d | note | Methods or Reference - NZTA M/6
9cd469b4-e036-5989-b33f-1298280a42b0 | note | Frequency - 1/500m3
3d7986b0-d0f4-58cb-b0fa-4ebad950154a | note | Acceptance Criteria - Size (ald mm)
b404e1f9-0260-531a-84e7-45ce0ed4b2ba | note | ○ G2 9.5-12.0
d7923a91-8d98-5f66-906d-f059e935686a | note | ○ G3 7.5-10.0
1dd0f860-23dd-5ad5-a079-3d690da1b28b | note | ○ G4 5.5-8.0
ad733c59-9580-57ba-a34b-2f49af676bbc | note | ○ G5 Report
3d1fd3d2-123e-58f4-b3f2-df416b27714d | note | Hold / Witness Point - Witness Point
bd024640-102f-52b6-9a23-8ef6f96a750f | note | Records - IANZ Lab Reports
f740777d-ef62-5280-a659-f270652f5311 | note | Responsible Person - Sealing Contract Manager / Engineer
| checkpoint | 2 - Size (Grades 2-5) & Shape (Grades 2-4)
3de44f12-cbac-5427-bd29-41bc0f4743c8 | note | Verification Activity - Lab Test
ad98f400-d4d7-5583-a3c7-f5681c24e66a | note | Methods or Reference - NZTA M/6
b57f5d99-d090-5903-964e-58782d40124e | note | Frequency - 1/500m3
46df09f2-f527-5840-96f2-a484a68964c8 | note | Acceptance Criteria - Shape
f5c6521c-9638-5d2b-bd12-36c96763e6b5 | note | ○ AGD/ALD Ratio G2,3,4 = 2.25 max
46978e06-8d81-58b4-ba19-6dbe19ea748d | note | ○ G2,3,4 = min 98% with 2+ broken faces
d8704148-4f83-5773-b7be-6a58ca0772ca | note | Hold / Witness Point - Witness Point
a84e7a4f-5b04-524f-9d8c-258288fb22fc | note | Records - IANZ Lab Reports
f42e08f6-d6c4-5b04-a87c-685a065d4a01 | note | Responsible Person - Sealing Contract Manager / Engineer
| checkpoint | 3 - Cleanliness (Grades 2-6)
09ff3d80-7d9d-5ea6-acba-cdfa74f16d76 | note | Verification Activity - Lab Test
a473ae1a-da03-534e-90a4-c7dc1dfa66f1 | note | Methods or Reference - NZTA M/6
8a5ce8d2-851e-500c-9dda-ef6a4f0c563c | note | Frequency - 1/500m3
45f4bc29-c7e2-5e23-8aee-3ae0f0448c2e | note | Acceptance Criteria - Cleanness value
3a3c2ded-7885-54ac-b57b-6bb91da5a6ff | note | ○ G2 = 89
dca0f9f6-7cb0-503d-894d-595b672347d8 | note | ○ G3 = 87
7eb294fd-7951-5352-ab78-f8a70f3c4737 | note | ○ G4 = 85
ee7da877-ed1b-5293-a104-0b60d3017b7d | note | ○ G5 & G6 Report only
32c208ab-72e8-519b-8159-a7961a435015 | note | Hold / Witness Point - Witness Point
3943d478-9ad9-5dd5-a0dd-700fa4513387 | note | Records - IANZ Lab Reports
4af6a67d-223c-578a-b36e-6c956b0d4475 | note | Responsible Person - Sealing Contract Manager / Engineer
| checkpoint | 4 - Compatibility (Multi Layered seals)
bd5bce0e-8797-5fdc-b9ab-5c0d43be4591 | note | Verification Activity - Comparison Of Chip ALD
dfeb114f-a2a9-5e23-a130-4bff113b4249 | note | Methods or Reference - Chipsealing in New Zealand NZTA (NZTA 2005)
fc7cd369-2f0d-5eaf-9302-2ceed29606ba | note | Frequency - 11.5
f9c507c3-e302-573d-ba85-acebae16bc02 | note | Acceptance Criteria - Two Coat Seal Aggregate Compatibility
2c37808e-8e72-5cdb-88a9-1fdbd99da1c0 | note | – – – – – – – – – – – – – –
081e78ff-06f7-5198-947f-4bff79a7021d | note | Upper Limit (x ¦ y) ¦¦¦ Lower Limit (x ¦ y)
0a54da32-2235-5670-8909-ff73bd22d109 | note | – – – – – – – – – – – – – –
ecda9c22-e0a1-5c01-aba7-dacf6d484fff | note | 0 ¦ -0.44 ¦¦¦ 0 ¦ -1.42
6e9e3a66-4010-5719-b9c5-0310628ad8d1 | note | 1 ¦ 0.27 ¦¦¦ 1 ¦ -0.84
65148c6d-3532-5070-ba53-3ed2b57f0f01 | note | 2 ¦ 0.98 ¦¦¦ 2 ¦ -0.26
aeb3b653-2b25-58da-8549-aa2a155eab2e | note | 3 ¦ 1.69 ¦¦¦ 3 ¦ 0.32
77feabca-708c-5aa0-a63d-82004922add2 | note | 4 ¦ 2.4 ¦¦¦ 4 ¦ 0.9
fd46e692-362e-5ece-b394-623b2bda6dfe | note | 5 ¦ 3.11 ¦¦¦ 5 ¦ 1.48
1160d91c-0d90-5388-b81a-9e678972d155 | note | 6 ¦ 3.82 ¦¦¦ 6 ¦ 2.06
ed48bc2d-de29-5586-8455-b0246653b5b4 | note | 7 ¦ 4.53 ¦¦¦ 7 ¦ 2.64
ee77e960-1fa3-5f09-a32c-a01b2e5640f1 | note | 8 ¦ 5.24 ¦¦¦ 8 ¦ 3.22
e45eb816-93f9-5936-9a4f-041e5d350a66 | note | 9 ¦ 5.95 ¦¦¦ 9 ¦ 3.8
24612e24-878c-57de-bb82-cad06d178015 | note | 10 ¦ 6.66 ¦¦¦ 10 ¦ 4.38
06dba8ff-aaba-517f-9ae6-f1c879764d6b | note | 11 ¦ 7.37 ¦¦¦ 11 ¦ 4.96
058f4422-6f0d-5010-9c41-61d0548850ab | note | 12 ¦ 8.08 ¦¦¦ 12 ¦ 5.54
abac5f86-b634-51f3-b7c0-f519e6816540 | note | 13 ¦ 8.79 ¦¦¦ 13 ¦ 6.12
e8b690c3-3b62-5c6f-8794-c9a0dc4a644a | note | 14 ¦ 9.5 ¦¦¦ 14 ¦ 6.7
13f6237e-705a-584a-9869-155ce0e9685b | note | 15 ¦ 10.21 ¦¦¦ 15 ¦ 7.28
712135b3-bd1c-5cf7-bcba-7c9dbceba12c | note | 16 ¦ 10.92 ¦¦¦ 16 ¦ 7.86
38bd2d9c-351a-59e0-9fba-1a3bddebe84a | note | – – – – – – – – – – – – – –
8404b4ab-08b4-5c79-8a3d-2aad39fc122a | note | Compatibility Point
3859bcdf-02e1-599b-a4b4-6b4fbf96e4b7 | note | x ¦ y
7890d083-d731-5891-a1b8-a8548f0f0e93 | note | 11.5 ¦ 7.2
f5a5d6da-8777-5f1d-adc2-9a33b3a7c828 | note | – – – – – – – – – – – – – –
b3ede0ef-57f3-5468-b613-0db9749a0eef | note | Hold / Witness Point - Witness Point
6929ceaf-0bf3-526a-bdd6-1cf77d537299 | note | Records - IANZ Lab Reports
13c53e10-c070-5e11-a7d0-79627aa02655 | note | Responsible Person - Sealing Contract Manager / Engineer
| checkpoint | 5 - Compatibility (Multi Layered seals)
b40f7402-74ba-5ae9-83c1-887b47a23a87 | note | Verification Activity - Comparison Of Chip ALD
aad88e1a-edc3-515c-a9c6-f754c07b924c | note | Methods or Reference - Chipsealing in New Zealand NZTA (NZTA 2005)
0837712b-73ee-5483-bada-328886379305 | note | Frequency - 7.2
fcd561db-4bf0-5fc5-ab86-36f126ce6fa8 | note | Acceptance Criteria - Two Coat Seal Aggregate Compatibility
79cf5fe2-ba07-52ed-8c52-1046d63a4904 | note | – – – – – – – – – – – – – –
0ef4686d-e0a1-5bce-b096-9334cc60d8e2 | note | Upper Limit (x ¦ y) ¦¦¦ Lower Limit (x ¦ y)
0518db59-a21d-5455-a861-40a27a0453ef | note | – – – – – – – – – – – – – –
a4bcff6d-12be-5548-b414-285999586f67 | note | 0 ¦ -0.44 ¦¦¦ 0 ¦ -1.42
1e45f48a-60ce-5cbf-9a03-47534beac279 | note | 1 ¦ 0.27 ¦¦¦ 1 ¦ -0.84
eecce50d-3bca-52b7-a2fb-40ddaee2e607 | note | 2 ¦ 0.98 ¦¦¦ 2 ¦ -0.26
db00ebef-e224-5347-b504-9b2ea7f9f2ed | note | 3 ¦ 1.69 ¦¦¦ 3 ¦ 0.32
028a0cb4-9e71-5726-9222-1385f77c32a8 | note | 4 ¦ 2.4 ¦¦¦ 4 ¦ 0.9
7da4dbf6-2a9d-527d-a263-2ecebba2fe5e | note | 5 ¦ 3.11 ¦¦¦ 5 ¦ 1.48
380c82a7-eb96-5b45-b023-3fb78036e714 | note | 6 ¦ 3.82 ¦¦¦ 6 ¦ 2.06
cafaf48f-c911-5a14-9b9b-69421f3d90bf | note | 7 ¦ 4.53 ¦¦¦ 7 ¦ 2.64
63e087d8-66e9-50ae-b626-85b55a4d1cb3 | note | 8 ¦ 5.24 ¦¦¦ 8 ¦ 3.22
de99cbb8-c8a5-558c-914e-dfe4f6b7f5b5 | note | 9 ¦ 5.95 ¦¦¦ 9 ¦ 3.8
1103e6ef-6b66-5c1e-838a-ecfa0ca5699f | note | 10 ¦ 6.66 ¦¦¦ 10 ¦ 4.38
6fca420f-a37b-5cda-bf94-ad32dfc1b8eb | note | 11 ¦ 7.37 ¦¦¦ 11 ¦ 4.96
f1fb8533-1e61-5737-8c56-60bb5b1172d9 | note | 12 ¦ 8.08 ¦¦¦ 12 ¦ 5.54
7bfcc63e-560b-5af2-8e0e-e28b1039f7b2 | note | 13 ¦ 8.79 ¦¦¦ 13 ¦ 6.12
6ba5341b-2779-58f9-b5ec-1b88d62c21f2 | note | 14 ¦ 9.5 ¦¦¦ 14 ¦ 6.7
073fa69d-93c3-5873-9744-7bab2a4734e7 | note | 15 ¦ 10.21 ¦¦¦ 15 ¦ 7.28
4117fae7-882a-5772-9d95-c07e6e06c0a3 | note | 16 ¦ 10.92 ¦¦¦ 16 ¦ 7.86
6bbf656f-e45b-5541-836a-22bf853fee58 | note | – – – – – – – – – – – – – –
c6c1963b-7ac8-5926-a890-764ce8ad88f8 | note | Compatibility Point
ff5f8dfb-fb7b-52ed-af07-ddface52152d | note | x ¦ y
d49ad839-0ad8-5da7-a8ca-a331cccefb0c | note | 11.5 ¦ 7.2
698e3af3-883c-5494-b632-bc4a72f6d934 | note | – – – – – – – – – – – – – –
7174a18c-03a9-5574-9de5-27648beb13dc | note | Hold / Witness Point - Witness Point
b6dc63cb-2b8e-55f0-b262-773f57d45921 | note | Records - IANZ Lab Reports
135adfcf-d7de-5536-9029-c7237117979e | note | Responsible Person - Sealing Contract Manager / Engineer
| checkpoint | 6 - Bitumen Distributor
96920bed-b19e-5c60-8792-1123aad4988b | note | Verification Activity - IANZ Lab E/2 Results
3f879b55-4a9e-528e-8d20-f2bac0ead35c | note | Methods or Reference - Code of Compliance
63931585-ad11-589f-8f53-d60d60f3be3b | note | Frequency - Annual
102d69b4-0977-5512-820b-193d999e0a58 | note | Acceptance Criteria - Speed Test(+-3% over 100m), Dipstick Test (+-50L over 2000L), Matt Test (app rate within 0.10L/m2, longitudinal within 10%, thirds within 5%, transverse within 20%)
4bfb7e84-93b9-5cd5-9e76-8b4a8a561254 | note | Hold / Witness Point - Mandatory HOLD POINT - Client - Engineer Witness
11cd3b06-b42f-515e-add6-78c691aace19 | note | Records - RNZ E2 Certificate
f3c36f82-0013-5fff-8415-cd717a0845db | note | Responsible Person - Sealing Contract Manager / Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Emulsion/PME Testing
3ff533ac-99b1-5ec9-b0e0-f1d44d43ddd1 | note | Verification Activity - Lab Testing
833f99d8-74b3-5d28-bdd1-ac8ba2707664 | note | Methods or Reference - Manufacture Specification
587c773f-24e2-53f1-bf10-957cced09eec | note | Frequency - Per Emulsion/Bitumen Production Batch
94e6497e-66eb-5726-bc23-a561262a423d | note | Acceptance Criteria - Bitumen Content, ITM 11-01, Viscosity, ITM 10-02, PH ITM-08-02
6e12188d-76b6-50ff-868c-9e2a23d72dea | note | Hold / Witness Point - Witness Point
0d1f3ca5-c998-5645-8b6d-012a6c5f7f6d | note | Records - IANZ Lab Reports
06b33136-ea2f-5b58-b325-161ab7e1b6c9 | note | Responsible Person - Road Science
| section | Surface Inspection
| checkpoint | 1 - Surface Texture - Measurement
30992215-6fb8-5829-9e30-e309637c2ea0 | note | Verification Activity - Sandcircle Measurement
975447bb-1fb7-51d9-880d-00334a3bd720 | note | Methods or Reference - NZTA T/3
1d55f0bf-b2be-5846-9553-f9420ade3074 | note | Frequency - At time of Seal Inspection
22dd72a9-5722-5204-b616-f6f218677460 | note | Acceptance Criteria - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture
cf7d8cb7-2288-5434-bc68-e5ae8455829d | note | Hold / Witness Point - Witness Point
a50e24d3-e404-5b10-8798-f093aa718d95 | note | Records - Sandcircle Data
6e286e95-7ef3-5c51-aa0e-886a754f056a | note | Responsible Person - Sealing Contract Manager / Engineer
| checkpoint | 2 - Surface Texture - Measurement
4c0e8f22-b5c9-5616-bd73-f66238f596de | note | Verification Activity - ARRB Hawkeye or
412d7379-8070-53b9-a467-53dec1c26b2a | note | Methods or Reference - NZTA T/3
a7ca3c4c-3427-5f43-82e6-64a9cfee8a8e | note | Frequency - At time of Seal Inspection
7624b646-b51f-57ab-9a11-0db722d94256 | note | Acceptance Criteria - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture
a4a7e926-04d6-5efc-98cb-281be8649653 | note | Hold / Witness Point - Witness Point
2543414f-5540-5633-933f-94b5e27783d5 | note | Records - Hawkeye Data
0f64c36d-e024-5600-a2a4-404e09bd41ec | note | Responsible Person - Sealing Contract Manager / Engineer
| checkpoint | 3 - Surface Texture - Measurement
ed320e9e-5aa0-5a3e-a6a9-b205234b6ff1 | note | Verification Activity - NZTA HSD
7b7cfdca-7dbb-56fd-a6cf-7922800cc5f7 | note | Methods or Reference - NZTA T/3
6549abc7-226c-5f50-a7ee-2255be93b0da | note | Frequency - At time of Seal Inspection
65642d1f-ecfe-50ff-934a-c6915fd1d4fb | note | Acceptance Criteria - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture
e317a46b-ad46-5628-8bd8-063daa683bd9 | note | Hold / Witness Point - Witness Point
475ca499-6980-5b17-8b0f-102c5cfee0f8 | note | Records - High Speed Data
db8477fd-9005-5c08-a19e-d49f9788b06d | note | Responsible Person - Sealing Contract Manager / Engineer
| checkpoint | 4 - Pre Seal Survey
6054e86d-39af-5c17-af2f-56ee861a7202 | note | Verification Activity - Downer Survey or MS Forms Pre Reseal Inspection
9ae8e63b-ac4c-5d9c-94b9-760e2d4b5352 | note | Methods or Reference - Downer Survey or MS Forms Pre Reseal Inspection
26475c83-67cf-5c8f-93f6-4c2c92d1eccb | note | Frequency - At time of Seal Inspection
c12a34b7-a74d-52aa-9736-b5576ddfe198 | note | Acceptance Criteria - Record & any noted issues / Client
81f33da8-a042-51a7-adba-78531e788a1b | note | Hold / Witness Point - Witness Point
b119a889-951d-5105-97dc-61db2f33c502 | note | Records - Lucidity
8c072e1a-d35a-5f6b-9978-c49736d0da60 | note | Responsible Person - Sealing Contract Manager / Engineer
| checkpoint | 5 - Construction Compliance testing
0863a61e-1c40-52f7-b933-3d09f9d79f06 | note | Frequency - 24 hours in advance of seal construction commencement
c09b6912-9f90-50bb-b7c6-d7c80ad9f6ee | note | Acceptance Criteria - Confirmation from renewals manager all testing has met requirements
049dc639-e617-5bc5-bb05-a7fe98bbb1db | note | Hold / Witness Point - Hold Point
1f47d3bf-281d-5df9-b4f0-9e228a420eec | note | Records - Email Confirmation
35c1d9d8-8231-5766-ae6e-d8c2387af9bb | note | Responsible Person - Sealing Contract Manager / Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Seal Construction
| checkpoint | 1 - Go/No Go Survey
bca26e88-6896-5edf-adf5-fd36ed05f748 | note | Verification Activity - Visual, Zeus, Iris
f7f26fa1-1cf9-5ef3-ac6b-45ae98948ae4 | note | Methods or Reference - Downer Survey Sealing Go / No Go, Road Science Zeus app & Downer Iris app
deb625d5-a6ee-5e3f-aef1-94b2f8a72037 | note | Frequency - Prior to sealing on each site
53ba1b38-58fb-5863-873b-e06beec3ff65 | note | Acceptance Criteria - Pass on Go / No Go, Marginal & discussion with Contract Manager or written approval from Rehab Manager
beb83ee0-3da5-5984-8a14-a6055749d4dc | note | Hold / Witness Point - Witness Point
31879bb6-da9b-5b0a-88a9-9bc2d0a2cd37 | note | Records - Lucidity
677c3fbc-19b3-50c0-ad44-7abede5df2dd | note | Responsible Person - Supervisor / Foreperson / QA
| checkpoint | 2 - Pavement Markings/RRPMs
463046a3-6332-5dc4-83ba-796bf26e236f | note | Verification Activity - Tagging of existing Pavement Markings, Removal of RRPMs
d94df56f-3fca-5526-8eeb-a3a52f4bec30 | note | Methods or Reference - Pavement Marking Set Out Sheet, CBP
814fecbb-1e33-5c24-ab64-2f26fd0208f7 | note | Frequency - Prior to sealing on each site
187fac4c-b001-5a07-8dc2-2bc07cb9269d | note | Acceptance Criteria - All raised pavement markers to be removed (1st & 2nd Coat Seal surfaces excluded) and existing line marking "tagged". Check for any new markings required
b29772df-1b5f-5b3c-a89f-d8ca19eeee48 | note | Hold / Witness Point - Witness Point
902dbefe-48f8-58d2-b56a-fdb1b0c8f66d | note | Records - None
05025bbf-acff-53f5-aeeb-b019491c5c88 | note | Responsible Person - Foreperson / QA
| checkpoint | 3 - Road Furniture & Sumps protected
eb22f242-5bf7-594d-8983-77eece26a63b | note | Verification Activity - Visual Inspection
c2fd0fb9-048f-510b-a629-44b8b6095476 | note | Methods or Reference - Crew Breifing Plan / Visual
ae2db8b4-3a9a-5889-863c-3e1a8da27c0f | note | Frequency - Prior to sealing on each site
e85868d2-3bc2-5a20-8a3c-28607eccdcd5 | note | Acceptance Criteria - Protect all road furniture in accordance with Crew Breifing Plan. Fabric & protect all sumps.
665c14ac-8e2e-5372-8f43-ac9c7fa9e458 | note | Hold / Witness Point - Witness Point
18a48f72-c264-5aa2-9ae4-ca778b8b81ed | note | Records - None
c2027490-11d9-5b9c-a5e1-0215a35d40fb | note | Responsible Person - Foreperson
| checkpoint | 4 - Surface Condition/Temp
f5a5f4a1-0b0c-5d74-a463-2fac7720acf5 | note | Verification Activity - Physical / Visual Inspection
01bd7a2b-377f-5b77-a8ad-9db868be5ac5 | note | Methods or Reference - Visual / NZTA T/3
910162ec-32ce-57d2-b7bf-67e76bb2ff77 | note | Frequency - Prior to sealing on each site
aa981376-f513-5b60-bccc-0e50b6b28332 | note | Acceptance Criteria - Surface area shall be dry and free from any loose chip, dust, dirt, vegetation. Temperature recorded on site prior to sealing commencing
34166aff-9c0f-5f9c-9f0d-4763587885a8 | note | Hold / Witness Point - Witness Point
10b1aa85-c671-5a1f-9f13-47fba4dbe015 | note | Records - None
e0ed8289-8561-58b9-9875-f0f99ba6785a | note | Responsible Person - Foreperson / QA
| checkpoint | 5 - Stockpiles
bad51d86-6373-55dc-9fc4-a42ab9bca83f | note | Verification Activity - Visual Inspection
37f32ab2-937d-5e62-8013-95931193c779 | note | Methods or Reference - CBP
c2c7a996-8eb0-558d-b25b-d5c905709b99 | note | Frequency - Each Stockpile
4c02514a-1c09-59f4-b9ac-4ac8d37f18a4 | note | Acceptance Criteria - Correct Source, Grade and quantity. Uniquely Identified.
0b70f602-a431-5d21-9a48-950440957a82 | note | Hold / Witness Point - Witness Point
dd23e5bf-8d44-51e2-b656-bed408d678eb | note | Records - Sealing Data Docket
c7c4a8c9-eeec-5321-a8f0-3b9b15adcc44 | note | Responsible Person - Foreperson
| checkpoint | 6 - Spraying
9ffc90e7-5936-57ca-8767-4a9ead7fc198 | note | Verification Activity - Paper Start and Finish all runs
eee19341-2ad7-5290-9597-579d57319390 | note | Methods or Reference - Spray Runs
36822b6a-9e05-5c98-b4a5-cead6cc73ae8 | note | Frequency - All Runs
4a9b844c-13d9-5b2a-950e-167e1b45f6bd | note | Acceptance Criteria - Mark out start / Finish
ba3cf6b8-2606-58e4-953a-3fdfbcadf8d6 | note | Hold / Witness Point - Witness Point
f87da80e-0748-5d43-8429-92b9f4f92848 | note | Responsible Person - Sealing Contract Engineer / QA
| checkpoint | 7 - Sealing
476ca91b-2ffb-5d8c-a0cf-d4e98a94547c | note | Verification Activity - Longitudinal Joints out side of wheel tracks
d56ad1a4-d9f7-5a7e-8dd8-9c83b0db61d1 | note | Methods or Reference - Spray Runs
e5d61f24-417e-5855-96e3-7c7ff7a89b76 | note | Frequency - All Runs
4359f1dd-24b6-5c4b-96e6-cc84fc34cf68 | note | Acceptance Criteria - Mark out lane lines by construction team
8ffe9fd2-f2aa-50c1-bd43-ccea9b2eb643 | note | Hold / Witness Point - Witness Point
3f07445d-637a-50ba-91e7-66e6dd3cbf88 | note | Responsible Person - Sealing Contract Engineer / QA
| checkpoint | 8 - Binder Application Rate
ead0f5c2-870c-510e-9826-8068a3cc84e7 | note | Verification Activity - Tank Level dips prior to and after spray run
1be6d777-7cf9-5c2c-bb32-be2864b646e1 | note | Methods or Reference - Dipstick
47dae73e-99fc-52cd-93a0-3034f11fe030 | note | Frequency - At Beginning of the day After 1st spray run of site After last spray run of site At end of tank prior to loading
2049d227-5cff-5809-a0b1-046d63e09973 | note | Acceptance Criteria - Quantities used to be within the desired tolerance of design Spray Rate
b73642c4-c0ae-5ba6-bf5a-8f89a7f9d434 | note | Hold / Witness Point - Mandatory HOLD POINT
13c5a645-e666-5276-b6f6-196e6e6c9a6d | note | Records - Spray Sheets
f84ce3d4-9971-5af3-964d-287817b1f64b | note | Responsible Person - QA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Chip Spread Rate
777b56db-3b3b-5cab-8956-4fe7ea72fa88 | note | Verification Activity - Visual
2e0239d0-2fc2-582b-8462-1dd63a3d8787 | note | Methods or Reference - Crew Briefing Plan/Visual
028ae5eb-989e-5c40-a780-e78b7c043b16 | note | Frequency - On going whilst seal being constructed
0e932287-8755-5dce-8bf3-c332e0e786f4 | note | Acceptance Criteria - Chip is applied in accordance with the appropriate coverage as specified in the Crew Briefing Plan
83b7acb4-5641-5481-9514-2623c8affb49 | note | Hold / Witness Point - Witness Point
0096e38f-ff07-59e9-82ff-a3fc9fbff7ea | note | Records - Data Docket
f3e23a70-4481-5655-922f-ff3707261478 | note | Responsible Person - QA/Foreperson
| checkpoint | 10 - Removal of Surplus Chip
49577832-d5c9-5791-9f88-b08967e63a5b | note | Verification Activity - Physical / Visual
15500140-14dc-51eb-8740-582ee5c25187 | note | Methods or Reference - Front Mounted Broom / Suction Truck, Downer Survey or MS Forms Post Seal Inspection
75881ae6-972d-5dbe-b21a-11beade9590a | note | Frequency - At conclusion of positive traffication within 48 hours
4d8fcd80-e4c9-5e55-8a6c-fe88978263fb | note | Acceptance Criteria - All sump and road furniture protection removed. Meets requirements of P/17 Table 2.
d9a1aab0-0398-5125-af55-ebb71de19d4a | note | Hold / Witness Point - Witness Point
58d042ae-4da8-5a33-990c-8ea6ebf09769 | note | Records - Post Seal Inspection
562d297e-ed14-551a-9619-b71612608589 | note | Responsible Person - Sealing Contract Engineer / QA
| section | Post Seal Construction
| checkpoint | 1 - Post Seal Traffic Management
244ce85d-fbba-5024-9846-bddd853817bd | note | Verification Activity - Physical / Visual
dbcc3c7c-91b7-55db-98c5-df6ec47389ef | note | Methods or Reference - As per TMP
5039ed17-12d1-5474-b02d-4d310838160e | note | Frequency - Full length and width of carriageway
a3b82f8c-d0c8-58d8-9b94-4e24dd609387 | note | Acceptance Criteria - Minimum of 48 hours under normal traffic flow. If rain forecast within 48 hours, traffication recommences until clear weather window of at least 48 hours
71e5db67-c562-50fe-8665-dd628c906f8d | note | Hold / Witness Point - Hold Point
dee97c17-2077-507b-976d-5abac7b2545a | note | Records - Zeus or suitable recorded weather data
3351725b-5018-5821-8a00-05dc56fbfa44 | note | Responsible Person - Sealing Contract Manager / Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Post Seal Inspection
19529b50-9753-5c38-82c5-9d79a1bfb01f | note | Verification Activity - On Site Visual
9a2f8c38-c468-57ae-8fff-9a6c342f7859 | note | Methods or Reference - Lucidity Post Seal Inpsection
8429ca27-78bd-513c-a810-21408c2d3b60 | note | Frequency - After sealing is complete
f6b50d8d-bd73-5fa8-a810-94b9bf2091a2 | note | Acceptance Criteria - Engineers requirements. Any defects identified, repairs programmed and costs estimated
bce1dd4e-62d7-555b-9282-a1afb8b177a7 | note | Hold / Witness Point - Witness Point
21845532-91bf-5fee-9ec5-fb8b3980044c | note | Records - Post Seal Inpsection
fd5ce92b-ef45-5b38-a697-baa8769bd2f6 | note | Responsible Person - Sealing Contract Engineer / Manager / QA
| checkpoint | 3 - Asbuilts and RAMM data
2074b931-7750-5889-a8cf-f8c7fda4fe35 | note | Verification Activity - RAMM Update Sheet
61547549-c397-5b32-af88-7365b50f42cf | note | Methods or Reference - RAMM Database
9f0947aa-9ff7-54e0-a8a2-7a93f85ee5db | note | Frequency - After sealing is complete
0f90bb80-6222-5e87-baab-e396bf03817d | note | Acceptance Criteria - RAMM update sheet 100% complete and accurate, note data provided for RAMM update to be uploaded by others. As Built Drawing Complete.
afedc4fa-85a1-5b4f-9af4-d22c193cc451 | note | Hold / Witness Point - Witness Point
893491fc-5cb9-502b-a279-b7ebe81ebbf7 | note | Records - As built information / RAMM Update Sheet
28e609c3-0912-5412-b4e3-86391093b747 | note | Responsible Person - Sealing Contract Manager/ QA/QE
| checkpoint | Quality Record Close Out:
317778d0-32ac-53f6-8c18-fbc44dec9644 | textbox | Name:
c945fbe5-2849-55a9-aa57-62966428ad60 | date | Date:
| signoff | Add Signature
| checklist | ITP - Foam Bitumen Stabilisation - FBS operation Rev 2 | itp | ITP - Foam Bitumen Stabilisation - FBS operation | 4216c747-4808-4716-ab13-9261e9574f94
| section | 3.0. BITUMEN STABILISATION OPERATION
| checkpoint | 3.01 - Production Plan
18f80137-e68d-5f5c-8e3c-ca8dd218f646 | note | Detail of Activity / Test - Plan showing cut lines and sequencing of works
63f62e1a-54de-5249-8342-5bfc793549b4 | note | Action (Hold, Monitor, Witness) - M
e515b63a-06f1-5a2a-819a-21de548e0da6 | note | Minimum Test Frequency - Prior to each section
8ba08741-6723-598e-8a1d-6729427c1e68 | note | Inspection / Test method - Daily Report
b7e509d1-a886-5812-a8f7-42034fc3db88 | note | Acceptance Criteria - Points covered in NZTA B/5
a7590362-aa7b-5de6-948e-b44b1989843c | note | Record documents (QCP - Quality Control Portal) - Daily Production Plan
32c71017-990a-5bf5-9de7-a9d04804cf76 | note | Responsibility - Stabilising Contractor
4bf3096c-f23b-548c-846d-4e08d38db8c2 | note | Eng. Rep - I
09355c40-6154-535d-a995-37d28d98a948 | note | Contractor - R
| checkpoint | 3.02 - Weather conditions
bf1c6484-4b5e-599c-aff6-4722bd752707 | note | Detail of Activity / Test - Material behind stabiliser
cdf1b233-2a1d-5c1a-b9c7-dd1bcb655c44 | note | Action (Hold, Monitor, Witness) - M
d838f44e-9a10-5cb5-b979-fd669fb2bab8 | note | Minimum Test Frequency - Prior to spreading
98a45d6b-e562-5ecd-8240-2dbf96931769 | note | Inspection / Test method - Measurement
4d534a52-1dc6-57b6-950e-bad9018476bc | note | Acceptance Criteria - Material after stabilisation: BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C
8786e057-2936-5946-b99d-128744a666e4 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
c1c867d9-57ac-5da8-8439-1f5e91066b83 | note | Responsibility - Stabilsing Contractor
04bdeb91-8204-5121-a78c-9fd9e57f7678 | note | Eng. Rep - I
c8c8c6d2-2d9a-5978-87e0-392a05228f96 | note | Contractor - R
| checkpoint | 3.03 - Weather conditions
9255db96-2df0-5fc4-919a-6424bfc78c63 | note | Detail of Activity / Test - Wind
f22f8524-43dd-5f8f-b417-136e8ffa5aab | note | Action (Hold, Monitor, Witness) - M
f6234824-4928-5d75-aedf-7c99101bfe98 | note | Minimum Test Frequency - Prior to spreading cement or lime
e262af5f-9d8d-5b2d-ada6-ebcb322dca50 | note | Inspection / Test method - Local weather stations
5e3fbcac-d352-59fe-b537-6d9b4966cef5 | note | Acceptance Criteria - Wind speed < 25 km/hr
1d78ceb9-6e31-5c53-89ff-cdbb31a7db45 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
5aef50e8-cbb7-5a16-a362-1d1db4d9b89d | note | Responsibility - Stabilsing Contractor
5c6b9215-5943-5ccd-acb7-57ba5020552b | note | Eng. Rep - I
28355262-de83-5a0d-b325-40df4aacdeeb | note | Contractor - R
| checkpoint | 3.04 - Weather conditions
3b794877-a84b-54cf-86fd-87a89688ddbd | note | Detail of Activity / Test - Rain
26b4d3f9-9704-5640-809b-7c837883e26a | note | Action (Hold, Monitor, Witness) - M
e4dd5ad0-7a3f-58a2-9707-2d02a96332e5 | note | Minimum Test Frequency - Prior to spreading cement or lime
7bf939e6-39e4-53a9-8246-e21f9ccc898f | note | Inspection / Test method - Local weather stations
c62bca29-645b-569f-96ba-3bd3961f6e0e | note | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
26a6ec8d-2d6c-5ffa-96a7-65dd831857a3 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
c3084073-454a-5df3-b6c1-ed5878fb6d32 | note | Responsibility - Stabilsing Contractor
21c67299-4991-5c32-b249-dc198fba966f | note | Eng. Rep - I
2399a71f-aec1-5630-b5c3-98c8fe71bbb5 | note | Contractor - R
| checkpoint | 3.05 - Stabilising Agents
ac012d0f-bb6d-5169-83a2-b0b2697666db | note | Detail of Activity / Test - Lime (if applicable - check PI delete otherwise)
e1443abc-af96-511e-be52-d2836221060e | note | Action (Hold, Monitor, Witness) - M
77224abf-986a-5b72-b5bf-f69505300d0e | note | Minimum Test Frequency - Per Batch
f26257c9-178c-5f01-9457-a072cf4425f9 | note | Inspection / Test method - TNZ M/15
0a0e3602-94e2-5d9e-b763-12297219ae7d | note | Acceptance Criteria - Conform to Specification
7574459d-092f-5a22-ba4d-29708eee3e85 | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
0e0304e3-d493-5a75-ad79-5b12cdcdabcb | note | Responsibility - Stabilising Contractor
e8659cf5-25dc-50ec-bedb-f450048094f6 | note | Eng. Rep - I
86a9969f-f5cc-534a-ba0c-fae22a39a84d | note | Contractor - R
| checkpoint | 3.06 - Stabilising Agents
57ef5a5f-ab5c-588e-b27b-80f51be2dc01 | note | Detail of Activity / Test - Cement, GP
9096ced6-64c6-5b6f-9575-25131ca6e6b9 | note | Action (Hold, Monitor, Witness) - M
25a6395a-c35a-5f75-9680-e5b9a3cdd15c | note | Minimum Test Frequency - Per Batch
27010c02-9c84-5dab-9661-64ebadcbf27b | note | Inspection / Test method - NZS 3122
eb97da68-39c0-50b3-afbc-b6d59a4d8224 | note | Acceptance Criteria - Conform to Specification
0fdc453b-3b12-5ee2-a5bd-eec4e5b79cdd | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
33bd8979-8bcf-5fd9-bbd1-75a043292645 | note | Responsibility - Stabilising Contractor
a8b69bd1-2bae-5440-9692-db15d5c5e051 | note | Eng. Rep - I
332ae894-bb5b-5ac5-bc24-8357d5082de6 | note | Contractor - R
| checkpoint | 3.07 - Stabilising Agents
4788fa12-5a60-5fb7-a6d2-064b9fcfcbe3 | note | Detail of Activity / Test - Bitumen (130/150)
7fb8e18c-949c-51ad-8d22-e78b78c8ec45 | note | Action (Hold, Monitor, Witness) - M
163cb6c7-e495-565a-9481-8c9ad5beed16 | note | Minimum Test Frequency - Per Batch
7ba0e458-8ec0-5f01-bea9-97d47ef6f5e1 | note | Inspection / Test method - M/1
523e76e3-a4db-5cdd-b1ed-0e226b960d90 | note | Acceptance Criteria - Conform to Specification
f45f8321-7e38-5e03-b1bb-fdbba563ac7b | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
c44ee264-6945-5ad7-a465-b15c9b41e725 | note | Responsibility - Stabilising Contractor
ec1d330a-2c28-501f-a77f-8c317478100a | note | Eng. Rep - I
2e1f689d-e116-534a-8de0-dbf7c83486db | note | Contractor - R
| checkpoint | 3.08 - Spreading of powdered stabilising agent (Cement / Lime)
ebdb1c69-d01e-542a-af29-cd00411caf01 | note | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
665587d1-b012-5647-8432-1169cb2afaf7 | note | Action (Hold, Monitor, Witness) - M
8533d432-e1b2-5c15-b878-ef3a8320e208 | note | Minimum Test Frequency - every 400 m2, every 150m for a 2.4m width
9cef32df-05e5-5425-9134-7f9fd809a187 | note | Inspection / Test method - Weigh mat or tray
aee8a673-c0dc-59b5-b3f8-bb8c5cbb09b1 | note | Acceptance Criteria - ± 0.5kg/m2 of specified rate
83e4c2fc-c068-5a10-b192-d0ac196c3388 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
89ceb06f-fee8-5bb4-86c0-307e7d9a6b2e | note | Responsibility - Stabilising Contractor
29cd1974-c2da-5922-baa2-88a4cbc5bac9 | note | Eng. Rep - I
c7f4d48b-4d9a-5019-b34b-d5df5e927170 | note | Contractor - R
| checkpoint | 3.09 - Spreading of powdered stabilising agent (Cement / Lime)
721b9694-e710-5062-a80a-2c1a80b7e893 | note | Detail of Activity / Test - Compare area spread with weight used for each spreader load
39bdd341-c01e-55b9-afeb-4829d9188ed0 | note | Action (Hold, Monitor, Witness) - M
898403a8-f1ab-5ede-b6b3-be8830b07c14 | note | Minimum Test Frequency - On-going measurement by computer/load cells
cd0ea3a3-dc21-5660-94b5-e5700441918e | note | Inspection / Test method - Measurement each run
eb69fde7-e6dd-5ded-9fa7-6a546d982673 | note | Acceptance Criteria - ± 2.5% of specified rate
ce11192f-f779-5859-8e34-89eb156ba096 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
f007fd1b-4641-5084-ae1a-e95076be6a89 | note | Responsibility - Stabilising Contractor
9dae86dc-7376-5177-8d7f-5f509797a55f | note | Eng. Rep - I
58ed924f-d949-5ef1-8aa7-c5bbfe1fdaff | note | Contractor - R
| checkpoint | 3.10 - Injection of bituminous stabilising agent (FBS or BE)
940f8bac-e707-5c09-921d-bfc2384abc8c | note | Detail of Activity / Test - Flow meter and operator's display readings
cbc6c9a2-98ec-5d4a-9fcc-c8405a95e72c | note | Action (Hold, Monitor, Witness) - M
ba0a952b-8b1e-5900-b5d8-c96c58f6f379 | note | Minimum Test Frequency - Continous monitoring by the operator and the grounds person
612965e8-1945-55f3-bbbe-1bd8f3e3f032 | note | Inspection / Test method - Visual display reading
f1bae931-f2bb-5e7a-8290-8f5e3f8b6929 | note | Acceptance Criteria - ± 5% of specified rate
3dae57ad-629a-57de-8d75-41d373c95675 | note | Record documents (QCP - Quality Control Portal) - N/A
330630e0-7f68-5251-b816-28e36f0f854e | note | Responsibility - Stabilising Contractor
b54dc74d-7779-5a9c-9438-9cc5cc5bf1b8 | note | Eng. Rep - I
b6370a95-48c9-50fd-bbcb-9b46560931af | note | Contractor - R
| checkpoint | 3.11 - Injection of bituminous stabilising agent (FBS or BE)
9320143c-0558-5fc9-b7ce-999549f52ac5 | note | Detail of Activity / Test - Compare tonnes used (from the stabiiser's PCU) with the measured area
cdaa59eb-ff58-5585-9e21-f93edc3474f3 | note | Action (Hold, Monitor, Witness) - M
160259bd-88e0-5a5d-8e1b-0cd57f49e9ad | note | Minimum Test Frequency - Record usage from PCU at the end of each run
dcc6f9b6-b9aa-5d01-80cf-c58c86534daf | note | Inspection / Test method - Record readings at the end of each run
4ab0a6de-ddff-53b9-9f23-8157df54b886 | note | Acceptance Criteria - ± 3% of specified rate
1dfd94d0-9320-5f6a-80c8-ff72b3a184e8 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
ec833f0c-252d-5576-bb29-ceee63c7e41d | note | Responsibility - Stabilising Contractor
4cf0a763-56b8-51d8-ad8c-2948b0ef7a15 | note | Eng. Rep - I
8347c761-20a3-5dbe-8303-aee196d54d13 | note | Contractor - R
| checkpoint | 3.12 - Injection of bituminous stabilising agent (FBS or BE)
2dd6d971-5a56-5978-950f-dca62e4477fa | note | Detail of Activity / Test - Compare tonnes used (from delivery docket) with measured area
16513ca9-3a36-5c1c-ad9f-fc4e6ea26e51 | note | Action (Hold, Monitor, Witness) - M
72ff0555-6dcd-5757-938b-2bba4c86928e | note | Minimum Test Frequency - For each bitumen tanker load
907e172b-62c4-5a34-90f8-8f3027a798d7 | note | Inspection / Test method - Dip bitumen tanker before and after
02bd6f9e-f851-5293-bb90-ff3fdddcdb03 | note | Acceptance Criteria - ± 2.5% of specified rate
3918916f-6cd1-5ae7-bcea-bb3743346dac | note | Record documents (QCP - Quality Control Portal) - Daily work Log
a4612f46-baf9-5726-9e84-32d33c073036 | note | Responsibility - Stabilising Contractor
69da0d7f-161a-5500-aa0d-84e1220a9e45 | note | Eng. Rep - I
53afbbac-fe02-58e7-aee1-0862280ba0aa | note | Contractor - R
| checkpoint | 3.13 - Injection & Mixing of Water
9164c521-fc99-5ef6-918b-143af100a014 | note | Detail of Activity / Test - In-situ Stabilisation process
eeb9939d-2e3e-5bd3-80b4-ce465bcff4b6 | note | Action (Hold, Monitor, Witness) - M
9077b394-9922-5c18-8188-434f7faee5bc | note | Minimum Test Frequency - On-going visual assessment
85f12cce-8a44-5d29-9303-933b7c6baad0 | note | Inspection / Test method - Visual and hand squeeze test
1d7be9ec-bc16-57fc-b2ae-e020b7a190d2 | note | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
a2d59421-dee9-58d9-b74d-466dcc535607 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
081cdd09-0532-5be3-ad5f-145b1451c3e7 | note | Responsibility - Stabilising Contractor
b4fc1109-2dd0-51ae-8355-6b154724a956 | note | Eng. Rep - I
40df0563-2e8c-5cf5-a35c-280d40772c0a | note | Contractor - R
| checkpoint | 3.14 - Depth of stabilisation
430efee4-866e-5c94-95ff-c2b89438033a | note | Detail of Activity / Test - Depth of stabilisation
e73d659d-a765-5b9f-8431-4c3482cd6067 | note | Action (Hold, Monitor, Witness) - M
318b605b-00c5-533d-bfa9-9abfdfc91ac2 | note | Minimum Test Frequency - Every 200m
dd1e137a-4bad-5474-8907-e3e2c2988ead | note | Inspection / Test method - Measurement
b0642379-449f-5949-89b9-b42debbc1ba7 | note | Acceptance Criteria - +15mm / -5mm from specified depth
43a3ff64-86db-5034-a083-78cb508d0002 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
7f4b1954-163c-51fd-91da-4363d2284609 | note | Responsibility - Stabilising Contractor
4a236261-8177-5f5a-b552-b774d90ab1ae | note | Eng. Rep - I
50774958-11af-5df4-b8cf-f823fb6197aa | note | Contractor - R
| checkpoint | 3.15 - FBS material
46ddfceb-e2dc-5285-bef1-5d42bbff8e5f | note | Detail of Activity / Test - Stabilised material strength - ITS
aba067f2-10d9-5920-9874-263c29977d4a | note | Action (Hold, Monitor, Witness) - M
9eddfadb-2bf8-55e1-b56d-864742308805 | note | Minimum Test Frequency - 3 soaked ITS + 3 dry ITS per Lot or when the material changes
9302794f-4594-5093-a1dc-020f08e22296 | note | Inspection / Test method - NZTA T/19N: 2020
243da002-7e36-5e35-88d7-d6a5361beda8 | note | Acceptance Criteria - Testing at 1mm/min:
a12c0c0a-c8ef-5ae4-8c5d-234cd28ade6b | note | – BSM Dry ITS: 150 kPa to 400 kPa
ad0ef415-126e-5b68-9b35-f156f5ecbda3 | note | – BSM Soaked ITS: 120 kPa to 350 kPa
3e92d676-8338-58c8-afeb-d3b2f94af728 | note | ○ Testing at 50.8mm/min:
0c75f157-1187-5bda-a8fe-e2dc77d687e3 | note | – BSM Dry ITS: 180 kPa to 450 kPa
dcd870d0-d701-54aa-8c7e-f95f2be36e84 | note | – BSM Soaked ITS: 150 kPa to 420 kPa
fd85fda4-7d45-5544-8430-b728d11602c2 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
bbb9674e-69f1-5c83-9126-4d55f4da1ef0 | note | Responsibility - Stabilising Contractor
6bfcaeac-1fab-5138-b203-6cffa1ba0cfe | note | Project Specific Notes / Instructions - ITS briquettes to be produced on site if travel time to lab > 30 minutes.
3194d33e-6103-5de6-b860-6d56d9eb56bb | note | Designer - I
44d1196c-c8e6-5363-9096-2a74ac38df9a | note | Eng. Rep - A
85966a30-6d1b-5449-a6ef-c17c4500b91f | note | Contractor - R
| checkpoint | 3.16 - Compaction
94df43cc-3457-5f64-9a9c-9b7c901de1dc | note | Detail of Activity / Test - Plateau Density Test
97c1bfc2-fe8d-5f3e-b0f0-5efdc97cc65d | note | Action (Hold, Monitor, Witness) - H
ce2ba0b4-32ec-5c6f-a084-6e613a485634 | note | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
619a2e82-8961-53ac-b044-885cf1ea6e39 | note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
8cfac5bb-cd9f-54ca-94db-717ae8f9debe | note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
fda27670-4486-58fe-9106-9305fa135f94 | note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed.
46fabe8f-2536-512b-b496-67468c67d8df | note | Responsibility - Stabilising Contractor
b38976f3-013d-5de3-a279-68d125e3211c | note | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
aff8f298-738e-59f2-8515-b4da5176d8d3 | note | Designer - I
337ccb98-0115-561f-8b36-affafc83a401 | note | Eng. Rep - A
bfa39a51-afb0-59a1-9454-0fa170473a11 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.17 - Compaction
895ffb88-e626-5b90-ae93-29cb6d7b2e5f | note | Detail of Activity / Test - Maximum Dry Density
dd87a4f8-5552-563b-b16b-c77ebc9dbefa | note | Action (Hold, Monitor, Witness) - M
135ee69a-60d5-5818-b118-62e6b8e39b42 | note | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
8f33c499-ffe7-508b-a7c4-d1db3d998c16 | note | Inspection / Test method - NZS 4402.4.1.3
6a862b84-251b-5649-8fa7-97c714e2aa62 | note | Acceptance Criteria - For analysis of DoC
2c1efbd0-5101-5e99-8226-3234f2dd5ee1 | note | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squeeze test on site
1c711be7-0074-50c3-96dd-6cc129d50e92 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
04f668bf-4e54-5c14-9dce-09bba300c67a | note | Responsibility - Stabilising Contractor
1f04e8eb-0cf1-5d60-be40-ad0335c75f2a | note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
2def514a-7ca6-5f8d-a5f4-e3a14069e43a | note | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
4b5f73eb-1e11-5297-b682-04741336cb04 | note | Designer - I
8eff42b5-fbe8-58db-bb8b-9fad6c1d48ab | note | Eng. Rep - A
602aa6ca-e822-5916-b1fe-be624525db29 | note | Contractor - R
| checkpoint | 3.18 - Compaction
ea7c2f8b-85da-5cae-9a2b-bed429949bcb | note | Detail of Activity / Test - Degree of Compaction (DoC)
a06659eb-2a21-5e7d-a1ea-5224ac7e6dc6 | note | Action (Hold, Monitor, Witness) - H
d2be0f71-255f-5330-a37e-665929025a42 | note | Minimum Test Frequency - 5 per 1,000m2
24996e1d-2b67-5194-baa0-e8735f9c7167 | note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
51d15499-b0f0-5b14-bcce-1578834a3321 | note | Acceptance Criteria - Average DoC ≥ 98%, Minimum DoC ≥ 95%
3c856d1e-d8a6-58b2-b2e3-48939a227795 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
cb326d81-f1c7-5b33-a680-19e6a606be28 | note | Responsibility - Stabilising Contractor
a31fbe3f-f80c-5432-8e27-9459b5a67caa | note | Designer - I
204779c9-1ab2-509b-8cdd-8f485e24b9e4 | note | Eng. Rep - A
845e8c38-421b-52ea-b999-778ed3d695b5 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.19 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
279a365b-eb80-5950-8b33-18400b76f6bb | note | Detail of Activity / Test - Clegg Impact Value
9ccbea11-2515-51b6-b136-0310bc9c1773 | note | Action (Hold, Monitor, Witness) - H
0d398692-c5db-5cb8-89e8-8dad889b3e49 | note | Minimum Test Frequency - 5 per 1000m2
2f454144-5322-5840-8b1a-9e6308c59667 | note | Acceptance Criteria - CIV ≥ 50
bd73bf20-b534-5666-9df9-a13d92368c17 | note | Record documents (QCP - Quality Control Portal) - CIV form - ConQA
3a1d5b3b-5040-5666-a36e-5dc27cdd0564 | note | Responsibility - Stabilising Contractor
9322bdb9-2f67-5cac-9cfd-5df2e99c2af9 | note | Designer - I
87b0d417-32cb-5566-9a04-cb4b936b8bd9 | note | Eng. Rep - A
8907282d-39fe-5149-8657-f7b421b9e6a5 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.20 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
076f6efb-1864-5aaa-b943-39404e4dc85c | note | Detail of Activity / Test - Degree of Saturation, DOS
7513f3ed-f9ac-5c1e-a55c-b08777cdd7a9 | note | Action (Hold, Monitor, Witness) - M
b12a852c-f85c-564a-8140-54251915d391 | note | Minimum Test Frequency - 5 per 1000m2
4bc976ad-567d-58db-9d01-ce89e5c7c727 | note | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
770a66a2-4b4e-5ade-a53a-49fa580e620c | note | Acceptance Criteria - aim for DOS ≤ 80%
c038888e-0ba7-524f-90e7-10f82f6f0348 | note | Record documents (QCP - Quality Control Portal) - IANZ report
1e36d244-7c1f-5908-b258-d0c17461c8e4 | note | Responsibility - Contractor
025eca51-65aa-5d1e-b0a3-249a203ec500 | note | Project Specific Notes / Instructions - Report only
83003806-b015-58b5-92f8-9896692fb120 | note | Designer - I
5dd4b705-ce13-554f-9a3c-dec1e8853a3e | note | Eng. Rep - A
b71769bc-6331-566c-bb51-a56302930a33 | note | Contractor - R
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
9f467806-3159-5af2-b225-c579ce379a68 | textbox | Contractor's Rep Name:
9175d3c1-8949-512c-87ba-fbc4f3ac627a | textbox | Engineer's Rep. Name:
6d81d04d-d8d1-5ae3-8178-e344ab519238 | date | Date:
| signoff | Add Signature
| checklist | ITP - Foam Bitumen Stabilisation - Material testing Rev 2 | itp | ITP - Foam Bitumen Stabilisation - Material testing | 6881fdb7-6c08-4ad8-90bd-1b9c4ffd247f
| section | 1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING / DESIGN and DRAWINGS
| checkpoint | 1.01 - AP40 Basecourse Aggregates used for overlay (if applicable)
2be96bb7-6c0c-5926-ac1b-ca0c880debba | note | Notes:
6b60cde3-a076-52c2-82cb-df72348a8c74 | note | ○ H = Hold point up to approval of Optimisation Testing
b8d9dc26-c68a-59c8-b140-84cb741e195a | note | ○ M = Monitor during production
44cb94e2-5deb-581d-9fdf-7decd2b94643 | note | Detail of Activity / Test - Crushing Resistance
a67ddada-b7d7-59f0-a839-8eb6538b623a | note | Action (Hold, Monitor, Witness) - H
abe27d99-e116-52e8-8500-ca71c2c91d9a | note | Minimum Test Frequency - 1 per 10,000 m3
1004da4d-d78a-5f86-a8b7-167c3ea963db | note | Inspection / Test method - NZS4407:3.10
835c398d-d1f2-5be2-972e-393135dfe6d8 | note | Acceptance Criteria - < 10% passing 2.36mm sieve at 130kN
bdd2553f-368c-5c42-90cb-7da4b2340459 | note | Record documents (QCP - Quality Control Portal) - IANZ report
358f516b-6ef8-56fc-a67e-819b6ce0c527 | note | Responsibility - Contractor
af8d10bb-b98c-5920-bf44-ba976690ee0b | note | Designer - A
8f75bd8f-5beb-5835-8727-0dcad67ca5d7 | note | Eng. Rep - I
dff76d2c-7bc4-5932-87ac-3a15feddf510 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.02 - AP40 Basecourse Aggregates used for overlay (if applicable)
4ffc1667-558d-5388-9a19-c25608ca297a | note | Notes:
5208cf25-d715-5648-b791-86dbcaf71eac | note | ○ H = Hold point up to approval of Optimisation Testing
3a938b9d-195f-5759-9869-f515bac7f3ea | note | ○ M = Monitor during production
9ac6ef2d-185e-5a2a-9c4e-4e0bfe5f9a86 | note | Detail of Activity / Test - Weathering Quality Index
831d9244-bb0d-5074-97b5-5b8ba2437ef0 | note | Action (Hold, Monitor, Witness) - H
36bacb34-47e9-506d-ba36-ea0b6a0c7e1f | note | Minimum Test Frequency - 1 per 10,000 m3
1ea0bfbc-c0bd-51d3-927a-712a8ff6869e | note | Inspection / Test method - NZS4407:3.11
8ff42178-5bad-5583-8443-e087b12c236c | note | Acceptance Criteria - AA, AB, AC, BA, BB, CA
e6ce47ce-3640-5558-b8f8-c90f901c4b1c | note | Record documents (QCP - Quality Control Portal) - IANZ Report
9f301995-af5d-599b-af26-6391a3c266d1 | note | Responsibility - Contractor
221c93a4-bdf9-5933-a11f-1992e3cc3311 | note | Designer - A
b7b87438-fb95-5e7c-aef0-894e66d5b883 | note | Eng. Rep - I
7630fb3e-7c51-5c6f-9373-4d8af63dd6e9 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.03 - AP40 Basecourse Aggregates used for overlay (if applicable)
7cef6196-93cb-5f10-85df-2deb45cb78cd | note | Notes:
41fa4727-9d24-56c1-b832-be570278357d | note | ○ H = Hold point up to approval of Optimisation Testing
3c555323-b2d0-5dbe-99c3-1390e979a593 | note | ○ M = Monitor during production
0c225179-17fe-572b-bd00-5aa340f45ce6 | note | Detail of Activity / Test - Calfornia Bearing Ratio (CBR)
3f7d1555-d69b-5bce-a03c-3ad6330875fd | note | Action (Hold, Monitor, Witness) - H
e5432fe0-047f-5ee2-9369-f3331185303c | note | Minimum Test Frequency - 1 per 10,000 m3
f95a00e1-b939-5c44-8fc2-43512b8cb33f | note | Inspection / Test method - NZS4402:4.1.3, NZS4407:3.15
aaf1f638-37d5-52f9-9d05-6c3727fca140 | note | Acceptance Criteria - Compaceted using NZ Vibe Hammer, 4-day soaked CBR ≥ 80%
839a0cbd-512c-5aad-8a6c-a24d2001a0ea | note | Record documents (QCP - Quality Control Portal) - IANZ Report
1fedaadb-0da6-54c7-9f88-564f09fcad4c | note | Responsibility - Contractor
d0919354-e816-596d-9c14-30a0531d1316 | note | Designer - A
f1c7cfb3-4f9b-518f-93e0-df4835143364 | note | Eng. Rep - I
06b309dc-9592-56ff-bacf-833d4cc24188 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.04 - AP40 Basecourse Aggregates used for overlay (if applicable)
29fcdce0-c389-5938-b623-1485fbcbba1e | note | Notes:
c4a5d39d-1721-5084-8ae0-791b9f28fe02 | note | ○ H = Hold point up to approval of Optimisation Testing
dc8f0e98-f62f-5ce8-ab9b-860ef99ece95 | note | ○ M = Monitor during production
61a25e50-cf99-5f27-be64-bb170fd19e4f | note | Detail of Activity / Test - Quality of Fines, either PI or SE or CI
a79f631f-322f-5335-b815-87d8d8e8918b | note | Action (Hold, Monitor, Witness) - H
82269d80-64b8-576f-8a68-b08f83f06e69 | note | Minimum Test Frequency - 1 per 1,000 m3
6dfe5250-37a9-5a4c-8629-42d16901527f | note | Inspection / Test method - NZS4407:3.4 - PI, NZS4407:3.5 - CI
c8042915-cf0c-5795-8a82-e189f07b399f | note | Acceptance Criteria - PI ≤ 5, CI ≤ 3
f5d8e078-c06b-5ec4-8238-7e433a310a72 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
fdfae6bf-3aeb-5d04-a63d-727e80ee607f | note | Responsibility - Contractor
7479c61b-713f-517c-abf5-761e0c5db5a1 | note | Project Specific Notes / Instructions - NZTA M04: 2024
ebe7da54-3c7a-5966-936d-b20cc790048e | note | ○ AP40 - Class 2
48518c5f-8864-5ac2-a828-d00caab28b47 | note | ○ PI and CI applies
36dd4c22-363b-59bf-a5cc-63d880ce3898 | note | Designer - A
50322dbc-73d3-5fb5-848d-1d329bf73e05 | note | Eng. Rep - I
32d3bbe7-7e78-523e-8559-ec0722529793 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.05 - AP40 Basecourse Aggregates used for overlay (if applicable)
0c8e92c7-7ed4-5e55-a6b1-c094cbfd809f | note | Notes:
5670b73e-8239-5ed4-975d-67de0012093e | note | ○ H = Hold point up to approval of Optimisation Testing
55f8240c-d2f9-5723-87b6-cc644a7b53f6 | note | ○ M = Monitor during production
ba53d257-936c-5200-9d7f-47ba0c1ae8cd | note | Detail of Activity / Test - Broken Faces Content
ff907705-dc70-5ab8-9370-466ce9e07338 | note | Action (Hold, Monitor, Witness) - H
61e0549e-a006-5b26-8501-fda74e9e538c | note | Minimum Test Frequency - 1 per 1,000 m3
68257f0d-71d4-5a88-b80e-3aabe1d9cce6 | note | Inspection / Test method - NZS4407:3.14
7d2908e5-c9cb-5b64-b3e9-333ee71491ef | note | Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm
1b96b731-05a8-5032-97b2-201415efc3b0 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
b691630f-ad4a-5d35-8a1b-39fa1398989a | note | Responsibility - Contractor
36088737-964a-5328-a9fb-81c5ee27000e | note | Project Specific Notes / Instructions - Waived if aggregate is from crushed hard rock quarry
e39af9a5-5302-5b14-85e4-3c63e757e768 | note | Designer - A
7608746f-7cfc-51fe-b885-4f448dccf5dc | note | Eng. Rep - I
2f4ff281-89e9-53bf-9ffc-bfb352ad1ffe | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.06 - AP40 Basecourse Aggregates used for overlay (if applicable)
330c3d66-c883-57af-98a4-2d261d85644a | note | Notes:
1cac7bad-f3a4-55fc-89c0-668808964e8b | note | ○ H = Hold point up to approval of Optimisation Testing
6d32ce48-c6f8-5c7c-82ca-0b3cb2dbc346 | note | ○ M = Monitor during production
3360b542-c969-5a28-9f98-80bd0c1e68a0 | note | Detail of Activity / Test - Particle Size Distribution
b8815777-d2c8-5db3-abb5-57a9320d1306 | note | Action (Hold, Monitor, Witness) - H
968e708b-f84e-569a-9a61-3d609440e0e1 | note | Minimum Test Frequency - 1 per 1,000 m3
e15ec36a-d3cd-5293-b4a8-8564744661dd | note | Inspection / Test method - NZS4407:3.8.1
aaa5a23e-c000-5d21-acc0-f98f5a181e30 | note | Acceptance Criteria - NZTA M04:2024-Class 2
1c59c933-0ade-5e3b-878d-10e94d0c2c4f | note | ○ Class 2 in Table 12 for PSD
9bf9f95d-3d07-57f6-914f-767b0adb961a | note | ○ Table 13 for shape control
df88dd2a-a737-5ca3-a67b-171d6c5abb55 | note | Record documents (QCP - Quality Control Portal) - IANZ report
d4c03406-3f39-5ed4-bbdc-b09b08d7f07c | note | Responsibility - Contractor
98119672-b744-502f-b9c1-c400e8fd798f | note | Designer - A
0bdab5ea-76d5-50de-8520-17b36a370269 | note | Eng. Rep - I
101f5f10-b192-5239-b8eb-8e8a82e01502 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.07 - Optimisation of Stabilising Agent(s)
c59cb70f-a542-5d0f-ac29-4bde8dc67a53 | note | Detail of Activity / Test - Blend Particle Size Distribution
e40a9819-80f4-5c76-bc58-8fc8f4f07a40 | note | Action (Hold, Monitor, Witness) - H
a76fc138-9412-5945-8caf-01a3e81813b9 | note | Minimum Test Frequency - 1 per 1,000 m3
3c7cfd20-f8e8-52fc-bc2f-f7388661b91b | note | Inspection / Test method - NZS4407:3.8.1
5d9d3997-c568-5166-8d5d-115b1ea8df4c | note | Acceptance Criteria - Check if average of existing (from TPs) and any overlay will meet the ideal FBS / BE grading.
6ed90226-d0d2-51c2-9269-886ed53b0c95 | note | Record documents (QCP - Quality Control Portal) - Report using IANZ Reports for AP40 and TP PSDs
ce2e495a-de60-5618-9cb8-b09f40f19297 | note | Responsibility - Designer
a6bea5a2-5454-56ec-ada1-96031f36b355 | note | Project Specific Notes / Instructions - Designer to advise if "average" blend is acceptable.
af2c082e-4053-5eab-9356-9c3c75d88c3c | note | Designer - R
cd0edee6-a0be-521a-a4d7-1a19b180149c | note | Eng. Rep - A
c81e4e7b-2b17-5be5-8e37-94bbfe9136a5 | note | Contractor - I
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.08 - Optimisation of Stabilising Agent(s)
b8e9cf8c-b981-546b-bf0a-e0e00d0d04e4 | note | Detail of Activity / Test - Indirect Tensile Strength, ITS
d3a8fcd3-444d-5d5d-bd54-bb0e37dc4f51 | note | Action (Hold, Monitor, Witness) - H
3c804a95-cc5c-540a-8881-6de58d0482aa | note | Minimum Test Frequency - 1 Optimisation test per aggregate type
74cbca82-d97a-5a9e-9ed3-3a454bd13b3d | note | Inspection / Test method - NZTA T/19: 2020
d0ab84cd-8747-5223-8a47-6edef0ef086e | note | Acceptance Criteria - Testing at 1mm/min:
6b36fd4d-306e-5241-9486-0be75b963fa1 | note | – BSM Dry ITS: 175 kPa to 400 kPa
d80eeca7-92f0-58bb-b447-2cfd4bff2890 | note | – BSM Soaked ITS: 150 kPa to 350 kPa
4be42e74-757e-51cb-ad97-62f97ba94f74 | note | ○ Testing at 50.8mm/min:
1aa46efc-7ec9-5e20-930e-dcaf9776fe55 | note | – BSM Dry ITS: 210 kPa to 480 kPa
9f9249ad-db95-5dcf-bfb1-65d999187cae | note | – BSM Soaked ITS: 180 kPa to 450 kPa
8a27c126-f71d-554c-b0ba-e7aa44571343 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
37996d42-76c0-5a62-b6b9-4aa8f47d0d61 | note | Responsibility - Designer
61007cb8-3a85-57c9-8445-0c9fac31e3dc | note | Project Specific Notes / Instructions - Designer to advise on binder content(s)
8a7d9996-331d-560b-931f-1ff888c72da0 | note | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
da00eef4-6cd9-5740-8650-6434740c164c | note | Designer - R
b6b33a87-f49c-55cf-b58d-d8dee93fdf8c | note | Eng. Rep - A
ccdbf693-802a-52fa-aa75-dad9369ec8b3 | note | Contractor - I
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.09 - Optimisation of Stabilising Agent(s)
a43eccaf-f3b5-5d54-b3aa-1ccc10dab72a | note | Detail of Activity / Test - Unconfined Compressive Strength, UCS
5163e712-a786-51e3-8069-17a32cc042ea | note | Action (Hold, Monitor, Witness) - H
d5033425-d998-5db1-b0a2-91fcc6156d5d | note | Minimum Test Frequency - 1 Optimisation test per aggregate type
1a3d7d3f-eba9-526a-8968-99f14d19ccae | note | Inspection / Test method - CCNZ / NPTG / CETANZ Industry Guide
dd908091-e0ec-5756-8afa-58542f7f37a8 | note | Acceptance Criteria - UCS limits set by the design engineeer
d10f92e6-d951-5ffd-89f1-c2eca2332b5d | note | Record documents (QCP - Quality Control Portal) - IANZ Report
32f5c099-7e9f-5928-beaf-b35549621023 | note | Responsibility - Designer
ef8b71cf-6267-503d-86cf-eaa6b44ac946 | note | Project Specific Notes / Instructions - Designer to advise on binder content(s)
d44724e7-6631-5725-b128-f939d46f2d8e | note | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
00c77a89-1741-5e69-a3dd-73078bdc2a38 | note | Designer - R
710e85aa-f817-508b-88f6-bccf0ac0a3bc | note | Eng. Rep - A
d32b622a-c529-583a-9105-bc0b874eab64 | note | Contractor - I
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.10 - Optimisation of Stabilising Agent(s)
5102cd68-90d2-5f9c-a82c-5880b9f96ac9 | note | Detail of Activity / Test - Modified Maximum Dry Density
2696df96-953a-5fd3-8a6b-698ca7ec44ff | note | Action (Hold, Monitor, Witness) - H
3cabd14b-f360-537d-b6f2-2ce15f9bc54e | note | Minimum Test Frequency - At Optimised Binder selection
9a915276-6433-5acc-ac28-a72f5029b9db | note | Inspection / Test method - NZS 4402.4.1.3
aaa84404-cd28-52ec-b0af-cb3219e22549 | note | Acceptance Criteria - To determine target density
beb493d0-25c7-5ada-ae3f-0d2a808d7a2d | note | Record documents (QCP - Quality Control Portal) - IANZ Report
ca37069a-6583-5821-a55e-4a2005c6c0bb | note | Responsibility - Designer
c2bd7448-1fc6-5d5e-aae3-f798e9e64b2f | note | Project Specific Notes / Instructions - Required before Stabilisation comences
2ee64c4e-f5ed-5bb8-87b1-d7b60069103c | note | Designer - R
7e0c8a3b-73f2-58af-9bc4-ba5b86cb8f11 | note | Eng. Rep - A
d32f49b2-7cf0-5a4f-8cad-2563797a760e | note | Contractor - I
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.11 - Stabilising Agents
c4ce7296-c36c-4013-8ca6-002309b6fa93 | note | Detail of Activity / Test - Lime (if applicable - check PI delete otherwise)
bad54209-3657-4c90-9f62-6c873e6964ec | note | Action (Hold, Monitor, Witness) - M
7b85f721-201d-4b25-a3ab-08d2516b25e2 | note | Minimum Test Frequency - Per Batch
36aa5dab-10d1-524c-b47f-ead486899240 | note | Inspection / Test method - TNZ M/15
935bf754-ffa7-50de-a0aa-f74c9b262f4b | note | Acceptance Criteria - Conform to Specification
8f195ba8-32b1-56e2-be03-c2c27ff002a2 | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
82922af0-569f-5f43-a6fe-cef54b8a1b91 | note | Responsibility - Stabilising Contractor
a76a6524-eac5-5436-b47c-b9a7e3b7f33a | note | Eng. Rep - I
32662f39-395e-54a3-8ca6-79d0083de5cd | note | Contractor - R
| checkpoint | 1.12 - Stabilising Agents
2a71928f-f6e8-5aa8-9b44-ad2173ea3bb0 | note | Detail of Activity / Test - Cement, GP
d14576ee-0953-574d-ad25-e8bbd702dd95 | note | Action (Hold, Monitor, Witness) - M
017160d4-1215-5c55-966c-27cacdbc9704 | note | Minimum Test Frequency - Per Batch
72f5dd1d-8efd-5df2-a878-55524fbd1ff3 | note | Inspection / Test method - NZS 3122
2e1bff71-7117-50de-add8-0d432f2ffcef | note | Acceptance Criteria - Conform to Specification
41134f69-b911-59aa-a51b-9b4534e3d04f | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
6d8e47c0-160b-509e-b789-a817012ce8c9 | note | Responsibility - Stabilising Contractor
c32b6bcd-6d75-5b8b-ab42-6354f04a80cb | note | Eng. Rep - I
923dd80c-15f1-548a-b020-9c1ad26295ac | note | Contractor - R
| checkpoint | 1.13 - Stabilising Agents
7c9e023a-aa4f-5b49-97c6-887c60fac9d3 | note | Detail of Activity / Test - Bitumen (130/150)
9f0f6b93-0b33-5bd8-8265-74934fb4fbaa | note | Action (Hold, Monitor, Witness) - M
cf385a56-b6a1-5519-9811-3a852321ae28 | note | Minimum Test Frequency - Per Batch
aeb405e1-9120-5281-bc9a-f8f4ca477fba | note | Inspection / Test method - M/1
d7293de5-c7ae-5eee-9a27-5942037a7774 | note | Acceptance Criteria - Conform to Specification
1e7f7990-1964-5e67-86f0-0d8d47ec9061 | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
f13a01f1-800b-56d3-b6de-353e4d3de7c9 | note | Responsibility - Stabilising Contractor
0fca182b-80f7-5cf5-94d3-7577addc0b85 | note | Eng. Rep - I
b772df7e-da45-5f7a-8d2f-8d4b397402e3 | note | Contractor - R
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
eafcf5ad-e777-5b4a-b855-eb62fa796eb8 | textbox | Contractor's Rep Name:
28925e9f-edf1-5c44-b410-ed24b68961b4 | textbox | Engineer's Rep. Name:
9d58d381-e766-5776-9b99-cbc21798a670 | date | Date:
| signoff | Add Signature
| checklist | ITP - Foam Bitumen Stabilisation - Post FBS testing Rev 2 | itp | ITP - Foam Bitumen Stabilisation - Post FBS testing | ce1d9b1e-9d89-47f8-9128-6b6367389dfb
| section | 4.0. Testing and Sgnoff
| checkpoint | 4.01 - Finished Pavement
96c1be4c-60c1-5af3-b10e-3ab1676e1599 | note | Detail of Activity / Test - Crossfall
303ee57f-7e45-5ed3-b9af-e69ff1d41927 | note | Action (Hold, Monitor, Witness) - H
e427087e-3806-5b1c-9a5d-696fdc1a6d8a | note | Minimum Test Frequency - every 20m
cd26945e-6c83-5332-9c4c-a4838a29ddac | note | Inspection / Test method - Measurement
d783f69d-f1d9-5fa4-bb5c-07d2402ba2b3 | note | Acceptance Criteria - ± 0.5% of specified crossfall measure 2m apart
6f3b24d5-e97c-5132-a9c9-b049e9d8f82f | note | Record documents (QCP - Quality Control Portal) - Survey
f99fdda2-79d3-5b01-94b9-579976d2a95a | note | Responsibility - Stabilising Contractor
1af74a00-ece8-5248-92d0-32e6ac4951fe | note | Eng. Rep - A
c288a246-2924-55f4-95db-dfabd4a429b5 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.02 - Finished Pavement
fb854560-f217-52d6-98bc-32e4bcaaf74f | note | Detail of Activity / Test - Stabilised width
6656ef11-04a7-5799-a0e0-84f9bd6e32fd | note | Action (Hold, Monitor, Witness) - H
be250ba6-823a-5bfd-9178-52044238cf01 | note | Minimum Test Frequency - 1 every 20m
0e59090d-6e7f-530d-bdae-0dd73ade6a95 | note | Inspection / Test method - Measurement
0a254045-5eaf-5241-a10c-375498b3e064 | note | Acceptance Criteria - -20mm, +100mm
7090634a-fd50-50b8-bab0-1381ebc1db90 | note | Record documents (QCP - Quality Control Portal) - Survey
df2a1356-65af-5d6f-8693-2fc9168375fd | note | Responsibility - Stabilising Contractor
5d696d34-0140-5877-87a0-5115d0fd463e | note | Eng. Rep - A
b2e1d640-6df6-5fda-a61e-72cc41705be7 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.03 - Finished Pavement
689d31fa-bccd-5568-825a-0ae6c72bc43c | note | Detail of Activity / Test - Surface Shape
737b2d76-73da-5158-86dd-102d50866d30 | note | Action (Hold, Monitor, Witness) - H
42e8bdea-ec00-56a0-a1ad-2f5be8abdc86 | note | Minimum Test Frequency - every 20m
1fe05709-b8e2-5a0d-80aa-4f5d5ba95b5e | note | Inspection / Test method - Measurement
6f9d14b2-46f4-50a8-af67-f8ccbb08df5d | note | Acceptance Criteria - < 10mm using 3m straight edge
3a0cd3d7-d49b-51c7-993b-605c78daad95 | note | Record documents (QCP - Quality Control Portal) - Survey
ae285b78-4acb-5d7f-8a07-512b1b10c016 | note | Responsibility - Stabilising Contractor
5a1bcd6d-e926-575b-9cc2-3691eab78352 | note | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
de955122-cb8e-510e-b716-0a18c6c9d246 | note | Eng. Rep - A
5dba1616-d55b-59d7-ab96-8cc6f7917e80 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.04 - Finished Pavement
0305029f-b78f-5ca7-9764-0e97885dc83c | note | Detail of Activity / Test - Surface Levels
8aa1d9c0-9856-5df4-8538-bdfbe4f21ed6 | note | Action (Hold, Monitor, Witness) - H
759311f6-505c-5d77-96a6-1a6fe0697e9e | note | Minimum Test Frequency - every 20m
6878214a-d5fb-5076-9855-6e8cf72854e7 | note | Inspection / Test method - Measurement
7fce1301-1f40-51fe-a9e1-fbd8e8bcb9e2 | note | Acceptance Criteria - -5mm, +15mm
b64790f4-39d8-58bd-9edb-0e75a248f2aa | note | Record documents (QCP - Quality Control Portal) - Survey
6a648ff2-1886-5207-84a3-9241ef3d88ac | note | Responsibility - Stabilising Contractor
7b0581f2-8f3e-561d-846c-5ddcbd87db02 | note | Eng. Rep - A
65b376ea-59cc-5737-82e8-a2b775df8de2 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.05 - Finished Pavement
689509f4-e511-5e09-ac74-9d2f562b6e7e | note | Detail of Activity / Test - Surface Finish
d6b1ee2c-44be-51c8-b99f-f3c7f784dc91 | note | Action (Hold, Monitor, Witness) - H
b9b7073b-f7a1-5587-ad70-46d0bde008ca | note | Minimum Test Frequency - Per Lot
7a1944e0-55bc-5927-98d3-2a902006222a | note | Inspection / Test method - Visual
0dd6c5ef-9088-5d24-a462-201fc044e19d | note | Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate
7be3d1f7-24f2-521e-b391-f315b69acacd | note | 2. Smaller aggregate held in place by fine material
eb34b168-bb56-57b7-a5df-618af16be619 | note | 3. matrix does not displace under normal trafficking and/or sweeping
7e34500f-4af4-5b88-b4d7-f0feaff4ef18 | note | Record documents (QCP - Quality Control Portal) - Survey
813c4773-95ab-5454-9ab4-2187fb2fc493 | note | Responsibility - Stabilising Contractor
0127748e-d36e-5a17-b62e-65ae51c4dabd | note | Project Specific Notes / Instructions - ER to be present at pre-seal inspection
c93da31d-8d3a-50d8-80ca-7a6e81a8df9b | note | Eng. Rep - A
a96b2e46-0455-5146-9e8b-5e388fe6e83b | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.06 - Finished Pavement
9e3201ae-a942-5a4a-bcdc-cc5db18ab0e5 | note | Detail of Activity / Test - Roughness
a4dac419-ac24-55c2-91bb-a00aa183ee37 | note | Action (Hold, Monitor, Witness) - H
969d6d55-4d71-57a3-8fab-fa4a935e7bd6 | note | Minimum Test Frequency - Before Sealing
5f431c6e-7e0a-516a-88c4-d43fd57e4bf2 | note | Inspection / Test method - TNZ TM 7003 v1
64247a25-5e34-5e9d-b060-1b068b66c40c | note | Acceptance Criteria - 100m rolling average ≤ 75 counts/km
9ead2cea-2a9d-5541-85b9-d9a319465190 | note | Record documents (QCP - Quality Control Portal) - Test Certificate
90feccc1-bc12-58b2-a483-3c45bdb5c05a | note | Responsibility - Contractor
404d4612-81e0-5ada-a4f4-804699b11957 | note | Eng. Rep - A
8d42ca14-67de-5863-81ff-3359bc06b541 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.07 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
f609e5f4-9f21-55c8-b5e6-639809885834 | note | Detail of Activity / Test - Clegg Impact Value
92e7565d-1fd8-5053-847c-d54c76d98e2e | note | Action (Hold, Monitor, Witness) - H
bf7182e8-0fc7-5ff4-98d1-8c309ffec07e | note | Minimum Test Frequency - 5 per 1000m2
73f414f4-2e9b-577c-aa4b-ac38e12dfc88 | note | Acceptance Criteria - CIV ≥ 50
55d07aa6-d51e-5913-b811-c769595ff291 | note | Record documents (QCP - Quality Control Portal) - CIV form - ConQA
253faca2-8fa0-5aa4-9231-f9c540774c71 | note | Responsibility - Stabilising Contractor
67f393de-03f0-5dc9-8598-ed1458f07db0 | note | Designer - I
5879cfc6-f54d-52c5-b49d-f3d183065cde | note | Eng. Rep - A
0f952d34-1784-50da-aa2b-075ba33b4205 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.08 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
769bf83c-afac-5518-b734-3e1645cca1b6 | note | Detail of Activity / Test - Degree of Saturation, DOS
78924db4-f33a-55d2-a996-12e95566b576 | note | Action (Hold, Monitor, Witness) - M
d9a4e6a0-2ae7-52ef-a2e4-cc560cb00456 | note | Minimum Test Frequency - 5 per 1000m2
34e02569-7033-530d-8cce-7fabf520a176 | note | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
694b0f07-07f5-5775-9203-3a9a312c270f | note | Acceptance Criteria - aim for DOS ≤ 80%
2e4568b6-fd36-5651-b47b-a2f6f3de5434 | note | Record documents (QCP - Quality Control Portal) - IANZ report
ca99d6c1-6f9e-5151-82f9-a787a0209250 | note | Responsibility - Contractor
b21f3d7c-8b55-53ae-95a3-dfe29ae193c8 | note | Project Specific Notes / Instructions - Report only
15b4fda8-ff06-574c-8fcf-0c65172d6d85 | note | Designer - I
98d6f31a-0228-5574-863f-64f0dba48ad7 | note | Eng. Rep - A
87c8315e-cfe7-5c49-8f09-e73acd65a55b | note | Contractor - R
| checkpoint | 4.09 - Pavement Layer Signoff
59db984f-18fc-5bbb-8c93-c40efc20b576 | note | Detail of Activity / Test - Assessment of all test results for conformity
3ff8f330-7dd1-5612-97cd-f61cb88f8986 | note | Action (Hold, Monitor, Witness) - H
24c5f4fa-69a4-5b90-9f12-ec06abc3a504 | note | Minimum Test Frequency - Each Lot
b08eb498-07a5-559b-b196-aece4f631eb7 | note | Inspection / Test method - Site Inspection
95857bec-9882-52ee-ae71-eecd084b9079 | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
40ea1a6d-5e3b-5a16-bf7c-5fb88d319f6c | note | Record documents (QCP - Quality Control Portal) - NCR
ec6aacfb-7a40-5e84-945f-4617db91e072 | note | Responsibility - Engineers Representative
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
c70b3a1f-4316-5bc1-b043-c02bb00899ab | textbox | Contractor's Rep Name:
d0b10919-6ee0-51a3-9ab1-5ce99b85cec7 | textbox | Engineer's Rep. Name:
89b0e04a-acb2-5690-9d09-1ed07e8437e9 | date | Date:
| signoff | Add Signature
| checklist | ITP - Foam Bitumen Stabilisation - Pre Treatments Rev 2 | itp | ITP - Foam Bitumen Stabilisation - Pre Treatments | 7dbd1865-b28c-4130-812d-582981eecfe7
| section | 2.0. BEFORE BITUMEN STABILISATION STARTS
| checkpoint | 2.01 - Setout section
9986ba90-c19e-53d7-b6d6-543561667f35 | note | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
d42cc76d-8c2c-5f25-9fdb-b5a43a1d8d6a | note | Action (Hold, Monitor, Witness) - H
50fd8f32-62cf-51f6-ac17-c53fbd7cbc91 | note | Minimum Test Frequency - Prior to each section
04e2fb85-c450-58d6-b7f8-ba471b0d3495 | note | Inspection / Test method - Survey
d59bd00e-cbe4-5658-8e55-bc7191d452b2 | note | Acceptance Criteria - Document existing furniture
aebf6bc9-949e-510f-b1b0-f77b7dcd0b8e | note | Record documents (QCP - Quality Control Portal) - Electronic survey files
c2209223-fd6f-5f44-bf2b-643faf798da6 | note | Responsibility - Contractor
b35cdc80-4ade-57cf-be0b-80128ce338e5 | note | Eng. Rep - I
62925157-f9bd-5bd5-a326-d480d3964f1b | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.02 - Pre-hoe, shape and proof roll
e86205a7-3a5e-544d-af31-274cae7c83d3 | note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
f225cb08-9cb7-55b8-bb68-3f285d265540 | note | Action (Hold, Monitor, Witness) - H
67e775ab-3697-554b-b93b-f667e659c874 | note | Minimum Test Frequency - Prior to stabilisation per section
2a715791-f618-5cf4-8e44-9adb1da04d7d | note | Inspection / Test method - Use grader's machine control and inspect shape
75aa2875-41ba-5425-a3bb-96b3f8541b25 | note | Record documents (QCP - Quality Control Portal) - N/A
336b9167-5e70-5cfb-8da8-3cd9ebbed80a | note | Responsibility - Stabilising Contractor
baf45511-898a-5660-b3d4-b5bde1ce1ab1 | note | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
79cf8e45-e680-530a-acf3-fc6b8913857d | note | Eng. Rep - A
8bdaa2e4-5a90-5288-9f3c-f2b88eb85969 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.03 - Pre-hoe, shape and proof roll
67c09e5e-9f7c-52f5-98c5-36988159ee07 | note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
a17a2f57-8250-5e9a-b9ee-ac5b932b2df6 | note | Action (Hold, Monitor, Witness) - H
e7e1b973-5f2a-5cd1-acac-b3548f626313 | note | Minimum Test Frequency - Prior to stabilisation per section
a95a23a8-7cac-51b7-b6f9-b216b30c979a | note | Inspection / Test method - Visual check or Vibratory Roller's response meter
ffa7385d-50db-511e-8b9f-ac59b0ab7d5b | note | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
eeddcd5e-3b16-5d6d-930f-e74bec2e70b2 | note | Responsibility - Stabiliisng Contractor
5df9f9d4-d87f-5c6e-8aaa-0be95a4e724c | note | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
54bd17e1-1b4d-5bfa-8423-e5bac4204f8b | note | Eng. Rep - A
a81a7ab6-3421-5636-a0a6-8e93a855df89 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.04 - Overlay and check levels
c3a51bfa-7a87-5b34-aa78-c70890ac5204 | note | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
0dedecaa-21cd-544e-99ed-5d5975f77bd0 | note | Action (Hold, Monitor, Witness) - H
b8165694-2c15-5b3d-8eaf-48aa667ab772 | note | Minimum Test Frequency - Prior to stabilisation per section
b9f35ebb-3655-5dde-98f0-4125773fa528 | note | Inspection / Test method - Survey
ec63e4c3-2d36-5cd6-b5ea-fbc5b713aee2 | note | Acceptance Criteria - As per NZTA Z/16
12bfcd31-7c74-5183-8aff-28f67e4b0602 | note | Record documents (QCP - Quality Control Portal) - Check with Grader and visual inspection
dcb2dd0e-2ac6-5a20-b5e6-ede5308ee183 | note | Responsibility - Stabilising Contractor with Main Contractor
bb4cca72-5c2c-5035-8201-71bc1f7e659c | note | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to):
ce01f28a-f4a2-5de6-ad2d-32e02eb1f21e | note | ○ overlay aggregate quality / consistency
b936cdfe-c3f4-5cff-9f95-0ee6d44746c3 | note | ○ moisture content
e871f201-2d14-5b09-9f6e-82eea378ac1d | note | ○ any concerns with shape and tie in
5dcc2e8a-2d26-576d-842a-48702c0e13cc | note | ○ etc.
070cd3b7-1635-521c-846e-ff3a7653b6ac | note | Eng. Rep - I
96baf954-914a-57c5-9e8b-313ff02458f3 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.05 - Production Plan
76f59c41-311e-581a-8b1b-dd5c9ed7ea45 | note | Detail of Activity / Test - Plan showing cut lines and sequencing of works
e7906efa-ddc0-52da-878e-f63410b4190c | note | Action (Hold, Monitor, Witness) - M
62ea7800-71a8-55f1-bdc0-08b361da46d4 | note | Minimum Test Frequency - Prior to each section
0b8692db-a34a-58c0-87eb-7217b37eb3d3 | note | Inspection / Test method - Daily Report
4a287c83-bd50-5cb0-a027-002df82957b9 | note | Acceptance Criteria - Points covered in NZTA B/5
55727680-c289-50b5-b90e-07c662c7358e | note | Record documents (QCP - Quality Control Portal) - Daily Production Plan
427b4c64-6026-5795-81a5-166b003a0572 | note | Responsibility - Stabilising Contractor
6de6d099-8cf1-55e7-a226-d8c7d249080f | note | Eng. Rep - I
ad938dbf-33c6-5ee1-bc7c-3f2580b9f3aa | note | Contractor - R
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
dec22408-23ba-52f0-ac47-94c4efe99291 | textbox | Contractor's Rep Name:
5297358a-d7fd-53d9-a3f4-60f28620cbc5 | textbox | Engineer's Rep. Name:
f587f3d4-b7fa-5105-bf17-8e59fbf7dd05 | date | Date:
| signoff | Add Signature
| checklist | ITP - Kerb and Channel Rev 0 | itp | ITP - Kerb and Channel | 923c7ed0-3b8e-4515-ae41-9ae903e76b87
| section | 1.0. AGGREGATE AND CONCRETE TESTING
| checkpoint | 1.01 - Concrete
c28dba65-dbc6-5e52-89c0-9fb7ea64c649 | note | Detail of Activity / Test - Concrete Supply
5f12d43f-3dff-5c08-bfa1-2342d2edc07d | note | Action (Hold, Monitor, Witness) - H
2351f1e3-82c8-5225-b768-59d4b42c8b08 | note | Minimum Test Frequency - 1 Test per material per source
7641424e-9196-54bf-821f-27c62b241939 | note | Inspection / Test method - NZS4407:3.10
056e1e39-2a06-5e9d-afc0-c56e3c60cdef | note | Acceptance Criteria - 20Mpa Minmum Strength after 28 Day
3041d1b1-8824-5b4a-baf8-3578504b58e5 | note | Record documents (QCP - Quality Control Portal) - IANZ report
27ebaebf-6d5f-5ff9-94f2-58e217253a84 | note | Responsibility - Contractor
e07f0d09-1ff5-5105-863d-c81c012b1b2d | note | Designer - A
29226a34-2ce8-5c8b-a1ce-fc2ae13a409e | note | Eng. Rep / NZTA - I
0eaa195f-a12a-5d36-83eb-424df7bd7c58 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.02 - NZTA M04
f4ab533c-1954-53c5-93d0-3e6b74e0b758 | note | Detail of Activity / Test - Crushing Resistance
cb00372a-cfba-5ff6-b291-ef5171be99fe | note | Minimum Test Frequency - 1 Test per material per source
4db60482-e034-57aa-87a0-2d97e68bc313 | note | Inspection / Test method - NZS4407:2.4.7
4ce8848b-6a40-53c9-81e2-8936d6eedafd | note | Acceptance Criteria - > 130KN
52179bef-1b1e-5132-9c57-b15233c67c6c | note | Record documents (QCP - Quality Control Portal) - IANZ report
5e81b707-77b3-5400-9d04-f3c5edf1fec3 | note | Responsibility - Contractor
cca007ec-b3ed-5851-99f0-e840665257ca | note | Designer - A
bd5b413a-d3ea-5e5e-89a4-2f809ff2a745 | note | Eng. Rep / NZTA - I
bb322f82-90fa-55ef-8ed0-51e3a4677e57 | note | Contractor - R
| checkpoint | 1.03 - NZTA M04
98e8f66f-9c88-5d84-9e9e-2bc26eca8cc8 | note | Detail of Activity / Test - Particle size distribution
a55fab7b-aa80-513a-9d44-f56d17d327d4 | note | Action (Hold, Monitor, Witness) - H
06612d8b-7922-5bae-88ec-ad70233077ed | note | Minimum Test Frequency - 1 Test per material per source
0d0e10a4-140b-52af-828a-f6897761ea5f | note | Inspection / Test method - NZS4407:2.4.7
e2e280fb-e315-526c-bdec-77cc1e93288f | note | Acceptance Criteria - As per NZTA M04 Specfication
632af8fd-4fa4-53ef-bbc9-2c80ac647cc3 | note | Record documents (QCP - Quality Control Portal) - IANZ report
53c4cc40-2b74-50d5-911b-c5f09e6cc645 | note | Responsibility - Contractor
de152650-e28c-5911-8c0c-e1595f940ff2 | note | Designer - A
b29ecef5-52be-521d-be40-843ff5ba9fa2 | note | Eng. Rep / NZTA - I
58b11fa7-b2aa-52fd-9d11-05f30f5cae34 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| section | 2.0. CONSTUCTION
| checkpoint | 2.01 - Earthworks
31780bbb-abb0-5b51-90fa-3992953f49dc | note | Detail of Activity / Test - Cut to Waste Existing Kerb and Channel
5c3124cd-c33b-53e9-baba-cc5de0eab82c | note | Action (Hold, Monitor, Witness) - M
f2e00d79-2fc3-58a1-81cd-f8633e8164b6 | note | Minimum Test Frequency - As per IFC drawings
b4521da3-d58e-5acf-9c69-99dac85808bd | note | Inspection / Test method - Visual / Photo
532fe4a3-0840-58a0-a9fb-eb9220469b0e | note | Acceptance Criteria - Site Engineers Approval
0baab63a-7ccf-5fd9-a3d6-f58ff3959e41 | note | Record documents (QCP - Quality Control Portal) - Checksheet
633c9b59-f2a0-5d05-821b-b731176e5989 | note | Responsibility - Contractor
09ac1f10-e8dc-5aed-9f14-64540d73d20a | note | Designer - A
3bbe3dff-ba77-540e-baf7-a40ed238e4f0 | note | Eng. Rep / NZTA - I
7b9487b4-a878-504f-ac73-3ae61da7047c | note | Contractor - R
| checkpoint | 2.02 - Prepare Subgrade
5152414b-b2f5-5232-b128-3b60c79cc8a6 | note | Detail of Activity / Test - Subgrade further compacted or excavate the unsuitable material and replace
6b333cae-6cb0-5dfb-a6ec-3486575f3146 | note | Action (Hold, Monitor, Witness) - M
d6d09cd5-c181-512c-9fe4-3f816cfc57d7 | note | Minimum Test Frequency - Test Every 10m
ad8c76ae-aaa5-52d3-8590-a71eafb7d211 | note | Inspection / Test method - Visual / Photo
8e4deab2-8dbb-52ae-8967-31f7318b0489 | note | Acceptance Criteria - Clegg Result >15
24729b58-04b7-566a-bbaa-d475abf12fb0 | note | Record documents (QCP - Quality Control Portal) - Checksheet
5553241d-5988-57f0-b520-facad70fd49d | note | Responsibility - Contractor
3c677786-259a-5ccc-acd9-dae2add4874a | note | Designer - A
44c7348c-8f4a-57a8-9fcb-e8e9de5964b0 | note | Eng. Rep / NZTA - I
270b20e4-c90e-56c2-9f35-d60b3f5c5ac8 | note | Contractor - R
| checkpoint | 2.03 - M4 Palcement
e930e4e7-e60b-5cdd-8dd6-7929e36f0b00 | note | Detail of Activity / Test - Compacted layer of GAP40 as required to adjust height of new K&C shall be placed over subgrade. (75mm Min)
67fbe963-46c0-5eac-9bba-de301fe7e56a | note | Action (Hold, Monitor, Witness) - H
5c98f86e-3ab6-5605-8418-05ec76a996bf | note | Minimum Test Frequency - Test Every 10m
c2b78627-cee3-51d2-bae7-71b3a040416c | note | Inspection / Test method - Clegg Test
7c94625a-28cd-5827-b209-cc2d6a66d064 | note | Acceptance Criteria - Clegg Result >30
bb54384a-3abe-5caf-8003-c7c2e176967f | note | Record documents (QCP - Quality Control Portal) - Checksheet
056043cf-c2eb-50dc-9a87-687092a36ae2 | note | Responsibility - Contractor
12147659-47fd-5fa9-befb-756659d510dd | note | Designer - I
ba2ef4ea-4e67-5430-b9df-9d75bf1aa80f | note | Eng. Rep / NZTA - A
423d42b5-d442-5ed0-9323-f883a49633f9 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.04 - Kerb and Channel Placement, Line and Level
331465c0-e040-5992-b3df-50d1cba9972a | note | Detail of Activity / Test - Construction of Kerb as per profile setout in IFC drawing
6c244b7a-4746-56ef-bb36-0bf6ad4eae3e | note | Action (Hold, Monitor, Witness) - M
ce4d77bb-f258-53fc-a5a9-4b59a2d43635 | note | Minimum Test Frequency - Throughout the activity
9d0cf89d-6b16-5084-8b61-220d5c3d7738 | note | Inspection / Test method - Meausre off Survey Pegs
c30b0585-385d-53f5-ba92-dd8db5b35cb5 | note | Acceptance Criteria - Check Sheet of Survey Pegs Versus Actual
8328c7b2-928b-5eb9-8adc-9f9339a43ad9 | note | Record documents (QCP - Quality Control Portal) - Checksheet
5ff24f96-f738-5815-8681-baf77732bfe6 | note | Responsibility - Contractor
ad9fd77f-9315-5780-875c-f33472bee601 | note | Designer - A
dfde453d-1cc5-5129-b72d-d52850109bf0 | note | Eng. Rep / NZTA - I
1d8957da-0904-56c3-a938-229dbd7ea404 | note | Contractor - R
| checkpoint | 2.05 - Contraction/Expansion Joints
5163d854-182e-5029-906e-78cdccf48483 | note | Detail of Activity / Test - Maximum spacing of 3m and minimum 50mm deep
172215c3-8d26-5308-9a2d-b79507a4df41 | note | Action (Hold, Monitor, Witness) - M
5cfaa435-fb95-535c-8220-8df1fceee4e8 | note | Minimum Test Frequency - Once
f5723d9d-a969-5a31-a22e-4d89e055789a | note | Inspection / Test method - Visual / Photo
f691f8a6-c050-53bf-9b1a-48994da3eb9b | note | Acceptance Criteria - Measure Cut Spacings
79232ae0-6bfd-50c2-977c-a13c231a483d | note | Record documents (QCP - Quality Control Portal) - Checksheet
2f07e8da-b154-5d4c-bcf2-3d0a32b8002f | note | Responsibility - Contractor
b1a8bf03-b862-5b66-86bd-c2e2167fa507 | note | Designer - A
98425e34-65fc-5ea1-94c0-50e9794bf192 | note | Eng. Rep / NZTA - I
775220d6-84d8-506a-a55a-600ea569039d | note | Contractor - R
| checkpoint | 2.06 - Curing of Concrete
d0f86cdf-a10f-5ff4-a961-bd3fcc055cad | note | Detail of Activity / Test - Curing period shall not be less than 1 day OR 36 hours
2ced8da0-95cc-56bf-a8fa-e1435a3b3f28 | note | Action (Hold, Monitor, Witness) - M
db7433eb-0cfa-5107-91b4-6cfcc2b67e7f | note | Minimum Test Frequency - Throughout the activity
bacb5928-9a52-5ac5-a141-a3c7342dc032 | note | Inspection / Test method - Visual / Photo
e0745b69-e3ef-5376-8521-91709ed8326b | note | Acceptance Criteria - Visual Inspection
4e93f544-166f-568e-815f-b931cb93e4af | note | Record documents (QCP - Quality Control Portal) - Checksheet
4fff75df-2ca5-55ab-a253-ca2e12eac5ec | note | Responsibility - Contractor
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
def521a5-19bc-57be-92d7-dbc032333c2a | textbox | Contractor's Rep Name:
2553d783-fc64-52ee-8c82-d2fb5be12e4f | textbox | Engineer's Rep. Name:
5264cd35-dfb2-525b-ab33-0067722a9d78 | date | Date:
| signoff | Add Signature
| checklist | ITP - Shoulder Construction Rev 0 | itp | ITP - Shoulder Construction | 25d21760-671c-46ff-a05b-ba49fc8158d4
| section | 1.0. AGGREGATE ACCEPTANCE TESTING
| checkpoint | 1.01 - AP65
35e57379-9b88-5f0d-9726-151f6267832c | note | Detail of Activity / Test - Crushing Resistance
1096744a-15aa-58d7-9ab1-70159ef03235 | note | Action (Hold, Monitor, Witness) - H
3938bc9e-a39d-5cdb-af61-f6c4fce3a908 | note | Minimum Test Frequency - 1 Test per material per source
3bba8581-9c0e-59c3-b17e-e937f33b9142 | note | Inspection / Test method - NZS4407:3.10
a6b737df-58e0-5384-b75c-d4d5dbd36ef0 | note | Acceptance Criteria - > 100KN
bcc8e6aa-3581-5054-aca3-69e9e553df1f | note | Record documents (QCP - Quality Control Portal) - IANZ report
8009b0da-dce5-5c67-a2e7-9c953693f0c6 | note | Responsibility - Contractor
3cb7bf7d-2863-556a-8d96-f63466479884 | note | Designer - A
837a181b-9571-5a55-9d08-15c1d16fa5a8 | note | Eng. Rep / NZTA - I
194c03c2-1e67-5464-aad4-ccfd2f18bd34 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.02 - AP65
3bb4ff76-e5df-5843-8bc5-3022912db289 | note | Detail of Activity / Test - Particle size distribution
ba2bae6a-93bb-5a10-8afb-93b8ffc8ed9b | note | Action (Hold, Monitor, Witness) - H
efe53eee-29c5-5973-abb1-a1969d5b31bb | note | Minimum Test Frequency - 1 Test per material per source
20042b9f-023f-58b6-bd2b-9f7a0bfaf07f | note | Inspection / Test method - NZS4407:3.8.1
17313f64-7cf6-51de-bec0-98fe0d434bf5 | note | Acceptance Criteria - As per NZTA M03 Specfication
5055d394-8d14-5ed8-9a56-d9c44a8b1dfb | note | Record documents (QCP - Quality Control Portal) - IANZ report
bc6c2611-62e0-5bb0-ba69-1173fdf5215e | note | Responsibility - Contractor
821cdb63-90de-50bf-ad5c-d92b82eed4fa | note | Designer - A
44f573e8-85d9-5866-9efd-10953d3c183c | note | Eng. Rep / NZTA - I
346523aa-14c1-5b38-b0c3-b2ac5b005b3a | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.03 - NZTA M04
68820bbd-afd5-5cad-880e-795f725f4a2d | note | Detail of Activity / Test - Crushing Resistance
ba456ba0-f434-5faf-b396-ae6d48bb8808 | note | Minimum Test Frequency - 1 Test per material per source
537f8eb0-6d6b-52f2-8ea4-05826d635919 | note | Inspection / Test method - NZS4407:2.4.7
d77e25f7-90b5-5865-8bb8-e14bcb2b52a9 | note | Acceptance Criteria - > 130KN
311a69ef-e279-5279-a017-a2079a2ebb5d | note | Record documents (QCP - Quality Control Portal) - IANZ report
bba1042d-6ada-5cef-8f7d-8cab188e7f9a | note | Responsibility - Contractor
8068d621-c464-5a6f-95fc-9cdfe52caa2c | note | Designer - A
7a9f4a90-b0d5-58e2-ab09-fbc6f5ceca12 | note | Eng. Rep / NZTA - I
0d816ef7-8056-50e8-ad1f-7498d6a46b79 | note | Contractor - R
| checkpoint | 1.04 - NZTA M04
f734e22d-647b-5fa2-831a-28dda86e6f9a | note | Detail of Activity / Test - Particle size distribution
2b48542e-5737-55b6-b565-9ed53fef28c6 | note | Action (Hold, Monitor, Witness) - H
c9d4f870-b5b8-558b-baf7-0023b3e9fca3 | note | Minimum Test Frequency - 1 Test per material per source
60097ba6-2fbb-51a3-a246-13361c159c75 | note | Inspection / Test method - NZS4407:2.4.7
788a29fc-6bc7-5fc9-93b6-6b840eea0a74 | note | Acceptance Criteria - As per NZTA M04 Specfication
9916145b-72a4-54a0-b139-9da64ec56b04 | note | Record documents (QCP - Quality Control Portal) - IANZ report
41324a53-1986-5995-aef2-826004648167 | note | Responsibility - Contractor
f2b3d62c-a149-53d8-938a-e052dfc37d9e | note | Designer - A
3e7d7ecc-78eb-5412-8add-2bf5f62ddeb9 | note | Eng. Rep / NZTA - I
c9e70f47-7ae6-5988-8057-72731abfb9fd | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| section | 2.0. CONSTUCTION
| checkpoint | 2.01 - Earthworks
b61e58c2-cc9c-5b35-90eb-2c40aaed6e5f | note | Detail of Activity / Test - Cut to Waste Insitu Shoulder
5d5d59b9-dd36-5543-a511-93418ac916d9 | note | Action (Hold, Monitor, Witness) - M
d5391111-a4fc-5224-823c-a9ca4e2f8bb9 | note | Minimum Test Frequency - As per design drawings
c29d8b4a-87d2-54f1-977a-f6d9b195acf4 | note | Inspection / Test method - Visual / Photo
4422d707-9e84-5db7-b49a-0d4564f919dd | note | Acceptance Criteria - Site Engineers Approval
d0b39179-1c91-5845-8268-28c75a4b99d0 | note | Record documents (QCP - Quality Control Portal) - Checksheet
559b55e9-d6cd-5282-956d-99ed63e9e40c | note | Responsibility - Contractor
cffadae0-de1f-5bc7-9414-e703e6d7c9e2 | note | Designer - A
fa63a1e3-cb09-5714-8e9a-b9d2981d5829 | note | Eng. Rep / NZTA - I
b24d30da-3c00-55be-935c-d4ee735dada1 | note | Contractor - R
| checkpoint | 2.02 - AP65 Placement
c4abc028-8aee-59f8-b927-9fbb7df8dd63 | note | Detail of Activity / Test - Gap 65 Placed in Accordance with Design and Survey
ee8958d7-a48c-5862-89c9-f15d5a5d7de7 | note | Action (Hold, Monitor, Witness) - M
d5075a69-4eed-5dc1-bd32-2477b41aef97 | note | Minimum Test Frequency - As per design drawings
459bdb0d-be26-52f8-ba75-d7346de03fbb | note | Inspection / Test method - Visual / Photo
67a4880a-685d-5674-86cd-e39b17507c6c | note | Acceptance Criteria - Site Engineers Approval
9c41f0d6-a996-58e8-b970-7c47aaaf8ced | note | Record documents (QCP - Quality Control Portal) - Checksheet
16db2f2c-2dcc-56a2-bc40-f7ab90d4f8ae | note | Responsibility - Contractor
d0deac72-dbd8-5a8c-9f57-140a4099f835 | note | Designer - A
45ea1efa-e37e-5b08-8847-be3c62defa0e | note | Eng. Rep / NZTA - I
3defcf44-2ff4-55db-adfc-a9034ea12277 | note | Contractor - R
| checkpoint | 2.03 - AP65 Compaction
1614fb7d-4e3d-53a5-b5ce-afde2cb34db0 | note | Detail of Activity / Test - Compact in Layers no greater than 200mm.
d05046d1-5be4-567b-81e7-44958069d048 | note | Action (Hold, Monitor, Witness) - H
fce7cf4d-b95b-5465-be02-fde96a3171bf | note | Minimum Test Frequency - 1 MDD Test per 50m
3fc660e5-07f3-5683-a165-2733938eb5ed | note | Inspection / Test method - Nuclear Densometer MDD Test
2af0169c-3963-51c0-8cb7-76a08d92199d | note | Acceptance Criteria - 95% MDD Achieved
961ea53e-17a3-5bec-a86c-27cc2c17dcfb | note | Record documents (QCP - Quality Control Portal) - IANZ report
b1b1df2a-886f-5fe1-8e2e-18f3c86145cb | note | Responsibility - Contractor
e45a41a5-817f-50bc-8983-7c3105dcb4ea | note | Designer - I
671d6270-4a90-5783-9d79-f70b5538934f | note | Eng. Rep / NZTA - A
17820d7b-c13c-577e-ae97-668df2e97395 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.04 - M4 Placement
f317e8fd-83e0-58f9-b6d1-f956fcc2d23c | note | Detail of Activity / Test - M4 Placed in Accordance with Design Drawing and Survey
2b9abca4-feea-503b-a0a3-de3ff7798540 | note | Action (Hold, Monitor, Witness) - M
0bfa817f-61ee-5fa8-a86b-e46c5e5d461c | note | Minimum Test Frequency - As per design drawings
591338a7-c1a2-5a44-b8c9-779aab333a15 | note | Inspection / Test method - Visual / Photo
fd5c0053-1cb1-50a2-9228-9478d82a3ce7 | note | Acceptance Criteria - Minimum Width 300mm.
723f53cb-ad4e-540e-8d2a-d4082357eaa3 | note | Record documents (QCP - Quality Control Portal) - Checksheet
71fb81c9-7a64-5437-a492-81ea3e6bd88f | note | Responsibility - Contractor
b128e269-c5a9-55ad-a435-98a89c5f32b2 | note | Designer - A
70804076-5b39-5600-8f06-30d8559a1beb | note | Eng. Rep / NZTA - I
b0f8acb0-6cae-5513-a27e-64a851a89397 | note | Contractor - R
| checkpoint | 2.05 - M4 Compaction
c647409c-f85c-52e9-ac6f-5ca999997459 | note | Detail of Activity / Test - Compact in Layers no greater than 150mm.
13f6bf66-2f9b-561a-8b59-8c56ae6417d7 | note | Action (Hold, Monitor, Witness) - H
8613a141-d1fe-54c0-b494-1627c2439b93 | note | Minimum Test Frequency - 1MDD Test per 50m
a0a2f320-23b8-5049-831b-d182c746c5ae | note | Inspection / Test method - Nuclear Densometer MDD Test
ffa3fdd3-2db3-521a-9786-49828baca648 | note | Acceptance Criteria - 98% MDD Achieved
267e30f7-415e-5abc-bcf7-d74096ac494c | note | Record documents (QCP - Quality Control Portal) - IANZ report
dd624d14-d62b-5e18-abc8-ed27a6dff1d4 | note | Responsibility - Contractor
9bcd581a-f1b8-5c91-aef0-f766f39a87ad | note | Designer - I
8193c8f2-ab15-50d0-8508-5c8c438b0f7c | note | Eng. Rep / NZTA - A
c9b70a26-f2f7-55c7-82dd-cbd939a89d85 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
53af85ce-03f6-585b-82a7-92cf0e32c471 | textbox | Contractor's Rep Name:
ce81b22d-8330-5659-8c3b-d70eb55b7eef | textbox | Engineer's Rep. Name:
460765d8-ad50-5b2d-ae5d-9ec641989812 | date | Date:
| signoff | Add Signature
| checklist | ITP - Subsoil Drainage Rev 1 | itp | ITP - Subsoil Drainage | 48c57658-3f65-4f95-9cd8-70a467d2e7ac
| section | 1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING
| checkpoint | 1.01 - Drainage aggregate
892bd164-7761-51df-8e27-7490f12610c1 | note | Detail of Activity / Test - Crushing Resistance
f34fe5e5-f850-5a41-ad7d-4c19f3207e77 | note | Action (Hold, Monitor, Witness) - H
0f482f64-9d69-596b-9dc1-aab3b0f19226 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
0cc2c27b-fc73-5ea4-ad39-7021495c136a | note | Inspection / Test method - NZS4407:3.10
72e1e5d1-24aa-5b72-a70c-aa9ac0bf7175 | note | Acceptance Criteria - > 100KN
a3f954bb-aa6d-526e-847a-2b8394d4c523 | note | Record documents (QCP - Quality Control Portal) - IANZ report
b85e7d7c-df5e-5fe7-9e27-e8d606d98895 | note | Responsibility - Contractor
c1d2251b-6dd0-54c0-bdfc-3e5b5989687e | note | Designer / PTG - A
91887811-8daf-59e9-8d6b-f1648e47d21f | note | Eng. Rep / NZTA - I
6255aca9-f902-59b8-afec-477d240bbdfe | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.02 - Drainage aggregate
a39be7b9-56b8-5f0a-9df8-f444f0f1ba4f | note | Detail of Activity / Test - Particle size distribution
95bf18d8-24eb-52de-a2c3-b590ef0b04a6 | note | Action (Hold, Monitor, Witness) - H
15c684ee-a28f-5cca-9c3d-07b6c2d8ebae | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
2f2e6f30-5519-5827-8fb7-252c3e84ef60 | note | Inspection / Test method - NZS4407:3.8.1
9aafa1ad-1738-5017-aa47-e1f31f7f0123 | note | Acceptance Criteria - as per IFC drawing
f0a83ad7-2ba9-52be-9a3a-fa3a59b0c5a5 | note | Record documents (QCP - Quality Control Portal) - IANZ report
b3e1d23f-72bf-5798-be46-12cf64e5cdc4 | note | Responsibility - Contractor
2ed164a7-a063-5cf5-8ad3-af4649b8a005 | note | Designer / PTG - A
9e7e174e-b7b0-5481-b880-ab8db2a84266 | note | Eng. Rep / NZTA - I
b9a195c4-2fad-5057-86c0-2a0211178461 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.03 - Pipe
043a4a1e-ad56-5d42-8fb6-1226ff2f83ad | note | Detail of Activity / Test - Subsoil Pipe Material
a5c212f6-676f-5130-a012-1859e28901bf | note | Action (Hold, Monitor, Witness) - H
81c98f48-df8f-590c-8a30-f6da899a610d | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - each delivery
c3f67e42-4975-5789-b7b3-3f892fb8d9e2 | note | Inspection / Test method - Dockets for each delivery
ad7b8bb5-35f5-5cee-87b5-59192a179345 | note | Acceptance Criteria - Compliance with TNZ F/2
72aa4e63-78e5-5f11-bc18-3a97a02dc777 | note | Record documents (QCP - Quality Control Portal) - Delivery Docket
77323653-8901-55d8-a8ce-09a1151f1bb6 | note | Responsibility - Contractor
b3ef01d4-5905-5c51-a9fd-b170d911a526 | note | Designer / PTG - A
21dbf408-3b0c-5dae-973f-d9a9427b8da1 | note | Eng. Rep / NZTA - I
dd8956b8-b4da-5615-bd99-e7d12cc8ff50 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| section | 2.0. CONSTUCTION
| checkpoint | 3.12 - Alignment
225b9fb8-1b4a-5cbb-a2e3-0d594a5c06b6 | note | Detail of Activity / Test - Subsoils to be placed behind the Kerb line or as instructed by Engineer
98b368a8-6c55-5105-b15a-67e58eee75a6 | note | Action (Hold, Monitor, Witness) - H
0afc5726-144e-5ee7-9769-e778a43deffa | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
3967d193-d43f-5725-b6ca-0cd961f6c630 | note | Acceptance Criteria - Engineers Approval
5e026732-6372-5e92-9a56-66e13674fd57 | note | Responsibility - Engineers Representative
41974f8b-875d-5194-bb01-fa11dcfddaf8 | note | Designer / PTG - A
1071ea6c-b3a8-5a30-9eb3-5212c6bb5811 | note | Eng. Rep / NZTA - I
321a7003-cbd6-5197-818c-1a77261ce656 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.13 - Excavation
3010a6e6-b323-5d74-bc62-f8eb21293df0 | note | Detail of Activity / Test - Excavtion of Trench should be within tolerances.
df3ddbbd-71e7-5bd9-ac0e-121fc0c2acb0 | note | Action (Hold, Monitor, Witness) - M
1992c47c-36af-5815-95fc-1baa0e291559 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
bfe43eb5-d0c7-594b-ae0f-1b71d06ba224 | note | Inspection / Test method - Visual / Photo
53e12fe7-038a-53b0-a118-4c1245242f0a | note | Acceptance Criteria - Trench width should be 300mm minimum. Trench height should be 800mm Min from top of the kerb OR Top of road level where Kerb is not present or as IFC drawing if detail specified
a63e362b-7adc-5674-95de-e0a9a8205384 | note | Record documents (QCP - Quality Control Portal) - Checksheet
f73563de-d3f5-5b64-b4a8-4a0632ba7434 | note | Responsibility - Contractor
b7e2b953-19c9-5826-be95-708e61151b82 | note | Designer / PTG - A
0e7235c6-411f-53a1-b018-0f5def003cfa | note | Eng. Rep / NZTA - I
934d1e6c-df2c-50fb-bdec-05a2b3356454 | note | Contractor - R
| checkpoint | 3.14 - Trench Lining
4ce4f9dd-6818-59c3-b6ad-28289ebd7dc6 | note | Detail of Activity / Test - A14 or other approved Bidim to be placed and wrapped around Trench.
5a1243fe-cfdc-5b70-a5f1-a92406dfc141 | note | Action (Hold, Monitor, Witness) - M
fe07117b-979e-5db8-afd7-ba84e9f1261f | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
474083fc-76ee-5d21-9407-2a55f3e95a93 | note | Inspection / Test method - Visual / Photo
98b53697-48e3-5cc0-8c1e-675044c4e7aa | note | Acceptance Criteria - Minimum Width 300mm.
e87bdc9f-4a27-5015-8ea8-3f1ab71bd97f | note | Record documents (QCP - Quality Control Portal) - Checksheet
92d1cab1-d48f-532b-bb4a-b0f3215e9991 | note | Responsibility - Contractor
817c4db7-b05f-5f87-98b5-0ada0b95ca61 | note | Designer / PTG - A
3eb79f8f-e01a-5870-95fb-abb268e186e7 | note | Eng. Rep / NZTA - I
50ba3960-a3dc-57c7-8c34-0b942f09d818 | note | Contractor - R
| checkpoint | 3.15 - Pipe laying
dd05e586-b285-56ea-994f-c14a98cbf6dd | note | Detail of Activity / Test - Pipe must have Min. 100mm of Cushion. Drainage 60:40 Material to be used.
994498ea-7c04-5e2d-803d-1da114ba5051 | note | Action (Hold, Monitor, Witness) - M
acfc6bf2-11cd-5794-ad03-d79c0637a5e8 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
4721141c-1830-5215-961c-2b3ba8c31f6f | note | Inspection / Test method - Visual / Photo
686ba410-5ef3-5823-a7d9-0761795b6caa | note | Acceptance Criteria - Minimum 100mm
acc4caa1-34d0-59cc-8fb0-b65caf60fd0f | note | Record documents (QCP - Quality Control Portal) - Checksheet
74cca688-9e98-574b-ba83-cfb86dcf0045 | note | Responsibility - Contractor
e26fdafa-62b5-5b5f-ac96-cebe5a45e7d5 | note | Designer / PTG - A
40587998-de58-5bce-bce7-342eb4a6130f | note | Eng. Rep / NZTA - I
88b97cf2-4ac2-50d2-a66c-58ab5b4ae729 | note | Contractor - R
| checkpoint | 3.16 - Pipe laying
34a97d49-6834-56d8-8abb-1479047c71f3 | note | Detail of Activity / Test - 110mm Perforated Pipe to be laid to a gradient not less than 1:200 to discharge
798e7c27-9a3e-5182-9d4b-aa774cb413a1 | note | Action (Hold, Monitor, Witness) - M
dac1bfc2-a633-5c02-8ca6-826c0857e0da | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
669ff28b-7aa5-59ec-9d19-19456949b44d | note | Inspection / Test method - Visual / Photo
4f0ef388-6f90-5ed4-b62d-91923b3436b4 | note | Acceptance Criteria - As Per IFC Drawings
af3508cc-387c-5394-b5be-e8a9ece99ec6 | note | Record documents (QCP - Quality Control Portal) - Checksheet
518de268-3038-503e-8907-f5318d5e0d4f | note | Responsibility - Contractor
900ba9b0-d336-5861-9fba-2784f3c90f40 | note | Designer / PTG - A
36b74398-9edc-56dd-a3bd-34e6f2662c15 | note | Eng. Rep / NZTA - I
6fce5f99-e748-54be-b7a2-0f9e9f304a78 | note | Contractor - R
| checkpoint | 3.17 - Backfill
0f0349b7-83d2-55d5-90bc-09859ecdf12f | note | Detail of Activity / Test - Drainage 60:40 Material to be used.
d1c9ee56-f318-5585-9173-fd2246960aa2 | note | Action (Hold, Monitor, Witness) - M
097c5c97-59d8-5edd-b816-db96a8f21189 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
d4026709-5a4b-57fc-b383-ce1ddc4b98bc | note | Inspection / Test method - Visual / Photo
af59712c-7bbf-50d8-9b71-55afbec36e81 | note | Acceptance Criteria - As Per IFC Drawings
6d1fb1a1-d590-53a7-9d87-5a2c33892e58 | note | Record documents (QCP - Quality Control Portal) - Checksheet
26cbdde5-6cef-5aae-a5f5-725870b27ed0 | note | Responsibility - Contractor
2da8a0ec-6810-5313-900d-9659becd20ac | note | Designer / PTG - A
2d587657-a17a-51cf-9a24-0a1c3f3d6e1f | note | Eng. Rep / NZTA - I
603ef748-a5fa-56bc-ba37-1c4e3691e06b | note | Contractor - R
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
039e84e0-dc07-5a3f-92dd-579192f38cab | textbox | Contractor's Rep Name:
15d42ad8-6804-55da-afef-962a10ebd38b | textbox | Engineer's Rep. Name:
cf3ae769-fb0e-549a-81b6-251edb874eee | date | Date:
| signoff | Add Signature
| checklist | Shoulder Clearing Checklist | itp | Shoulder Clearing Checklist | 6bbfb255-b493-4437-b829-9a352584fbf3
| section | Pre-site checks for the following
| checkpoint | Photos taken @ Pre start of works
31f33bbd-b990-58c9-8b9d-cc285d03fdb9 | note | Responsibility - FP/Su
f8a85bed-dcec-5d78-a485-fa951ca62bd8 | note | Comment - Field evidence for ITP
| checkpoint | Check culverts in vicinty of work inlet/outlets
33ca181a-550a-5984-b965-e85fb5d2de8b | note | Responsibility - FP/Su
89e19212-9364-5f6b-8da2-1cf5d168e948 | note | Comment - Field evidence for ITP
| checkpoint | Edge Delineators - offset position to re-instate if required
fcf70c19-6229-509d-8d08-222fc744504c | note | Responsibility - FP/Su
ac60b28b-00d3-58d0-8842-51662efa6209 | note | Comment - Field evidence for ITP
| checkpoint | Permanent Roadside Signage - Offset position to re-instate if required
ff28d3da-8737-5e5d-9079-8732e62388da | note | Responsibility - FP/Su
24b5329e-5718-56e3-9ea6-2ee18fcb9644 | note | Comment - Field evidence for ITP
| checkpoint | Photos - Post completion of works
9404eeba-5ce8-5a5c-a782-4b0e1a108e33 | note | Responsibility - FP/Su
08d6ecf5-a0b7-56fb-b83a-285aa90dbcd4 | note | Comment - Field evidence for ITP