## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
346e49e8-47bc-4749-a343-58c3eff9d7ff | checklist | Concrete Pour Record |  | Concrete Pour Record
decc4ae7-db80-4b2e-9c80-491b697b9bd9 | section | Preliminaries
6e950b39-a789-4a0b-ba42-dc989a63186c | checkpoint | Survey (1)
a114b964-e012-58fb-8340-55a850003857 | note | ACCEPTANCE CRITERIA: Sufficient survey set out information is available.
474cdf33-f47e-52b0-84e6-29403e6bd4d3 | date | Date Completed:
82f9ca9a-9501-4382-b55b-810793d47c6c | checkpoint | Survey (2)
85db5add-8502-5029-b2ec-ae09d1faa949 | note | ACCEPTANCE CRITERIA: Correct line and level for placement of concrete
285592e8-42c0-5dc6-87a1-273e1883a1b1 | date | Date Completed:
034faf9a-6a66-4786-89d8-40d3397f1f07 | checkpoint | Material Delivery (1)
9dbb26a4-74e8-55b8-ad79-3342a3d953a8 | note | ACCEPTANCE CRITERIA: Items conform with the applicable Australian Standard/s
2a663534-a869-564b-a1d3-c75332b03fa1 | note | COMMENTS / RECORDS: Delivery Docket, Supplier’s Certificate of Compliance
9c3afd1a-26b1-5adf-9da2-7dc563393a42 | date | Date Completed:
8aaff2a1-7e1f-4989-b52e-7c945da54714 | checkpoint | Material Delivery (2)
4bc8b152-1424-5b11-9cc3-4bf43c217e16 | note | ACCEPTANCE CRITERIA: Items delivered with no visible signs of damage
b99e1221-caae-5d4c-9147-5e452db78b5a | note | COMMENTS / RECORDS: Delivery Docket, Supplier’s Certificate of Compliance
968fee1d-b0d7-58c5-920f-1907084d08e1 | date | Date Completed:
d2f998cd-73eb-43c3-bf78-6dcca650d515 | section | Pre-Pour Check (to be completed by Engineer or Supervisor)
3d48c77e-4c03-4047-b2ef-854a4568a7c9 | checkpoint | Confirm Dimensions
03f8e694-66c7-5ce3-8f49-358df6ac7235 | note | ACCEPTANCE CRITERIA: Visual Check and Measure dimensions are correct for trench width or Thrust Block dimensions
a035709c-8844-5a32-89c5-81642f7fb875 | date | Date Completed:
d6a0cde7-a8d1-4f05-a053-a3e953512410 | checkpoint | Initial pour against ground (1)
ec31f62c-c010-5018-8503-ff962a5ec8de | note | ACCEPTANCE CRITERIA: Surface free of water and soft spots
0a38ec50-ace2-54d5-89b5-f632576bd5d7 | date | Date Completed:
72f7bbb4-0fb0-4cd5-a883-b9793b55368e | checkpoint | Initial pour against ground (2)
c4e99a11-9f3e-5e7a-b700-bfe3736dca78 | note | ACCEPTANCE CRITERIA: Hardstand/ ground suitable for concrete pump location
8763fea4-0af4-526c-8607-0b43ac3382fb | date | Date Completed:
df69d467-c00f-456c-b3b7-07ec65493b63 | checkpoint | Initial pour against ground (3)
4815e622-24a3-51a7-8bdc-c1d1c8812ddf | note | ACCEPTANCE CRITERIA: 50mm blinding UNO
3adbb4d9-d41e-5ebc-9864-a6529bf134a2 | date | Date Completed:
0720518c-3fce-49b2-bb20-ee47ee93791b | checkpoint | Initial pour against ground (4)
1eef74ae-9b2c-567c-840f-5c415e67da25 | note | ACCEPTANCE CRITERIA: If for Thrust Block no loose Material
7203128f-e7c3-5fe7-aaf0-c9581bcae687 | date | Date Completed:
4d7f6957-b9e3-42eb-b13a-af7159f88f8d | checkpoint | Construction joints & surfaces
9f08a4d0-929e-5db5-8f8e-1924e83978f3 | note | ACCEPTANCE CRITERIA: Clean and free of laitance, scabble where required.
a4dc1e1f-575f-5bf5-94a9-ba2609840e02 | date | Date Completed:
23ef06e0-b7bf-495c-8ca0-5ac8058e4b7e | checkpoint | Reinforcement
4248ec4c-9262-5269-96fb-3b0e7dd17fba | note | ACCEPTANCE CRITERIA: Installed as per IFC drawings
41120141-3825-5274-a47a-93fa08f18e0d | note | ○ Type, size, position, chairs, cover all as specified & within tolerance; laps and splices as specified
29f194f3-f336-5401-a06b-dd5d6174ed8d | note | ○ Extra tie wire on splice bars around construction joints and wedges fixed to support splice bars in stop end formwork
08361996-3304-51d8-a416-e774593941f9 | note | COMMENTS / RECORDS:
baac8399-01fb-56bb-9ab1-9426475d0780 | note | Cover (mm):
f88a314e-48fb-5ca6-a7e8-7c1ff5016e94 | tickbox | 50mm above obvert
327bd230-15e6-513e-a677-f96e126870e2 | tickbox | 75mm ground clearance
b970f5d1-15ec-57ce-bfdd-30e2e1b8bcaa | note | Reo Count:
b73e1354-4e60-54c5-bd59-b2c3ebcf9bfe | tickbox | Reo Count
c4ce3874-e841-554a-beb3-c4237202c3d7 | date | Date Completed:
740bc3c3-cc8e-475d-a527-7d075b4af213 | checkpoint | Cast-in items, block outs and hold down bolts
7864c898-f51b-5f4a-9699-eed662aee989 | note | ACCEPTANCE CRITERIA: Type, quantity and location as per design.
b3d27ff4-4e2c-5b11-adf1-8211568b8fba | date | Date Completed:
8a872082-341e-4ed7-81a0-d0fc075e8cbd | checkpoint | Final inspection (1)
dd142f68-b156-54f2-89ed-a8a02158097e | note | ACCEPTANCE CRITERIA: Pour arrangements agreed and equipment adequate
6c821076-40ab-592a-a64b-af72e3167ff9 | date | Date Completed:
00bfd1a0-4d52-4679-89da-342b1ec84756 | checkpoint | Final inspection (2)
7b0c96fe-19fa-5239-be3d-ac8c7bff5203 | note | ACCEPTANCE CRITERIA: Surface free of water, dust, debris and stains.
512f9628-b920-50ad-adb8-4a6fc1e47372 | date | Date Completed:
c2e6ef42-4272-4bb3-a25c-bab3b75d1a68 | section | Concrete Pour (to be completed by Engineer or Supervisor)
01d832be-7b8e-415d-8e5f-7a2411b6552f | checkpoint | Correct Batch / Grade of Concrete
fba7b12e-6163-5715-9268-b3bdbf481736 | note | ACCEPTANCE CRITERIA: Visual Acceptance of the docket prior to pouring
352ac658-1e55-535c-9c17-163c1f4dd291 | date | Date Completed:
c79fec9a-7d09-49fb-96ae-39bf42c253c8 | checkpoint | Concrete quality
981abd6b-3662-51d7-be6b-99638520e738 | note | ACCEPTANCE CRITERIA: Visual assessment of quality - note details of any loads rejected
38b1a9f5-3a07-5556-b84e-7c2a144c78fe | date | Date Completed:
b3468d4a-6dc3-48a3-9ece-2f4591d422ef | checkpoint | Concrete Testing (Vertical Crest Thrust Block)
e35a273e-aa90-5bce-8168-2e217760ca82 | note | ACCEPTANCE CRITERIA: 3 sample Cylinder taken (7day and 2 X 28 day tests)
f6675274-38c0-5bfe-8d55-28c89f1db898 | date | Date Completed:
e44c8bd4-231f-448e-8d29-daa2b12d1964 | checkpoint | Concrete Testing (All Other Concrete Pours)
1d5e1b6e-5a98-5b75-a165-8d228e158bb1 | note | ACCEPTANCE CRITERIA: 3 sample Cylinder taken (7day and 2 X 28 day tests)
58b7d6d1-48fe-5423-a467-d3692d14415a | date | Date Completed:
4c66d260-243b-41e2-8953-d645341b917e | checkpoint | Compaction Method
41dd52de-885f-5885-9de5-fa662439db3d | note | ACCEPTANCE CRITERIA:
895441a0-5808-5a83-840a-0b1d70a487cc | tickbox | Pencil vibrators
3c7d4070-81c6-52e5-b46f-93b7156ac22b | textbox | ____No
18408afc-737d-5d08-a20d-410df604ae23 | date | Date Completed:
a2fff851-145a-5612-8ba5-dba6a106c273 | textbox | Signed:
f2154298-e766-5972-9282-3dca100e366d | note | Engineer (initial & date)
6cc2f104-bd57-5b69-b029-19d0b56e0be3 | textbox | Engineer - Initials:
66d9882e-6202-55d8-84fe-d1564f13127e | date | Engineer - Date:
16d7dfa5-957f-5236-9457-494209a670b3 | note | Supervisor (initial & date)
b7c4edba-9f75-53af-904a-4094072b890a | textbox | Supervisor - Initials:
4691252d-5de4-59cc-a63b-2711103ff57d | date | Supervisor - Date:
68224f10-8759-4236-8874-5632ed536fd8 | section | Post Pour Check (to be completed by Engineer or Supervisor)
9d7d7ab9-b41e-4fc9-9c1c-fb5274178168 | checkpoint | Curing of exposed surfaces
810d7661-c45a-58d5-9056-e92a37b33c7e | note | ACCEPTANCE CRITERIA: Exposed surfaces cured
695f7040-2d56-5d6b-8ed5-1925048a1a9f | tickbox | Polyethylene sheeting (edges / laps sealed, 300mm min laps)
0f764953-e7a3-5488-8c6c-0b97ba962a58 | tickbox | Curing compound
94bd2c9d-f0e0-55d0-b48b-f976111dadc9 | tickbox | Water curing (continuous spraying, ponding, wet Hessian)
a7fbe6bb-16ba-5669-82cf-c858ac2bfaa0 | date | Date Completed:
5adaa3d2-86e0-4aa8-9b63-05c0841af3ba | checkpoint-no-value | Location of embedment, hold down bolts and penetrations
3f001e90-eaf7-5acd-8a54-e35cb9665764 | note | ACCEPTANCE CRITERIA: All embedded items, hold down bolts and penetration located in accordance with drawings
0c1ee87d-e0e7-5e2d-abf8-15d5615cd58a | note | Refer defects list below
5ce42010-82fd-5992-9218-27d2b36cc1cb | date | Date Completed:
a2d76aaf-179f-4c02-93d6-caeac17676b8 | checkpoint | Details of defects – cracking in slab pours and Inspection of repairs.
9b872936-2b65-59ec-b422-b6dcaecc3d9b | note | ACCEPTANCE CRITERIA: Finish concrete surfaces inspected by Supervisor. Within specification tolerances (≤ 0.2mm)
f2f8830a-7f46-5633-a117-bb42f8b492e0 | note | ○ All defects repaired
f7c0e7d7-f120-54c7-8a86-747a264c440a | tickbox | Cracks requiring repairs observed
3696c69f-4807-5d18-9987-ae3c98f774ed | tickbox | Refer to attached location plan
f8646abb-b6ff-5be6-ada7-86d282f3631f | textbox | RFI
17b5c1bb-fd76-51be-ab19-b6df65cb6bd5 | tickbox | Repairs in accordance with approved specification.
d0e1305f-deab-5434-ae78-96cd570aaa49 | note | COMMENTS / RECORDS:
896ae33c-4c17-58a4-8e9f-cbcaf97a05be | textbox | Type of surface finish:
7a510f27-dc30-51a7-8a95-605ecc952634 | date | Date Completed:
2a0f2917-4d5d-4207-ad23-08c5caa415b1 | section | Final inspection
46e83414-5521-40ad-a330-342f5ca61e0a | checkpoint | Witness Point
795ae5a8-f08d-5a00-8a40-6ca6167546b4 | note | Engineer (initial & date)
93e5323b-4739-55ed-a797-1377245aac9e | textbox | Engineer - Name:
a8006b88-b4b3-5238-835c-5f5e874fd2fc | date | Engineer - Date:
7ea072b4-ebcd-5529-b506-56cfda3153a1 | note | Supervisor (initial & date)
d61d0af2-03b4-5807-b251-0471abe253e4 | textbox | Supervisor - Name:
bec9f298-d258-5126-8453-d304a57cd661 | date | Supervisor - Date:
2dedd558-a4a8-4b40-ae58-6fcbef100903 | signoff | Signatures
ed109a49-6696-48fe-80fd-76697dccd6ba | checkpoint | Details of other defects
797c68be-ddfe-5b6b-b1d0-b3e407f4347b | button | Defects listed and NCR raised (Y/N) | Yes,No
2eeae433-ef6a-57a2-bfca-1af92cef8424 | textbox | NCR #
44490003-4a69-40c4-bd75-b550f3f07db7 | checkpoint | As Built survey complete
df0f97ac-1a28-4cac-8e86-8a8e850388a4 | checkpoint | Close out
7c59119c-22a3-56ba-8246-28b3c6af462b | note | Final inspection: All work completed accordance with applicable procedures, drawings, specifications and approved changes
70e1cc3e-2e8b-5302-8287-12d0db41692c | note | Engineer (Name, Sign & Date)
f77088a2-379c-51ee-8612-ed2eb88eb4ac | textbox | Name:
1d642801-a9d3-5046-94f6-e0eea2272e21 | date | Date:
522d8b50-41c3-423e-b541-dd53a93435bc | signoff | Sign ITP
f9f3ce1a-52b6-42e7-8ebc-5f8f5dfa08d2 | checkpoint | Final Inspection
294182eb-db36-5a4a-877f-6128166bbc91 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
154d2203-e473-5f8b-94ed-928fca373454 | textbox | Print Name:
91ffa316-85cf-58cc-bd53-6295a9ec1c04 | textbox | Position:
d2eb4d9f-27a7-5568-b75a-b5e7f47d26d9 | date | Date: