## Table 1
[9 empty] | Inspection and Test Plan | [8 empty] | Doc ID: ITP# 1
Client: DTP | [8 empty] | Project Number: 7ABC0160 | [5 empty] | Prepared By: Simon Welsh
Project: Glenelg Highway Bridge (over Back Creek), Barrier Replacement | [12 empty] | Reviewed By: | [5 empty] | Date:
Construction Process: Bridge Rail Installation | [12 empty] | Approved By: | [5 empty] | Date:
Specifications: AS5100
Structure / Component: SN2097 Glenelg Highway Bridge (over Back Creek), Barrier Replacement
Lot No: 1 |  |  |  |  | Lot Details: South and North side of the Bridge |  |  | Lot size/Quantity: 2 No. | [5 empty] | Date: 10/10/2022
Item No. |  | Task/Activity Description |  | Inspection/Test | [8 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility |  | Checked by:
|  |  |  | Frequency |  |  | Acceptance Criteria | Reference Documents | Inspection/Test Method |  |  | Record of conformity |  |  |  | Client | Fulton Hogan |  | Other | Date
1 |  | Receive Materials |  | Inspection prior to receiving |  |  | To comply with requirements of the IFC drawings | AS5131 | All measures in accordance with relevant documentation |  |  | This Inspection & Test Plan (ITP) | HP AP | Project Manager Clients Superintendent
2 |  | Material Testing |  | Each Lot and as required |  |  | All materials to comply with IFC drawings | Drawings | All measures in accordance with relevant documentation |  |  | Material Certificates, D/Dockets Matched & Signed | HP AP | Project Manager Clients Superintendent
3 |  | Welding |  | Visual Inspection |  |  | All welds to comply with IFC drawings | AS5131 | All measures in accordance with relevant documentation |  |  | Qualified Welder Certification Reports | HP AP | Project Manager Clients Superintendent
4 |  | Dimensional Inspection |  | Tolerance as per design |  |  | To comply with requirements of the IFC drawings | Drawings | All measures in accordance with relevant documentation |  |  | This Inspection & Test Plan (ITP) | IP IP | Project Manager Clients Superintendent
5 |  | Surface Treatments |  | Inspection prior to receiving |  |  | Superintendent shall confirm the quality of rail surface before the erection of rails commence. | Drawings | All measures in accordance with relevant documentation |  |  | This Inspection & Test Plan (ITP) | IP IP | Project Manager Clients Superintendent
6 |  | Fixtures |  | Visual inspection |  |  | Superintendent shall confirm the positioning/number of bolted connections. | - | All measures in accordance with relevant documentation |  |  | This Inspection & Test Plan (ITP) | IP IP | Project Manager Clients Superintendent
7 |  | Concrete Infills |  | Visual inspection prior to pour |  |  | Superintendent shall complete a visual inspection of the positioning of bolted connections before the installation of the concrete infill commence. | - | All measures in accordance with relevant documentation |  |  | This Inspection & Test Plan (ITP) | HP WP | Project Manager Clients Superintendent
8 |  | Finishings |  | Visual inspection upon completion |  |  | Superintendent shall complete a visual inspection of the finished bridge rail in accordance to the design drawings. | - | All measures in accordance with relevant documentation |  |  | This Inspection & Test Plan (ITP) | IP IP | Project Manager Clients Superintendent
Final Inspection The signature below verifies that this ITP has been completed in accordance with the SWA’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
Legend:
| HP |  | Hold Point |  |  | Work shall not proceed past the HP until released by the Superintendent |  |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
| HP* |  | SWA Hold Point |  |  | Work shall not proceed past the HP* until released by the SWA |  |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
| WP |  | Witness Point |  |  | An inspection which must be witnessed by the Superintendent |  |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
| AP |  | Approval Point |  |  | Written or verbal approval given by the Superintendent
[9 empty] | Inspection and Test Plan | [8 empty] | Doc ID: ITP# 1
Client: DTP | [8 empty] | Project Number: 7ABC0160 | [5 empty] | Prepared By: Simon Welsh
Project: Glenelg Highway Bridge (over Back Creek), Barrier Replacement | [12 empty] | Reviewed By: | [5 empty] | Date:
Construction Process: Bridge Rail Installation | [12 empty] | Approved By: | [5 empty] | Date:
Specifications: AS5100
Structure / Component: SN2097 Glenelg Highway Bridge (over Back Creek), Barrier Replacement