## Table 1
[9 empty] | Inspection and Test Plan | [9 empty] | Doc ID: ITP# 2
Client: DoT | [8 empty] | Contract No: 8929/0437 | [6 empty] | Prepared By: Joshua Kliemt
Project: GOR – Sheoak Creek Bridge Rail Replacement Project | [12 empty] | Reviewed By: | [6 empty] | Date:
Construction Process: Bored Pile Installation | [12 empty] | Approved By: | [6 empty] | Date:
Specifications: Section 204, 604 and design drawings
Structure / Component: off-structure bored piles
Lot No: 1 |  |  |  |  | Lot Details: South and North side of the Bridge |  |  | Lot size/Quantity: 2 No. | [6 empty] | Date: 10/10/2022
Item No. |  | Task/Activity Description |  | Inspection/Test | [8 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  | Responsibility |  | Checked by:
|  |  |  | Frequency |  |  | Acceptance Criteria | Reference Documents | Inspection/Test Method |  |  | Record of conformity |  |  |  |  | Client | Fulton Hogan |  | Other | Date
1 |  | Survey Setout |  | Inspection all new Setout |  |  | Site inspection and client witness point | Section 204 | Inspection |  |  | This Inspection & Test Plan (ITP) | HP WP |  | Project Manager Clients Superintendent
2 |  | Clearing and stripping of topsoil |  | Clearing and stripping lot 1 of site |  |  | Compliance with drawings | Section 204 | Inspection |  |  | This Inspection & Test Plan (ITP) | IP IP
3 |  | Supply & install of bored piles |  | Each bored Pile |  |  | Compliance with drawings through completion of pile which includes: Material conformance checks Line, level, cover, and angle checks | Section 606 | Pre-pour inspection Delivery dockets |  |  | This Inspection & Test Plan (ITP) | HP WP |  | Project Manager Clients Superintendent
4 |  | Earthwork reinstatement |  | Each lot where 1 lot is 1 site |  |  | Compliance with drawings. checks for line, length and level | Section 201 | Inspection |  |  | This Inspection & Test Plan (ITP) | HP WP |  | Project Manager Clients Superintendent
5 |  | Practical Completion submission and acceptance |  | Each lot where 1 lot is 1 site |  |  | Project completion achieved in accordance with subcontract agreement. | N/A | Inspection |  |  | This Inspection & Test Plan (ITP) | HP WP |  | Project Manager Clients Superintendent
Final Inspection The signature below verifies that this ITP has been completed in accordance with the SWA’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
Legend:
| HP |  | Hold Point |  |  | Work shall not proceed past the HP until released by the Superintendent |  |  |  | IP | Inspection point |  |  | Formal Inspection to be done and recorded
| HP* |  | SWA Hold Point |  |  | Work shall not proceed past the HP* until released by the SWA |  |  |  | TP | Test Point |  |  | Product compliance test to be undertaken and recorded/reported
| WP |  | Witness Point |  |  | An inspection which must be witnessed by the Superintendent |  |  |  | SCP | Survey conformance point |  |  | A qualified surveyor to check product/section/structure and report
| AP |  | Approval Point |  |  | Written or verbal approval given by the Superintendent