## Table 1
[9 empty] | Inspection and Test Plan | [9 empty] | Doc ID: ITP# 3
Client: DoT | [8 empty] | Contract No: 8929/0437 | [6 empty] | Prepared By: Joshua Kliemt
Project: GOR – Sheoak Creek Bridge Rail Replacement Project | [12 empty] | Reviewed By: | [6 empty] | Date:
Construction Process: Guardrail Installation | [12 empty] | Approved By: | [6 empty] | Date:
Specifications: Section 708 and design drawings
Structure / Component: Guardrail
Lot No: 1 |  |  |  |  | Lot Details: South and North side of the Bridge |  |  | Lot size/Quantity: 2 No. | [6 empty] | Date: 10/10/2022
Item No. |  | Task/Activity Description |  | Inspection/Test | [8 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  | Responsibility |  | Checked by:
|  |  |  | Frequency |  |  | Acceptance Criteria | Reference Documents | Inspection/Test Method |  |  | Record of conformity |  |  |  |  | Client | Fulton Hogan |  | Other | Date
1 |  | Setout |  | Prior to commencing any activity |  |  | Chainage locations clearly identified for extent | Design drawings Section 708 | Inspection |  |  | This Inspection & Test Plan (ITP) | HP AP |  | Project Manager Clients Superintendent
2 |  | Supply of materials |  | Each delivery |  |  | All materials are to be on VicRoads current accepted products list and conform with the detailed design | Design drawings Section 708 | Inspection Certificate of materials |  |  | Material Certificates, D/Dockets Matched & Signed | HP AP |  | Project Manager Clients Superintendent
3 |  | Installation |  | Each lot as required |  |  | The offset, height and post spacing is to conform with VicRoads specifications and the detailed design | Design drawings Section 708 | Inspection |  |  | This Inspection & Test Plan (ITP) | HP AP |  | Project Manager Clients Superintendent
4 |  | End Treatments |  | Each lot as required |  |  | Guardrail end treatments are to be installed to VicRoads specifications | Design drawings Section 708 | Inspection |  |  | Qualified Welder Certification Reports | IP IP |  | Project Manager Clients Superintendent
5 |  | Motorcycle rub rail |  | Each lot as required |  |  | Where specified, motorcycle rub rail is to be installed on the new length of guardrail | Design drawings Section 708 | Inspection |  |  | This Inspection & Test Plan (ITP) | IP IP |  | Project Manager Clients Superintendent
Final Inspection The signature below verifies that this ITP has been completed in accordance with the SWA’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
Legend:
| HP |  | Hold Point |  |  | Work shall not proceed past the HP until released by the Superintendent |  |  |  | IP | Inspection point |  |  | Formal Inspection to be done and recorded
| HP* |  | SWA Hold Point |  |  | Work shall not proceed past the HP* until released by the SWA |  |  |  | TP | Test Point |  |  | Product compliance test to be undertaken and recorded/reported
| WP |  | Witness Point |  |  | An inspection which must be witnessed by the Superintendent |  |  |  | SCP | Survey conformance point |  |  | A qualified surveyor to check product/section/structure and report
| AP |  | Approval Point |  |  | Written or verbal approval given by the Superintendent