## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP No. 1 - Bridge Rail Installation | itp |  |  |  |  | ITP No. 1 - Bridge Rail Installation
section | Details
checkpoint | 1 - Receive Materials
label | FREQUENCY: Inspection prior to receiving
label | ACCEPTANCE CRITERIA: To comply with requirements of the IFC drawings
label | REFERENCE DOCUMENTS: AS5131
label | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
label | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
label | HP, AP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Material Testing
label | FREQUENCY: Each Lot and as required
label | ACCEPTANCE CRITERIA: All materials to comply with IFC drawings
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
label | RECORD OF CONFORMITY: Material Certificates, D/Dockets Matched & Signed
label | HP AP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Welding
label | FREQUENCY: Visual Inspection
label | ACCEPTANCE CRITERIA: All welds to comply with IFC drawings
label | REFERENCE DOCUMENTS: AS5131
label | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
label | RECORD OF CONFORMITY: Qualified Welder Certification Reports
label | HP, AP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Dimensional Inspection
label | FREQUENCY: Tolerance as per design
label | ACCEPTANCE CRITERIA: To comply with requirements of the IFC drawings
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
label | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
label | IP, IP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
checkpoint | 5 - Surface Treatments
label | FREQUENCY: Inspection prior to receiving
label | ACCEPTANCE CRITERIA: Superintendent shall confirm the quality of rail surface before the erection of rails commence.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
label | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
label | IP, IP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
checkpoint | 6 - Fixtures
label | FREQUENCY: Visual inspection
label | ACCEPTANCE CRITERIA: Superintendent shall confirm the positioning/number of bolted connections.
label | REFERENCE DOCUMENTS: -
label | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
label | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
label | IP, IP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
checkpoint | 7 - Concrete Infills
label | FREQUENCY: Visual inspection prior to pour
label | ACCEPTANCE CRITERIA: Superintendent shall complete a visual inspection of the positioning of bolted connections before the installation of the concrete infill commence.
label | REFERENCE DOCUMENTS: -
label | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
label | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
label | HP, WP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Finishings
label | FREQUENCY: Visual inspection upon completion
label | ACCEPTANCE CRITERIA: Superintendent shall complete a visual inspection of the finished bridge rail in accordance to the design drawings.
label | REFERENCE DOCUMENTS: -
label | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
label | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
label | IP, IP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the SWA’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP No. 2 - Bored Pile Installation | itp |  |  |  |  | ITP No. 2 - Bored Pile Installation
section | Details
checkpoint | 1 - Survey Setout
label | FREQUENCY: Inspection all new Setout
label | ACCEPTANCE CRITERIA: Site inspection and client witness point
label | REFERENCE DOCUMENTS: Section 204
label | INSPECTION / TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
label | HP, WP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Clearing and stripping of topsoil
label | FREQUENCY: Clearing and stripping lot 1 of site
label | ACCEPTANCE CRITERIA: Compliance with drawings
label | REFERENCE DOCUMENTS: Section 204
label | INSPECTION / TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
label | IP, IP
label | RESPONSIBILITY:
date | Date Completed:
checkpoint | 3 - Supply & install of bored piles
label | FREQUENCY: Each bored Pile
label | ACCEPTANCE CRITERIA: Compliance with drawings through completion of pile which includes:
label | ○ Material conformance checks
label | ○ Line, level, cover, and angle checks
label | REFERENCE DOCUMENTS: Section 606
label | INSPECTION / TEST METHOD: Pre-pour inspection, Delivery dockets
label | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
label | HP, WP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Earthwork reinstatement
label | FREQUENCY: Each lot where 1 lot is 1 site
label | ACCEPTANCE CRITERIA: Compliance with drawings. checks for line, length and level
label | REFERENCE DOCUMENTS: Section 201
label | INSPECTION / TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
label | HP, WP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Practical Completion submission and acceptance
label | FREQUENCY: Each lot where 1 lot is 1 site
label | ACCEPTANCE CRITERIA: Project completion achieved in accordance with subcontract agreement.
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
label | HP, WP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the SWA’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP No. 3 - Guardrail Installation | itp |  |  |  |  | ITP No. 3 - Guardrail Installation
section | Details
checkpoint | 1 - Setout
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Chainage locations clearly identified for extent
label | REFERENCE DOCUMENTS: Design drawings Section 708
label | INSPECTION / TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
label | HP, AP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Supply of materials
label | FREQUENCY: Each delivery
label | ACCEPTANCE CRITERIA: All materials are to be on VicRoads current accepted products list and conform with the detailed design
label | REFERENCE DOCUMENTS: Design drawings Section 708
label | INSPECTION / TEST METHOD: Inspection, Certificate of materials
label | RECORD OF CONFORMITY: Material Certificates, D/Dockets Matched & Signed
label | HP AP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Installation
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: The offset, height and post spacing is to conform with VicRoads specifications and the detailed design
label | REFERENCE DOCUMENTS: Design drawings Section 708
label | INSPECTION / TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
label | HP, AP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - End Treatments
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed to VicRoads specifications
label | REFERENCE DOCUMENTS: Design drawings Section 708
label | INSPECTION / TEST METHOD: Inspection
label | RECORD OF CONFORMITY: Qualified Welder Certification Reports
label | IP, IP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
checkpoint | 5 - Motorcycle rub rail
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Where specified, motorcycle rub rail is to be installed on the new length of guardrail
label | REFERENCE DOCUMENTS: Design drawings Section 708
label | INSPECTION / TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
label | IP, IP
label | RESPONSIBILITY: Project Manager, Clients Superintendent
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the SWA’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP