## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
b849aa9c-3499-4cfe-8c92-37d07218d432 | checklist | FH-ZU2-QU-ITP013 - PCC Pavements - Rev 1 |  | FH-ZU2-QU-ITP013 - PCC Pavements - Rev 1
41d57e7b-b85e-4c2b-8c69-2d5be4783788 | section | 1.0 - Preliminary Activities
506d8e88-725b-4b0f-bb9d-371aa11636a1 | checkpoint-no-value | 1.5 - Production and Construction Trials
8533ae0b-11c0-5240-93ee-e491b2f920a4 | note | Frequency - Prior to commencing works
1273a315-0f09-5324-94f0-80142de96d0d | note | Acceptance Criteria - A production and construction trial must be completed as per the requirements in the specification.
58ecf80b-2aef-5e1b-94f3-e36e522f2955 | note | ○ The results, control procedures, construction methods and completed trial pavement will be presented for review and approval by the Contract Administrator.
19d96463-aef4-5c57-9e00-5610cfa2d829 | note | Reference Documents - Beca Spec 002 - 11.6.1 to 11.6.4
6afce25a-9fb2-5811-8ccd-852825b2f8f9 | note | Inspection/Test Method - Verify
4eef049f-8897-5e7a-a7ae-41f1e2ad5dea | note | Record of conformity - Aconex Reference
e9b1dc10-4192-5845-b5db-479f56cc203c | note | HP
c2f8440a-7a28-5313-b6e9-31816264f5b1 | note | Responsibility - Project / Site Engineer, Principal’s Representative
ea4f7e3a-5d1c-5f9a-b4df-580d21f072f3 | note | Date Completed: 19/08/2024
6ad10ec8-c744-5707-9ea8-f3620932c588 | note | Principal’s Representative: DCWC Mgt-GCOR-009917
27526bf1-51af-4886-9a99-392bff118b3a | checkpoint | 1.7 - Impermeable Blanket Material Submission
efe787e3-4d7f-560f-bc8c-24e13baf56f8 | note | Frequency - Prior to use of impermeable blanket
f94a480a-ae1d-5ff0-8a1f-f1ded9efcaa9 | note | Acceptance Criteria - If required to be used, impermeable blankets shall comply with the requirements of ASTM C.171.
b0437f2f-6c25-59b8-9136-30dea4c645ac | note | ○ The blankets shall have sufficient strength and weight to meet the required conditions of service and shall be approved by the Contract Administrator before use.
b0e07ec2-1cf6-5781-8f6f-13b35cf4b62f | note | Reference Documents - Beca Spec 002 - 11.4.11.2
b2281fff-5958-58bc-8369-a3c9704e5ae3 | note | Inspection/Test Method - Verify
56678456-ceba-56c0-a878-e318270e54f6 | note | Record of conformity - Aconex Reference
fd404a8e-46cb-5c5c-8e46-84b242aee735 | note | HP
03930a72-0b19-5f57-a908-780a203c9fb5 | note | Responsibility - Project / Site Engineer, Principal’s Representative
6f039916-818e-5a6d-b7ae-88abf7af32d5 | date | Date Completed:
fe2a5923-fa2e-4263-b85c-7b316011158c | signoff | AUTHORITY HOLDPOINT