## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | FH-ZU2-QU-ITP013 - PCC Pavements - Rev 1
section | 1.0 - Preliminary Activities
checkpoint-no-value | 1.5 - Production and Construction Trials
note | Frequency - Prior to commencing works
note | Acceptance Criteria - A production and construction trial must be completed as per the requirements in the specification.
note | ○ The results, control procedures, construction methods and completed trial pavement will be presented for review and approval by the Contract Administrator.
note | Reference Documents - Beca Spec 002 - 11.6.1 to 11.6.4
note | Inspection/Test Method - Verify
note | Record of conformity - Aconex Reference
note | HP
note | Responsibility - Project / Site Engineer, Principal’s Representative
note | Date Completed: 19/08/2024
note | Principal’s Representative: DCWC Mgt-GCOR-009917
checkpoint | 1.7 - Impermeable Blanket Material Submission
note | Frequency - Prior to use of impermeable blanket
note | Acceptance Criteria - If required to be used, impermeable blankets shall comply with the requirements of ASTM C.171.
note | ○ The blankets shall have sufficient strength and weight to meet the required conditions of service and shall be approved by the Contract Administrator before use.
note | Reference Documents - Beca Spec 002 - 11.4.11.2
note | Inspection/Test Method - Verify
note | Record of conformity - Aconex Reference
note | HP
note | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
signoff | AUTHORITY HOLDPOINT