## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
6e8bc74f-80db-42bb-ab09-732a71191745 | checklist | FH-ZU2-QU-ITP013 - PCC Pavements - Rev 1 |  | FH-ZU2-QU-ITP013 - PCC Pavements - Rev 1
a94fc54b-dfe1-4cdc-8154-fb8397eae999 | section | 1.0 - Preliminary Activities
2f02770b-6975-44bd-9123-018b9f37a167 | checkpoint-no-value | 1.5 - Production and Construction Trials
01e4ff47-2fac-548d-80ec-69161487d54b | note | HP
f6fdcfb5-dd4a-5f5d-877c-4104264561d1 | note | Frequency - Prior to commencing works
03e32d4c-4048-54db-823e-ae3e06bc7faf | note | Acceptance Criteria - A production and construction trial must be completed as per the requirements in the specification.
1f96aad4-19c6-5282-8da2-743bc98ba224 | note | ○ The results, control procedures, construction methods and completed trial pavement will be presented for review and approval by the Contract Administrator.
b1b33481-08ad-59e7-b0ad-8802df216de6 | note | Reference Documents - Beca Spec 002 - 11.6.1 to 11.6.4
e2434618-9671-5f41-b980-5fa9c0af3312 | note | Inspection/Test Method - Verify
ce98d1c7-47a1-5813-be21-7ebfbe635407 | note | Record of conformity - Aconex Reference
2d144726-3ed0-5c5c-bb0d-b0892188190b | note | Responsibility - Project / Site Engineer, Principal’s Representative
71380c09-576c-5109-8698-5f36c5e4c2a3 | note | Date Completed: 19/08/2024
e434948b-e4d0-5a1f-bbc4-7b98e08020a1 | note | Principal’s Representative: DCWC Mgt-GCOR-009917
92ac859a-9d7e-4f39-b8ed-20a4db9fce76 | checkpoint | 1.7 - Impermeable Blanket Material Submission
5bc93eea-08ef-5c87-9b64-f66191351c23 | note | Responsibility - Project / Site Engineer, Principal’s Representative
5b1dde0e-4451-56f8-902f-2c58d7979dfa | date | Date Completed:
fdc3b6fa-6ba8-5b80-a231-eba8804375c6 | note | Frequency - Prior to use of impermeable blanket
5341824e-83ea-5abe-8a23-0b89c56fe8ef | note | Acceptance Criteria - If required to be used, impermeable blankets shall comply with the requirements of ASTM C.171.
d7ca64b2-9759-5732-8bb2-bda3ce4c977a | note | ○ The blankets shall have sufficient strength and weight to meet the required conditions of service and shall be approved by the Contract Administrator before use.
6b3b5c64-5f58-5780-ba50-02a634095b22 | note | Reference Documents - Beca Spec 002 - 11.4.11.2
575cc1a8-4557-56a4-bdd6-79c28123130c | note | Inspection/Test Method - Verify
a9359f10-c550-57d0-86f3-f4c39895ced0 | note | Record of conformity - Aconex Reference
e9a2068e-b920-574f-ae6c-47200b624719 | note | HP
af397316-96ab-405d-86ac-e5784374b0b7 | signoff | AUTHORITY HOLDPOINT