## Sheet1
Wellington Girls College
Pipitea and Brook Seismic Remediation
East Elevation Façade - Stage 2 Enabling
Pipitea Seismic Remediation | Pipitea Enabling Works - Stage 2 - East Façade | Brook Block - Seismic Upgrade
Pile Caps - Ground Floor - Grid 3 B, Grid 4 A, Grid 4 B | Structual steel façade - Grid 3 B, Grid 4 B, Grid 5 B, Grid 6 B | Ground Floor Corridor - Dilapadation, Grid F - G
- Engineer inspection for existing reinforcement post concrete Break out
- Hold point - (Bolt placement plants to be submitted for review prior to core drilling/ fabrication of plates) | - Check for plumb and grid reference is correct of vertical 250mm DHS members | - Temporary propping - Sign off Hawkins
- Hold point - Engineer sign off - pre-fabrication | - Check that all bolts installed to horizontal 150mm DHS members | - Demolition of brick infill as per design
- Core drilling for hold down bolts - check embedmant is as per detail and core size | - Hold point - Engineer sign off - roof height connection detail - Type A, B and C | - Hold point - MHA sign off installation of new lighweight infill
- Hold point - Pre-grout inspection of hold downs | - Hold point - Engineer sign off - DHS slab edge/ Nib brackets
- Check welding of new plates and gussets is as per specification | - Check for correct exposure of threaded rod anchors and correct washers
- Hold point - Weld inspection and Engineer sign off |  | First Floor - Level 1 Corridor - Dilapdation, Grid F - G
- Installation of hold down bolts - check correct exposed thread from nut | MSB Lean-To
- Protective coating system - check proudct and application is as per specifcations |  | - Temporary propping - Sign off Hawkins
- Hold point - Coating system inspection | - Check Roof timber framing is as per 3604 with correct timber connections | - Demolition of brick infill as per design
- Top coating system check proudct and application is as per specifcations | - Check correct bolts for DHS Stringer mounted to 150mm horozontal members | - Hold point - MHA sign off installation of new lighweight infill
- Hold point - Coating system inspection | - Installation of baffle is as per MHA detail
- Concrete Pour - check correct engineered mix | - Hold point - Hawkins sign off - Installation of underlay is as per Thermakraft specification | Second Floor - Level 2 - Dilapadation,Grid C, Grid D, Grid F and Grid G
- Hold point - Holmes - Final Sign Off | - Check batten spacing and fixings as per MHA CAN
| - Hold point - Hawkins sign off - Roof/wall cladding, fixings and flashings. | - Serivce isolations completed and isolation/ lock out obtained from contractor
Cantilever Enabling Works - Level 1, 2 and 3 - Grids 1 A, 1 B, 8 A, 8B | - Check downpipe storm connection as per MHA detail. | - Check demolition of internal walls is sufficient
| - Hold point - MHA final sign off | - Check installation of new slab plates is as per design and bolt thread
- Installation of new 2-230PFC and 310UB40 check FPW to plate and bolt thread |  | - Check installation of new plates and bolts to existing 200UB column and 250UB31 beam
- Hold point -Engineer - Sign off Inspection |  | - Check FPW of Gusset
| Sprinkler Lean-To | - Hold point - Weld inspection
External Work K Frames - Level 2, 3 - Between Grid 3 A - Grid 4 A |  | - Check installation of 125x9SHS brace is as per design
| - Check DHS - Lintel connection roof framing as per Holmes CAN | - Hold Point - Engineer inspection
- Dilapidation report of external cladding condition | - Hold point - Engineer sign off | - Hawkins sign off - Framing, Services, wall linings and finishing works are as per details
- Check suffiecnt concrete is broken and removal doubler plates preperation | - Hawkins sign off - Installation of underlay is as per Thermakraft specification | - Hold point - MHA Sign off
- Check for FPW of new stiffners | - Check surface preperation to nib/ slab prior to installation of TPO membrane
- Hold Point -Weld Inspection sign off | - Check Base flashing installation and tape
- Hawkins sign off - protective coating system application as per specification | - Check batten spacing and fixings as per MHA CAN
- Hold point - Coating system inspection | - Hold point - Hawkins sign off - Roof/wall cladding, fixings and flashings. | Second Floor - Level 2 - Dilapadation, Grid 1 C/D, Grid 1, D/E, Grid 1 E/F, Grid 1, F/G. Grid 2 B/C, Grid 2 C/D,
- Hawkins sign off - Top coating system application as per specification | - Check downpipe storm connection as per MHA detail. | Grid 2 D/E, Grid 2, E/F, Grid 2 F/G
- Hold point - Coating system inspection | - Hold point - MHA final sign off
- Welding of new reinforcement as per Holmes specification |  | - Serivce isolations completed and isolation/ lock out obtained from contractor
- Hold point - Engineer sign off | East Elevation Façade - Grid 3 B, Grid 4 B, Grid 5 B, Grid 6 B | - Check demolition of internal walls is sufficient
- Check formwork is secure |  | - Check break out of slab chamfer enabling works
- Hold point - Pre grount inspection | - Check thermal insulation is as per specifications | - Check installation of new slab plates/ bolts are as per design
- Hawkins sign off - supplied grout is as per specification Eng mix design | - Hold point - WCC Inspection - Pre wrap | - Check FPW of Gusset
- Hold point - post pour inspection | - Hawkins sign off - Installation of underlay is as per Thermakraft specification | - Hold point - Weld inspection
- Reinstated cladding is as per previous installation | - Hold point - WCC Inspection - Pre clad | - Check installation of new 125x9SHS Column
- Hold point - MHA Defect inspection | - Hold point - Engineer inspection - Structual steel sign off | - Check installation of new 200UB30 beam and splice plates bolts
| - Installation of wall cladding - Level 1, 2 and 3 | - Check Installation of new 125x9SHS brace
| - Installation of flashings/ inter-story | - Hold point - Engineer inspection
Pipitea Columns - Level 1, 2 and 3 - Dilapadation, Grid 1A, 2A, 3A, 4A, 5A, 6A, 7A, 8A, 1B, 2B, 3B, 4B, 5B, 6B, 7B and 8B | - Hawkins sign off - Roof/wall cladding, fixings and flashings. | - Hawkins sign off - Framing, Services, wall linings and finishing works are as per details
| - Kingspan remedials - damage and paint defects - Thermakraft warranty supplied | - Hold point - MHA Sign off
- Serivce isolations completed and isolation/ lock out obtained from contractor | - Hold point - MHA/ WCC Final inspection - Weathertightness
- Building obstructions removed/ Demolition works
- Check sufficient concrete break out around columns (Width/depth)
- Hold Point - Engineer inspection of break out and exsisting reinforcement
- Hawkins sign off - Check installation of formwork for grout pour | TPO Installation - Ground Floor - Grid 3-8 | Third Floor - Level 3 - Dilapadation, Grid 1 D/E, Grid 1 E/F, Grid 2 D/E, Grid 2, E/F
- Hold Point - Engineer pre pour inspection
- Check correct grout and mix prior to column pour | - Check surface preperation is within tolerances | - Serivce isolations completed and isolation/ lock out obtained from contractor
- Hold Point - Engineer Final inspection | - Check TPO Installation is as per manufactures specifications | - Check installation of slab base plates and hold downs bolts
- Reinstatement of exsisiting building compotents | - Hold point - MHA Final inspection | - Check FPW of Gusset
- Hold point - MHA Final inspection |  | - Hold point - Weld Inspection
- Check conection of 250UB37 beam to existing 200UB30 portal frame
- Check head connection plate to 250UB37
- Check FPW of Gusset
Pipitea Floor Chasing - Level 1, 2 and 3 - Dilapadation, Grids 3-4 |  | - Hold point - Weld Inspection
- Installation of 250x6SHS longitudinal braces
- Concrete floor chasing for diaphragm rods - check width/ depth is as per drawings |  | - Hold point - Engineer Inspection
- Hold point - Engineer inspection |  | - Hawkins sign off - Framing, Services, wall linings and finishing works are as per details
- Installation of new reinforcement for floor chase - check as per drawings |  | - Hold point - MHA Sign off
- Hold point - Engineer inspection of reinforcement and pre pour
- Check correct grout and mix prior to floor chase pour
- Reinstate floor coverings as per existing
- Hold point - MHA sign off
Third Floor - Level 3 - Dilapadation, Grid 1 B, Grid 1 C, Grid 1 D, Grid 1 E, Grid 1 F, Grid 1 G,
Grid 2 B, Grid 2 C, Grid 2 D, Grid 2 E, Grid 2 F, Grid 2 G, Grid 2 G/H,
Grid 3 B, Grid 3 C, Grid 3 D, Grid 3 E, Grid 3, F, Grid 3 G and Grid 3 G/H.
- Check demolition of wall linings, fixed furtinure, framing and services enabling works
- C1 Column strengthening detail 16a
- Hold point - Engineer inspection
- Hawkins sign off - Framing, Services, wall linings and finishing works are as per details
- Hold point - MHA Sign off