## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Pile Caps Checklist | [5 empty] | Pipitea Seismic Remediation - Pile Caps (Ground Floor - Grid 3 B, Grid 4 A, Grid 4 B)
section | Details
checkpoint | Engineer inspection for existing reinforcement post concrete Break out
holdpoint | Hold point - Bolt placement plants to be submitted for review prior to core drilling/ fabrication of plates
checkpoint | Engineer sign off - pre-fabrication
holdpoint | Hold point - Engineer sign off - pre-fabrication
checkpoint | Core drilling for hold down bolts - check embedmant is as per detail and core size
holdpoint | Hold point - Pre-grout inspection of hold downs
checkpoint | Check welding of new plates and gussets is as per specification
holdpoint | Hold point - Weld inspection and Engineer sign off
checkpoint | Installation of hold down bolts - check correct exposed thread from nut
checkpoint | Protective coating system - check proudct and application is as per specifcations
holdpoint | Hold point - Coating system inspection
checkpoint | Top coating system check proudct and application is as per specifcations
holdpoint | Hold point - Coating system inspection
checkpoint | Concrete Pour - check correct engineered mix
holdpoint | Hold point - Holmes - Final Sign Off
checklist | Cantilever Enabling Works Checklist | [5 empty] | Pipitea Seismic Remediation - Cantilever Enabling Works (Level 1, 2 and 3 - Grids 1 A, 1 B, 8 A, 8B)
section | Details
checkpoint | Installation of new 2-230PFC and 310UB40 check FPW to plate and bolt thread
holdpoint | Hold point -Engineer - Sign off Inspection
checklist | External Work K Frames Checklist | [5 empty] | Pipitea Seismic Remediation - External Work K Frames (Level 2, 3 - Between Grid 3 A - Grid 4 A)
section | Details
checkpoint | Dilapidation report of external cladding condition
checkpoint | Check suffiecnt concrete is broken and removal doubler plates preperation
checkpoint | Check for FPW of new stiffners
holdpoint | Hold Point -Weld Inspection sign off
checkpoint | Hawkins sign off - protective coating system application as per specification
holdpoint | Hold point - Coating system inspection
checkpoint | Hawkins sign off - Top coating system application as per specification
holdpoint | Hold point - Coating system inspection
checkpoint | Welding of new reinforcement as per Holmes specification
holdpoint | Hold point - Engineer sign off
checkpoint | Check formwork is secure
holdpoint | Hold point - Pre grount inspection
checkpoint | Hawkins sign off - supplied grout is as per specification Eng mix design
holdpoint | Hold point - post pour inspection
checkpoint | Reinstated cladding is as per previous installation
holdpoint | Hold point - MHA Defect inspection
checklist | Pipitea Columns Checklist | [5 empty] | Pipitea Seismic Remediation - Pipitea Columns (Level 1, 2 and 3 - Dilapadation, Grid 1A, 2A, 3A, 4A, 5A, 6A, 7A, 8A, 1B, 2B, 3B, 4B, 5B, 6B, 7B and 8B)
section | Details
checkpoint | Service isolations completed and isolation/ lock out obtained from contractor
checkpoint | Building obstructions removed/ Demolition works
checkpoint | Check sufficient concrete break out around columns (Width/depth)
holdpoint | Hold Point - Engineer inspection of break out and exsisting reinforcement
checkpoint | Hawkins sign off - Check installation of formwork for grout pour
holdpoint | Hold Point - Engineer pre pour inspection
checkpoint | Check correct grout and mix prior to column pour
holdpoint | Hold Point - Engineer Final inspection
checkpoint | Reinstatement of exsisiting building compotents
holdpoint | Hold point - MHA Final inspection
checklist | Pipitea Floor Chasing Checklist | [5 empty] | Pipitea Seismic Remediation - Pipitea Floor Chasing (Level 1, 2 and 3 - Dilapadation, Grids 3-4)
section | Details
checkpoint | Concrete floor chasing for diaphragm rods - check width/depth is as per drawings
holdpoint | Hold point - Engineer inspection
checkpoint | Installation of new reinforcement for floor chase - check as per drawings
holdpoint | Hold point - Engineer inspection of reinforcement and pre pour
checkpoint | Check correct grout and mix prior to floor chase pour
checkpoint | Reinstate floor coverings as per existing
holdpoint | Hold point - MHA sign off
checklist | Structual Steel Façade Checklist | [5 empty] | Pipitea Enabling Works - Stage 2 - East Façade - Structual Steel Façade (Grid 3 B, Grid 4 B, Grid 5 B, Grid 6 B)
section | Details
checkpoint | Check for plumb and grid reference is correct of vertical 250mm DHS members
checkpoint | Check that all bolts installed to horizontal 150mm DHS members
holdpoint | Hold point - Engineer sign off - roof height connection detail - Type A, B and C
checkpoint | Engineer sign off - DHS slab edge/ Nib brackets
holdpoint | Hold point - Engineer sign off - DHS slab edge/ Nib brackets
checkpoint | Check for correct exposure of threaded rod anchors and correct washers
checklist | MSB Lean-To Checklist | [5 empty] | Pipitea Enabling Works - Stage 2 - East Façade - MSB Lean-To Checklist
section | Details
checkpoint | Check Roof timber framing is as per 3604 with correct timber connections
checkpoint | Check correct bolts for DHS Stringer mounted to 150mm horozontal members
checkpoint | Installation of baffle is as per MHA detail
holdpoint | Hold point - Hawkins sign off - Installation of underlay is as per Thermakraft specification
checkpoint | Check batten spacing and fixings as per MHA CAN
holdpoint | Hold point - Hawkins sign off - Roof/wall cladding, fixings and flashings.
checkpoint | Check downpipe storm connection as per MHA detail.
holdpoint | Hold point - MHA final sign off
checklist | Sprinkler Lean-To Checklist | [5 empty] | Pipitea Enabling Works - Stage 2 - East Façade - Sprinkler Lean-To
section | Details
checkpoint | Check DHS - Lintel connection roof framing as per Holmes CAN
holdpoint | Hold point - Engineer sign off
checkpoint | Hawkins sign off - Installation of underlay is as per Thermakraft specification
checkpoint | Check surface preperation to nib/ slab prior to installation of TPO membrane
checkpoint | Check Base flashing installation and tape
checkpoint | Check batten spacing and fixings as per MHA CAN
holdpoint | Hold point - Hawkins sign off - Roof/wall cladding, fixings and flashings.
checkpoint | Check downpipe storm connection as per MHA detail.
holdpoint | Hold point - MHA final sign off
checklist | East Elevation Façade Checklist | [5 empty] | Pipitea Enabling Works - Stage 2 - East Façade - East Elevation Façade (Grid 3 B, Grid 4 B, Grid 5 B, Grid 6 B)
section | Details
checkpoint | Check thermal insulation is as per specifications
holdpoint | Hold point - WCC Inspection - Pre wrap
checkpoint | Hawkins sign off - Installation of underlay is as per Thermakraft specification
holdpoint | Hold point - WCC Inspection - Pre clad
checkpoint | Engineer inspection - Structual steel sign off
holdpoint | Hold point - Engineer inspection - Structual steel sign off
checkpoint | Installation of wall cladding - Level 1, 2 and 3
checkpoint | Installation of flashings/ inter-story
checkpoint | Hawkins sign off - Roof/wall cladding, fixings and flashings.
checkpoint | Kingspan remedials - damage and paint defects - Thermakraft warranty supplied
holdpoint | Hold point - MHA/ WCC Final inspection - Weathertightness
checklist | TPO Installation Checklist | [5 empty] | Pipitea Enabling Works - Stage 2 - East Façade - TPO Installation (Ground Floor - Grid 3-8)
section | Details
checkpoint | Check surface preperation is within tolerances
checkpoint | Check TPO Installation is as per manufactures specifications
holdpoint | Hold point - MHA Final inspection
checklist | Ground Floor Corridor Checklist | [5 empty] | Brook Block - Seismic Upgrade - Ground Floor Corridor (Dilapadation, Grid F - G)
section | Details
checkpoint | Temporary propping - Sign off Hawkins
checkpoint | Demolition of brick infill as per design
holdpoint | Hold point - MHA sign off installation of new lighweight infill
checklist | First Floor - Level 1 Corridor Checklist | [5 empty] | Brook Block - Seismic Upgrade - First Floor - Level 1 Corridor (Dilapdation, Grid F - G)
section | Details
checkpoint | Temporary propping - Sign off Hawkins
checkpoint | Demolition of brick infill as per design
holdpoint | Hold point - MHA sign off installation of new lighweight infill
checklist | Second Floor - Level 2 Checklist | [5 empty] | Brook Block - Seismic Upgrade - Second Floor - Level 2 (Dilapadation,Grid C, Grid D, Grid F and Grid G)
section | Details
checkpoint | Service isolations completed and isolation/ lock out obtained from contractor
checkpoint | Check demolition of internal walls is sufficient
checkpoint | Check installation of new slab plates is as per design and bolt thread
checkpoint | Check installation of new plates and bolts to existing 200UB column and 250UB31 beam
checkpoint | Check FPW of Gusset
holdpoint | Hold point - Weld inspection
checkpoint | Check installation of 125x9SHS brace is as per design
holdpoint | Hold Point - Engineer inspection
checkpoint | Hawkins sign off - Framing, Services, wall linings and finishing works are as per details
holdpoint | Hold point - MHA Sign off
checklist | Second Floor - Level 2 Checklist | [5 empty] | Brook Block - Seismic Upgrade - Second Floor - Level 2 (Dilapadation, Grid 1 C/D, Grid 1, D/E, Grid 1 E/F, Grid 1, F/G. Grid 2 B/C, Grid 2 C/D, Grid 2 D/E, Grid 2, E/F, Grid 2 F/G)
section | Details
checkpoint | Service isolations completed and isolation/ lock out obtained from contractor
checkpoint | Check demolition of internal walls is sufficient
checkpoint | Check break out of slab chamfer enabling works
checkpoint | Check installation of new slab plates/ bolts are as per design
checkpoint | Check FPW of Gusset
holdpoint | Hold point - Weld inspection
checkpoint | Check installation of new 125x9SHS Column
checkpoint | Check installation of new 200UB30 beam and splice plates bolts
checkpoint | Check Installation of new 125x9SHS brace
holdpoint | Hold point - Engineer inspection
checkpoint | Hawkins sign off - Framing, Services, wall linings and finishing works are as per details
holdpoint | Hold point - MHA Sign off
checklist | Third Floor - Level 3 Checklist | [5 empty] | Brook Block - Seismic Upgrade - Third Floor - Level 3 (Dilapadation, Grid 1 D/E, Grid 1 E/F, Grid 2 D/E, Grid 2, E/F)
section | Details
checkpoint | Service isolations completed and isolation/ lock out obtained from contractor
checkpoint | Check installation of slab base plates and hold downs bolts
checkpoint | Check FPW of Gusset
holdpoint | Hold point - Weld Inspection
checkpoint | Check conection of 250UB37 beam to existing 200UB30 portal frame
checkpoint | Check head connection plate to 250UB37
checkpoint | Check FPW of Gusset
holdpoint | Hold point - Weld Inspection
checkpoint | Installation of 250x6SHS longitudinal braces
holdpoint | Hold point - Engineer Inspection
checkpoint | Hawkins sign off - Framing, Services, wall linings and finishing works are as per details
holdpoint | Hold point - MHA Sign off
checklist | Third Floor - Level 3 Checklist | [5 empty] | Brook Block - Seismic Upgrade - Third Floor - Level 3 (Dilapadation, Grid 1 B, Grid 1 C, Grid 1 D, Grid 1 E, Grid 1 F, Grid 1 G, Grid 2 B, Grid 2 C, Grid 2 D, Grid 2 E, Grid 2 F, Grid 2 G, Grid 2 G/H, Grid 3 B, Grid 3 C, Grid 3 D, Grid 3 E, Grid 3, F, Grid 3 G and Grid 3 G/H)
section | Details
checkpoint | Check demolition of wall linings, fixed furtinure, framing and services enabling works
checkpoint | C1 Column strengthening detail 16a
holdpoint | Hold point - Engineer inspection
checkpoint | Hawkins sign off - Framing, Services, wall linings and finishing works are as per details
holdpoint | Hold point - MHA Sign off