## Master List Templates
Id | Type | Name | Values | Prompting Name
9260ee0c-4730-4cb7-a9dd-5755522b437d | checklist | ITP - B1101A - Te Ngarue Bridge - Asphalt - Rev2 | itp | ITP - B1101A - Te Ngarue Bridge - Asphalt - Rev2
df2342ed-88c7-4af1-8335-d65f231e9c63 | section | 1 - Pre Construction
172eb5e6-cd7b-431b-955f-337c4d592e6f | checkpoint | CPS Approver
23b6156e-5a7f-5bf5-bcab-eb4005393d79 | textbox | Name / Signature
875df8b1-0b69-4459-adbf-e4609db3c21e | checkpoint | Quality Approver
8734fa42-0d09-531d-bff3-50a786ca947f | textbox | Name / Signature
fe49cfc1-d938-55fb-9845-d736deccf402 | textbox | CPS Eng.
2a0d9bc5-bcc4-5bcc-adcf-6a16afc9cac3 | textbox | Site Engineer
b6c89dcd-f3df-531c-9b8b-37c694ac0a5c | textbox | Quality Eng.
eacb0e88-9809-4ecd-beb8-2fbcbfef451c | checkpoint | 1.1 - Survey Setout - Milling
964d5869-1097-5cc4-ab42-765c63b682f8 | note | ACTION (Hold, Monitor, Witness) - WITNESS
849aa071-455b-5277-a95a-e3d1e240425f | note | Detail - Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
5f40d8ca-358f-5e4d-9e29-bfb58cc62720 | note | Frequency - Prior to commencement
775619d5-de76-5f99-b4d3-e41f1e2d765f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out on site
77e676ef-b9f7-5834-949f-0fd32cd40193 | note | Conformance Criteria - Visual inspection, Survey
e72e3e98-2d79-530c-881b-45970baca99b | note | Records - Subcontractor QA, Photos, COR
c0a5f281-72ec-4d5a-8001-e1252e6d7647 | checkpoint | 1.2 - Milling Existing AC
d3fa9f3c-cbdd-5f91-8d0f-00c5e8f106bd | note | ACTION (Hold, Monitor, Witness) - MONITOR
a767a845-ee11-53d4-892e-91e8bc98018c | note | Detail - Milling undertaken to correct depth of nominal thickness
4b2f4135-01a5-5e90-b72c-fa7c951fd248 | note | Frequency - During operation
bd90d34b-4a4f-578a-940c-6b0ba81ed2c9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Maeasurements
f99f4c7e-b25d-5f07-8719-8542de7de35f | note | Conformance Criteria - Visual Inspection
919a5e98-2351-54f3-b876-4bf41a3d819e | note | Records - Sub-contractor QA, Photos, COR
23783a05-ed57-4502-8b98-d36cf7be9d5f | section | 2 - Material Compliance
dc76e6f0-ab2a-4c8c-a32a-d024cf14566d | checkpoint | 2.1 - Binder Penetration Grade
3a6b6414-7581-5473-a9e0-d41cd5763e98 | note | ACTION (Hold, Monitor, Witness) - WITNESS
c3c78b76-fd91-5956-ba58-9f672c5fec5d | note | Detail - To comply with NZTA M01: 2020 - Table 6.1
fc701603-db6b-5541-983d-6d6c13a084bd | note | Frequency - Prior to commencement
d2ea8cf8-e13c-52d7-8c15-5eaddc1d728c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
f147bbe4-ba1d-55fd-a5d3-d800789ed1e6 | note | Conformance Criteria - NZTA M01: 2020 - Table 6.1, TNZ P11: 2007 - Table 5.2 Lab Mix Design Volumetric and Physical requirements
0e7d2ee4-7dbc-5167-a86b-6936619bba90 | note | Records - Lab Report
93dbb921-002f-44d1-80aa-72c05258ca0c | checkpoint | 2.2 - Coarse Aggregate Source
5949dc79-ff89-5659-a6a2-445b3347c02b | note | ACTION (Hold, Monitor, Witness) - WITNESS
4d1445d2-13f1-5333-8fde-2007065a769b | note | Detail - To comply with NZTA M10 - Refer to Section 2
748dbe25-7476-5d52-b50e-853a8a0b0a99 | note | Frequency - Testing frequency shall be in accordance with CCNZ BPG05 Quality Assurance of Aggregates.
338e2a0d-96ef-5e60-be8f-281e517b87c5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Table 2.1 in NZTA M10
8a837215-681e-582c-a1c7-d0336b3b385d | note | Conformance Criteria - Property Test
49f2d7bf-086f-548b-b470-1247db5347bd | note | Records - IANZ Report
10006e02-0066-46c0-a0f3-5f7f6ebe9b14 | checkpoint | 2.3 - Fine Aggregate Sources
bd6d7872-7493-5b2d-bfa3-0f153ff7012e | note | ACTION (Hold, Monitor, Witness) - WITNESS
82d36a7d-c978-581c-9439-2fae69071740 | note | Detail - To comply with NZTA M10 - Refer to Section 2
d1c629a0-0076-5ffd-8528-19d1cf8dc88b | note | Frequency - Testing frequency shall be in accordance with CCNZ BPG05 Quality Assurance of Aggregates.
823c8d88-ce03-5ea1-9a26-a3d6f4dbb232 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Table 2.2 in NZTA M10
49d037c0-a0e4-50cd-ad00-600fccbc21d1 | note | Conformance Criteria - Property Test
d9e6886e-ec2b-57fa-943f-5d044fdba436 | note | Records - IANZ Report
39f8e14c-4693-471c-b36f-357d23aaf808 | section | 3 - Construction
f22f62a8-b5a9-472a-9219-4f24f8af2427 | checkpoint | 3.1 - Survey Setout - Paving
867501e5-6823-592b-bb1c-bedd491ae832 | note | ACTION (Hold, Monitor, Witness) - WITNESS
131d8f1c-79ed-581b-a730-c9eca17c267f | note | Detail - Determine paving run start/stop locations
048a8f32-2a42-513c-b55e-d43bb4dd058d | note | Frequency - Prior to commencement
1bf8321d-acc1-5185-a73f-0144d4a41a07 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
54919f9d-428d-50eb-85ea-2693006a790a | note | Conformance Criteria - Ensure accurate survey setting out is in place.
4d4cfcd4-5ec1-54de-90b9-d40fef4c1d5e | note | Records - Subcontractor QA, Photos, COR
68920754-e16f-49f0-951f-1ab08b32d1a8 | checkpoint | 3.2 - Weather Check
ceb17488-c40f-501d-b371-468529440af9 | note | ACTION (Hold, Monitor, Witness) - WITNESS
400c6644-dfd1-5eeb-b46d-14650e5c8cc7 | note | Detail - Ensure weather conditions are acceptable for work to proceed
c1c9409e-e12d-5a71-a79b-fc946b270660 | note | Frequency - Prior to commencement
a16cf94b-d5b6-5109-bb4e-42a7395f403c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Weather Forecast
28a1f9e4-2b86-5cf1-9680-d0b9b168e8fe | note | Conformance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C
29769bca-24ad-5bd4-ad75-ca97572a2d79 | note | Records - Subcontractor QA, Photos, COR
9a422b84-b97c-4b2d-84fa-19249e9ab2ff | checkpoint | 3.3 - Surface Preparation
a813e16e-84eb-56cb-80a7-47cb41bd6065 | note | ACTION (Hold, Monitor, Witness) - WITNESS
ac87120f-48d9-5afc-8ee8-bb3c750ee678 | note | Detail - Ensure previous layer is broomed clean.
5b3e6d86-119c-5d2e-9731-763529d0fc46 | note | Frequency - Prior to commencement
e49eab43-d22c-5b3d-9717-af714225f25d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Truck broom to have been used and surface approved by CPS Engineer
3749a817-5d21-5fb3-a69d-f0fc50317eb6 | note | Conformance Criteria - Visual inspection
b1a9db95-f10d-5afd-9241-3414ee7abf9d | note | Records - Subcontractor QA, Photos, COR
47fb4558-546e-4584-84b4-2781ee283252 | checkpoint | 3.4 - Membrane seal
eb5bf02e-2fc6-5032-8d11-92318c12d23c | note | ACTION (Hold, Monitor, Witness) - WITNESS
0a21139e-2e65-517a-9879-223607f98e94 | note | Detail - Application as per Design Requirements (Chip size / binder application rate)
45d65ed4-9bfb-5583-890a-51ff33d56245 | note | Frequency - Prior to asphalt, Spray sheet for everyday.
5f1a2b86-1aca-5697-853b-3edbd29e88a6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Spray sheet, QA records
2a7d3988-a655-5738-bb61-00202008bbea | note | Conformance Criteria - Application as per Design Requirements (Chip size / binder application rate)
7ab17f84-28fb-5a60-9d3c-82cc3b2947e8 | note | Records - Subcontractor QA, Photos, COR
6ac57b02-201a-45b1-8291-23b8b960306e | checkpoint | 3.5 - Temperature of Asphalt for paving
4d6b07e9-1207-52ce-b226-70845d6e0346 | note | ACTION (Hold, Monitor, Witness) - WITNESS
3cd2f76d-8d5a-5c03-a35b-1d59eb383f23 | note | Detail - The temperature of the asphalt shall enable compaction required to achieve air voids %..
f46452b4-306d-5204-a73d-508e20708b25 | note | Frequency - 1 test per 20m of a
822bed8c-b498-5c5d-b6de-6bc89b1bda8f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Temperature Check
6d3f9486-ce60-5b82-8afc-2c3a1f83cf02 | note | Conformance Criteria - The asphalt shall have a minimum temperature of 80 degrees Celsius on completion of compaction.
92c92095-e220-5b3a-bebb-d5885d50704d | note | Records - Subcontractor QA, Photos, COR
56ca3580-e5dc-448c-8b08-e6f749bee102 | checkpoint | 3.6 - Thickness (Cores)
188e560f-6467-5bac-9109-787b85f7bdb9 | note | ACTION (Hold, Monitor, Witness) - HOLD
3de975b7-7a96-5332-8425-9c69cc3a861a | note | Detail - Layer thickness measured from core samples.
4127a9a4-70c3-5473-bb12-e4def42eada7 | note | Frequency - Each core taken for density
ea274fea-eff3-5e54-81e7-1361e102c495 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Core Test
234a0a0e-69d3-536e-a3ab-a92cdc7ecdef | note | Conformance Criteria - ±5mm nominal thickness as shown in the Drawings, Plans and/or Specifications
49c62a43-ce7c-5952-8de6-c010b7509058 | note | Records - Lab test report
cbb10b46-b91e-4f18-94cb-c12e9ab81a12 | signoff | AUTHORITY HOLDPOINT
04efb912-4e2c-4946-a089-2594999a7b78 | checkpoint | 3.7 - Compaction and air voids
20ff26c4-ec6d-5c43-9a07-1a3112a4708c | note | ACTION (Hold, Monitor, Witness) - HOLD
32b24579-61c0-5aa8-920e-5e8b380891ae | note | Detail - To comply with NZTA M10: or project specification
54cc6c30-5327-588f-b6f6-3e25438ff9d5 | note | Frequency - AS per specification
a74eae61-5ef1-557e-8f26-822a74be4bd8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM for Quality Control Only
886d9a3d-7c41-5a94-9a22-1973f2bf486d | note | Conformance Criteria - NZTA M/10:Section 9.9.3
8fab3964-0618-508d-aea6-c8a573fff36c | note | Records - IANZ Report, QA Records
6b8e6e11-e356-4900-9854-9909dfc8d120 | signoff | AUTHORITY HOLDPOINT
ce259c97-7fc7-4719-9bff-c7df43703900 | checkpoint | 3.8 - Surface Finish and Roughness
0329d52d-1884-5ead-9ae6-e4ce35c44e55 | note | ACTION (Hold, Monitor, Witness) - HOLD
1845d171-6e4b-55c1-b325-1c56ff32ef7e | note | Detail - No visible cracks, defects related to poorly constructed joints, water ponding,
30a541a7-0ad2-5425-941c-95bbcf809e3a | note | Frequency - Post Construction Site walkover.
52e8e30f-845d-5ffa-9ed8-b90dabb279b5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection.
df49cdff-2329-5a3c-9680-1b84837dbf42 | note | Conformance Criteria - No visible crack, no obvious defect related to poorly constructed joints. No areas with water ponding. Good ride quality.
301f3467-181c-520f-b37b-3eb76af84299 | note | Records - Subcontractor QA, Photos, COR
fdd5a08a-f60f-4ba6-98e6-3fa60695bdb6 | signoff | AUTHORITY HOLDPOINT
fbe7b7fc-bb3c-4190-941f-5f19f00d97a3 | section | 4 - Post-Construction Closeout
44d00399-5c4b-4d62-ac70-c5945e565ecf | checkpoint | 4.1 - Construction Walkover (Snags)
570b5d69-5bf4-5acc-86ed-dab239f0d1ec | note | ACTION (Hold, Monitor, Witness) - HOLD
ceb2c9c5-2da8-5ee2-8f8c-c449dfe66b9c | note | Detail - The Construction Walkover must be scheduled at least one week before the site's completion or demobilisation.
bc8442ce-1e4b-5f8d-8ea0-37ee45ef6682 | note | ○ Walkover must be attended by Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
e82a9927-6658-5a2f-829d-42e4159912f1 | note | Frequency - Before site works end
1b70f8ec-9097-5fa4-91ee-1c5526887e8f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Construction Walkover Report: with date, list of attendees and full defect/snag list.
d9ea7886-8df6-58c4-b319-1ecc0aa9dcd3 | note | ○ Defect List closed by Final Approver or Transferred to Master Snag List.
d533206e-24ba-503c-83b0-f17286d23bf3 | note | Conformance Criteria - Visual Inspection, Quality Site Inspection Report (QSIR)
ec06539d-f594-5763-a15e-6f37b4cc28e6 | note | Records - Walkover Report (COR or QSIR), Procore Defect List
b6d525d6-8199-4075-a8d7-a83a81516820 | signoff | AUTHORITY HOLDPOINT
3c8bbc3b-19e2-4c2b-9149-6f7ab562d8b8 | checkpoint | 4.2 - As-Built Survey & Red-Line Markups
8944ba0b-c017-554a-9b4e-0e7540c1893b | note | ACTION (Hold, Monitor, Witness) - HOLD
f0ed2e1b-0ef1-52f3-a311-cfb01e065eab | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
e37e4aaf-09e2-5b93-aa1f-31e076fa0fbc | note | ○ A survey of completed work must be requested and completed by the survey team.
36ec1eea-e674-5b76-a87b-d6e5be8802bb | note | Frequency - At the completion of the ITP of work
f8bac347-5832-55b2-8c74-ac51e9b3ae79 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - All RFI, NCRs and site changes must be recorded on the red-line drawing.
3dcedb78-2a38-5532-a4ce-f22e11ac1085 | note | ○ Signed and dated by author.
fccbb472-122b-5d08-a6e1-c2318e4384aa | note | ○ Approved by CPS
05373640-3b6e-5b5e-959d-e2fa944b54f9 | note | Conformance Criteria - Closed ABMS, Survey Confirmation
e38d2486-9832-578f-b894-adbf45089d80 | note | Records - Redline Markups, Closed ABMS, Survey Confirmation
75f04b8f-ca41-444e-bcfa-067ed6fe2e47 | signoff | AUTHORITY HOLDPOINT
f1eb1827-a638-4dd5-84a0-739f74a68bff | checkpoint | 4.3 - Quality Assurance Deliverables
d182b2f5-e70c-534d-b972-d5504ef9e434 | note | ACTION (Hold, Monitor, Witness) - WITNESS
d9c485d6-d4f9-5927-8277-2f552aff30fa | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
99eb541f-bec9-5e3d-a846-0c7cb6eea978 | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
9c823f1b-ec7a-537f-868e-0025abeaab33 | note | Frequency - At the completion of the ITP
a7301af7-a17c-5359-a1ba-f5cab86d5e7e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure all QA is uploaded into Procore
6fce8b96-d29f-506d-85bc-767f72c5e15a | note | Conformance Criteria - Document Review
746b01e5-0148-570b-a856-ec72245e18c8 | note | Records - NCRs, RFI's, Approved Redline mark-ups
c04339c2-a35f-45be-ae89-9d81d42230ec | checkpoint | 4.4 - Final Approvals
75a01b24-26fc-5eb0-b051-8554910be503 | note | ACTION (Hold, Monitor, Witness) - HOLD
7622fed6-e05c-5a2a-a39f-0e699595462a | note | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
81709d42-a3a4-5f23-b808-8af6ad3bf955 | note | Frequency - At the completion of the ITP
13ddbcb5-6cba-5628-8719-97ff7c2fcaaa | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure all parties have signed and approved the ITP QA records as being complete.
dc4c51b9-e421-538d-8fd3-64dbb87a29eb | note | Conformance Criteria - Document Review
e192e081-c87c-5b0b-bad0-6d58f5e1f98a | note | Records - Signatures
b971c9fe-bf1a-4e2c-b175-955e230a4cca | signoff | AUTHORITY HOLDPOINT