## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - B1101A - Te Ngarue Bridge - Asphalt - Rev2 | itp |  |  |  |  | ITP - B1101A - Te Ngarue Bridge - Asphalt - Rev2
section | 1 - Pre Construction
checkpoint | CPS Approver
textbox | Name / Signature
checkpoint | Quality Approver
textbox | Name / Signature
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Survey Setout - Milling
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out on site
label | Conformance Criteria - Visual inspection, Survey
label | Records - Subcontractor QA, Photos, COR
checkpoint | 1.2 - Milling Existing AC
label | ACTION (Hold, Monitor, Witness) - MONITOR
label | Detail - Milling undertaken to correct depth of nominal thickness
label | Frequency - During operation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Maeasurements
label | Conformance Criteria - Visual Inspection
label | Records - Sub-contractor QA, Photos, COR
section | 2 - Material Compliance
checkpoint | 2.1 - Binder Penetration Grade
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - To comply with NZTA M01: 2020 - Table 6.1
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | Conformance Criteria - NZTA M01: 2020 - Table 6.1, TNZ P11: 2007 - Table 5.2 Lab Mix Design Volumetric and Physical requirements
label | Records - Lab Report
checkpoint | 2.2 - Coarse Aggregate Source
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - To comply with NZTA M10 - Refer to Section 2
label | Frequency - Testing frequency shall be in accordance with CCNZ BPG05 Quality Assurance of Aggregates.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Table 2.1 in NZTA M10
label | Conformance Criteria - Property Test
label | Records - IANZ Report
checkpoint | 2.3 - Fine Aggregate Sources
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - To comply with NZTA M10 - Refer to Section 2
label | Frequency - Testing frequency shall be in accordance with CCNZ BPG05 Quality Assurance of Aggregates.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Table 2.2 in NZTA M10
label | Conformance Criteria - Property Test
label | Records - IANZ Report
section | 3 - Construction
checkpoint | 3.1 - Survey Setout - Paving
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Determine paving run start/stop locations
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
label | Conformance Criteria - Ensure accurate survey setting out is in place.
label | Records - Subcontractor QA, Photos, COR
checkpoint | 3.2 - Weather Check
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Ensure weather conditions are acceptable for work to proceed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Weather Forecast
label | Conformance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C
label | Records - Subcontractor QA, Photos, COR
checkpoint | 3.3 - Surface Preparation
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Ensure previous layer is broomed clean.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Truck broom to have been used and surface approved by CPS Engineer
label | Conformance Criteria - Visual inspection
label | Records - Subcontractor QA, Photos, COR
checkpoint | 3.4 - Membrane seal
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Application as per Design Requirements (Chip size / binder application rate)
label | Frequency - Prior to asphalt, Spray sheet for everyday.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Spray sheet, QA records
label | Conformance Criteria - Application as per Design Requirements (Chip size / binder application rate)
label | Records - Subcontractor QA, Photos, COR
checkpoint | 3.5 - Temperature of Asphalt for paving
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - The temperature of the asphalt shall enable compaction required to achieve air voids %..
label | Frequency - 1 test per 20m of a
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Temperature Check
label | Conformance Criteria - The asphalt shall have a minimum temperature of 80 degrees Celsius on completion of compaction.
label | Records - Subcontractor QA, Photos, COR
checkpoint | 3.6 - Thickness (Cores)
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Layer thickness measured from core samples.
label | Frequency - Each core taken for density
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Core Test
label | Conformance Criteria - ±5mm nominal thickness as shown in the Drawings, Plans and/or Specifications
label | Records - Lab test report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Compaction and air voids
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - To comply with NZTA M10: or project specification
label | Frequency - AS per specification
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM for Quality Control Only
label | Conformance Criteria - NZTA M/10:Section 9.9.3
label | Records - IANZ Report, QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Surface Finish and Roughness
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - No visible cracks, defects related to poorly constructed joints, water ponding,
label | Frequency - Post Construction Site walkover.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection.
label | Conformance Criteria - No visible crack, no obvious defect related to poorly constructed joints. No areas with water ponding. Good ride quality.
label | Records - Subcontractor QA, Photos, COR
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Post-Construction Closeout
checkpoint | 4.1 - Construction Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - The Construction Walkover must be scheduled at least one week before the site's completion or demobilisation.
label | ○ Walkover must be attended by Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Frequency - Before site works end
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Construction Walkover Report: with date, list of attendees and full defect/snag list.
label | ○ Defect List closed by Final Approver or Transferred to Master Snag List.
label | Conformance Criteria - Visual Inspection, Quality Site Inspection Report (QSIR)
label | Records - Walkover Report (COR or QSIR), Procore Defect List
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - As-Built Survey & Red-Line Markups
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | ○ A survey of completed work must be requested and completed by the survey team.
label | Frequency - At the completion of the ITP of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - All RFI, NCRs and site changes must be recorded on the red-line drawing.
label | ○ Signed and dated by author.
label | ○ Approved by CPS
label | Conformance Criteria - Closed ABMS, Survey Confirmation
label | Records - Redline Markups, Closed ABMS, Survey Confirmation
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the ITP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure all QA is uploaded into Procore
label | Conformance Criteria - Document Review
label | Records - NCRs, RFI's, Approved Redline mark-ups
checkpoint | 4.4 - Final Approvals
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
label | Frequency - At the completion of the ITP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure all parties have signed and approved the ITP QA records as being complete.
label | Conformance Criteria - Document Review
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT