## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP - B1101A - Te Ngarue Bridge - Asphalt - Rev2 | itp | ITP - B1101A - Te Ngarue Bridge - Asphalt - Rev2 |  | f1ad6906-600a-4b4c-a178-3e66cf8cfd8f
| section | 1 - Pre Construction
| checkpoint | CPS Approver
a35cdbb7-5b6f-538c-8e5b-91f123212fbe | textbox | Name / Signature
| checkpoint | Quality Approver
2f998671-b154-5e42-ba67-aba4afc4263e | textbox | Name / Signature
3a93e92a-168f-505d-8543-a00f3e6f187e | textbox | CPS Eng.
358f1a18-ad7f-5ec4-9eb5-a26a82b14b40 | textbox | Site Engineer
39bfcef6-c2c0-52d8-86d0-70f980d00c2e | textbox | Quality Eng.
| checkpoint | 1.1 - Survey Setout - Milling
bfd8d095-a35c-5868-8048-732aba30c407 | note | ACTION (Hold, Monitor, Witness) - WITNESS
191c8f46-713e-519c-b52b-0fe11e484cfa | note | Detail - Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
cb40da36-47c9-5ebd-a1d4-72bcb3bca5dd | note | Frequency - Prior to commencement
bb215748-4aaf-5b9d-a9e8-eb4c3af7a8b2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out on site
6b4a695e-3f07-5c78-abab-2d3fad48a041 | note | Conformance Criteria - Visual inspection, Survey
9f8e74a7-fbe5-5815-b15d-b18627262b27 | note | Records - Subcontractor QA, Photos, COR
| checkpoint | 1.2 - Milling Existing AC
f275bb6d-1410-558e-972a-360884dfbf14 | note | ACTION (Hold, Monitor, Witness) - MONITOR
03e759ff-905d-5cc8-b3ff-20a0dedb7df4 | note | Detail - Milling undertaken to correct depth of nominal thickness
135b4016-e807-5d48-a7f1-6c15635d294b | note | Frequency - During operation
c68afe87-214c-5791-b1c9-843b412ebcd8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Maeasurements
e7acbf09-1e65-53b1-be9f-398d3bb30eaa | note | Conformance Criteria - Visual Inspection
f081db27-1ac9-5698-b9f6-fc36ad5671fe | note | Records - Sub-contractor QA, Photos, COR
| section | 2 - Material Compliance
| checkpoint | 2.1 - Binder Penetration Grade
34ea2d6d-62a0-5612-b142-248103ac2055 | note | ACTION (Hold, Monitor, Witness) - WITNESS
57d77748-a9be-5741-bc44-9cfaa59d04c6 | note | Detail - To comply with NZTA M01: 2020 - Table 6.1
682076de-62f2-5aa9-89e7-ba34eeab82c1 | note | Frequency - Prior to commencement
01d97a5d-e0b0-508d-8a77-1969dc22aeac | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
973fa2d8-282c-5d89-ba0b-1469afe66d3c | note | Conformance Criteria - NZTA M01: 2020 - Table 6.1, TNZ P11: 2007 - Table 5.2 Lab Mix Design Volumetric and Physical requirements
b9a04121-0037-5ce9-b5f7-5d7d25b03881 | note | Records - Lab Report
| checkpoint | 2.2 - Coarse Aggregate Source
37f9c9b5-db79-5af3-b22c-52022c0b9900 | note | ACTION (Hold, Monitor, Witness) - WITNESS
2ae8c69f-e303-5b9d-b9d6-6ffa1d2abeef | note | Detail - To comply with NZTA M10 - Refer to Section 2
35d64cad-2502-56fa-9be1-9ff815eeb19e | note | Frequency - Testing frequency shall be in accordance with CCNZ BPG05 Quality Assurance of Aggregates.
eb0aef08-65c4-5b56-8440-0c263170ab12 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Table 2.1 in NZTA M10
aad611ee-b88b-5edc-a85d-96e98f448c9c | note | Conformance Criteria - Property Test
9bc333d0-4eb4-5318-a1d6-8b1766d94bb1 | note | Records - IANZ Report
| checkpoint | 2.3 - Fine Aggregate Sources
0d4399fd-f118-5824-80f2-b09018bb0545 | note | ACTION (Hold, Monitor, Witness) - WITNESS
19666b07-c8d5-5510-bb49-1161ffb08755 | note | Detail - To comply with NZTA M10 - Refer to Section 2
e934bce4-94cc-5eb9-a8b2-48fa3f888579 | note | Frequency - Testing frequency shall be in accordance with CCNZ BPG05 Quality Assurance of Aggregates.
6088fd67-94d2-553d-abfb-6d3e60efafa9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Table 2.2 in NZTA M10
7d7d27a8-30da-5a98-a437-ed73af146078 | note | Conformance Criteria - Property Test
f358fdf8-efcf-521d-8610-f37f21fbe427 | note | Records - IANZ Report
| section | 3 - Construction
| checkpoint | 3.1 - Survey Setout - Paving
d733d34e-8406-5f95-b8f9-25564bc65259 | note | ACTION (Hold, Monitor, Witness) - WITNESS
3cceb7ad-143e-5b28-b74c-c04150b67fbe | note | Detail - Determine paving run start/stop locations
c46720ae-8a56-5f7f-9291-b143cc754a0b | note | Frequency - Prior to commencement
78ea2011-9dcc-5b41-aa06-c7dcc0107436 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
2c9e0da4-500f-5df4-a938-06b9573e2971 | note | Conformance Criteria - Ensure accurate survey setting out is in place.
940e3a30-084f-5e8d-98b9-fd6dfd0bbedb | note | Records - Subcontractor QA, Photos, COR
| checkpoint | 3.2 - Weather Check
ed22c21c-0f7d-5d17-a4a9-2a22102766f2 | note | ACTION (Hold, Monitor, Witness) - WITNESS
ad403731-0a6f-53d4-9744-49d098f4320a | note | Detail - Ensure weather conditions are acceptable for work to proceed
c1788ac8-7849-5a6d-858e-0fec065b0fc3 | note | Frequency - Prior to commencement
2ecfad9a-37f9-58cb-a7a2-7c8eacd3f3ef | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Weather Forecast
166a9427-9371-5b3b-9c01-6e473b9ac862 | note | Conformance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C
f77d85de-236a-536d-8d12-3496d1b3b85c | note | Records - Subcontractor QA, Photos, COR
| checkpoint | 3.3 - Surface Preparation
876c4991-d608-57f2-8496-8d066342bc24 | note | ACTION (Hold, Monitor, Witness) - WITNESS
593a5f3e-c3d8-5ffa-81c8-f5c5b393878a | note | Detail - Ensure previous layer is broomed clean.
0d455c47-3560-53c6-9eb7-9e209f168be5 | note | Frequency - Prior to commencement
e6e66a87-80b2-5327-aee4-9b8b5baeaab6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Truck broom to have been used and surface approved by CPS Engineer
688dc740-3d6b-59ff-b9ea-1e3158f2660f | note | Conformance Criteria - Visual inspection
fa42c2d6-adbb-5a6b-b031-97b3f91e9a2f | note | Records - Subcontractor QA, Photos, COR
| checkpoint | 3.4 - Membrane seal
5a284096-bcbd-5db1-bc0f-933d46c5fc58 | note | ACTION (Hold, Monitor, Witness) - WITNESS
c54f5024-3552-5606-89bc-bc557a086215 | note | Detail - Application as per Design Requirements (Chip size / binder application rate)
7d06ea85-b51d-57a4-8867-aee054741723 | note | Frequency - Prior to asphalt, Spray sheet for everyday.
ae955b25-14b7-5307-a76e-56c478953944 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Spray sheet, QA records
1d46c1eb-9b42-54c3-99bd-a0217c1d3c7b | note | Conformance Criteria - Application as per Design Requirements (Chip size / binder application rate)
a8440403-581d-5405-aa8c-a73241612d01 | note | Records - Subcontractor QA, Photos, COR
| checkpoint | 3.5 - Temperature of Asphalt for paving
b0d3845f-d3fa-562c-a84b-63e3f1e03873 | note | ACTION (Hold, Monitor, Witness) - WITNESS
87109b15-1c8a-5fba-92b1-eaf40fbb0819 | note | Detail - The temperature of the asphalt shall enable compaction required to achieve air voids %..
03441d5c-0ad8-5230-ae80-68e5eeb3898a | note | Frequency - 1 test per 20m of a
19925f7b-4a56-5199-a438-4a6d016c14ff | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Temperature Check
cf1490a7-47de-578b-a975-3015a2ec26af | note | Conformance Criteria - The asphalt shall have a minimum temperature of 80 degrees Celsius on completion of compaction.
df9aa0c2-8ab2-561e-aada-7ca0ef040234 | note | Records - Subcontractor QA, Photos, COR
| checkpoint | 3.6 - Thickness (Cores)
841ef03d-5bdc-5bb1-b9e7-2677ede5a00e | note | ACTION (Hold, Monitor, Witness) - HOLD
061fd960-4f3d-5a5f-a40b-06b17ffe34d6 | note | Detail - Layer thickness measured from core samples.
6bf94861-5162-548d-9c0a-80649ac78630 | note | Frequency - Each core taken for density
a559fe9f-24a2-54d0-ab32-95b1e6735913 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Core Test
1b813315-4135-5862-b8cc-b7c66a50fd00 | note | Conformance Criteria - ±5mm nominal thickness as shown in the Drawings, Plans and/or Specifications
8649a857-13a9-50e3-a81e-1db1f149e5d7 | note | Records - Lab test report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Compaction and air voids
d4177dc2-6969-5f86-bfc2-757bc356ac14 | note | ACTION (Hold, Monitor, Witness) - HOLD
007abf0d-62b8-5977-b4e5-f3ac0214c4a1 | note | Detail - To comply with NZTA M10: or project specification
b45c291f-8eed-5a6c-bf5b-fa5027aec6e9 | note | Frequency - AS per specification
ceda1b67-1c97-5acd-8766-6807b5b6f796 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM for Quality Control Only
c06aeb3d-2e5d-5ede-a0d4-b23ea50df00d | note | Conformance Criteria - NZTA M/10:Section 9.9.3
ec50b1b6-0e58-5a28-8abb-4ee37dddf362 | note | Records - IANZ Report, QA Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Surface Finish and Roughness
9b3da267-2585-5c59-ba46-8e739f53dac6 | note | ACTION (Hold, Monitor, Witness) - HOLD
f4d1145b-6807-5ef6-a415-d1ec5fa825b9 | note | Detail - No visible cracks, defects related to poorly constructed joints, water ponding,
858105e3-cc49-5b2e-b9e5-7589a84e2471 | note | Frequency - Post Construction Site walkover.
00d813f7-dd07-5813-95ed-5100b3380bbf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection.
b1d4c02e-fe7e-52e8-8c80-aaddf50d73cc | note | Conformance Criteria - No visible crack, no obvious defect related to poorly constructed joints. No areas with water ponding. Good ride quality.
a26bc67a-59ec-596c-b2fc-9aa71da350f2 | note | Records - Subcontractor QA, Photos, COR
| signoff | AUTHORITY HOLDPOINT
| section | 4 - Post-Construction Closeout
| checkpoint | 4.1 - Construction Walkover (Snags)
a5ef9c37-aec6-5f97-8253-664cff68acfd | note | ACTION (Hold, Monitor, Witness) - HOLD
d5837341-8b7e-573f-8a67-5d6c38ca668a | note | Detail - The Construction Walkover must be scheduled at least one week before the site's completion or demobilisation.
f80b5213-542b-5f5c-9a57-e65f2c69b98b | note | ○ Walkover must be attended by Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
b69f4494-0750-582e-9cd8-697371fab551 | note | Frequency - Before site works end
1ec3f914-39eb-58b7-93f4-2e9632c6d858 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Construction Walkover Report: with date, list of attendees and full defect/snag list.
30fff47d-c4b7-50f0-81fa-672ac8ae213b | note | ○ Defect List closed by Final Approver or Transferred to Master Snag List.
2bdd33fa-54a3-51b7-a659-2b370cd4f3aa | note | Conformance Criteria - Visual Inspection, Quality Site Inspection Report (QSIR)
a3955341-d89b-5c39-a645-03b6638239f0 | note | Records - Walkover Report (COR or QSIR), Procore Defect List
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - As-Built Survey & Red-Line Markups
8b039735-ed93-5b38-b5f0-1a4428c5f7af | note | ACTION (Hold, Monitor, Witness) - HOLD
51cd8c4a-6960-535d-a31b-f492775533cd | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
e85adfb3-4c6c-5bc0-b56f-52c104c10071 | note | ○ A survey of completed work must be requested and completed by the survey team.
b9113a19-b6df-5d28-af45-3f84cbe8ef14 | note | Frequency - At the completion of the ITP of work
d4ff379d-5b74-56d5-8177-9359f27c261f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - All RFI, NCRs and site changes must be recorded on the red-line drawing.
813dfec6-2705-5925-8a5e-f14c7ac5f876 | note | ○ Signed and dated by author.
839cb979-e9fb-5d32-bb49-91902863bc05 | note | ○ Approved by CPS
e4c6611e-6bdc-50e2-a549-c15cf9a7c33a | note | Conformance Criteria - Closed ABMS, Survey Confirmation
51c3941a-44f0-5322-9646-acde7981730b | note | Records - Redline Markups, Closed ABMS, Survey Confirmation
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Quality Assurance Deliverables
2e7fa278-28b4-5134-ab47-e20c8366f78a | note | ACTION (Hold, Monitor, Witness) - WITNESS
261ec18e-d1ce-5251-8791-1e9d9aa7d858 | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
c090ab77-a970-5ad8-bd79-eaae3f17057a | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
be6d480a-b470-5c82-a291-c1978ed9d313 | note | Frequency - At the completion of the ITP
7a92551c-69c6-5ebd-a884-0f970df890c5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure all QA is uploaded into Procore
50dd5d48-aa60-5932-8b40-f355a57d3675 | note | Conformance Criteria - Document Review
b8aba472-00d0-5492-91b3-54f254bb5b19 | note | Records - NCRs, RFI's, Approved Redline mark-ups
| checkpoint | 4.4 - Final Approvals
399e2687-aa8c-5884-96f7-dda65768e44f | note | ACTION (Hold, Monitor, Witness) - HOLD
bb0d99a0-55a8-58b2-83fd-31d16c00eeea | note | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
4e166037-5ff4-5589-9ca9-abc3f701f986 | note | Frequency - At the completion of the ITP
e4e90304-cc94-5a1e-a7ec-0aa822f77de5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure all parties have signed and approved the ITP QA records as being complete.
077d2401-c82d-5914-a3ba-a738f4b7339c | note | Conformance Criteria - Document Review
3382cc77-6797-55fb-8c49-23b360cfe162 | note | Records - Signatures
| signoff | AUTHORITY HOLDPOINT