## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Fibertite to Plywood Checklist |  |  |  |  | Yes | QA - Fibertite to Plywood Checklist | 02394e50-12c9-4f1d-bd44-f9c8490a93d4
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Plywood Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status |  |  | checkpoint | No Screws/nails/fixings popping up
checkpoint-status |  |  | checkpoint | Joints flush and even
checkpoint-group |  |  | section | Fibertite Membrane
checkpoint-status |  |  | checkpoint | Correct Glue used per spec
checkpoint-status |  |  | checkpoint | Fibertite fully glued to plywood
checkpoint-status |  |  | checkpoint | Broom / roll fibertite into glue
checkpoint-status |  |  | checkpoint | All laps, details, penetrations fully closed & QA'd with hook
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Clamps / rings / baskets installed
checkpoint-status |  |  | checkpoint | Flooded / ILD checked
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications (right way around)
checkpoint-status |  |  | checkpoint | Fixings and welding done according to details
checkpoint-status |  |  | checkpoint | Welding of Fibertite to flashings fully finished and QA'd with hook
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-flat |  |  | checklist | Defect - |  |  |  |  | Yes | Add Defect Checklist | 0fbdb55a-8b50-4b38-8335-a6baa1771674
checkpoint-status |  |  | checkpoint | Defect details recorded
text | 9b18e909-7530-4d08-ad54-acb417409980 |  | textbox | Explanation of defect:
text | 3af60290-922d-4e09-aeb9-b795186cbbd5 |  | textbox | Area:
text | da7b5fcc-182d-4ccf-ade5-02dfaae6dedb |  | textbox | Party responsible for damages:
text | f37cdc9e-47d2-43c7-b8ce-36034d624bbc |  | textbox | Efforts required for repair:
text | 16d78d9b-0a7d-4e07-bb38-68e664e6d30e |  | textbox | Man hours required for repair:
holdpoint |  |  | signoff | Request Approval from Main Contractor
checkpoint-status |  |  | checkpoint | Defect Fixed
holdpoint |  |  | signoff | Request Defect signoff
checklist-flat |  |  | checklist | Site Visit date: |  |  |  |  | Yes | Supplier Site Visit | 10480266-5557-4ed8-89e0-9c48effad31b
checkpoint-no-status |  |  | checkpoint | Site Details
text | 6d41fa6a-4e1a-577e-a624-6bd736f97876 |  | textbox | Job Name
text | 22044acf-ec81-5b86-a826-c71cabe41273 |  | textbox | Who is in attendance
text | 1235194d-88da-53a0-854a-ce85145c2b1e |  | textbox | Area/Gridlines/Detail
checkpoint-status |  |  | checkpoint | Photos
text | e4f72de6-232e-5c0f-a8f5-0b30ac9ea698 |  | textbox | Inspection Notes
holdpoint |  |  | signoff | Signoff Required
checklist-sectioned |  |  | checklist | Metal Roof Installation Checklist |  |  |  |  | Yes | QA - Metal Roof Installation Checklist | 19540bfb-edf5-4252-8896-1ddbfda7351e
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Safety Mesh Installation
checkpoint-status |  |  | checkpoint | Laid perpindicular to the purlins.
checkpoint-status |  |  | checkpoint | Fully secured to Purlins/Timber.
checkpoint-status |  |  | checkpoint | No protruding bits or loose ends.
checkpoint-group |  |  | section | Covertek Roofing Paper Installation
checkpoint-status |  |  | checkpoint | Laid either perpindicular or parallel with purlins.
checkpoint-status |  |  | checkpoint | Overlapped a minimum 150mm
checkpoint-status |  |  | checkpoint | All areas completely covered.
checkpoint-status |  |  | checkpoint | Laid tight to timeber/purlins.
checkpoint-status |  |  | checkpoint | Secured so it will not blow away if roof not being installed immediately.
checkpoint-group |  |  | section | Metal Roof Installation
checkpoint-status |  |  | checkpoint | Drip edge installed
checkpoint-status |  |  | checkpoint | Laid straight & perpindicular to gutter/purlins
checkpoint-status |  |  | checkpoint | Gutter overhang 75mm minimum
checkpoint-status |  |  | checkpoint | Top ends of sheets turned up.
checkpoint-status |  |  | checkpoint | Fixings back into purlins and laid in a straight line as per Code of Practice.
checkpoint-status |  |  | checkpoint | Closure foam to gutter ends.
checkpoint-group |  |  | section | Roof Flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to drawings and to the Code of Practice.
checkpoint-status |  |  | checkpoint | All fixings in place and done according to code of practice.
checkpoint-status |  |  | checkpoint | All laps and junctions sealed properly.
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Soffit Checklist |  |  |  |  | Yes | QA - Soffit Checklist | 27f47415-d2a2-41db-945e-72d11030a50f
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Substrate ready (check plans) with proper purlin spacing
checkpoint-status |  |  | checkpoint | Design/Spec/Approvals complete
checkpoint-group |  |  | section | Install
checkpoint-status |  |  | checkpoint | Flashings installed according to plans
checkpoint-status |  |  | checkpoint | All sealant work complete
checkpoint-status |  |  | checkpoint | Install soffit lining according to plans/spec/best practice
checkpoint-status |  |  | checkpoint | Screw pattern according to plans/spec/best practice
checkpoint-status |  |  | checkpoint | Finish flashings complete
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Cladding Install Complete
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | Sheet Tanking System Checklist |  |  |  |  | Yes | QA - Sheet Tanking System Checklist | 2d98a6e7-5832-4072-9718-55f1634f3a7e
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Primer
checkpoint-status |  |  | checkpoint | Applied as per specification on dry substrate at 5m2 per litre
checkpoint-group |  |  | section | Membrane
checkpoint-status |  |  | checkpoint | Temperature must be over 4 degrees for membrane install
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear
checkpoint-status |  |  | checkpoint | Membrane applied with min 50mm overlap
checkpoint-status |  |  | checkpoint | Overlap is to pressure applied or rolled for seal
checkpoint-group |  |  | section | Protection
checkpoint-status |  |  | checkpoint | Works to be protected by main contractor
checklist-sectioned |  |  | checklist | MSR checklist |  |  |  |  | Yes | MSR checklist | 2e3f515c-adab-46f0-8cb2-464379fd2baf
checkpoint-group |  |  | section | Pre start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Purlins installed and QA / handover received from main contractor
checkpoint-status |  |  | checkpoint | visual inspection by SWP
checkpoint-group |  |  | section | Liner deck
checkpoint-status |  |  | checkpoint | Liner deck fixed down in every purlin and every pan
checkpoint-status |  |  | checkpoint | Correct fixing installed
checkpoint-group |  |  | section | Vapor control layer
checkpoint-status |  |  | checkpoint | Substrate clean, dry, free of debris
checkpoint-status |  |  | checkpoint | Z flashing installed
checkpoint-status |  |  | checkpoint | VCL installed and covered all surface
checkpoint-status |  |  | checkpoint | VCL lapped with a minimum of 100mm side and end laps
checkpoint-group |  |  | section | Acoustic board install
checkpoint-status |  |  | checkpoint | VCL clean, no ponding water, free of debris prior to install
checkpoint-status |  |  | checkpoint | VCL has been cheeked for damages
checkpoint-status |  |  | checkpoint | All holes/penetrations patched
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Boards tightly butted all areas covered
checkpoint-status |  |  | checkpoint | Correct insulation installed as per spec
checkpoint-group |  |  | section | Underlay installed
checkpoint-status |  |  | checkpoint | Correct underlay installed as per specifications
checkpoint-status |  |  | checkpoint | Overlapped a minimum 150mm side laps and 200mm end laps
checkpoint-status |  |  | checkpoint | All areas covered
checkpoint-status |  |  | checkpoint | Underlay installed as per specifications
checkpoint-status |  |  | checkpoint | Joints taped together as per drawings and specifications
checkpoint-group |  |  | section | Metal roof installation
checkpoint-status |  |  | checkpoint | Drip edge installed as per drawings and specifications
checkpoint-status |  |  | checkpoint | Laid straight and perpendicular to gutter/purlins
checkpoint-status |  |  | checkpoint | Gutter overhang as per drawings and specifications
checkpoint-status |  |  | checkpoint | Top end turned up
checkpoint-status |  |  | checkpoint | Bottom ends turned down
checkpoint-status |  |  | checkpoint | Closure foam installed
checkpoint-status |  |  | checkpoint | Screw pattern according to plan/specs/fixing plan
checkpoint-group |  |  | section | Flashing install
checkpoint-status |  |  | checkpoint | Sealant installed with 2 continues beads
checkpoint-status |  |  | checkpoint | Clean excess sealant
checkpoint-status |  |  | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
checkpoint-status |  |  | checkpoint | Flashings installed as per drawings and specifications and facing away from waterflow
checkpoint-status |  |  | checkpoint | Fixings installed as per drawings and specifications
checkpoint-group |  |  | section | Review and sign off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work completed, checked and reviewed as per specifications
holdpoint |  |  | signoff | Client/main contractor sign off
checklist-flat |  |  | checklist | Final inspection |  |  |  |  | Yes | Add Final Inspection Checklist | 329dc5e6-4826-4947-9f68-a1642b5aeb7c
checkpoint-status |  |  | checkpoint | Final inspection
text | 5c48b2f9-7155-5010-a625-9c61273b1f4a |  | textbox | Date
text | cd590b2d-dfd9-5926-aa7f-cbbffee96ba3 |  | textbox | Area/elevation/grids
text | f185db39-ef5a-566f-a627-b84ed061402b |  | textbox | Description
label | bc73c8d4-7e08-5fa4-a4f2-97028cc937d1 |  | note | Attach Photos
holdpoint |  |  | signoff | Request Signature Signoff
checklist-flat |  |  | checklist | Variation Details - |  |  |  |  | Yes | Add Variation Checklist | 346ad1ae-2db9-4943-98f4-9eec5f7af0fb
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Reference/Drawing/Instruction Number
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Variation Area
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Materials & labour breakdown
holdpoint |  | Invalid dependant | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  | Invalid dependant | signoff | Request Variation Signoff
checklist-sectioned |  |  | checklist | Fibertherm Checklist |  |  |  |  | Yes | QA - Fibertherm Checklist | 3b574f13-34f2-4bc2-8138-d2aa5c2cddbf
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Metal Deck
checkpoint-status |  |  | checkpoint | Timber to have separation
checkpoint-status |  |  | checkpoint | End openings to have closure foam installed
checkpoint-status |  |  | checkpoint | Base deck screwed down in every pan
checkpoint-status |  |  | checkpoint | VCL tape to be installed to all sheet laps
checkpoint-status |  |  | checkpoint | VCL tape to all upstands
checkpoint-group |  |  | section | Post and Rail install
checkpoint-status |  |  | checkpoint | Post installed at correct fixing centers
checkpoint-status |  |  | checkpoint | Thermal break pad under post foot
checkpoint-status |  |  | checkpoint | Rail installed to posts
checkpoint-status |  |  | checkpoint | Gutter line colsure/drip edge flashing installed
checkpoint-group |  |  | section | Insulation install
checkpoint-status |  |  | checkpoint | Specified Insulation installed
checkpoint-status |  |  | checkpoint | No Gaps
checkpoint-group |  |  | section | Top Deck install
checkpoint-status |  |  | checkpoint | Lay sheets straight
checkpoint-status |  |  | checkpoint | Hang over into gutter min 75mm
checkpoint-status |  |  | checkpoint | Top end of sheets turned up
checkpoint-status |  |  | checkpoint | Bottom end of sheets turned down
checkpoint-status |  |  | checkpoint | Fixing back to rail
checkpoint-status |  |  | checkpoint | Profile washers
checkpoint-status |  |  | checkpoint | Screwed off as per fixing plan
checkpoint-group |  |  | section | Flashing install
checkpoint-status |  |  | checkpoint | Installed correctly, accoriding to spec's & drawings
checkpoint-status |  |  | checkpoint | Fixings according to specs & details
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Torch on Warmroof Over Metal Deck Checklist |  |  |  |  | Yes | QA - Torch on Warmroof Over Metal Deck Checklist | 4dc9f947-5e62-4411-98ab-38c047d71ecb
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Metal Deck
checkpoint-status |  |  | checkpoint | Timber to have separation barrier
checkpoint-status |  |  | checkpoint | Base deck screwed down in every pan
checkpoint-status |  |  | checkpoint | Sheet edges stitched together at 300mm centres
checkpoint-status |  |  | checkpoint | No sharp edges protruding
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with recessed flat plates
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-status |  |  | checkpoint | Prime of Securrock
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Bleed of bitumen on overlap should be up to 10mm
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check of all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint-status |  |  | checkpoint | Clamps / rings / baskets installed and press into overflows and outlets
checkpoint-status |  |  | checkpoint | Flood test / ILD tested
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Fiberglass System Checklist |  |  |  |  | Yes | QA - Fiberglass System Checklist | 4e8855d3-f0fa-45e7-a65a-018cb9230a2d
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Surface Prep
checkpoint-status |  |  | checkpoint | Concrete free of contaminants
checkpoint-status |  |  | checkpoint | Concrete flat and smooth
checkpoint-status |  |  | checkpoint | Bug holes in plinths filled and smooth
checkpoint-status |  |  | checkpoint | All 90deg corners chamfered
checkpoint-group |  |  | section | Membrane install
checkpoint-status |  |  | checkpoint | Install sealant angle fillets to all wall floor junctions
checkpoint-status |  |  | checkpoint | Prime surfaces with Epistixx
checkpoint-status |  |  | checkpoint | 1st body coat with 300gram fiberglass installed
checkpoint-status |  |  | checkpoint | 2nd body coat
checkpoint-status |  |  | checkpoint | 3rd body coat
checkpoint-status |  |  | checkpoint | Traxx 2000 wear coat.
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | MSR Cladding Checklist |  |  |  |  | Yes | QA - MSR Cladding Checklist | 57ce0832-ebc3-4a45-a7f7-f4e22565d269
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Substrate clean and ready
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes / penetrations patched and watertight
checkpoint-group |  |  | section | Brackets and Rails
checkpoint-status |  |  | checkpoint | Z brackets installed to fixing plan
checkpoint-status |  |  | checkpoint | Rhom rail installed to fixing plan
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | VCL no damage
checkpoint-status |  |  | checkpoint | Insulation installed with no gaps
checkpoint-group |  |  | section | Cladding
checkpoint-status |  |  | checkpoint | Covertek installed with 150mm laps
checkpoint-status |  |  | checkpoint | Starter flashings installed
checkpoint-status |  |  | checkpoint | Soaker flashings installed
checkpoint-status |  |  | checkpoint | Sheets laid straight
checkpoint-status |  |  | checkpoint | Closure foam installed
checkpoint-status |  |  | checkpoint | Correct screw pattern / fixings used
checkpoint-group |  |  | section | Flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to spec and drawings
checkpoint-status |  |  | checkpoint | Fixings according to spec and details
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Weather Monitoring |  |  |  |  | Yes | Weather Monitoring | 595991e9-7a95-4145-9d5f-2d452dd03de0
checkpoint-group |  |  | section | Current Weather
checkpoint-status |  |  | checkpoint | Todays date & Time
checkpoint-status |  |  | checkpoint | Wind / weather conditions
checkpoint-status |  |  | checkpoint | Record any delays
checkpoint-status |  |  | checkpoint | area / gridlines
checkpoint-status |  |  | checkpoint | Comments / issues / observations
checkpoint-group |  |  | section | Weather Forecast
checkpoint-status |  |  | checkpoint | What is the weather forecast this week
checkpoint-status |  |  | checkpoint | Record any delays
checkpoint-status |  |  | checkpoint | area / gridlines
checkpoint-status |  |  | checkpoint | Comments / issues / observations
checklist-sectioned |  |  | checklist | Metal Flashing Install Checklist |  |  |  |  | Yes | QA - Metal Flashing Install Checklist | 5b8ecbf1-cf8d-4cf8-b36a-84962de6774b
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Metal Flashing Install
checkpoint-status |  |  | checkpoint | Installed with a minimum upstand of 150mm or according to drawings
checkpoint-status |  |  | checkpoint | Expansion joint installed if needed (i.e. with runs longer than 12m for coloursteel or 8m for Ali.)
checkpoint-status |  |  | checkpoint | Fixings according to Code as a minimum (or plans if more are required) in a straight line
checkpoint-status |  |  | checkpoint | Laid in a straight and tidy manner
checkpoint-status |  |  | checkpoint | All laps and junctions sealed properly and facing away from waterflow
checkpoint-status |  |  | checkpoint | All visible ends & junctions cut and folded straight and tidy
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Torch on Warmroof Over Plywood Checklist |  |  |  |  | Yes | QA - Torch on Warmroof Over Plywood Checklist | 5cd1b383-82ca-42b2-be14-e322381fefb8
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Plywood
checkpoint-status |  |  | checkpoint | Plywood clean and dry. Free from dirt/debris and and ready for priming
checkpoint-status |  |  | checkpoint | No screws/nails/fixings popping up
checkpoint-status |  |  | checkpoint | Plywood joints flush and even
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with recessed flat plates
checkpoint-status |  |  | checkpoint | Prime of Securrock
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check of all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint-status |  |  | checkpoint | Clamps / rings / baskets installed and press into overflows and outlets
checkpoint-status |  |  | checkpoint | Flood test / ILD checked
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Fibertite Warm Roof Over Plywood Checklist |  |  |  |  | Yes | QA - Fibertite Warm Roof Over Plywood Checklist | 65e58486-8ea9-4c05-92ff-fad05b1ed13f
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Plywood Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status |  |  | checkpoint | No Screws/nails/fixings poping up
checkpoint-status |  |  | checkpoint | Plywood joints flush and even
checkpoint-group |  |  | section | Vapor Control Layer
checkpoint-status |  |  | checkpoint | Substrate clean, dry, and free of debris
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapor control layer has been checked and no damage
checkpoint-status |  |  | checkpoint | Insulation boards installed
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards)
checkpoint-status |  |  | checkpoint | Correct length of fixing with load washer if no Securock
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length of fixing with load washer
checkpoint-group |  |  | section | Fibertite
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with the welding machines
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Claps/rings/baskets installed
checkpoint-status |  |  | checkpoint | Flood/ILD tested
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Carpark MMA Checklist |  |  |  |  | Yes | QA - Carpark MMA Checklist | 77ca425d-0b28-4174-a9e7-2fc08cd862a6
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | SSSP onsite
checkpoint-status |  |  | checkpoint | Photos of any existing linemarkings installed
checkpoint-status |  |  | checkpoint | Fencing demarcation installed
checkpoint-status |  |  | checkpoint | Site signage installed
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Surface Prep
checkpoint-status |  |  | checkpoint | Removal of coatings
checkpoint-status |  |  | checkpoint | Grind of substrate
checkpoint-status |  |  | checkpoint | Shotblast of substrate to achieve suitable profile
checkpoint-group |  |  | section | Pre-start of membrane install
checkpoint-status |  |  | checkpoint | Substrate dry
checkpoint-group |  |  | section | Membrane install
checkpoint-status |  |  | checkpoint | Prime of substrate
checkpoint-status |  |  | checkpoint | Stripe out cracks
checkpoint-status |  |  | checkpoint | Map out areas based on coverage rates for install
checkpoint-status |  |  | checkpoint | Membrane layer installed
checkpoint-status |  |  | checkpoint | Wear layer installed and broadcast
checkpoint-status |  |  | checkpoint | Excess broadcast swept and removed
checkpoint-status |  |  | checkpoint | 1st Top coat
checkpoint-status |  |  | checkpoint | 2nd top coat
checkpoint-status |  |  | checkpoint | Linemarking installed
checkpoint-status |  |  | checkpoint | Site cleared and broken down
checkpoint-status |  |  | checkpoint | Site cleared and broken down
checklist-flat |  |  | checklist | Delay Checklist |  |  |  |  | Yes | Add Delay Checklist | 7922a7c8-755b-4127-a02d-f613d6eceac2
checkpoint-no-status |  |  | checkpoint | Delay details.
text | ae5b692f-ee75-4a3d-90e7-43a6b2bca49e |  | textbox | Date:
text | 8e11a44b-51f7-4a8f-9494-ec9e467452ec |  | textbox | Description:
text | 22cd20b8-86af-49a9-97d4-39d5b860ca1a |  | textbox | Area/Grids:
text | e5ab19af-90b5-4328-9a8b-ee0707087643 |  | textbox | Wind/Weather Conditions:
checklist-sectioned |  |  | checklist | Fibertite Warm Roof Over Metal Deck Checklist |  |  |  |  | Yes | QA - Fibertite Warm Roof Over Metal Deck Checklist | 7b6a78cd-33eb-4b9c-8167-428765295228
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Metal Deck
checkpoint-status |  |  | checkpoint | Timber to have separation barrier
checkpoint-status |  |  | checkpoint | Base deck screwed down in every pan
checkpoint-status |  |  | checkpoint | Sheet edges stiched together at 300mm centres
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed in a brick pattern
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-status |  |  | checkpoint | Fixings at correct spacing according to spec if no Securock in system.
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with load washer
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-group |  |  | section | FiberTite
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into the adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean of laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with welding machine
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Clamps / rings / baskets installed
checkpoint-status |  |  | checkpoint | Flooded / ILD checked
checkpoint-group |  |  | section | Fiberclad flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications (Right way around)
checkpoint-status |  |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of weld with QA hook
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-flat |  |  | checklist | Flood Test Area: |  |  |  |  | Yes | Add Flood Testing Checklist | 83a26037-8132-4aec-a44c-16aece8cad53
checkpoint-status |  |  | checkpoint | Is area fully finished, QA’d and ready to be tested
checkpoint-no-status |  |  | checkpoint | Flood test details
text | dc968f8f-9cf1-485a-a65f-e4087427ee32 |  | textbox | Date:
text | b0fb2bc4-3c3c-47bb-93fe-add4a651804d |  | textbox | Area tested:
text | befd486d-6456-4e39-ba95-1395566ebfda |  | textbox | Duration:
button | 3fff6840-5866-4f4c-96c8-494f7e9efd79 |  | button | Have you checked regularly for leaks | Yes, No, N/A
button | 050fef10-15f2-4590-ba62-2a0b1b1b0a29 |  | button | Is there rain in the forecast | Yes, No, N/A
button | 0816c7fc-09ce-4e48-9a88-625c7f8c9a23 |  | button | Have you eft some outlets/scuppers so that the building doesn't flood | Yes, No, N/A
button | b9de0cd4-9c7a-42cb-89ee-535d7ebdcd00 |  | button | Have all leaks been repaired | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Flood test complete
button | 5d04628a-e7a1-4bd7-b9ee-92a88ef12e94 |  | button | Have the plugs been removed from the drains | Yes, No, N/A
button | b74c91b9-0371-4641-ad5b-1c9d76ee0c77 |  | button | Debris and materials removed from the gutter/membrane/roof | Yes, No, N/A
holdpoint |  |  | signoff | Sign Off
checklist-sectioned |  |  | checklist | Fibertite Overlay Install Checklist |  |  |  |  | Yes | QA - Fibertite Overlay Install Checklist | 86fa3ae5-b498-4c1a-b47a-4a8f2db7c644
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Substrate
checkpoint-status |  |  | checkpoint | Mechanically Fix existing roof pans to Purlins after checking underneath from inside that we're not going to puncture pipes or wires
checkpoint-status |  |  | checkpoint | Cut back existing roof edge at gutter
checkpoint-status |  |  | checkpoint | Remove ridge as we go
checkpoint-group |  |  | section | VCL-Vapour Control Layer
checkpoint-status |  |  | checkpoint | Surface/Substrate is dry, clean and free from sharp edges
checkpoint-status |  |  | checkpoint | All areas covered and lapped a minimum of 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and made watertight
checkpoint-group |  |  | section | Roof Pan Infills
checkpoint-status |  |  | checkpoint | Surface is dry before installing Poly
checkpoint-status |  |  | checkpoint | Infills to be a minimum 5mm above ridges on roof
checkpoint-status |  |  | checkpoint | Every pan has been infilled
checkpoint-group |  |  | section | Roofboard
checkpoint-status |  |  | checkpoint | Substrate/surface dry & clean prior to being installed
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct screws with load washer
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-status |  |  | checkpoint | Install 70mm X 100mm zincalume flashing at gutter edge for strength
checkpoint-group |  |  | section | Fibertite
checkpoint-status |  |  | checkpoint | Correct Glue being used for substrate
checkpoint-status |  |  | checkpoint | Fibertite fully glued to substrate
checkpoint-status |  |  | checkpoint | Broom/rolling of fibertite
checkpoint-status |  |  | checkpoint | Wipe/clean laps with acetone prior to welding
checkpoint-status |  |  | checkpoint | All laps, details, penetrations fully welded/closed and QA'd with hook
checkpoint-status |  |  | checkpoint | Clamps / rings / baskets installed
checkpoint-status |  |  | checkpoint | Flooded / ILD checked
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly
checkpoint-status |  |  | checkpoint | Fixed down according to specification
checkpoint-status |  |  | checkpoint | Cleaned down with acetone prior to welding
checkpoint-status |  |  | checkpoint | Fibertite fully welded to flashing and QA'd with hook
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Fibertite to Concrete Checklist |  |  |  |  | Yes | QA - Fibertite to Concrete Checklist | 8b43d48e-9fe6-4899-8efa-b52c471f762d
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Concrete Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status |  |  | checkpoint | All lumps and sharp concrete bits ground/hammered down
checkpoint-status |  |  | checkpoint | Large holes filled with grout
checkpoint-group |  |  | section | Fibertite
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with the welding machines
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Claps/rings/baskets installed
checkpoint-status |  |  | checkpoint | Flood/ILD tested
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications (right way around)
checkpoint-status |  |  | checkpoint | Fixing and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of weld with QA hook
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
folder-normal |  |  | checklist | New Files Folder: |  |  |  |  | Yes | Add Files Folder | a1ef9ba1-314d-4515-935e-8977f81394ea
checklist-sectioned |  |  | checklist | Torch On Warmroof to Concrete Checklist |  |  |  |  | Yes | QA - Torch On Warmroof to Concrete Checklist | a52624ac-8f95-40f0-8e12-acf5ed5ce688
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Concrete
checkpoint-status |  |  | checkpoint | Concrete clean and dry. Free from dirt/debris and ready for priming
checkpoint-status |  |  | checkpoint | All lumps and sharp concrete bits ground down/hammered down
checkpoint-status |  |  | checkpoint | Large holes filled with grout
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with load washer
checkpoint-status |  |  | checkpoint | Prime of Securrock
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check of all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint-status |  |  | checkpoint | Clamps / rings / baskets press into overflows and outlets
checkpoint-status |  |  | checkpoint | Flood test / ELD tested
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Fibertite Warm Roof Over Concrete Checklist |  |  |  |  | Yes | QA - Fibertite Warm Roof Over Concrete Checklist | a63cb575-2a50-4515-bfad-d13f180955c9
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Concrete Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status |  |  | checkpoint | All lumps and sharp concrete bits ground/hammered down
checkpoint-status |  |  | checkpoint | Large holes filled with grout
checkpoint-group |  |  | section | Vapor Control Layer
checkpoint-status |  |  | checkpoint | Substrate clean, dry, and free of debris
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapor control layer has been checked and no damage
checkpoint-status |  |  | checkpoint | Insulation boards installed
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards)
checkpoint-status |  |  | checkpoint | Correct length of fixing with load washer if no Securock
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length of fixing with load washer
checkpoint-group |  |  | section | Fibertite
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with the welding machines
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Claps/rings/baskets installed
checkpoint-status |  |  | checkpoint | Flood/ILD tested
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications (right way around)
checkpoint-status |  |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of weld with QA hook
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Torch On to Concrete Checklist |  |  |  |  | Yes | QA - Torch On to Concrete Checklist | b6435835-f637-494c-94ff-323b43773e3e
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Concrete Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status |  |  | checkpoint | All lumps and sharp concrete bits ground/hammered down
checkpoint-status |  |  | checkpoint | Large holes filled with grout
checkpoint-group |  |  | section | Prime of Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and free from debris
checkpoint-status |  |  | checkpoint | Primer installed
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Install clamps/rings/baskets
checkpoint-status |  |  | checkpoint | Flood/ILD test
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-flat |  |  | checklist | Dayworks - |  |  |  |  | Yes | Add Dayworks Checklist | ca83f8f1-ecf9-4a21-bb06-00062795c8c8
checkpoint-status |  |  | checkpoint | Day Work Details
text | d27d8079-cce6-47f2-bc8f-5447bd0b63c3 |  | textbox | NTSC / SI #:
text | d63889f7-ee5a-4b1a-8284-614d5f938189 |  | textbox | Labours (HR)
text | 926bb36c-59db-4b70-828c-6bc1bf2ce049 |  | textbox | Work Description:
text | 693bbb1a-ade5-4140-a549-223cae16f4cb |  | textbox | Materials:
text | 6d1abe7d-16c2-45ff-b354-7f74775359b8 |  | textbox | SWP Representative. Prepared By:
text | 7e548609-67fa-4b3f-91fa-027d546e556f |  | textbox | Client Representative. Confirmed By:
holdpoint |  |  | signoff | Request Signature Signoff
checklist-sectioned |  |  | checklist | Metal Cladding Install Checklist |  |  |  |  | Yes | QA - Metal Cladding Install Checklist | da19ab95-f38c-4240-89c4-a010dd479929
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Install
checkpoint-status |  |  | checkpoint | Bottom flashing installed straight/level all the way around
checkpoint-status |  |  | checkpoint | Building wrap installed
checkpoint-status |  |  | checkpoint | Flashing tape installed (check plans)
checkpoint-status |  |  | checkpoint | Soaker flashings installed
checkpoint-status |  |  | checkpoint | Cladding installed plumb and straight
checkpoint-status |  |  | checkpoint | Screw pattern according to plan/spec/best practice
checkpoint-no-status |  |  | checkpoint | Flashings installed as per specification
checkpoint-status |  |  | checkpoint | Closure foams installed
checkpoint-status |  |  | checkpoint | Fixings installed correctly
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-flat |  |  | checklist | Daily Cassette Log - |  |  |  |  | Yes | Add Daily Cassette Log | e9e04f0b-8887-4255-b764-fbeb1737c43a
checkpoint-no-status |  |  | checkpoint | Date:
text | e5ab19af-90b5-4328-9a8b-ee0707087643 |  | textbox
checkpoint-no-status |  |  | checkpoint | Cassette Number:
text | 8e11a44b-51f7-4a8f-9494-ec9e467452ec |  | textbox
checkpoint-no-status |  |  | checkpoint | Record any delays:
text | 22cd20b8-86af-49a9-97d4-39d5b860ca1a |  | textbox
checkpoint-no-status |  |  | checkpoint | Wind/Weather Conditions:
text | 5114a122-dcf7-44a7-be38-8623182196af |  | textbox
checkpoint-no-status |  |  | checkpoint | Comments/Issues/Observations:
text | a6aebd36-6433-4aca-b8f4-ef6216c059cf |  | textbox
checklist-sectioned |  |  | checklist | Torch On to Plywood Checklist |  |  |  |  | Yes | QA - Torch On to Plywood Checklist | f053e528-0d97-4ddd-906e-c099a1c727d8
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Plywood Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status |  |  | checkpoint | No Screws/nails/fixings popping up
checkpoint-status |  |  | checkpoint | Joints flush and even
checkpoint-group |  |  | section | Prime of Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and free from debris
checkpoint-status |  |  | checkpoint | Primer installed
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Install clamps/rings/baskets
checkpoint-status |  |  | checkpoint | Flood/ILD test
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Metal Gutter Install Checklist |  |  |  |  | Yes | QA - Metal Gutter Install Checklist | f51f5199-03e8-4f27-9484-1b4203f215b5
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Install
checkpoint-status |  |  | checkpoint | Brackets installed according to plans/spec/best practice
checkpoint-status |  |  | checkpoint | Gutter lapped and sealed correctly according to best practice
checkpoint-status |  |  | checkpoint | All terminations and ends folded/sealed properly
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | MSR Checklist |  |  |  |  | Yes | QA - MSR Checklist | f7aabcfa-80a2-4617-8513-dd1ddf4bc877
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Metal Deck
checkpoint-status |  |  | checkpoint | Timber to have separation barrier
checkpoint-status |  |  | checkpoint | Base deck screwed down and secure
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Acoustic Board
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed with no gaps
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-group |  |  | section | Topdeck Install
checkpoint-status |  |  | checkpoint | Covertek Installed with 150mm overlap
checkpoint-status |  |  | checkpoint | Drip edge installed
checkpoint-status |  |  | checkpoint | Lay sheet with minimum 75mm gutter overhang
checkpoint-status |  |  | checkpoint | Top end of sheet turned up
checkpoint-status |  |  | checkpoint | Fixing back into purlin
checkpoint-status |  |  | checkpoint | Closure foam to gutter end
checkpoint-status |  |  | checkpoint | Profile Washers over 12m
checkpoint-status |  |  | checkpoint | Sheets straight & perpendicular to gutter
checkpoint-status |  |  | checkpoint | Screw pattern as per fixing plan
checkpoint-group |  |  | section | Roof flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specification & drawings
checkpoint-status |  |  | checkpoint | Fixings done according to specifications and details
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off