## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 5a5bc47c-a109-405d-8b0e-f08c60280b0a |  | checklist | Rooflogic Fibertite Over Plywood |  |  |  |  | Yes | Rooflogic Fibertite Over Plywood | 13b5a5bb-fdc8-448a-9a02-3c859afa29e7
checkpoint-group | f04b0e4d-d92b-4d0b-a4d1-9ac02cc2e19e |  | section | Pre Start
checkpoint-status | 9d2edbba-0da0-4c9e-85e8-67f7c549e1d7 |  | checkpoint | Area Accessible
checkpoint-status | 8ce4592a-e152-4f4a-8e47-bbbef3b16a6c |  | checkpoint | Edge protection in place
checkpoint-status | 57894996-b773-4642-9483-bcfda6ec67ec |  | checkpoint | Substrate clean and clear of debris and moss/mould
checkpoint-group | 1703d146-39ac-4df4-9ed4-e579d958ce17 |  | section | Plywood substrate
checkpoint-status | 868b14a3-4226-490e-a393-953089588f83 |  | checkpoint | Fixed off at correct centres
checkpoint-status | 7e6ec9bc-aa1f-446d-95ae-c61b33849fc6 |  | checkpoint | No damage to substare
checkpoint-status | b4d44e27-c91e-4837-936e-894d38004132 |  | checkpoint | Install ILD SS Mesh over substrate
checkpoint-group | 51a382e4-9a96-490d-ab3d-da1026e76f28 |  | section | Roof board HDP
checkpoint-status | 43b6d60e-6a89-4b3b-ac93-134054a92e3e |  | checkpoint | Roof boards Installed tight and in brick pattern
checkpoint-status | ab868f43-5c7f-43ab-b84a-a457e40fc1f0 |  | checkpoint | Correct length screw with laod washer
checkpoint-status | 0064345d-786f-4dd3-a193-76576e951447 |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-group | f19553e9-77ab-4cbb-8122-ef5c26955f69 |  | section | Fibertite XT
checkpoint-status | 96eb8b44-0361-4878-9142-2930e700d624 |  | checkpoint | Surface clean and free from debris
checkpoint-status | d3c22c6a-1cff-47f1-b05b-c41d0caa6097 |  | checkpoint | Adhesive installed to base sheet the width of the roll
checkpoint-status | 172cfbac-c6be-477c-b041-3fa05fd68b19 |  | checkpoint | Laying of membrane into the adhesive
checkpoint-status | 4523da7d-ec78-4a6f-af80-69f851008a3a |  | checkpoint | Laping on adjacent membrane to be minimum of 75mm
checkpoint-status | 4af2d85f-b8d8-488a-b722-fe10dcdb60b3 |  | checkpoint | Broom/rolling of membrane into adhesive
checkpoint-status | 26d4cb02-bf6f-40d8-8bac-debd2f77b118 |  | checkpoint | Wipe and clean of laps prior to welding
checkpoint-status | 69576865-fdcc-4f24-8234-07fc5d35579d |  | checkpoint | Test weld with welding machine
checkpoint-status | 7775ed5d-6791-4114-a305-6b7def41a400 |  | checkpoint | Probe of seam with QA hook
checkpoint-status | f5e993d1-6b4c-4dde-921c-7cc7f69385d9 |  | checkpoint | ILD test
checkpoint-group | 965b84f0-11cd-47e2-9792-f76656eb7399 |  | section | Fiberclad Flashings
checkpoint-status | 4f29d985-bf27-49c4-862a-018f3634e4f0 |  | checkpoint | Installed correctly accordnig to specifications
checkpoint-status | dd43b619-437a-462d-bfa7-fe06b2a2dcdf |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status | 5aa23474-e444-44bb-84f6-4df1928da51d |  | checkpoint | Probe of weld with QA hook
checkpoint-group | f26c0c72-b737-4cc4-8b61-7743543d395d |  | section | Review and Sign off
checkpoint-status | 8da6332f-aad8-44b4-9969-fccf6fca048e |  | checkpoint | All installation work complete, checked and reviwed as per specification
checkpoint-status | ebe1f39e-b805-4557-bdcb-c9898adf02e0 |  | checkpoint | FCC project manager sign off
holdpoint | da50790d-f605-422a-bd77-a3dddf744bb3 |  | signoff | Sign off
checklist-flat | df6b7d66-7278-4acb-b75a-e71b3ca8695d |  | checklist | ILD Report |  |  |  |  | Yes | ILD Report Checklist | 165b8f4e-bbc6-4b03-ba0e-58d52d7a536f
checkpoint-status | 49ab4eb7-bd61-4aac-a775-f05b1d43de3b |  | checkpoint | ILD report attached
checklist-flat | 03d08f73-208d-49d7-9f6f-2e5483036271 |  | checklist | 1.6 Aluminium Flashing Checklist |  |  |  |  | Yes | 1.6 Aluminium Flashing Checklist (221) | 1e11b932-434b-447a-baa3-7584a391a9ff
checkpoint-status | 9e1e6c9b-2c6d-4780-8621-11c49dd52fc7 |  | checkpoint | Measured twice and dry fitting signed off before wet apply
checkpoint-status | aa13f51c-4477-4196-a902-637bb95d1300 |  | checkpoint | Surface preparation complete
label | dc4fc1a3-9535-4003-8b20-91f744022b46 |  | note | Aluminium properly cleaned and all oil is removed.
label | dd627cc7-862f-4f01-83ef-5c4f4d3820ce |  | note | Resene SIPDS No 4 and spec sheet 4: 8/1
checkpoint-status | ba1403bb-20a0-41bc-b94a-888309d3d871 |  | checkpoint | Coating as per specification
label | 55e2d1ec-9186-4547-a671-5c378cdd794d |  | note | 1st Coat - Resene Armourcote 221, brushable, Epoxy Primer, 50 microns.
label | c74c8546-c2d2-4034-8483-6252df3f94da |  | note | 2nd Coat - Resene Uracryl 404 Solvent Urethane Acrylic LowSheen, 50 microns.
label | 22e87da0-0fe5-4b01-9c34-27576f44d531 |  | note | 3rd Coat - Resene Uracryl 404 Solvent Urethane Acrylic LowSheen, 50 microns.
checkpoint-status | 83d258b4-5fd3-4234-937c-6d236f5d6733 |  | checkpoint | Paint sales slips / batch numbers attached or photographed
checkpoint-status | c9d00cc1-20f4-470e-88ea-989caf130581 |  | checkpoint | Flashing installed according to drawings
checkpoint-status | d0accb92-8d87-4e51-b8bb-6b9a2f02c050 |  | checkpoint | Fixings according to Code as a minimum (or plans if more are required)
checkpoint-status | 26ea0c0c-d97e-47cd-b401-746afd024f88 |  | checkpoint | All laps and junctions sealed properly and facing away from waterflow
checklist-flat | 8181e75e-b523-473d-b267-87840e841356 |  | checklist | Flashing no. |  |  |  |  | Yes | Rainwater Outlet Checklist | 24918d08-8c0e-49b0-93aa-d986ce7698f1
checkpoint-status | bb5691b9-3b80-44bc-bd5f-4099cb570643 |  | checkpoint | Measured twice and dry fitting signed off before wet apply
checkpoint-status | a7fe06cd-6cf2-4923-807f-9730ea0dcdb8 |  | checkpoint | Surface preparation complete
checkpoint-status | 740674ec-cc11-41e0-afaa-37471a0246c5 |  | checkpoint | Coating as per specification
boolean | 3549df58-6ec0-4cce-b2d3-08d8a3042d00 |  | tickbox | 1st coat - Resene Armourcote 221 at 50microns
boolean | a8c11ef4-7236-4871-b50a-796942c31bc9 |  | tickbox | 2nd coat - Resene Uracryl-403 at 50microns
boolean | 5ca32c00-89ca-47f3-909b-a2803772ed49 |  | tickbox | 2nd coat - Resene Uracryl-403 at 50microns
checkpoint-status | 36214c7d-d044-4ee1-8256-42b3a42c83d9 |  | checkpoint | Paint sales slips / batch numbers attached or photographed
checkpoint-status | 92b58719-ed73-4dcc-ae6f-c955fc39bbf3 |  | checkpoint | Flashing installed according to drawings
checkpoint-status | 1781146d-d437-4f54-a273-a3ebac2d6816 |  | checkpoint | Fixings according to Code as a minimum (or plans if more are required)
checkpoint-status | 5b339d47-c037-4da0-b4f2-31d44262b660 |  | checkpoint | All laps and junctions sealed properly and facing away from waterflow
checklist-flat | ce5f4195-32e6-437a-87ad-6a2547367ba4 |  | checklist | 1.6 Aluminium Flashing Checklist |  |  |  |  | Yes | 1.6 Aluminium Flashing Checklist (220) | 2a400ff6-4362-4994-8b7b-0cd4bbd15ab0
checkpoint-status | 05fb7942-835e-4552-8260-eb4a8fc53437 |  | checkpoint | Measured twice and dry fitting signed off before wet apply
checkpoint-status | 3743d068-40b9-435f-8478-47946c96ceea |  | checkpoint | Surface preparation complete
label | dc4fc1a3-9535-4003-8b20-91f744022b46 |  | note | Aluminium properly cleaned and all oil is removed.
label | dd627cc7-862f-4f01-83ef-5c4f4d3820ce |  | note | Resene SIPDS No 4 and spec sheet 4: 8/1
checkpoint-status | 1e93b6e9-1900-498e-b002-54296d9640e0 |  | checkpoint | Coating as per specification
label | 55e2d1ec-9186-4547-a671-5c378cdd794d |  | note | 1st Coat - Resene Armourcote 220 Epoxy Primer, 50 microns.
label | c74c8546-c2d2-4034-8483-6252df3f94da |  | note | 2nd Coat - Resene Uracryl 404 Solvent Urethane Acrylic LowSheen, 50 microns.
label | 22e87da0-0fe5-4b01-9c34-27576f44d531 |  | note | 3rd Coat - Resene Uracryl 404 Solvent Urethane Acrylic LowSheen, 50 microns.
checkpoint-status | 904f3ae0-dcfc-4ba4-a2e3-7d19d41d6910 |  | checkpoint | Paint sales slips / batch numbers attached or photographed
checkpoint-status | 79297540-4a88-427a-bbce-2e5fea9808c6 |  | checkpoint | Flashing installed according to drawings
checkpoint-status | 48b163f1-e74f-4922-8484-ea772173b2d8 |  | checkpoint | Fixings according to Code as a minimum (or plans if more are required)
checkpoint-status | e507cc0f-b9e8-46eb-ac36-0c2f8fc6216a |  | checkpoint | All laps and junctions sealed properly and facing away from waterflow
checklist-sectioned | 89d7fc3c-f8cb-424d-8bf8-92bb5347f4c8 |  | checklist | Rooflogic Ultratherm Xtreme Tappered Gutter |  |  |  |  | Yes | Rooflogic Ultratherm Xtreme Tappered Gutter | 2e06c403-b35b-4c0d-b0d9-c9c731ae5a57
checkpoint-group | e2a7e0ef-5831-4134-9a66-a202a41e8065 |  | section | Pre Start
checkpoint-status | 935c8bac-b719-4734-8602-e081e6c51cfd |  | checkpoint | Area Accessible
checkpoint-status | 7521342a-6931-4f5f-810c-6164a75cc8d6 |  | checkpoint | Edge protection in place
checkpoint-status | 3484f5ab-330a-42d4-8027-5d3c3b6cf6ee |  | checkpoint | Steel plate gutter liner installed by others
checkpoint-group | b9d1aeb2-f4b9-4026-8388-452b3579e08b |  | section | Steel plate gutter liner
checkpoint-status | a05ffa77-19a2-484d-8e2c-7737fcada25d |  | checkpoint | Gutter liner installed signed off and handed over
checkpoint-status | bec94799-5f54-4b78-b449-1dc478b7b271 |  | checkpoint | Outlet holes cut into base
checkpoint-group | b30c3fc6-0153-4aaf-9cbd-e6ded9f7de26 |  | section | VCL
checkpoint-status | a3a21986-bad7-4347-ba1b-ceb53b30f525 |  | checkpoint | Is the substrate clean, dry clear of swarf
checkpoint-status | b2d0b087-4fb3-494b-bbeb-67ad5be7c8a1 |  | checkpoint | Prime steel deck with SA primer
checkpoint-status | 9e4bd818-29d0-46b7-8d7f-344c5bac96f3 |  | checkpoint | All areas covered and sheets lapped 100mm min
checkpoint-status | 5a4841bd-9844-4ce1-8395-2631f08958f4 |  | checkpoint | All holes/penetrations pactehd and watertight
checkpoint-group | 4c3e0820-1fc8-44ab-92d9-734374d9accf |  | section | Stonewool Insulation above VCL
checkpoint-status | 19541eff-fbfd-4731-bc3d-4484fce7f6d7 |  | checkpoint | Surface is dry prior to install
checkpoint-status | ae0f77dd-6435-4914-a94e-11aef37c387f |  | checkpoint | VCL has been checked for no damage
checkpoint-status | fe7aa65b-1599-4c1a-bffa-8ca63ce000c7 |  | checkpoint | 600mm wide stonewool insulation installed above tall wall
checkpoint-status | ee9fd854-0cd1-4506-b75f-ac825ad2df7e |  | checkpoint | Joints flush (no gaps between boards)
checkpoint-group | 7ffe3b1f-cc05-41fa-b1db-12f0bd7730c9 |  | section | PIR Insulation
checkpoint-status | c13a1bd1-e89f-4d31-8fe7-d68e47fa05b5 |  | checkpoint | Surface is dry prior to install
checkpoint-status | 7ff9f548-f7fa-4a4d-90f0-d953eba33764 |  | checkpoint | VCL has been checked for no damage
checkpoint-status | c093849f-487b-442a-aa0a-2d314795c6f6 |  | checkpoint | Gutter edge flashing installed
checkpoint-status | 27041ef9-27e3-4496-9bd4-e9677b0c03a8 |  | checkpoint | Prime top of VCL with SA primer
checkpoint-status | 3a078ffb-804f-476e-8cdf-8c25b829806c |  | checkpoint | Install board bond adhesive
checkpoint-status | c48f7982-e3bc-42c4-a32d-43540d282e3c |  | checkpoint | Insulation Board installed tight and no gaps
checkpoint-group | 7857457c-396b-4cfd-b847-1082f446995e |  | section | ILD system
checkpoint-status | 159a8302-4800-4978-a0f6-c0028e634842 |  | checkpoint | PIR insualtion linked with conductive metal tape
checkpoint-status | 89a19099-11bf-45f2-83ff-cd734fc0d83e |  | checkpoint | Conductive continuity Ribbon installed at 1200mm centres
checkpoint-group | c14ea406-10e4-42b9-84ed-bb7ae8f37edf |  | section | Roof board HDP
checkpoint-status | d333b823-9ea3-420a-988f-af6519c1973f |  | checkpoint | Install board bond to PIR board
checkpoint-status | bab2399c-4343-488b-b477-1b253ca0dc7e |  | checkpoint | Roof boards Installed tight
checkpoint-status | aaa0dc6d-da12-4683-8758-6046a6e87a4b |  | checkpoint | Install RL roof outlet to sit flush at roof board
checkpoint-group | 938f92a9-100a-4e57-af91-9899e0f15ea0 |  | section | Fibertite XT
checkpoint-status | 0e0d6bcc-f12f-41e7-9998-1e21b2fb996d |  | checkpoint | Surface clean and free from debris
checkpoint-status | 511616f3-cf9f-419b-b469-0212d2d74eaf |  | checkpoint | Adhesive installed to substrate the width of the roll
checkpoint-status | 1cc092d0-f909-4a48-a251-13b6d0a2f6ed |  | checkpoint | Laying of membrane into the adhesive
checkpoint-status | 55c267c7-2245-4879-8a33-07ac4039acf4 |  | checkpoint | Laping on adjacent membrane to be minimum of 75mm
checkpoint-status | 59f7704c-0620-414d-9e5a-443d9ceab3f0 |  | checkpoint | Broom/rolling of membrane into adhesive
checkpoint-status | 5929ad59-f346-4169-b019-f0729f06f2e3 |  | checkpoint | Wipe and clean of laps prior to welding
checkpoint-status | 5dca108c-08e4-4821-9ee3-80bfd34ba0b3 |  | checkpoint | Test weld with welding machine
checkpoint-status | 79ddec75-9213-46bc-8bfb-a174eb6d581f |  | checkpoint | Probe of seam with QA hook
checkpoint-status | 41f592ca-f1a7-453f-bca3-b106f8597595 |  | checkpoint | ILD test
checkpoint-group | 7612366d-eb41-463c-b80a-83189e36a4a2 |  | section | Fiberclad Flashings
checkpoint-status | 54ad44a5-f9fb-4a1e-8635-cf1ffa530236 |  | checkpoint | Installed correctly accordnig to specifications
checkpoint-status | 74a9f8d5-2960-4b9f-89aa-d551f1e06db6 |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status | 06cc958c-a832-439c-913b-f6148860c675 |  | checkpoint | Probe of weld with QA hook
checkpoint-group | dc6dfb86-cb88-4c88-9fd7-4994cb726d39 |  | section | Review and Sign off
checkpoint-status | a9efdb4f-42b5-4f70-92ee-d5c8b11105bc |  | checkpoint | All installation work complete, checked and reviwed as per specification
checkpoint-status | acc3fe16-8ec4-4eb9-876d-c00fb9d9c288 |  | checkpoint | FCC project manager sign off
holdpoint | cb15ffdb-0cbe-47cb-8da7-6d40bbdcb363 |  | signoff | Sign off
checklist-flat | 12b53aa4-5195-4b4b-b6a9-9dcfb1616273 |  | checklist | ILD Wire |  |  |  |  | Yes | ILD Wire Checklist | 2ed073da-8ebe-4abb-b5c8-d5d9e040c926
checkpoint-status | c6aab795-881c-4eab-acec-1e44f08d3cc7 |  | checkpoint | ILD wire installed with connection plate
checklist-flat | 37bd4857-cf4f-4c9e-a659-c152d67e851f |  | checklist | Plywood Substrate |  |  |  |  | Yes | Fibertite to Plywood Gutters Prestart - Plywood Substrate Checklist | 38498ea4-d9e5-4397-ad3d-cf6ec0c1d592
checkpoint-status | 182679c8-ff82-441a-b77a-15f785fe4158 |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status | 8613cf5d-fbc9-4699-97dd-12f81a2700b9 |  | checkpoint | No Screws/nails/fixings popping up
checkpoint-status | 7bc09f1e-ae5e-4167-8f90-844199593440 |  | checkpoint | Joints flush and even
checklist-flat | 6f907fc4-1499-4387-9b8f-8959fd6440cb |  | checklist | Prestart |  |  |  |  | Yes | Fibertite to Plywood Gutters - Prestart Checklist | 486bff95-4821-42c5-9904-7f1dce6ef25f
checkpoint-status | 9ad8970d-5ab4-4648-95d5-476006129bc7 |  | checkpoint | Area accessible (free of gear and materials from other contractors)
checkpoint-status | 61cf1ca8-fad5-4397-806b-0803ed2cfe71 |  | checkpoint | Area fully ready for Membrane
checklist-sectioned | 70fd21a9-3f7b-4327-8f01-c0b218881194 |  | checklist | Rooflogic Xtreme Fibertite Gutter over PLY System AWL |  |  |  |  | Yes | Rooflogic Xtreme Fibertite Gutter over PLY System AWL | 57a9a176-de73-4d20-8189-7742c34f443f
checkpoint-group | b79d35d2-e773-4e58-af6e-7fc9b0d38252 |  | section | Pre Start
checkpoint-status | ae37986d-5cf7-467a-8d0a-ba5bbee3219f |  | checkpoint | Area Accessible
checkpoint-status | c4a2cddb-4d94-4856-9787-e69e4fe14a3b |  | checkpoint | Edge protection in place
checkpoint-status | c542c03a-939f-4c92-ad2c-18b2da90fff6 |  | checkpoint | Structure and substrate has been handedover by LTM. No check of falls by SWP
checkpoint-status | 4e9c96e8-5db0-4750-92e0-9d59323a4fd4 |  | checkpoint | Max weight load on roof per pack is 500kg
checkpoint-group | 06735b78-613a-45e7-99fa-98ec01c8391c |  | section | Plywood gutters
checkpoint-status | 876cfcd2-e144-498c-892c-080e9dad6b8e |  | checkpoint | Plywood installed as per agreed scope with LTM
checkpoint-status | 343d5538-d2bb-4ae4-820b-fc1937450913 |  | checkpoint | Handover of QA from LTM
checkpoint-status | 2d2e38b7-3e35-4ba1-a58a-493722a6aeca |  | checkpoint | Plywood below 18% moisture
checkpoint-status | 781c8a09-3513-4e02-8d19-0bf58fa42c61 |  | checkpoint | Plywood joints/screws flush
checkpoint-status | a903b1f0-210d-4f33-b650-4c2f7da7d321 |  | checkpoint | All screws in place
checkpoint-group | 95a81373-0a0e-495f-bc21-5f5501d053fd |  | section | VCL
checkpoint-status | 2ad1668d-345e-48cc-802c-7d9ea0771168 |  | checkpoint | Is the substrate clean, dry clear of swarf and debris
checkpoint-status | 3e871801-f419-4706-b15b-76e8a01ab83d |  | checkpoint | All areas covered and sheets lapped 100mm min
checkpoint-group | 507e2549-6be8-4add-b9be-731e3d6755eb |  | section | Stonewool 150mm Insulation above VCL
checkpoint-status | 2b65539b-5214-4cac-b748-dd8bd905dd58 |  | checkpoint | Surface is dry prior to install
checkpoint-status | d0f108e9-2ca4-4da9-aec0-ade5a4a79404 |  | checkpoint | VCL has been checked for no damage (100x100 patch)
checkpoint-status | 4b562e21-8e03-4551-8b00-d2b65ba4a2d5 |  | checkpoint | Joints flush (no gaps between stonewool)
checkpoint-status | bc29f975-74e4-49f6-916d-c2ee66c8ee97 |  | checkpoint | Gutter edge flashing installed
checkpoint-group | f4a66f4a-561b-4820-a1b8-a2128c7e6bf3 |  | section | Roof board HDP mechanically fixed
checkpoint-status | 55c5ea65-8026-458c-bab2-542acb9f6099 |  | checkpoint | Surface is dry prior to install
checkpoint-status | 786e3438-9090-47bc-bd96-0bb8d36cc050 |  | checkpoint | Roof boards Installed tight and in brick pattern
checkpoint-status | bff5fc18-535f-4026-bd1b-db1875c486a2 |  | checkpoint | Correct length screw with load washer min 20mm penetration into base deck
checkpoint-status | 66daf402-3e0b-4bc0-a247-d4e0cc28d0d7 |  | checkpoint | Insulation Board installed tight and no gaps
checkpoint-status | c9a61847-9007-4b89-bcf7-538063c3be74 |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-group | 5f52dac1-e93b-48e5-bd5e-61e5bbe6843f |  | section | ILD system
checkpoint-status | 017ed93b-7b24-4a6b-a172-e499f65a7b63 |  | checkpoint | Conductive continuity mesh installed
checkpoint-group | b95f311a-896d-4a5b-9cdb-8e9600cb3fbf |  | section | Roof board HDP Adhered with 600 board bond glue
checkpoint-status | 28746f69-095b-4961-a0a6-cf264e369f77 |  | checkpoint | Roof boards Installed tight and in brick pattern
checkpoint-status | 165adb51-650f-484b-bd37-af693e500300 |  | checkpoint | Correct glue Armac 600u
checkpoint-status | e4ec754a-f1e4-415c-9fdf-f8ea3b068be9 |  | checkpoint | Glue Installed as per suppliers specifcation Spray Armac 600u Board Bond 30mm wide beads continuously as 100mm centres.
checkpoint-status | 796fa6f9-813a-4366-9d68-a53d3dfa3a8a |  | checkpoint | Installed insulation to be covered with fibretite membrane in the same day
checkpoint-status | 737ee639-d536-4aa5-8686-9c019704721a |  | checkpoint | Any damaged board to be replaced with a full new board
checkpoint-group | 7246eecc-e47b-4cb7-82fa-638a02488fc9 |  | section | Fibertite
checkpoint-status | f849f171-6edc-4cb3-8881-b3ff39dcc9d6 |  | checkpoint | Surface clean and free from debris, no excess moisture
checkpoint-status | 6d4bcc18-64f7-43ca-b8ea-e19ef7a017aa |  | checkpoint | Adhesive installed to substrate the width of the roll
checkpoint-status | e28f676c-d4ba-4d47-a2ac-e6c0782c469f |  | checkpoint | Laying of membrane into the adhesive and Correct glue Armac 400u
checkpoint-status | e34a6967-1dc1-4e2f-bf41-5d587641de1b |  | checkpoint | Laping on adjacent membrane to be minimum of 75mm
checkpoint-status | b05ca38f-94c0-4b67-bb0d-d3c9f1fdb0da |  | checkpoint | Broom/weighted rolling of membrane into adhesive
checkpoint-status | e92a1223-0470-4640-842f-1d05eec53666 |  | checkpoint | Wipe and clean of laps prior to welding with acetone
checkpoint-status | 4f263a40-51cd-409a-b218-58d9ba23f02b |  | checkpoint | Test weld with welding machine
checkpoint-status | 6658b385-07db-411d-8b32-00d73f373ccb |  | checkpoint | Probe of seam with QA hook
checkpoint-status | fc02ba88-406e-4794-8a7c-6e752fc8e161 |  | checkpoint | ILD test
checkpoint-group | 51c6ccf6-e5ea-4449-981a-1996077fac30 |  | section | Fiberclad Flashings
checkpoint-status | 2e3e3b92-51e6-4911-9c44-b240b8b98e09 |  | checkpoint | Installed correctly according to specifications
checkpoint-status | f4df5716-2d3d-4e4f-8c75-0a8c308d36b6 |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status | d543b4ca-6b8d-4f6e-8427-b2ce89f609c7 |  | checkpoint | Probe of weld with QA hook
checkpoint-group | e21336eb-b3db-482d-8691-dcc55004b017 |  | section | Review and Sign off
checkpoint-status | 0e88ceba-5a6e-45a0-b802-6d27dbf7f60e |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status | 0671115f-6f94-4be3-a06b-217373181498 |  | checkpoint | LT Mcguiness project manager sign off
holdpoint | 3b862646-f97f-4264-8607-3724c32a9e2e |  | signoff | Sign off
checklist-sectioned | 8cfd5321-4137-4275-bee3-c40d5e8c7328 |  | checklist | Parapets AWL |  |  |  |  | Yes | Parapets AWL | 5d3cc62d-6c33-4eb8-8077-b6d3a4c9e0b7
checkpoint-group | 687535ea-555d-4d7a-a203-d4831619e1d7 |  | section | Pre Start
checkpoint-status | abad8f5f-8bf6-40eb-a063-447d7c84f063 |  | checkpoint | Area Accessible
checkpoint-status | 4352c63d-a044-471b-a7f1-a32c6e889579 |  | checkpoint | Edge protection in place
checkpoint-status | 968e78e5-b75d-4167-a7da-50a6fd01b142 |  | checkpoint | Structure and substrate has been handed over by LTM. No check of falls by SWP
checkpoint-status | 1b9d826d-95f7-475e-8982-ab8cd7deaf6b |  | checkpoint | Max weight load on roof per pack is 500kg
checkpoint-group | 2a65a02e-d0ee-40d8-a297-f39e5d35931f |  | section | Base Deck
checkpoint-status | 4ef9eb7f-4fd5-4a64-9b58-d24f6dae6e33 |  | checkpoint | Base deck installed as per agreed scope with lts
checkpoint-status | cacb2bb3-e719-4a87-bce7-d34131cc9f86 |  | checkpoint | All penetration boxes and pipes to be installed through the base deck
checkpoint-status | 68c823d2-8546-438b-a1af-25540d64cd60 |  | checkpoint | Approved fixings used 12-14x20 class 4 steelteks with neos
checkpoint-status | 74bee12f-c87e-4946-9cb2-221766f543e1 |  | checkpoint | Base deck screwed off at every purlin and every pan
checkpoint-status | bc8c971c-e2a9-457a-a351-d2bfba3fee6d |  | checkpoint | Base deck stitched along side-laps at 300mm centres
checkpoint-group | c0cc3546-72e1-40e9-ad49-00c35fc17e24 |  | section | VCL
checkpoint-status | 2e36766d-5e6a-41dd-8624-e4d559ecbcd3 |  | checkpoint | Is the substrate clean, dry clear of swarf
checkpoint-status | 9a4eb2ec-2b01-466b-91f2-a27c3384d89e |  | checkpoint | Plywood parapet upstand joints flush and moisture under 18%
checkpoint-status | 8843904e-6e22-49a3-b97d-22424f0d5570 |  | checkpoint | All areas covered and sheets lapped 100mm min
checkpoint-status | adf6c512-728f-4a7f-990d-b619b7a4c318 |  | checkpoint | All holes/penetrations patched and watertight
checkpoint-group | 3bdbce0d-8fc0-42be-a4bd-eb905c966739 |  | section | Stonewool 150mm Insulation above VCL
checkpoint-status | c406b68d-b9f9-4388-976e-ab2663afbde8 |  | checkpoint | Surface is dry prior to install
checkpoint-status | 06933b8c-c262-4d19-ab56-8facf68e9fb9 |  | checkpoint | VCL has been checked for no damage (100x100 patch)
checkpoint-status | 0e8c232e-27b7-44ce-849a-589f60485f98 |  | checkpoint | Joints flush (no gaps between stonewool)
checkpoint-status | 035b9d4d-d57a-4b87-9dee-5b6db407f4c6 |  | checkpoint | Gutter edge flashing installed
checkpoint-group | 2cafebb3-f8b2-4a8d-ad42-f984c2914f5a |  | section | Roof board HDP mechanically fixed
checkpoint-status | 0f48e95f-6b44-42f7-af92-d047d5d6c7eb |  | checkpoint | Surface is dry prior to install
checkpoint-status | 1f9133d7-a9d2-4747-9e2d-27881e81f003 |  | checkpoint | Roof boards Installed tight and in brick pattern
checkpoint-status | 3b6071d7-0128-40fc-b55c-11fa9521343f |  | checkpoint | Correct length screw with load washer min 20mm penetration into base deck and plywood upstand
checkpoint-status | 39a2071c-031b-4fef-90b0-5e7f43c75060 |  | checkpoint | Insulation Board installed tight and no gaps
checkpoint-status | 8ce29f34-e4ee-4a3e-9a9b-b00d41446ac9 |  | checkpoint | Any damaged board to be replaced with a full new board
checkpoint-status | 38aa35bf-2534-4714-9f94-c33c8a4eab18 |  | checkpoint | Installed insulation to be covered with fibretite membrane in the same day
checkpoint-status | acee0f56-0c53-41f8-adf8-82c9ee0490f3 |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-group | fef1cedb-a900-4ca4-8cdc-68a9a25d5286 |  | section | ILD system
checkpoint-status | b52363e5-11d5-43b3-9c19-15d8079f6cd2 |  | checkpoint | Conductive continuity mesh installed
checkpoint-group | a0929038-fa5a-4ac5-b930-5de21cc9b37a |  | section | Fibertite
checkpoint-status | 65f444e2-27ee-489b-a093-22a4bfb43db2 |  | checkpoint | Surface clean and free from debris, no excess moisture
checkpoint-status | 5f119482-1cfb-4c52-9d15-5332cfedbaf7 |  | checkpoint | Adhesive installed to substrate the width of the roll
checkpoint-status | 96ad6920-db0c-483d-be0b-9469eda86e6c |  | checkpoint | Laying of membrane into parapet upstand with 220 glue
checkpoint-status | aea6e33b-e4a9-488a-8130-dfdad2e1f8a9 |  | checkpoint | Laying of membrane into the adhesive and Correct glue Armac 400u
checkpoint-status | 01d2adc4-65f5-4dd6-9ae6-f148fe449037 |  | checkpoint | Laping on adjacent membrane to be minimum of 75mm
checkpoint-status | 1c3bbe79-a742-428c-933c-1bc2f171dd1e |  | checkpoint | Broom/weighted rolling of membrane into adhesive
checkpoint-status | acba90e7-2634-4a11-9f1f-a3b8b5d4b102 |  | checkpoint | Wipe and clean of laps prior to welding with acetone
checkpoint-status | d9ae22c5-6d93-4554-b013-c231749c7950 |  | checkpoint | Test weld with welding machine
checkpoint-status | 74a50821-dfd8-49f7-ae1e-104179675267 |  | checkpoint | Probe of seam with QA hook
checkpoint-status | cc105ebd-fc0c-4f21-a8db-baa049dbd6bf |  | checkpoint | ILD test
checkpoint-group | a99977d4-ef88-4a0b-a373-b268041ed01c |  | section | Fiberclad Flashings
checkpoint-status | d23fbc18-d744-480f-895c-e4ebcf40ea9c |  | checkpoint | Installed correctly according to specifications
checkpoint-status | c2ce5421-bfcc-409c-a87d-58cec3e22486 |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status | 74036dcd-1f2f-4343-bd6d-1ae2a9d05de6 |  | checkpoint | Probe of weld with QA hook
checkpoint-group | d06a7173-40ec-47ae-9e66-ff464ba20a54 |  | section | Review and Sign off
checkpoint-status | c12ec06c-24d5-4eca-8472-acf8d4c1b195 |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status | 86934bfc-8d2f-41b6-9485-27e31a92bf87 |  | checkpoint | LT Mcguiness project manager sign off
holdpoint | 0429067d-78ae-425f-9f47-f714fd9fa18a |  | signoff | Sign off
checklist-sectioned | a40ac36c-3a1b-4b18-86a0-a5839ae3c547 |  | checklist | Fibertite to Plywood |  |  |  |  | Yes | FibreTite to Plywood Checklist | 5f524642-27da-4ed3-be1a-fdc2ef708248
checkpoint-group | d0850008-2cb1-47e5-b387-ade37c8fd54d |  | section | Prestart
checkpoint-status | dc0e22f9-198a-45e9-b022-e21183af8573 |  | checkpoint | Area accessible (free of gear and materials from other contractors)
checkpoint-status | 62110944-ebd3-481e-9a84-1b1b76a48b0b |  | checkpoint | Area fully ready for Membrane
checkpoint-group | 9ce4c2dc-f772-4535-a424-677a8228b368 |  | section | Plywood Substrate
checkpoint-status | e75f189e-50a7-449c-b256-8740b11ec2bd |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status | 6d96731a-4ed8-43b3-ac8c-278a7b9102ee |  | checkpoint | No Screws/nails/fixings popping up
checkpoint-status | 4c73937b-2427-402f-b721-52c444a30ad2 |  | checkpoint | Joints flush and even
checkpoint-group | 4bc0038a-040d-47ea-9f5b-3929e1ae143f |  | section | Fibertite Membrane
checkpoint-status | f887f8b3-1268-420d-8c07-5a3abb791180 |  | checkpoint | Installed so that laps are facing down(towards drain)
checkpoint-status | 1ae373f9-d09f-4f2e-8a7b-3fcb77110845 |  | checkpoint | Correct Glue used per spec
checkpoint-status | fb4880c4-9b50-4a88-8324-356338384ef4 |  | checkpoint | Fibertite fully glued to plywood
checkpoint-status | 16c5f652-4aaa-4108-b28f-7fa14e03c744 |  | checkpoint | Glue evenly spread and no lumps
checkpoint-status | 66f3c947-09f6-4fd3-a7db-2038f0dd3380 |  | checkpoint | All laps, details, penetrations fully closed & QA'd with hook
checkpoint-group | 7f8b36dc-a036-4f69-979c-d294247f400a |  | section | Fiberclad Flashings
checkpoint-status | 69050ada-c019-49d8-92b8-d490057a53b5 |  | checkpoint | Installed correctly according to specifications (right way around)
checkpoint-status | 4d46b41f-0744-4847-8fdd-f9359673f954 |  | checkpoint | Fixings and welding done according to details
checkpoint-status | 3df9b754-f6d6-41ae-bb2f-d7dc2db39ff5 |  | checkpoint | Welding of Fibertite to flashings fully finished and QA'd with hook
checkpoint-group | 114320bc-6b3c-4487-b2ae-69745baa33ca |  | section | Final Sign Off
checkpoint-status | 203584ba-adb4-41e3-8e5c-bdfdea970465 |  | checkpoint | Area complete and ready for MC sign off
holdpoint | 53cf5719-3492-4f20-b95a-7961db6f25c8 |  | signoff | Request Sign Off Signature
checklist-sectioned | 61c581c9-ead8-41d5-b5a5-180a5970e716 |  | checklist | Metal Flashing Install |  |  |  |  | Yes | Metal Flashing Install Checklist | 6249d9a6-b912-482f-aff5-2d651d471ffa
checkpoint-group | b57865e0-399b-4902-ae24-8a41f1458637 |  | section | Prestart
checkpoint-status | a4bcb6a4-b4b8-4321-93e1-a219c3a11192 |  | checkpoint | Area accessible
checkpoint-status | d672f103-ae5a-46f4-9170-cfe2a60fd99e |  | checkpoint | Edge Protection/safe access installed (safe to be on the roof)
checkpoint-status | 715c6bb3-6ccc-43db-8618-2f20a3884206 |  | checkpoint | Substrate complete and ready for flashings
checkpoint-group | 4485aae1-9851-4991-a62c-e86b5f94cdb8 |  | section | Underlay
checkpoint-status | 1ffbda80-9c87-405a-a03c-8e3031504bbe |  | checkpoint | Underlay installed between substrate and new flashing
checkpoint-status | f2a2d42f-a1d5-4fd0-9f88-f70adca11eab |  | checkpoint | Overlapped a minimum of 100mm
checkpoint-status | 80edd2bf-9545-4d72-ae38-814bd9956a92 |  | checkpoint | All areas under new flashing completely covered
checkpoint-status | df3e3791-e537-4a37-8f1a-f8999eeb5e61 |  | checkpoint | Secured so it will not blow away if flashing not being installed immediately
checkpoint-group | f4021a32-655a-439f-afb7-2721ccb39312 |  | section | Metal Flashing Install
checkpoint-status | 03f79ae7-eeec-4837-90fa-bca3fe7ab685 |  | checkpoint | Installed with a minimum upstand of 150mm or according to drawings
checkpoint-status | cba20b36-ee2d-4171-9cb6-bc963d8bf032 |  | checkpoint | Expansion joint installed if needed (i.e. with runs longer than 12m for coloursteel or 8m for Ali.)
checkpoint-status | 502fd60f-2b62-459a-8947-9d2612f95f36 |  | checkpoint | Fixings according to Code as a minimum (or plans if more are required) in a straight line
checkpoint-status | 231ac54a-5d66-44cc-be05-c2730f2fab0f |  | checkpoint | Laid in a straight and tidy manner
checkpoint-status | 9f1fbb4b-5e19-42e9-b372-888a9d762bd3 |  | checkpoint | All laps and junctions sealed properly and facing away from waterflow
checkpoint-status | ee86a55d-55a3-4c6a-98dd-22edc590451c |  | checkpoint | All visible ends & junctions cut and folded straight and tidy
checkpoint-group | c950ef8b-9cc8-434c-b409-24a2eaf7a6a3 |  | section | Sign Off
checkpoint-status | acf779fb-5605-4b9e-bf19-5950b7322467 |  | checkpoint | Area complete and ready for MC sign off
holdpoint | 61cf4fa9-9600-4bc3-9e80-6ab877e7c5a6 |  | signoff | REQUEST SIGNATURE SIGN OFF
checklist-flat | 92609a27-e06b-4c9f-b111-698f164aec40 |  | checklist | Final inspection |  |  |  |  | Yes | Add Final inspection Checklist | 63d22881-a049-448b-9e49-77a87c136491
checkpoint-status | 53694bdf-90ff-4d8c-996a-b9229311ce34 |  | checkpoint | Final inspection
text | e08f7be0-1cde-567c-b96f-6244b9db5d30 |  | textbox | Date
text | d5b9ba29-bcb6-5057-a6af-a8164538440e |  | textbox | Area/elevation/grids
text | cff2b86e-590f-5fc7-a02d-b7255effeba2 |  | textbox | Description
label | 77e01590-121c-5e63-8aa0-4d070170266a |  | note | Attach Photos
holdpoint | 277939c1-53c1-4124-ae18-7506c904b7ee |  | signoff | Request Signature Signoff
checklist-flat | de3f6e1f-e3ab-4be2-96f3-f2986b170d5e |  | checklist | Final Sign Off |  |  |  |  | Yes | Fibertite to Plywood Gutters Prestart - Final Sign Off Checklist | 649d7ef8-cc8b-4732-be9b-b97c828aa79f
checkpoint-status | c058ba8b-4f46-49a9-b426-7342f4fdb396 |  | checkpoint | Area complete and ready for MC sign off
holdpoint | fd433522-b8fa-4842-949d-6bd945a45d38 |  | signoff | Request Sign Off Signature
checklist-flat | 7c4e9547-1646-484b-bb42-9022cf78446d |  | checklist | Add Flood Testing Checklist |  |  |  |  | Yes | Add Flood Testing Checklist | 7877b389-a71a-411a-a739-28dae617d01b
checkpoint-status | 01f6f79e-617c-4263-a2d0-c668d747f562 |  | checkpoint | Is area fully finished, QA’d and ready to be tested
checkpoint-status | 46b00ccd-7419-4b7d-be21-898cc49c099b |  | checkpoint | Flood test details
text | 6462dc07-93fa-5e80-ad5e-557cb9a6f356 |  | textbox | Date:
text | def9d506-37b3-5ad9-b748-8c7d6234a287 |  | textbox | Area tested:
text | 64936efb-e851-56fd-8650-50cb0c9138af |  | textbox | Duration:
button | f8ad9cf8-3808-55a2-abb0-6ebf0dd5d6ef |  | button | Have you checked regularly for leaks | Yes, No, N/A
button | ae53c973-98f8-523b-a75a-6914dfcf56c1 |  | button | Is there rain in the forecast | Yes, No, N/A
button | 36cccc17-8750-5aa3-a260-e3c7632a3f96 |  | button | Have you eft some outlets/scuppers so that the building doesn't flood | Yes, No, N/A
button | eed285ab-f2b8-596e-8d20-01e6d5111db0 |  | button | Have all leaks been repaired | Yes, No, N/A
checkpoint-status | 4713f1e8-081b-4256-8b07-4c48bfb2d646 |  | checkpoint | Flood test complete
button | b2fad026-497e-52ec-be6b-368ac6a67db0 |  | button | Have the plugs been removed from the drains | Yes, No, N/A
button | a6d3255f-94bc-52c2-baa3-90527f5056b9 |  | button | Debris and materials removed from the gutter/membrane/roof | Yes, No, N/A
holdpoint | 0191b106-eea4-4fe0-b76d-801943818f28 |  | signoff | Sign Off
checklist-sectioned | 39e645e4-cf37-4664-9277-ccde4390a87b |  | checklist | MSR checklist |  |  |  |  | Yes | MSR checklist | 7894970a-5e23-47ff-ba87-75f3d6175b4e
checkpoint-group | caafade5-1515-4076-88fe-f364fcc06ca8 |  | section | Pre start
checkpoint-status | 14de69a0-bf24-4c26-aa4e-f94e6e9b6e96 |  | checkpoint | Area accessible
checkpoint-status | 1dc7a0a8-bc5a-408e-8c64-437ccda1a767 |  | checkpoint | Edge protection and safety installed
checkpoint-status | 7bfc4461-63b5-44da-8884-5f0cadcdd7ca |  | checkpoint | Purlins installed and QA / handover received from main contractor
checkpoint-status | 88afff14-c4b3-4b26-9cef-a1424fe3f1bb |  | checkpoint | visual inspection by SWP
checkpoint-group | c6788814-eec7-48cb-abec-96d6d9ae571b |  | section | Liner deck
checkpoint-status | c22db4ab-67e0-4177-8c28-801cc33eff75 |  | checkpoint | Liner deck fixed down in every purlin and every pan
checkpoint-status | 684e81a8-bd3e-4f87-8c0a-64b294fc8b06 |  | checkpoint | Correct fixing installed
checkpoint-group | 877cda82-e30f-42b2-ac18-abf52c132f7e |  | section | Vapor control layer
checkpoint-status | cd288f1c-3d45-43f5-b5d5-4544ce24bb09 |  | checkpoint | Substrate clean, dry, free of debris
checkpoint-status | 50102763-e38e-4d79-a6ad-8404b71a1a61 |  | checkpoint | Z flashing installed
checkpoint-status | 06679c51-1d8e-4a96-bf0e-90fd2da7bac3 |  | checkpoint | VCL installed and covered all surface
checkpoint-status | 1026e989-9f9b-497c-a869-d0488beaded3 |  | checkpoint | VCL lapped with a minimum of 100mm side and end laps
checkpoint-group | 88a9e7d3-6d92-4b7a-bdaa-58400a0f0318 |  | section | Acoustic board install
checkpoint-status | 37444970-843f-4aa9-a59f-7a6c6ba4150d |  | checkpoint | VCL clean, no ponding water, free of debris prior to install
checkpoint-status | 448f9188-61bb-47cf-a092-5cf8954f9c6e |  | checkpoint | VCL has been cheeked for damages
checkpoint-status | d37c0b91-e60b-4b1c-a1ad-ff5562a117d1 |  | checkpoint | All holes/penetrations patched
checkpoint-group | c98fb6f1-16a0-44a4-bb8e-cd1d6d513fe3 |  | section | Insulation
checkpoint-status | bcd9fc1b-fa98-49e2-8e0e-3cdb8c9ffb06 |  | checkpoint | Boards tightly butted all areas covered
checkpoint-status | e968932c-a603-4cf5-8823-849ff4b69be8 |  | checkpoint | Correct PIR installed as per spec
checkpoint-group | 980df18b-66b9-4a85-8c30-637d3dfd66a0 |  | section | Underlay installed
checkpoint-status | fb27ba66-b765-4010-9f15-9502db7b8a74 |  | checkpoint | Correct underlay installed as per specifications
checkpoint-status | 1bfcbd30-fed7-417d-aefe-8938a24b41f7 |  | checkpoint | Overlapped a minimum 150mm side laps and 200mm end laps
checkpoint-status | 89360bc2-1938-4d22-bdf2-19b7ce22dfb0 |  | checkpoint | All areas covered
checkpoint-status | 2ee3ddbe-8c01-4f69-9fb7-1e3cae139720 |  | checkpoint | Underlay installed as per specifications
checkpoint-status | 59635009-5bca-415a-a439-9d1182801d76 |  | checkpoint | Joints taped together as per drawings and specifications
checkpoint-group | a4e8d96a-fcbf-4b52-bd1f-4be6e39159e0 |  | section | Metal roof installation
checkpoint-status | ec8b2907-92f2-4a96-a563-be9a3ad30595 |  | checkpoint | Drip edge installed as per drawings and specifications
checkpoint-status | 9fecc7e7-75ef-4050-b550-d4f5a21086b4 |  | checkpoint | Laid straight and perpendicular to gutter/purlins
checkpoint-status | 81a2c946-034c-42b9-af71-2dc2855ef41c |  | checkpoint | Gutter overhang as per drawings and specifications
checkpoint-status | 67f872d8-0fc0-4d3c-8d7b-b5ae63ffc7c5 |  | checkpoint | Top end turned up
checkpoint-status | c0e3ba7a-c66f-470c-beaa-6f04dda195b4 |  | checkpoint | Bottom ends turned down
checkpoint-status | 6f162cb2-58cb-4768-8cf2-00aaf45824e3 |  | checkpoint | Closure foam installed
checkpoint-status | cfc9e797-cb9f-4202-9dd0-14844d4f019a |  | checkpoint | Screw pattern according to plan/specs/fixing plan
checkpoint-group | b5b5f951-e868-478c-8303-d89579bbeb5b |  | section | Flashing install
checkpoint-status | 70fb014b-9df1-40fb-8843-3fffb11989a6 |  | checkpoint | Sealant installed with 2 continues beads
checkpoint-status | 9cebcdd4-b9ad-441d-9771-f7be24abab40 |  | checkpoint | Clean excess sealant
checkpoint-status | 9f4388ef-203a-4f33-87d8-bbac0f860470 |  | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
checkpoint-status | d5dbed4a-76f5-4fd5-8154-9d4018f7a912 |  | checkpoint | Flashings installed as per drawings and specifications and facing away from waterflow
checkpoint-status | 9510eebe-1d94-4b72-9169-232e4afe2aee |  | checkpoint | Fixings installed as per drawings and specifications
checkpoint-group | 7d56867e-c056-4ec3-abad-5acc5541c428 |  | section | Review and sign off
checkpoint-status | 8e10ce1c-3401-4ccc-9cfd-d636cf215e94 |  | checkpoint | Area left clean and tidy
checkpoint-status | e822b554-f1b4-427a-92da-37ca7ddd1290 |  | checkpoint | All installation work completed, checked and reviewed as per specifications
holdpoint | 89ac0f75-5621-49ba-93f3-49919eef3424 |  | signoff | Client/main contractor sign off
checklist-flat | cedf25eb-22f0-47e4-a237-5bb87708c1e7 |  | checklist | Delivery Slips |  |  |  |  | Yes | Delivery Slips Checklist | 7d5aa2b3-7af0-484b-b6ef-61a10d3c87fb
checkpoint-status | 315bee62-7eae-48a6-959c-b0878d9de3b1 |  | checkpoint | Flashing dockets attached
checkpoint-status | f7b8bf43-940b-4dce-8abd-30e652ae021d |  | checkpoint | Iron dockets attached
checklist-sectioned |  |  | checklist | Weather Monitoring |  |  |  |  | Yes | Weather Monitoring | a8d5f8ba-7da1-4e65-ab85-a793befa61d0
checkpoint-group |  |  | section | Current Weather
checkpoint-status |  |  | checkpoint | Todays date & Time
checkpoint-status |  |  | checkpoint | Wind / weather conditions
checkpoint-status |  |  | checkpoint | Record any delays
checkpoint-status |  |  | checkpoint | area / gridlines
checkpoint-status |  |  | checkpoint | Comments / issues / observations
checkpoint-group |  |  | section | Weather Forecast
checkpoint-status |  |  | checkpoint | What is the weather forecast this week
checkpoint-status |  |  | checkpoint | Record any delays
checkpoint-status |  |  | checkpoint | area / gridlines
checkpoint-status |  |  | checkpoint | Comments / issues / observations
checklist-sectioned | 35a51773-35ba-4a8b-9808-88540c63b62d |  | checklist | Metal Roof Installation Checklist |  |  |  |  | Yes | Metal Roof Installation Checklist | ace6f946-84f1-487e-80a8-e5e12899932e
checkpoint-group | 8668e6c2-5873-4b04-b73e-31c16ed76a5e |  | section | Prestart
checkpoint-status | 4b8da64c-8c88-4e8a-b338-41473b6408cb |  | checkpoint | Area accessible.
checkpoint-status | 2877097f-3324-41cf-94b4-306aa6cddcf1 |  | checkpoint | Edge protection/ Safe access installed. (Safe to be on roof)
checkpoint-status | f89ac708-b038-4d38-a07b-9652e61a9b9c |  | checkpoint | Substrate (i.e. timberwork/Purlins) complete and ready for system.
checkpoint-status | ee41c697-6648-4f62-89f8-d4c0bdac45f5 |  | checkpoint | Drip edge, screws ordered for entire roof.
checkpoint-group | 9fcac364-b5e1-491f-8abc-b5927055d5f8 |  | section | Safety Mesh Installation
checkpoint-status | c1fab892-6a64-47da-bfcd-857c6de57d2f |  | checkpoint | Laid perpindicular to the purlins.
checkpoint-status | a67f25c0-f1ff-4939-b533-19ac63aeafce |  | checkpoint | Fully secured to Purlins/Timber.
checkpoint-status | 5f791f32-a8d4-485e-a37e-62a2789cb5d2 |  | checkpoint | No protruding bits or loose ends.
checkpoint-group | 51f66ef0-fe01-4774-b629-84c16f288995 |  | section | Covertek Roofing Paper Installation
checkpoint-status | 21e18bbb-90a5-438b-8dcd-85656f3b6546 |  | checkpoint | Laid either perpindicular or parallel with purlins.
checkpoint-status | 0156388b-891b-4db9-9b02-2690a57a46a6 |  | checkpoint | Overlapped a minimum 150mm
checkpoint-status | e97b9b26-9496-4acc-b3d5-3b4761939a7e |  | checkpoint | All areas completely covered.
checkpoint-status | 3464c9a2-c0b4-4879-9523-874c5e147c10 |  | checkpoint | Laid tight to timeber/purlins.
checkpoint-status | 5fb16e74-ea07-4bf4-b999-6c4dcb613455 |  | checkpoint | Secured so it will not blow away if roof not being installed immediately.
checkpoint-group | ea338fac-3a55-4b1f-9ad5-cdc7d795878a |  | section | Metal Roof Installation
checkpoint-status | f0dd5016-af66-4544-814e-7f1d1c78c4b1 |  | checkpoint | Drip edge installed
checkpoint-status | 0e4dc092-f103-44e8-bba0-5003c8c6f887 |  | checkpoint | Laid straight & perpindicular to gutter/purlins
checkpoint-status | 12fa4ef1-13a8-43a5-9c54-5658c19c0319 |  | checkpoint | Correct gutter overhang 65/75mm
checkpoint-status | 6baf7167-7431-4dc8-9269-d5fcc1169692 |  | checkpoint | Top ends of sheets turned up.
checkpoint-status | 43a90c7d-18d6-49a3-8c1d-831bb3432524 |  | checkpoint | Fixings back into purlins and laid in a straight line as per Code of Practice.
checkpoint-status | 78045339-5e7e-48e2-aeaa-5dfb8e9f979f |  | checkpoint | Closure foam to gutter ends.
checkpoint-group | 8d268940-f58c-4100-bb5f-6ea57f2d67ea |  | section | Roof Flashings
checkpoint-status | 07356dc2-831d-4a68-96a0-4f88b0058efa |  | checkpoint | Installed correctly according to drawings and to the Code of Practice.
checkpoint-status | 05900b4a-0876-4d2c-9c3d-3ca0bcd99e44 |  | checkpoint | All fixings in place and done according to code of practice.
checkpoint-status | b01780e3-a797-4173-a4c9-d43f1a471368 |  | checkpoint | All laps and junctions sealed properly.
checkpoint-group | 5bdb2d9e-e1ad-4cd1-8d3d-fcf6db5bea20 |  | section | Sign Offs
checkpoint-status | aa8845c2-f8cf-4e80-a360-8de7ae949a14 |  | checkpoint | Area complete and ready for MC sign off
holdpoint | 73c45532-fa35-44b2-ad8d-132b61913be5 |  | signoff | REQUEST SIGN OFF SIGNATURE
checklist-sectioned | a7c071ce-8f1e-4eb4-9f64-c407f7f3fff0 |  | checklist | Rooflogic Xtreme Fibertite Roofing System AWL |  |  |  |  | Yes | Rooflogic Xtreme Fibertite Roofing System AWL | b4679d42-f5ec-44eb-9a22-c0fafb537603
checkpoint-group | 0b7e8bb7-5f73-42a4-bd3d-a3bb3dde026f |  | section | Pre Start
checkpoint-status | dbc74b80-78ba-4967-9ec6-51f7192b690b |  | checkpoint | Area Accessible
checkpoint-status | d04e986d-18e9-4c13-ba50-a8206f0cf3e4 |  | checkpoint | Edge protection in place
checkpoint-status | c8d966b0-8618-4a64-bc18-9484147a9cab |  | checkpoint | Structure and substrate has been handed over by LTM. No check of falls by SWP
checkpoint-status | 1cd20276-a675-4bc6-85bc-70bc33226cf4 |  | checkpoint | Max weight load on roof per pack is 500kg
checkpoint-group | dfd4c890-49d2-4f75-a4b1-842dad726da2 |  | section | Base Deck
checkpoint-status | 29824a95-5ec3-4025-b174-3404b826e178 |  | checkpoint | Base deck installed as per agreed scope with lts
checkpoint-status | 3a059541-b2b1-4639-8852-f24f3cd3bebf |  | checkpoint | All penetration boxes and pipes to be installed through the base deck
checkpoint-status | 3884431d-c0ea-4aa6-983e-f2d2f16d4230 |  | checkpoint | Approved fixings used 12 -14x20 class 4 steelteks with neos
checkpoint-status | 4fc8d66e-f0c5-4fdd-8250-caf93751e4b0 |  | checkpoint | Base deck screwed off at every purlin and every pan
checkpoint-status | 087ed81f-0d75-4c69-8d9b-267635ddda92 |  | checkpoint | Base deck stitched along side-laps at 300mm centres
checkpoint-group | afe93ab2-3b52-4ae9-9772-1fd453bdaf7e |  | section | VCL
checkpoint-status | 58f2ac8f-e089-4461-8ad3-707831c062bd |  | checkpoint | Is the substrate clean, dry clear of swarf
checkpoint-status | 94514c81-f8cb-4814-ae11-da4ee9ddc0f2 |  | checkpoint | All areas covered and sheets lapped 100mm min
checkpoint-status | 928039d3-d0bf-49d0-b476-3cbd17829f76 |  | checkpoint | All holes/penetrations patched and watertight
checkpoint-group | a5cebdd1-6f0d-466a-92cf-ac48389d2a39 |  | section | Stonewool 150mm Insulation above VCL
checkpoint-status | 46c3f531-4049-4bb2-ab4a-1dd79d3cd1ff |  | checkpoint | Surface is dry prior to install
checkpoint-status | dc24b91d-4746-49a1-9a61-95f812f5973a |  | checkpoint | VCL has been checked for no damage (100x100 patch)
checkpoint-status | e802d5b1-84fc-40d1-9dad-f601ae861c7e |  | checkpoint | Joints flush (no gaps between stonewool)
checkpoint-status | b460cda6-77b8-4dd8-8758-035453692a49 |  | checkpoint | Gutter edge flashing installed
checkpoint-group | e1b5e8e1-7cb2-46f3-bd26-f5427a9b375c |  | section | Roof board HDP mechanically fixed
checkpoint-status | 17d09fa6-9016-4e44-bbfd-4f8a9f3325bc |  | checkpoint | Surface is dry prior to install
checkpoint-status | a4079f83-1726-49c4-bb44-80727b635243 |  | checkpoint | Roof boards Installed tight and in brick pattern
checkpoint-status | 98cd9b84-c630-48a6-ae5b-f08860de42fb |  | checkpoint | Correct length screw with load washer min 20mm penetration into base deck
checkpoint-status | e8b2aa6c-b8de-426f-8323-1ad6ddb4fff0 |  | checkpoint | Insulation Board installed tight and no gaps
checkpoint-status | dcf50724-913f-4aff-8b76-7ae6df2874bf |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-group | 8bc47de0-cb5e-4777-88d8-7bc9e29d6670 |  | section | ILD system
checkpoint-status | 473e2889-c1f3-4832-8b1e-2cdb7992ce8c |  | checkpoint | Conductive continuity mesh installed
checkpoint-group | 55239a8b-b967-4291-aaf8-187698b05f8b |  | section | Roof board HDP Adhered with 600 board bond glue
checkpoint-status | edd6bc4b-8279-484b-9eb6-5a1561cb9576 |  | checkpoint | Roof boards Installed tight and in brick pattern
checkpoint-status | f3090550-fcad-4759-99c5-0c90f77b6531 |  | checkpoint | Correct glue Armac 600u
checkpoint-status | d847c03b-e602-4443-bf24-7c86615ea844 |  | checkpoint | Glue Installed as per suppliers specification Spray Armac 600u Board Bond 30mm wide beads continuously as 100mm centres.
checkpoint-status | 3c5534dd-6f18-4dfa-a1b2-6ccad3f997d6 |  | checkpoint | Installed insulation to be covered with fibretite membrane in the same day
checkpoint-status | 1fd09640-7240-43d9-b259-2ff693be3e96 |  | checkpoint | Any damaged board to be replaced with a full new board
checkpoint-group | e51c2cf7-9495-4078-9bd7-bb77a1079748 |  | section | Fibertite
checkpoint-status | 091cc10a-acba-4855-9d48-66d63b6b334b |  | checkpoint | Surface clean and free from debris, no excess moisture
checkpoint-status | d02b41be-439f-4984-872e-b31e1fe03f8a |  | checkpoint | Adhesive installed to substrate the width of the roll
checkpoint-status | 04d34394-260b-4955-9c57-aea9fa8d7ffa |  | checkpoint | Laying of membrane into the adhesive and Correct glue Armac 400u
checkpoint-status | a0afe8fc-eb17-4ffe-a072-02f41af1962a |  | checkpoint | Laping on adjacent membrane to be minimum of 75mm
checkpoint-status | 76d2ec7c-323a-4fea-bc31-c75bf91519c3 |  | checkpoint | Broom/weighted rolling of membrane into adhesive
checkpoint-status | 354b0fd0-406b-43f4-b8e9-34f65310f2da |  | checkpoint | Wipe and clean of laps prior to welding
checkpoint-status | 7ee94824-e500-46f5-b313-d660370153df |  | checkpoint | Test weld with welding machine
checkpoint-status | a4d99ce1-8213-4531-a21d-55af1cf9432a |  | checkpoint | Probe of seam with QA hook
checkpoint-status | 907082fb-2f05-4e5d-8e8b-5977eebdde94 |  | checkpoint | ILD test
checkpoint-group | 2e8065fc-964f-46c9-a08a-3661c01d7a5d |  | section | Pipe penetrations
checkpoint-status | 103503a7-6cbe-4d0c-ac32-9524b4ed4ab2 |  | checkpoint | 150mm minimum upstand
checkpoint-status | 8e7ddd41-1c64-4e05-b2df-0e9c8ff0308a |  | checkpoint | RL E-101 Sealant applied as per specifications
checkpoint-status | 5ae0f67c-d6ae-40fc-b208-9add1d18f66e |  | checkpoint | Clamped with stainless steel hose clamp
checkpoint-group | 685249c6-aec2-482d-a4d2-881e21307af7 |  | section | Fiberclad Flashings
checkpoint-status | a83d737c-2c9d-4ea7-816f-e05725958c59 |  | checkpoint | Installed correctly according to specifications
checkpoint-status | 7425b267-aaeb-442d-b7c8-5f2391b4f128 |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status | 4358011d-3017-4e1d-9390-c942147a64be |  | checkpoint | Probe of weld with QA hook
checkpoint-group | afec91de-90a6-458d-be36-1aa15290490e |  | section | Review and Sign off
checkpoint-status | 9bacaa98-3f8a-46da-ab41-041ebbf4c895 |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status | 514563f6-af49-411f-9217-b40b66584047 |  | checkpoint | LT Mcguiness project manager sign off
holdpoint | 69e9cea5-db53-4072-86db-d03749516949 |  | signoff | Sign off
checklist-flat | 40ceb8b7-87c5-4cce-a90c-d0f893abe107 |  | checklist | Fiberclad Flashings |  |  |  |  | Yes | Fibertite to Plywood Gutters Prestart - Fiberclad Flashings Checklist | b60226e7-7beb-4bde-b974-1ec0bb352e25
checkpoint-status | 8a8c62df-fefb-4fe8-85aa-ddcc99f4a985 |  | checkpoint | Installed correctly according to specifications (right way around)
checkpoint-status | e940a9bb-6144-4943-b3c4-51696a72d119 |  | checkpoint | Fixings and welding done according to details
checkpoint-status | cb26a64c-e035-44a1-8dbb-4b5602c47a0b |  | checkpoint | Welding of Fibertite to flashings fully finished and QA'd with hook
checklist-flat | fba2c88e-edba-436b-93c1-afe0a855aa74 |  | checklist | Site Visit date: |  |  |  |  | Yes | Supplier Site Visit | ba09c9b0-37b5-4b4c-a706-243624c54428
checkpoint-no-status | 1253168d-76d3-4b8f-9662-885034ceeff0 |  | checkpoint | Site Details
checkpoint-status | 6e7a15f7-5c28-47b2-bae6-c1d5a3869479 |  | checkpoint | Photos
holdpoint | be014856-44b7-4cea-8a33-bea16a58cc39 |  | signoff | Signoff Required
checklist-flat | c3212394-2ef2-40f7-b5ce-5840402be67e |  | checklist | Job Details |  |  |  |  | Yes | Job Details Checklist | cd1c7609-c152-46ea-8135-0ec4d6532b88
checkpoint-status | cb2826d5-53ae-4fa1-ab8b-34d9a937fa1e |  | checkpoint | Site Info
text | 4e739149-fe6d-425d-b45e-4a4ff63e7c1e |  | textbox | Site Address
text | e326d577-6e3a-40b7-870a-8e178eda7195 |  | textbox | Main Contractor Details
text | 6c1ef37c-4d31-4405-b668-f398c4ad1275 |  | textbox | Project Managers Details
text | 351c3436-2ae9-42ae-9ee9-1146e81bffa2 |  | textbox | Site Manager Details
checkpoint-status | 63bdcb7e-5f88-489a-88c2-365617db7e0e |  | checkpoint | Latest Drawings
checkpoint-status | d37993a2-a35d-4598-80a5-4d9d4ffc2413 |  | checkpoint | Scope of Works Attached
checkpoint-status | ae1aadbf-2229-4444-a303-a107ca865a8e |  | checkpoint | Additional Pre Start Docs
checkpoint-status | 2989cefd-1b15-4b7e-8852-2015d8d7d799 |  | checkpoint | Fixing Plan Attached
checklist-sectioned | 4229d397-79fb-461f-8fc3-158b57b40990 |  | checklist | Rooflogic Fibertite Hybrid System |  |  |  |  | Yes | Rooflogic Fibertite Hybrid System | d49a14d3-4037-492f-96c6-5e0bd040d795
checkpoint-group | 2f88f5e5-e920-4508-b653-050396b329a4 |  | section | Pre Start
checkpoint-status | 74cd2e41-578c-4728-84e4-8667e4b325d4 |  | checkpoint | Area Accessible
checkpoint-status | c5343d44-febd-4ec7-9509-d94a79d27d30 |  | checkpoint | Edge protection in place
checkpoint-status | 730fb1fa-c871-483e-b2b6-49b128ff7009 |  | checkpoint | Substrate clean and clear of debris and moss/mould
checkpoint-group | 59bd6b4d-aff2-438c-a7b5-8525bf0fe995 |  | section | Concrete substrate
checkpoint-status | 07dcbee7-70db-4b60-a134-d754999ee839 |  | checkpoint | Free from holes & lumps of concrete
checkpoint-status | c2aa4b4e-9a6a-40d6-b1e3-487213c202c8 |  | checkpoint | Outlet holes cut into base
checkpoint-group | b99bb0b2-d6f1-4d15-84f3-6b4468f6af86 |  | section | Bitumen Base sheet
checkpoint-status | fbba5bdf-88fc-4743-9aaa-f71422e4176f |  | checkpoint | Is the substrate clean, dry and clear
checkpoint-status | 860415de-51fe-448e-8d17-edf0c5eb24fe |  | checkpoint | Install FTR SBS Adhesive
checkpoint-status | ce89c480-9f17-46a6-9a6d-ed84edfc217f |  | checkpoint | Install Bitumen base sheet into adhesive with 80mm min laps
checkpoint-status | 31ecc903-6cbd-4a00-aae8-8decaa24454c |  | checkpoint | Roll/broom of membrane into adhesive
checkpoint-status | 686b510f-d49d-425d-989e-d3bfa6f1c452 |  | checkpoint | Hot air weld any laps
checkpoint-status | b0afef2e-c175-48ba-973b-6f87d05b4a68 |  | checkpoint | Probe of laps with QA hook
checkpoint-group | bf4cb6c4-1669-4f18-846f-bc2ab593f597 |  | section | Fibertite XT
checkpoint-status | ceff2827-fbd0-4184-bf8f-6d4d80d073cf |  | checkpoint | Surface clean and free from debris
checkpoint-status | c49fdc26-ad23-43c8-849d-39288174cf7f |  | checkpoint | Adhesive installed to base sheet the width of the roll
checkpoint-status | 662fae4f-8572-4790-bc9d-4598068ace01 |  | checkpoint | Laying of membrane into the adhesive
checkpoint-status | fae3c590-660e-4e66-a563-6220a3eb05d2 |  | checkpoint | Laping on adjacent membrane to be minimum of 75mm
checkpoint-status | 30800df0-384d-49fd-adf7-ac9128079ce7 |  | checkpoint | Broom/rolling of membrane into adhesive
checkpoint-status | f03e5ac2-8c72-400e-b2b5-aed7336d6c6a |  | checkpoint | Wipe and clean of laps prior to welding
checkpoint-status | 75a0e0b2-f389-4d84-95b7-01b847a5366b |  | checkpoint | Test weld with welding machine
checkpoint-status | a37a8006-c720-4731-a04b-48eaf72a73b8 |  | checkpoint | Probe of seam with QA hook
checkpoint-status | c55f274a-62ed-444e-abb9-6528f16ef35e |  | checkpoint | ILD test
checkpoint-group | ac35f4af-dc93-4317-b04b-2099f3ede073 |  | section | Fiberclad Flashings
checkpoint-status | c1c51283-f1d2-40f2-b72a-0455ddcd65f3 |  | checkpoint | Installed correctly accordnig to specifications
checkpoint-status | edfb6187-12fa-471e-846c-901a587d0d2d |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status | 004caf27-5c9c-4a7a-963a-e7c1006f33cb |  | checkpoint | Probe of weld with QA hook
checkpoint-group | f0d6f92c-b60b-4446-96d3-5962881afaad |  | section | Review and Sign off
checkpoint-status | fc18de3f-757d-4842-ae67-5f72a3bac8d1 |  | checkpoint | All installation work complete, checked and reviwed as per specification
checkpoint-status | 98ba5d22-971f-4cf3-a380-26a38abbe3b5 |  | checkpoint | FCC project manager sign off
holdpoint | 932af59b-6fd3-4d24-b8c3-308d69d0f472 |  | signoff | Sign off
checklist-flat | 15ba340e-b1b9-4bd9-b825-94f2a0814d01 |  | checklist | Fibertite Membrane |  |  |  |  | Yes | Fibertite to Plywood Gutters Prestart - Fibertite Membrane Checklist | d84f37d9-cb34-4ff1-87f9-79c39ac2679a
checkpoint-status | f99c706f-41ab-4734-9967-789329b9664a |  | checkpoint | Installed so that laps are facing down(towards drain)
checkpoint-status | a3199d10-1db5-40ad-b533-f2bfb9e22549 |  | checkpoint | Correct Glue used per spec
checkpoint-status | 58df411d-5b3d-489e-acdb-7af6e559b2a6 |  | checkpoint | Fibertite fully glued to plywood
checkpoint-status | 292cb7f0-0d0d-4e47-80f0-326bcabae230 |  | checkpoint | Glue evenly spread and no lumps
checkpoint-status | f6385375-a242-46b8-8cdf-deb894da7eaf |  | checkpoint | All laps, details, penetrations fully closed & QA'd with hook
checklist-flat | c372e648-64eb-4c6a-888b-37500bc22031 |  | checklist | Dayworks - |  |  |  |  | Yes | Dayworks Checklist | e6724851-d5d2-4dd1-92d1-111ec836525b
checkpoint-status | 046f5aae-d62d-425a-91df-2a1fbf914e0d |  | checkpoint | Day Work Details
text | d27d8079-cce6-47f2-bc8f-5447bd0b63c3 |  | textbox | NTSC / SI #:
text | d63889f7-ee5a-4b1a-8284-614d5f938189 |  | textbox | Labours (HR)
text | 926bb36c-59db-4b70-828c-6bc1bf2ce049 |  | textbox | Work Description:
text | 693bbb1a-ade5-4140-a549-223cae16f4cb |  | textbox | Materials:
text | 6d1abe7d-16c2-45ff-b354-7f74775359b8 |  | textbox | SWP Representative. Prepared By:
text | 7e548609-67fa-4b3f-91fa-027d546e556f |  | textbox | Client Representative. Confirmed By:
holdpoint | a8deec19-7a48-40d7-8860-799bb6b0ba11 |  | signoff | Request Signature Signoff
checklist-flat | 41317154-f3e1-4661-9a00-187a5456a28c |  | checklist | Variation Details - |  |  |  |  | Yes | Variation Checklist | e791a42f-651f-4328-82aa-657af12b229e
checkpoint-status | d660d2ad-c3be-45cd-b326-9a74d956e45c |  | checkpoint | Variation Details Approved
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Reference/Drawing/Instruction Number
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Variation Area
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Materials & labour breakdown
holdpoint | 58316cec-d748-4e9a-a597-1363bb53575f | Invalid dependant | signoff | Request Variation Acknowledgement
checkpoint-status | 0e48dbe0-9f3e-42af-847b-00ca9ed4a68f |  | checkpoint | Variation Completed
holdpoint | 76404acb-3347-459e-b957-ea8bde9c5ea0 | Invalid dependant | signoff | Request Variation Signoff