## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Variation Details - |  |  |  |  | Yes | Add Variation | 066d4acc-3a29-41fd-b2cf-e9ac373fee69
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Reference/Drawing/Instruction Number
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Variation Area
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Materials & labour breakdown
holdpoint |  | Invalid dependant | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  | Invalid dependant | signoff | Request Variation Signoff
checklist-sectioned |  |  | checklist | Project Name: |  |  |  |  | Yes | SWP Maintain Project Checklist | 06bea580-57c0-493f-a139-3d559dd85e08
checkpoint-group |  |  | section | Job Information Sheet
checkpoint-status |  |  | checkpoint | Job Details
text | e99d4e25-308f-4e0a-bb9c-6888c62518b9 |  | textbox | Customer
text | 2c5b5511-e823-4c8c-ac34-289a99d210ab |  | textbox | Name of property manager if applicable
text | ca1924bd-a538-429f-91a5-8a48e251c167 |  | textbox | Building Name
text | bb2e4a4c-9779-4d26-9c85-51bc976b6559 |  | textbox | Address
text | 2443c43c-7250-46d6-bbc9-d114422c5434 |  | textbox | Site Contact - name and number
text | 6575f5fb-5072-4f4f-8f5c-b36c97dfcbb5 |  | textbox | Materials used in roofing
text | 9044b83b-e937-4bb5-9a0a-4b352860959c |  | textbox | Roof Areas - Locations
text | f9ad3fc0-3749-4b80-a086-538387ecb959 |  | textbox | Client drawings / warranty / completed repairs
checkpoint-status |  |  | checkpoint | Additional Notes or Comments
text | 832ca12f-421d-4443-9f1c-43b74f91c373 |  | textbox | where / why / mark up
checkpoint-status |  |  | checkpoint | Roof Plan - drawing or Satellite
checkpoint-status |  |  | checkpoint | Pre Inspection Requirements
text | 94eb08b2-41bd-40c8-8db7-43d8698e98fe |  | textbox | ACCESS - How do you access key / locks/ door?
text | c2215f33-3cf8-49a5-ae77-150871e344cf |  | textbox | Safety requirements for Roof - harness - SSSP - Site Login
select | dea04a9c-3772-402b-bbf1-3504be2ab88c |  | dropdown | Is there an induction required online / offline | no,yes
checkpoint-group |  |  | section | Inspection checklist
checkpoint-status |  |  | checkpoint | Vegetation and debris
label | 839d3809-cc7a-4d29-80db-2d13ee777dc0 |  | note | If failed, please take photos
checkpoint-status |  |  | checkpoint | Is Moss and Mold present
label | 3b5d3303-7082-4e7e-a3ec-c912a135b69d |  | note | If failed, please take photos
checkpoint-status |  |  | checkpoint | Inspect gutters, drains and outlets.
label | 8797d552-ab34-4706-8d94-03c6bc9d12ff |  | note | If failed, please take photos
checkpoint-status |  |  | checkpoint | Condition of roof
label | 8ae7d157-ba7b-4269-8be0-b4e606bbaaeb |  | note | If failed, please take photos
checkpoint-status |  |  | checkpoint | Check parapets
label | ec5f1c85-bf3c-4848-86dd-d5e2c1b2e08d |  | note | If failed, please take photos
checkpoint-status |  |  | checkpoint | Inspect laps
label | e445cbdd-98e0-4a02-a6f8-20cff28ae451 |  | note | If failed, please take photos
checkpoint-status |  |  | checkpoint | Check penetrations.
label | a579bd0e-c1a5-44ea-8981-f6cff8a28160 |  | note | If failed, please take photos
checkpoint-status |  |  | checkpoint | Area around HVAC and plant for damage.
label | f5e00594-db1a-4bdd-bb14-a63f06dc4836 |  | note | If failed, please take photos
checkpoint-status |  |  | checkpoint | Check perimeter termination points. E.g. Pressure bar
label | 9dafa712-f97d-4fae-974d-cd843e8cef65 |  | note | If failed, please take photos
checkpoint-status |  |  | checkpoint | Check associated roof flashings
label | dc2b0ed5-c5dd-4ad1-b76b-1b43540fb149 |  | note | If failed, please take photos
checkpoint-status |  |  | checkpoint | Check Seismic inter-building flashings
label | cd76aa8e-b8d6-4816-a296-00111b564b22 |  | note | If failed, please take photos
checkpoint-status |  |  | checkpoint | Check visual condition of Plant
label | f88fe6b8-2bc1-4fd2-ace2-b12f691a8d2a |  | note | If failed, please take photos
checkpoint-status |  |  | checkpoint | Main roof fixings in good condition
label | 31f637ba-9b8e-4741-98ef-7c4afb99db53 |  | note | If failed, please take photos
checkpoint-status |  |  | checkpoint | Other items noted during inspection
label | e44a0074-45ed-4d8a-beb5-8d3ca5e20298 |  | note | If failed, please take photos
checkpoint-status |  |  | checkpoint | Works to be undertaken that fall outside of annual maintenance
checkpoint-group |  |  | section | Maintain Completion checklist
checkpoint-status |  |  | checkpoint | Vegetation and debris removed
checkpoint-status |  |  | checkpoint | Moss and mold removed
checkpoint-status |  |  | checkpoint | Gutters, drains and outlets clean and clear
checkpoint-status |  |  | checkpoint | Job Inspection form remedial work carried out
checkpoint-status |  |  | checkpoint | Additional comments
checkpoint-status |  |  | checkpoint | Maintenance complete and signed off
holdpoint |  |  | signoff | Request Sign off
checklist-sectioned |  |  | checklist | Metal Roof Installation Checklist |  |  |  |  | Yes | Add Metal Roof Installation Checklist | 0a2a9a8b-f1d9-42b8-b915-824bd69ec5ef
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible.
checkpoint-status |  |  | checkpoint | Edge protection/ Safe access installed. (Safe to be on roof)
checkpoint-status |  |  | checkpoint | Substrate (i.e. timberwork/Purlins) complete and ready for system.
checkpoint-status |  |  | checkpoint | Drip edge, screws ordered for entire roof.
checkpoint-group |  |  | section | Safety Mesh Installation
checkpoint-status |  |  | checkpoint | Laid perpindicular to the purlins.
checkpoint-status |  |  | checkpoint | Fully secured to Purlins/Timber.
checkpoint-status |  |  | checkpoint | No protruding bits or loose ends.
checkpoint-group |  |  | section | Covertek Roofing Paper Installation
checkpoint-status |  |  | checkpoint | Laid either perpindicular or parallel with purlins.
checkpoint-status |  |  | checkpoint | Overlapped a minimum 150mm
checkpoint-status |  |  | checkpoint | All areas completely covered.
checkpoint-status |  |  | checkpoint | Laid tight to timeber/purlins.
checkpoint-status |  |  | checkpoint | Secured so it will not blow away if roof not being installed immediately.
checkpoint-group |  |  | section | Metal Roof Installation
checkpoint-status |  |  | checkpoint | Drip edge installed
checkpoint-status |  |  | checkpoint | Laid straight & perpindicular to gutter/purlins
checkpoint-status |  |  | checkpoint | Correct gutter overhang 65/75mm
checkpoint-status |  |  | checkpoint | Top ends of sheets turned up.
checkpoint-status |  |  | checkpoint | Fixings back into purlins and laid in a straight line as per Code of Practice.
checkpoint-status |  |  | checkpoint | Closure foam to gutter ends.
checkpoint-group |  |  | section | Roof Flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to drawings and to the Code of Practice.
checkpoint-status |  |  | checkpoint | All fixings in place and done according to code of practice.
checkpoint-status |  |  | checkpoint | All laps and junctions sealed properly.
checkpoint-group |  |  | section | Sign Offs
checkpoint-status |  |  | checkpoint | Area complete and ready for MC sign off
holdpoint |  |  | signoff | REQUEST SIGN OFF SIGNATURE
checklist-sectioned |  |  | checklist | Concrete Torch On Checklist - |  |  |  |  | Yes | Concrete Torch On Checklist | 0a4987d6-70dd-4196-8e00-1e83e80d8e33
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP (metal/concrete/ply)
checkpoint-status |  |  | checkpoint | Perimeter support installed installed if metal deck substrate
checkpoint-group |  |  | section | Concrete
checkpoint-status |  |  | checkpoint | Concrete clean and dry. Free from dirt/debris and ready for priming
checkpoint-status |  |  | checkpoint | All lumps and sharp concrete bits ground down/hammered down
checkpoint-status |  |  | checkpoint | Large holes filled with grout
checkpoint-group |  |  | section | Prime of Substrate
checkpoint-status |  |  | checkpoint | Substrate swept, dry and free of debri
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed in a brick pattern
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-status |  |  | checkpoint | Fixings at correct spacing according to spec if no Securock in system.
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with recessed flat plates
checkpoint-status |  |  | checkpoint | Prime of Securrock
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Bleed of bitumen on overlap should be up to 10mm
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check of all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 200mm
checkpoint-status |  |  | checkpoint | Clamp and weld into overflows and outlets
checkpoint-status |  |  | checkpoint | Flood test of outlets
checkpoint-group |  |  | section | Sign Offs
checkpoint-status |  |  | checkpoint | Area complete and ready for MC sign off
holdpoint |  |  | signoff | REQUEST SIGN OFF SIGNATURE
checklist-sectioned |  |  | checklist | Sheet Tanking - Area: |  |  |  |  | Yes | Add Sheet Tanking System Checklist | 138aaadc-a287-4267-a7ee-40bc7836b322
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Primer
checkpoint-status |  |  | checkpoint | Applied as per specification on dry substrate at 5m2 per litre
checkpoint-group |  |  | section | Membrane
checkpoint-status |  |  | checkpoint | Temperature must be over 4 degrees for membrane install
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear
checkpoint-status |  |  | checkpoint | Membrane applied with min 50mm overlap
checkpoint-status |  |  | checkpoint | Overlap is to pressure applied or rolled for seal
checkpoint-group |  |  | section | Protection
checkpoint-status |  |  | checkpoint | Works to be protected by main contractor
checklist-sectioned |  |  | checklist | Rooflogic Fibertite Over Plywood |  |  |  |  | Yes | Rooflogic Fibertite Over Plywood | 13b5a5bb-fdc8-448a-9a02-3c859afa29e7
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection in place
checkpoint-status |  |  | checkpoint | Substrate clean and clear of debris and moss/mould
checkpoint-group |  |  | section | Plywood substrate
checkpoint-status |  |  | checkpoint | Fixed off at correct centres
checkpoint-status |  |  | checkpoint | No damage to substare
checkpoint-status |  |  | checkpoint | Install ILD SS Mesh over substrate
checkpoint-group |  |  | section | Roof board HDP
checkpoint-status |  |  | checkpoint | Roof boards Installed tight and in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with laod washer
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-group |  |  | section | Fibertite XT
checkpoint-status |  |  | checkpoint | Surface clean and free from debris
checkpoint-status |  |  | checkpoint | Adhesive installed to base sheet the width of the roll
checkpoint-status |  |  | checkpoint | Laying of membrane into the adhesive
checkpoint-status |  |  | checkpoint | Laping on adjacent membrane to be minimum of 75mm
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane into adhesive
checkpoint-status |  |  | checkpoint | Wipe and clean of laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with welding machine
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-status |  |  | checkpoint | ILD test
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly accordnig to specifications
checkpoint-status |  |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of weld with QA hook
checkpoint-group |  |  | section | Review and Sign off
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviwed as per specification
checkpoint-status |  |  | checkpoint | FCC project manager sign off
holdpoint |  |  | signoff | Sign off
checklist-flat |  |  | checklist | Flood Test Area: |  |  |  |  | Yes | Add Flood Testing Checklist | 1558648f-6327-4727-b1c6-6fa74bfa36e4
checkpoint-status |  |  | checkpoint | Is area fully finished, QA’d and ready to be tested
checkpoint-no-status |  |  | checkpoint | Flood test details
text | dc968f8f-9cf1-485a-a65f-e4087427ee32 |  | textbox | Date:
text | b0fb2bc4-3c3c-47bb-93fe-add4a651804d |  | textbox | Area tested:
text | befd486d-6456-4e39-ba95-1395566ebfda |  | textbox | Duration:
button | 3fff6840-5866-4f4c-96c8-494f7e9efd79 |  | button | Have you checked regularly for leaks | Yes, No, N/A
button | 050fef10-15f2-4590-ba62-2a0b1b1b0a29 |  | button | Is there rain in the forecast | Yes, No, N/A
button | 0816c7fc-09ce-4e48-9a88-625c7f8c9a23 |  | button | Have you eft some outlets/scuppers so that the building doesn't flood | Yes, No, N/A
button | b9de0cd4-9c7a-42cb-89ee-535d7ebdcd00 |  | button | Have all leaks been repaired | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Flood test complete
button | 5d04628a-e7a1-4bd7-b9ee-92a88ef12e94 |  | button | Have the plugs been removed from the drains | Yes, No, N/A
button | b74c91b9-0371-4641-ad5b-1c9d76ee0c77 |  | button | Debris and materials removed from the gutter/membrane/roof | Yes, No, N/A
holdpoint |  |  | signoff | Sign Off
checklist-sectioned |  |  | checklist | Fibertherm Checklist |  |  |  |  | Yes | Fibertherm Checklist | 21075296-c19e-44c0-8a0e-2e9f5c00e534
checkpoint-group |  |  | section | Pre start
checkpoint-status |  |  | checkpoint | Area Accessable
checkpoint-status |  |  | checkpoint | Edge Protection and sfatey installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready (purlins/ply)
checkpoint-status |  |  | checkpoint | Perimtere support installed if metal deck substrate
checkpoint-group |  |  | section | Metal Deck
checkpoint-status |  |  | checkpoint | Timber to have separation
checkpoint-status |  |  | checkpoint | End openings to have closure foam installed
checkpoint-status |  |  | checkpoint | Base deck screwed down in every pan
checkpoint-status |  |  | checkpoint | VCL tape to be installed to all sheet laps
checkpoint-status |  |  | checkpoint | VCL tape to all upstands
checkpoint-group |  |  | section | Post and Rail install
checkpoint-status |  |  | checkpoint | Post installed at correct fixing centers
checkpoint-status |  |  | checkpoint | Thermal break pad under post foot
checkpoint-status |  |  | checkpoint | Rail installed to posts
checkpoint-status |  |  | checkpoint | Gutter line colsure/drip edge flashing installed
checkpoint-group |  |  | section | Insulation install
checkpoint-status |  |  | checkpoint | Specified Insulation installed
checkpoint-status |  |  | checkpoint | No Gaps
checkpoint-group |  |  | section | Top Deck install
checkpoint-status |  |  | checkpoint | Lay sheets straight
checkpoint-status |  |  | checkpoint | Hang over into gutter min 75mm
checkpoint-status |  |  | checkpoint | Top end of sheets turned up
checkpoint-status |  |  | checkpoint | Bottom end of sheets turned down
checkpoint-status |  |  | checkpoint | Fixing back to rail
checkpoint-status |  |  | checkpoint | Profile washers
checkpoint-status |  |  | checkpoint | Screwed off as per fixing plan
checkpoint-group |  |  | section | Flashing install
checkpoint-status |  |  | checkpoint | Installed correctly, accoriding to spec's & drawings
checkpoint-status |  |  | checkpoint | Fixings according to specs & details
checkpoint-group |  |  | section | Sign offs
checkpoint-status |  |  | checkpoint | Sign off
checklist-sectioned |  |  | checklist | Rooflogic Ultratherm Xtreme Tappered Gutter |  |  |  |  | Yes | Rooflogic Ultratherm Xtreme Tappered Gutter | 2e06c403-b35b-4c0d-b0d9-c9c731ae5a57
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection in place
checkpoint-status |  |  | checkpoint | Steel plate gutter liner installed by others
checkpoint-group |  |  | section | Steel plate gutter liner
checkpoint-status |  |  | checkpoint | Gutter liner installed signed off and handed over
checkpoint-status |  |  | checkpoint | Outlet holes cut into base
checkpoint-group |  |  | section | VCL
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry clear of swarf
checkpoint-status |  |  | checkpoint | Prime steel deck with SA primer
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 100mm min
checkpoint-status |  |  | checkpoint | All holes/penetrations pactehd and watertight
checkpoint-group |  |  | section | Stonewool Insulation above VCL
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | VCL has been checked for no damage
checkpoint-status |  |  | checkpoint | 600mm wide stonewool insulation installed above tall wall
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards)
checkpoint-group |  |  | section | PIR Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | VCL has been checked for no damage
checkpoint-status |  |  | checkpoint | Gutter edge flashing installed
checkpoint-status |  |  | checkpoint | Prime top of VCL with SA primer
checkpoint-status |  |  | checkpoint | Install board bond adhesive
checkpoint-status |  |  | checkpoint | Insulation Board installed tight and no gaps
checkpoint-group |  |  | section | ILD system
checkpoint-status |  |  | checkpoint | PIR insualtion linked with conductive metal tape
checkpoint-status |  |  | checkpoint | Conductive continuity Ribbon installed at 1200mm centres
checkpoint-group |  |  | section | Roof board HDP
checkpoint-status |  |  | checkpoint | Install board bond to PIR board
checkpoint-status |  |  | checkpoint | Roof boards Installed tight
checkpoint-status |  |  | checkpoint | Install RL roof outlet to sit flush at roof board
checkpoint-group |  |  | section | Fibertite XT
checkpoint-status |  |  | checkpoint | Surface clean and free from debris
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate the width of the roll
checkpoint-status |  |  | checkpoint | Laying of membrane into the adhesive
checkpoint-status |  |  | checkpoint | Laping on adjacent membrane to be minimum of 75mm
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane into adhesive
checkpoint-status |  |  | checkpoint | Wipe and clean of laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with welding machine
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-status |  |  | checkpoint | ILD test
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly accordnig to specifications
checkpoint-status |  |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of weld with QA hook
checkpoint-group |  |  | section | Review and Sign off
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviwed as per specification
checkpoint-status |  |  | checkpoint | FCC project manager sign off
holdpoint |  |  | signoff | Sign off
checklist-flat |  |  | checklist | Delay Checklist |  |  |  |  | Yes | Add Delay Checklist | 339b4916-4b79-43eb-b292-6ccd20d6d86c
checkpoint-no-status |  |  | checkpoint | Delay details.
text | ae5b692f-ee75-4a3d-90e7-43a6b2bca49e |  | textbox | Date:
text | 8e11a44b-51f7-4a8f-9494-ec9e467452ec |  | textbox | Description:
text | 22cd20b8-86af-49a9-97d4-39d5b860ca1a |  | textbox | Area/Grids:
text | e5ab19af-90b5-4328-9a8b-ee0707087643 |  | textbox | Wind/Weather Conditions:
checklist-flat |  |  | checklist | Dayworks - |  |  |  |  | Yes | Add Dayworks Checklist | 3aab97e3-bf39-4784-b0c9-d812bd602938
checkpoint-status |  |  | checkpoint | Day Work Details
text | d27d8079-cce6-47f2-bc8f-5447bd0b63c3 |  | textbox | NTSC / SI #:
text | d63889f7-ee5a-4b1a-8284-614d5f938189 |  | textbox | Labours (HR)
text | 926bb36c-59db-4b70-828c-6bc1bf2ce049 |  | textbox | Work Description:
text | 693bbb1a-ade5-4140-a549-223cae16f4cb |  | textbox | Materials:
text | 6d1abe7d-16c2-45ff-b354-7f74775359b8 |  | textbox | SWP Representative. Prepared By:
text | 7e548609-67fa-4b3f-91fa-027d546e556f |  | textbox | Client Representative. Confirmed By:
holdpoint |  |  | signoff | Request Signature Signoff
checklist-sectioned |  |  | checklist | FiberTite Checklist - Area: |  |  |  |  | Yes | Add FibreTite Checklist | 3b5b3db8-b360-4a3a-87a6-c1c8f458b588
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP (metal/concrete/ply)
checkpoint-status |  |  | checkpoint | Perimeter support installed installed if metal deck substrate
checkpoint-group |  |  | section | Metal Deck
checkpoint-status |  |  | checkpoint | Timber to have separation barrier
checkpoint-status |  |  | checkpoint | Base deck screwed down in every pan
checkpoint-status |  |  | checkpoint | Sheet edges stiched together at 300mm centres
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed in a brick pattern
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-status |  |  | checkpoint | Fixings at correct spacing according to spec if no Securock in system.
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | correct length screw with recessed flat plates
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
checkpoint-group |  |  | section | FiberTite
checkpoint-status |  |  | checkpoint | Test weld with welding machine
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into the adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean of laps prior to welding
checkpoint-status |  |  | checkpoint | Probe of seams with QA hook
checkpoint-status |  |  | checkpoint | Clamp and weld of outlets and overflows
checkpoint-status |  |  | checkpoint | Flood test of outlets
checkpoint-group |  |  | section | Fiberclad flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications (Right way around)
checkpoint-status |  |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of weld with QA hook
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Area Complete (Request MC Signoff)
holdpoint |  | Invalid dependant | signoff | Request Signoff
checklist-sectioned |  |  | checklist | Carpark MMA - |  |  |  |  | Yes | Add Carpark MMA Checklist | 3c85bf5c-272d-4019-af85-a17b5d278ff8
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | SSSP onsite
checkpoint-status |  |  | checkpoint | Photos of any existing linemarkings installed
checkpoint-status |  |  | checkpoint | Fencing demarcation installed
checkpoint-status |  |  | checkpoint | Site signage installed
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Surface Prep
checkpoint-status |  |  | checkpoint | Removal of coatings
checkpoint-status |  |  | checkpoint | Grind of substrate
checkpoint-status |  |  | checkpoint | Shotblast of substrate to achieve suitable profile
checkpoint-group |  |  | section | Pre-start of membrane install
checkpoint-status |  |  | checkpoint | Substrate dry
checkpoint-group |  |  | section | Membrane install
checkpoint-status |  |  | checkpoint | Prime of substrate
checkpoint-status |  |  | checkpoint | Stripe out cracks
checkpoint-status |  |  | checkpoint | Map out areas based on coverage rates for install
checkpoint-status |  |  | checkpoint | Membrane layer installed
checkpoint-status |  |  | checkpoint | Wear layer installed and broadcast
checkpoint-status |  |  | checkpoint | Excess broadcast swept and removed
checkpoint-status |  |  | checkpoint | 1st Top coat
checkpoint-status |  |  | checkpoint | 2nd top coat
checkpoint-status |  |  | checkpoint | Linemarking installed
checkpoint-status |  |  | checkpoint | Site cleared and broken down
checkpoint-status |  |  | checkpoint | Site cleared and broken down
checklist-sectioned |  |  | checklist | Metal Deck Torch On Checklist - |  |  |  |  | Yes | Metal Deck Torch On Checklist | 3f149580-791c-4991-a1f6-f1d18a0c233a
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP (metal/concrete/ply)
checkpoint-status |  |  | checkpoint | Perimeter support installed installed if metal deck substrate
checkpoint-group |  |  | section | Metal Deck
checkpoint-status |  |  | checkpoint | Timber to have separation barrier
checkpoint-status |  |  | checkpoint | Base deck screwed down in every pan
checkpoint-status |  |  | checkpoint | Sheet edges stitched together at 300mm centres
checkpoint-status |  |  | checkpoint | No sharp edges protruding
checkpoint-group |  |  | section | Prime of Substrate
checkpoint-status |  |  | checkpoint | Substrate swept, dry and free of debri
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed in a brick pattern
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-status |  |  | checkpoint | Fixings at correct spacing according to spec if no Securock in system.
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with recessed flat plates
checkpoint-status |  |  | checkpoint | Prime of Securrock
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Bleed of bitumen on overlap should be up to 10mm
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check of all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 200mm
checkpoint-status |  |  | checkpoint | Clamp and weld into overflows and outlets
checkpoint-status |  |  | checkpoint | Flood test of outlets
checkpoint-group |  |  | section | Sign Offs
checkpoint-status |  |  | checkpoint | Area complete and ready for MC sign off
holdpoint |  |  | signoff | REQUEST SIGN OFF SIGNATURE
checklist-sectioned |  |  | checklist | Soffit |  |  |  |  | Yes | Soffit Checklist | 40f0e68d-d659-4f32-8f32-fe6b2e68fabc
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Substrate ready (check plans) with proper purlin spacing
checkpoint-status |  |  | checkpoint | Design/Spec/Approvals complete
checkpoint-group |  |  | section | Install
checkpoint-status |  |  | checkpoint | Flashings installed according to plans
checkpoint-status |  |  | checkpoint | All sealant work complete
checkpoint-status |  |  | checkpoint | Install soffit lining according to plans/spec/best practice
checkpoint-status |  |  | checkpoint | Screw pattern according to plans/spec/best practice
checkpoint-status |  |  | checkpoint | Finish flashings complete
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Cladding Install Complete
holdpoint |  |  | signoff | Request Sign Off
folder-normal |  |  | checklist | New Files Folder: |  |  |  |  | Yes | Add Files Folder | 51d3794c-5fa7-459e-97c7-61ed1c1861c2
checklist-sectioned |  |  | checklist | Weather Monitoring |  |  |  |  | Yes | Weather Monitoring | 52a0ad6f-5692-4a01-aafb-3274fe84dee6
checkpoint-group |  |  | section | Current Weather
checkpoint-status |  |  | checkpoint | Todays date & Time
checkpoint-status |  |  | checkpoint | Wind / weather conditions
checkpoint-status |  |  | checkpoint | Record any delays
checkpoint-status |  |  | checkpoint | area / gridlines
checkpoint-status |  |  | checkpoint | Comments / issues / observations
checkpoint-group |  |  | section | Weather Forecast
checkpoint-status |  |  | checkpoint | What is the weather forecast this week
checkpoint-status |  |  | checkpoint | Record any delays
checkpoint-status |  |  | checkpoint | area / gridlines
checkpoint-status |  |  | checkpoint | Comments / issues / observations
checklist-sectioned |  |  | checklist | Rooflogic Xtreme Fibertite Gutter over PLY System AWL |  |  |  |  | Yes | Rooflogic Xtreme Fibertite Gutter over PLY System AWL | 57a9a176-de73-4d20-8189-7742c34f443f
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection in place
checkpoint-status |  |  | checkpoint | Structure and substrate has been handedover by LTM. No check of falls by SWP
checkpoint-status |  |  | checkpoint | Max weight load on roof per pack is 500kg
checkpoint-group |  |  | section | Plywood gutters
checkpoint-status |  |  | checkpoint | Plywood installed as per agreed scope with LTM
checkpoint-status |  |  | checkpoint | Handover of QA from LTM
checkpoint-status |  |  | checkpoint | Plywood below 18% moisture
checkpoint-status |  |  | checkpoint | Plywood joints/screws flush
checkpoint-status |  |  | checkpoint | All screws in place
checkpoint-group |  |  | section | VCL
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry clear of swarf and debris
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 100mm min
checkpoint-group |  |  | section | Stonewool 150mm Insulation above VCL
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | VCL has been checked for no damage (100x100 patch)
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between stonewool)
checkpoint-status |  |  | checkpoint | Gutter edge flashing installed
checkpoint-group |  |  | section | Roof board HDP mechanically fixed
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Roof boards Installed tight and in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with load washer min 20mm penetration into base deck
checkpoint-status |  |  | checkpoint | Insulation Board installed tight and no gaps
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-group |  |  | section | ILD system
checkpoint-status |  |  | checkpoint | Conductive continuity mesh installed
checkpoint-group |  |  | section | Roof board HDP Adhered with 600 board bond glue
checkpoint-status |  |  | checkpoint | Roof boards Installed tight and in brick pattern
checkpoint-status |  |  | checkpoint | Correct glue Armac 600u
checkpoint-status |  |  | checkpoint | Glue Installed as per suppliers specifcation Spray Armac 600u Board Bond 30mm wide beads continuously as 100mm centres.
checkpoint-status |  |  | checkpoint | Installed insulation to be covered with fibretite membrane in the same day
checkpoint-status |  |  | checkpoint | Any damaged board to be replaced with a full new board
checkpoint-group |  |  | section | Fibertite
checkpoint-status |  |  | checkpoint | Surface clean and free from debris, no excess moisture
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate the width of the roll
checkpoint-status |  |  | checkpoint | Laying of membrane into the adhesive and Correct glue Armac 400u
checkpoint-status |  |  | checkpoint | Laping on adjacent membrane to be minimum of 75mm
checkpoint-status |  |  | checkpoint | Broom/weighted rolling of membrane into adhesive
checkpoint-status |  |  | checkpoint | Wipe and clean of laps prior to welding with acetone
checkpoint-status |  |  | checkpoint | Test weld with welding machine
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-status |  |  | checkpoint | ILD test
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications
checkpoint-status |  |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of weld with QA hook
checkpoint-group |  |  | section | Review and Sign off
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | LT Mcguiness project manager sign off
holdpoint |  |  | signoff | Sign off
checklist-sectioned |  |  | checklist | Parapets AWL |  |  |  |  | Yes | Parapets AWL | 5d3cc62d-6c33-4eb8-8077-b6d3a4c9e0b7
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection in place
checkpoint-status |  |  | checkpoint | Structure and substrate has been handed over by LTM. No check of falls by SWP
checkpoint-status |  |  | checkpoint | Max weight load on roof per pack is 500kg
checkpoint-group |  |  | section | Base Deck
checkpoint-status |  |  | checkpoint | Base deck installed as per agreed scope with lts
checkpoint-status |  |  | checkpoint | All penetration boxes and pipes to be installed through the base deck
checkpoint-status |  |  | checkpoint | Approved fixings used 12-14x20 class 4 steelteks with neos
checkpoint-status |  |  | checkpoint | Base deck screwed off at every purlin and every pan
checkpoint-status |  |  | checkpoint | Base deck stitched along side-laps at 300mm centres
checkpoint-group |  |  | section | VCL
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry clear of swarf
checkpoint-status |  |  | checkpoint | Plywood parapet upstand joints flush and moisture under 18%
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 100mm min
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and watertight
checkpoint-group |  |  | section | Stonewool 150mm Insulation above VCL
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | VCL has been checked for no damage (100x100 patch)
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between stonewool)
checkpoint-status |  |  | checkpoint | Gutter edge flashing installed
checkpoint-group |  |  | section | Roof board HDP mechanically fixed
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Roof boards Installed tight and in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with load washer min 20mm penetration into base deck and plywood upstand
checkpoint-status |  |  | checkpoint | Insulation Board installed tight and no gaps
checkpoint-status |  |  | checkpoint | Any damaged board to be replaced with a full new board
checkpoint-status |  |  | checkpoint | Installed insulation to be covered with fibretite membrane in the same day
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-group |  |  | section | ILD system
checkpoint-status |  |  | checkpoint | Conductive continuity mesh installed
checkpoint-group |  |  | section | Fibertite
checkpoint-status |  |  | checkpoint | Surface clean and free from debris, no excess moisture
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate the width of the roll
checkpoint-status |  |  | checkpoint | Laying of membrane into parapet upstand with 220 glue
checkpoint-status |  |  | checkpoint | Laying of membrane into the adhesive and Correct glue Armac 400u
checkpoint-status |  |  | checkpoint | Laping on adjacent membrane to be minimum of 75mm
checkpoint-status |  |  | checkpoint | Broom/weighted rolling of membrane into adhesive
checkpoint-status |  |  | checkpoint | Wipe and clean of laps prior to welding with acetone
checkpoint-status |  |  | checkpoint | Test weld with welding machine
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-status |  |  | checkpoint | ILD test
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications
checkpoint-status |  |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of weld with QA hook
checkpoint-group |  |  | section | Review and Sign off
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | LT Mcguiness project manager sign off
holdpoint |  |  | signoff | Sign off
checklist-sectioned |  |  | checklist | Resiplast to Nibs & Rattle Space - |  |  |  |  | Yes | Add Resiplast to Nibs & Rattle Space Checklist | 6c474b5b-a9a2-48c7-9ad1-605373b6e631
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | SSSP onsite
checkpoint-status |  |  | checkpoint | Photos of any existing linemarkings installed
checkpoint-status |  |  | checkpoint | Fencing demarcation installed
checkpoint-status |  |  | checkpoint | Site signage installed
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Surface Prep
checkpoint-status |  |  | checkpoint | Removal of existing coatings completed
checkpoint-status |  |  | checkpoint | Grind of substrate
checkpoint-status |  |  | checkpoint | Shortblast of substrate to achieve suitable profile
checkpoint-group |  |  | section | Pre-start of membrane install
checkpoint-status |  |  | checkpoint | Substrate Dry
checkpoint-group |  |  | section | Membrane Install
checkpoint-status |  |  | checkpoint | Prime of substrate
checkpoint-status |  |  | checkpoint | Membrane layer installed
checkpoint-status |  |  | checkpoint | Wear layer installed and broadcast
checkpoint-status |  |  | checkpoint | Excess broadcast swept and removed
checkpoint-status |  |  | checkpoint | Top coat
checkpoint-status |  |  | checkpoint | Area handover
checklist-sectioned |  |  | checklist | Cladding Install |  |  |  |  | Yes | Cladding Install Checklist | 6da692ea-8137-40cc-851f-79764aaf8585
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Substrate ready (check plans)
checkpoint-status |  |  | checkpoint | Design/plans/approval complete
checkpoint-group |  |  | section | Install
checkpoint-status |  |  | checkpoint | Bottom flashing installed straight/level all the way around
checkpoint-status |  |  | checkpoint | Flashing tape installed (check plans)
checkpoint-status |  |  | checkpoint | Window/door/louvre flashings installed according to plans/best practice
checkpoint-status |  |  | checkpoint | First sheet laid straight/plumb
checkpoint-status |  |  | checkpoint | Screw pattern according to plan/spec/best practice
checkpoint-status |  |  | checkpoint | Finish flashings completed and sealed properly
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Cladding Install Complete
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | Gutter Install |  |  |  |  | Yes | Gutter Install Checklist | 70fb8fc4-29fc-4a24-bd22-2368cc5de7f3
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible and ready to install
checkpoint-status |  |  | checkpoint | Materials ready
checkpoint-status |  |  | checkpoint | Substrate ready (check plans)
checkpoint-group |  |  | section | Install
checkpoint-status |  |  | checkpoint | Brackets installed according to plans/spec/best practice
checkpoint-status |  |  | checkpoint | Gutter lapped and sealed correctly according to best practice
checkpoint-status |  |  | checkpoint | All terminations and ends folded/sealed properly
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Cladding Install Complete
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | Metal Flashing Install |  |  |  |  | Yes | Metal Flashing Install | 84956317-7b7d-480d-8d9b-21fa3ad98cd6
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge Protection/safe access installed (safe to be on the roof)
checkpoint-status |  |  | checkpoint | Substrate complete and ready for flashings
checkpoint-group |  |  | section | Underlay
checkpoint-status |  |  | checkpoint | Underlay installed between substrate and new flashing
checkpoint-status |  |  | checkpoint | Overlapped a minimum of 100mm
checkpoint-status |  |  | checkpoint | All areas under new flashing completely covered
checkpoint-status |  |  | checkpoint | Secured so it will not blow away if flashing not being installed immediately
checkpoint-group |  |  | section | Metal Flashing Install
checkpoint-status |  |  | checkpoint | Installed with a minimum upstand of 150mm or according to drawings
checkpoint-status |  |  | checkpoint | Expansion joint installed if needed (i.e. with runs longer than 12m for coloursteel or 8m for Ali.)
checkpoint-status |  |  | checkpoint | Fixings according to Code as a minimum (or plans if more are required) in a straight line
checkpoint-status |  |  | checkpoint | Laid in a straight and tidy manner
checkpoint-status |  |  | checkpoint | All laps and junctions sealed properly and facing away from waterflow
checkpoint-status |  |  | checkpoint | All visible ends & junctions cut and folded straight and tidy
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Area complete and ready for MC sign off
holdpoint |  |  | signoff | REQUEST SIGNATURE SIGN OFF
checklist-sectioned |  |  | checklist | Fibertite to Plywood |  |  |  |  | Yes | Add FibreTite to Plywood Checklist | 868e357f-f648-4639-98c3-83b9770f98ba
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible (free of gear and materials from other contractors)
checkpoint-status |  |  | checkpoint | Area fully ready for Membrane
checkpoint-group |  |  | section | Plywood Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status |  |  | checkpoint | No Screws/nails/fixings popping up
checkpoint-status |  |  | checkpoint | Joints flush and even
checkpoint-group |  |  | section | Fibertite Membrane
checkpoint-status |  |  | checkpoint | Installed so that laps are facing down(towards drain)
checkpoint-status |  |  | checkpoint | Correct Glue used per spec
checkpoint-status |  |  | checkpoint | Fibertite fully glued to plywood
checkpoint-status |  |  | checkpoint | Glue evenly spread and no lumps
checkpoint-status |  |  | checkpoint | All laps, details, penetrations fully closed & QA'd with hook
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications (right way around)
checkpoint-status |  |  | checkpoint | Fixings and welding done according to details
checkpoint-status |  |  | checkpoint | Welding of Fibertite to flashings fully finished and QA'd with hook
checkpoint-group |  |  | section | Final Sign Off
checkpoint-status |  |  | checkpoint | Area complete and ready for MC sign off
holdpoint |  |  | signoff | Request Sign Off Signature
checklist-sectioned |  |  | checklist | MSR Checklist - Area: |  |  |  |  | Yes | Add MSR Checklist | a1d211ff-57d2-489b-b562-f1e8a8db7621
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP (purlins/ply)
checkpoint-status |  |  | checkpoint | Perimeter support installed installed if metal deck substrate
checkpoint-group |  |  | section | Metal Deck
checkpoint-status |  |  | checkpoint | Timber to have separation barrier
checkpoint-status |  |  | checkpoint | Base deck screwed down in every pan
checkpoint-status |  |  | checkpoint | Sheet edges stiched together at 300mm centres
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed in a brick pattern
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-status |  |  | checkpoint | Fixings at correct spacing according to spec if no Securock in system.
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | correct length screw with recessed flat plates
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
checkpoint-group |  |  | section | Topdeck Install
checkpoint-status |  |  | checkpoint | Covertek Installed with 150mm overlap
checkpoint-status |  |  | checkpoint | Drip edge installed
checkpoint-status |  |  | checkpoint | Lay sheet with 75mm gutter overhang
checkpoint-status |  |  | checkpoint | Top end of sheet turned up
checkpoint-status |  |  | checkpoint | Fixing back into purlin
checkpoint-status |  |  | checkpoint | Closure foam to gutter end
checkpoint-status |  |  | checkpoint | Profile Washers over 12m
checkpoint-status |  |  | checkpoint | Sheets straight & perpendicular to gutter
checkpoint-status |  |  | checkpoint | Screw pattern as per fixing plan
checkpoint-group |  |  | section | Roof flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specification & drawings
checkpoint-status |  |  | checkpoint | Fixings done according to specifications and details
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Area Complete (Request MC Signoff)
holdpoint |  | Invalid dependant | signoff | Request Signoff
checklist-sectioned |  |  | checklist | Rooflogic Xtreme Fibertite Roofing System AWL |  |  |  |  | Yes | Rooflogic Xtreme Fibertite Roofing System AWL | b4679d42-f5ec-44eb-9a22-c0fafb537603
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection in place
checkpoint-status |  |  | checkpoint | Structure and substrate has been handed over by LTM. No check of falls by SWP
checkpoint-status |  |  | checkpoint | Max weight load on roof per pack is 500kg
checkpoint-group |  |  | section | Base Deck
checkpoint-status |  |  | checkpoint | Base deck installed as per agreed scope with lts
checkpoint-status |  |  | checkpoint | All penetration boxes and pipes to be installed through the base deck
checkpoint-status |  |  | checkpoint | Approved fixings used 12 -14x20 class 4 steelteks with neos
checkpoint-status |  |  | checkpoint | Base deck screwed off at every purlin and every pan
checkpoint-status |  |  | checkpoint | Base deck stitched along side-laps at 300mm centres
checkpoint-group |  |  | section | VCL
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 100mm min
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and watertight
checkpoint-group |  |  | section | Stonewool 150mm Insulation above VCL
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | VCL has been checked for no damage (100x100 patch)
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between stonewool)
checkpoint-status |  |  | checkpoint | Gutter edge flashing installed
checkpoint-group |  |  | section | Roof board HDP mechanically fixed
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Roof boards Installed tight and in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with load washer min 20mm penetration into base deck
checkpoint-status |  |  | checkpoint | Insulation Board installed tight and no gaps
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-group |  |  | section | ILD system
checkpoint-status |  |  | checkpoint | Conductive continuity mesh installed
checkpoint-group |  |  | section | Roof board HDP Adhered with 600 board bond glue
checkpoint-status |  |  | checkpoint | Roof boards Installed tight and in brick pattern
checkpoint-status |  |  | checkpoint | Correct glue Armac 600u
checkpoint-status |  |  | checkpoint | Glue Installed as per suppliers specification Spray Armac 600u Board Bond 30mm wide beads continuously as 100mm centres.
checkpoint-status |  |  | checkpoint | Installed insulation to be covered with fibretite membrane in the same day
checkpoint-status |  |  | checkpoint | Any damaged board to be replaced with a full new board
checkpoint-group |  |  | section | Fibertite
checkpoint-status |  |  | checkpoint | Surface clean and free from debris, no excess moisture
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate the width of the roll
checkpoint-status |  |  | checkpoint | Laying of membrane into the adhesive and Correct glue Armac 400u
checkpoint-status |  |  | checkpoint | Laping on adjacent membrane to be minimum of 75mm
checkpoint-status |  |  | checkpoint | Broom/weighted rolling of membrane into adhesive
checkpoint-status |  |  | checkpoint | Wipe and clean of laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with welding machine
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-status |  |  | checkpoint | ILD test
checkpoint-group |  |  | section | Pipe penetrations
checkpoint-status |  |  | checkpoint | 150mm minimum upstand
checkpoint-status |  |  | checkpoint | RL E-101 Sealant applied as per specifications
checkpoint-status |  |  | checkpoint | Clamped with stainless steel hose clamp
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications
checkpoint-status |  |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of weld with QA hook
checkpoint-group |  |  | section | Review and Sign off
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | LT Mcguiness project manager sign off
holdpoint |  |  | signoff | Sign off
checklist-sectioned |  |  | checklist | Fibretite onto metal base |  |  |  |  | Yes | Add Fibertite onto metal base checklist | c6e59964-12eb-448e-b8b2-24bc19ee40b9
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Area safe to work in
checkpoint-status |  |  | checkpoint | Framing and purlins complete and ready for metal base
checkpoint-group |  |  | section | Metal Base installation
checkpoint-status |  |  | checkpoint | All fixings (metal base secured to frame/structure)
checkpoint-status |  |  | checkpoint | No gaps in between metal base
checkpoint-status |  |  | checkpoint | All areas of gutter covered
checkpoint-group |  |  | section | Fibertite installation
checkpoint-status |  |  | checkpoint | Metal base dry and clean
checkpoint-status |  |  | checkpoint | Correct glue used
select | 90f40eb4-0611-4d47-95d4-3d6a3fe688e1 |  | dropdown | Select glue type | 490u,190e
checkpoint-status |  |  | checkpoint | Fibertite fully glued to metal base substrate
checkpoint-status |  |  | checkpoint | Fibertite installed up and over first purlin on both sides
checkpoint-status |  |  | checkpoint | All laps, details, corners fully closed and QA'd
checkpoint-status |  |  | checkpoint | Sign Off
checklist-sectioned |  |  | checklist | Rooflogic Fibertite Hybrid System |  |  |  |  | Yes | Rooflogic Fibertite Hybrid System | d49a14d3-4037-492f-96c6-5e0bd040d795
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection in place
checkpoint-status |  |  | checkpoint | Substrate clean and clear of debris and moss/mould
checkpoint-group |  |  | section | Concrete substrate
checkpoint-status |  |  | checkpoint | Free from holes & lumps of concrete
checkpoint-status |  |  | checkpoint | Outlet holes cut into base
checkpoint-group |  |  | section | Bitumen Base sheet
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear
checkpoint-status |  |  | checkpoint | Install FTR SBS Adhesive
checkpoint-status |  |  | checkpoint | Install Bitumen base sheet into adhesive with 80mm min laps
checkpoint-status |  |  | checkpoint | Roll/broom of membrane into adhesive
checkpoint-status |  |  | checkpoint | Hot air weld any laps
checkpoint-status |  |  | checkpoint | Probe of laps with QA hook
checkpoint-group |  |  | section | Fibertite XT
checkpoint-status |  |  | checkpoint | Surface clean and free from debris
checkpoint-status |  |  | checkpoint | Adhesive installed to base sheet the width of the roll
checkpoint-status |  |  | checkpoint | Laying of membrane into the adhesive
checkpoint-status |  |  | checkpoint | Laping on adjacent membrane to be minimum of 75mm
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane into adhesive
checkpoint-status |  |  | checkpoint | Wipe and clean of laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with welding machine
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-status |  |  | checkpoint | ILD test
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly accordnig to specifications
checkpoint-status |  |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of weld with QA hook
checkpoint-group |  |  | section | Review and Sign off
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviwed as per specification
checkpoint-status |  |  | checkpoint | FCC project manager sign off
holdpoint |  |  | signoff | Sign off
checklist-sectioned |  |  | checklist | Fibertite Overlay Install |  |  |  |  | Yes | Fibertite Overlay Install | d90d2857-1c63-44f4-88b1-4769390630c4
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection installed (safe to go onto roof)
checkpoint-status |  |  | checkpoint | Substrate ready for overlay
checkpoint-group |  |  | section | Substrate
checkpoint-status |  |  | checkpoint | Mechanically Fix existing roof pans to Purlins after checking underneath from inside that we're not going to puncture pipes or wires
checkpoint-status |  |  | checkpoint | Cut back existing roof edge at gutter
checkpoint-status |  |  | checkpoint | Remove ridge as we go
checkpoint-group |  |  | section | Polystyrene Infills
checkpoint-status |  |  | checkpoint | Surface is dry before installing Poly
checkpoint-status |  |  | checkpoint | Infills to be a minimum 5mm above ridges on roof
checkpoint-status |  |  | checkpoint | Every pan has been infilled
checkpoint-group |  |  | section | VCL-Vapour Control Layer
checkpoint-status |  |  | checkpoint | Surface/Substrate is dry, clean and free from sharp edges
checkpoint-status |  |  | checkpoint | All areas covered and lapped a minimum of 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and made watertight
checkpoint-group |  |  | section | Roofboard
checkpoint-status |  |  | checkpoint | Substrate/surface dry & clean prior to being installed
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct screws with recessed flat plates. check that screws have grabbed and are tight
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-status |  |  | checkpoint | Install 70mm X 100mm zincalume flashing at gutter edge for strength
checkpoint-group |  |  | section | Fibertite
checkpoint-status |  |  | checkpoint | Correct Glue being used for substrate (refer to training module/specification for correct glue to use for each substrate)
checkpoint-status |  |  | checkpoint | Fibertite fully glued to substrate
checkpoint-status |  |  | checkpoint | Broom/rolling of fibertite
checkpoint-status |  |  | checkpoint | Wipe/clean laps with acetone prior to welding
checkpoint-status |  |  | checkpoint | All laps, details, penetrations fully welded/closed and QA'd with hook
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly (right way around)
checkpoint-status |  |  | checkpoint | Fixed down accordingto specification (tapits, screws, rivets)
checkpoint-status |  |  | checkpoint | Cleaned down with acetone prior to welding
checkpoint-status |  |  | checkpoint | Fibertite fully welded to flashing and QA'd with hook
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Area fully complete and ready for MC sign off
holdpoint |  |  | signoff | REQUEST SIGNATURE SIGN OFF
checklist-flat |  |  | checklist | Site Visit date: |  |  |  |  | Yes | Supplier Site Visit | dacad0ee-1c23-44c2-b4c7-29ca2835fbe7
checkpoint-no-status |  |  | checkpoint | Site Details
text | 6d41fa6a-4e1a-577e-a624-6bd736f97876 |  | textbox | Job Name
text | 22044acf-ec81-5b86-a826-c71cabe41273 |  | textbox | Who is in attendance
text | 1235194d-88da-53a0-854a-ce85145c2b1e |  | textbox | Area/Gridlines/Detail
checkpoint-status |  |  | checkpoint | Photos
text | e4f72de6-232e-5c0f-a8f5-0b30ac9ea698 |  | textbox | Inspection Notes
holdpoint |  |  | signoff | Signoff Required
checklist-flat |  |  | checklist | MSR Cladding: |  |  |  |  | Yes | MSR Cladding Checklist | dd9fffb5-1eba-4558-b9c7-c75dfb2f2b52
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Substrate QA received from Main Contractor
checkpoint-status |  |  | checkpoint | Vapour Barrier
checkpoint-status |  |  | checkpoint | Brackets installed to fixing plan
checkpoint-status |  |  | checkpoint | Insulation - no gaps
checkpoint-status |  |  | checkpoint | Rom Rail
checkpoint-status |  |  | checkpoint | Cladding straight
checkpoint-status |  |  | checkpoint | Flashings installed
checkpoint-status |  |  | checkpoint | Sign off
holdpoint |  |  | signoff | Hold Point
checklist-flat |  |  | checklist | Final inspection |  |  |  |  | Yes | Add Final Inspection Checklist | e1f3055a-7d57-4911-85dd-fd02bf930fa5
checkpoint-status |  |  | checkpoint | Final inspection
text | 5c48b2f9-7155-5010-a625-9c61273b1f4a |  | textbox | Date
text | cd590b2d-dfd9-5926-aa7f-cbbffee96ba3 |  | textbox | Area/elevation/grids
text | f185db39-ef5a-566f-a627-b84ed061402b |  | textbox | Description
label | bc73c8d4-7e08-5fa4-a4f2-97028cc937d1 |  | note | Attach Photos
holdpoint |  |  | signoff | Request Signature Signoff
checklist-sectioned |  |  | checklist | Plywood Torch On Checklist - |  |  |  |  | Yes | Plywood Torch On Checklist | e5a42195-8fda-4082-8e46-8004d263584f
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP (metal/concrete/ply)
checkpoint-status |  |  | checkpoint | Perimeter support installed installed if metal deck substrate
checkpoint-group |  |  | section | Plywood
checkpoint-status |  |  | checkpoint | Plywood clean and dry. Free from dirt/debris and and ready for priming
checkpoint-status |  |  | checkpoint | No screws/nails/fixings popping up
checkpoint-status |  |  | checkpoint | Plywood joints flush and even
checkpoint-group |  |  | section | Prime of Substrate
checkpoint-status |  |  | checkpoint | Substrate swept, dry and free of debri
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed in a brick pattern
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-status |  |  | checkpoint | Fixings at correct spacing according to spec if no Securock in system.
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with recessed flat plates
checkpoint-status |  |  | checkpoint | Prime of Securrock
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Bleed of bitumen on overlap should be up to 10mm
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check of all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 200mm
checkpoint-status |  |  | checkpoint | Clamp and weld into overflows and outlets
checkpoint-status |  |  | checkpoint | Flood test of outlets
checkpoint-group |  |  | section | Sign Offs
checkpoint-status |  |  | checkpoint | Area complete and ready for MC sign off
holdpoint |  |  | signoff | REQUEST SIGN OFF SIGNATURE
checklist-flat |  |  | checklist | Ridge & Valley Flashing Installation - |  |  |  |  | Yes | Add Ridge & Valley Flashing Installation Checklist | ea50d492-d108-45e2-99e0-827ad911b01e
checkpoint-status |  |  | checkpoint | Install Metal deck, VCL, PIr and Securock into lifting eyes
checkpoint-status |  |  | checkpoint | Check vapour barrier is connected
checkpoint-status |  |  | checkpoint | Install expansion foam to joint if required
checkpoint-status |  |  | checkpoint | Install flashing under Roof membrane, screws at 300mm centres
checkpoint-status |  |  | checkpoint | Glue FB membrane onto flashing
checkpoint-status |  |  | checkpoint | Install 70mm x 70mm FiberTite SM membrane to valley/ridge to a straight chalk line
checkpoint-status |  |  | checkpoint | Probe membrane joins
checklist-flat |  |  | checklist | Daily Cassette Log - |  |  |  |  | Yes | Add Daily Cassette Log | f10fa2a5-0a80-450c-a553-ceaa1a1e4b9b
checkpoint-no-status |  |  | checkpoint | Date:
text | e5ab19af-90b5-4328-9a8b-ee0707087643 |  | textbox
checkpoint-no-status |  |  | checkpoint | Cassette Number:
text | 8e11a44b-51f7-4a8f-9494-ec9e467452ec |  | textbox
checkpoint-no-status |  |  | checkpoint | Record any delays:
text | 22cd20b8-86af-49a9-97d4-39d5b860ca1a |  | textbox
checkpoint-no-status |  |  | checkpoint | Wind/Weather Conditions:
text | 5114a122-dcf7-44a7-be38-8623182196af |  | textbox
checkpoint-no-status |  |  | checkpoint | Comments/Issues/Observations:
text | a6aebd36-6433-4aca-b8f4-ef6216c059cf |  | textbox
checklist-sectioned |  |  | checklist | Cladding - |  |  |  |  | Yes | Add Cladding Checklist | f33c5e1b-f50f-410c-b386-98c7412c2dd7
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Coil ordered, colour sorted
checkpoint-status |  |  | checkpoint | Clips, screwed ordered
checkpoint-status |  |  | checkpoint | Pan width, Set out of pans agreed with main contractor/architect
checkpoint-status |  |  | checkpoint | Flashing details agreed with main contractor/architect
checkpoint-status |  |  | checkpoint | Substrate ready, battens paper
checkpoint-group |  |  | section | Install
checkpoint-status |  |  | checkpoint | Bottom starter flashing installed
checkpoint-status |  |  | checkpoint | First pan straight/plumb
checkpoint-status |  |  | checkpoint | Clip spacing correct for length of sheet, right number of expansion clips
checkpoint-status |  |  | checkpoint | Cladding running straight/plumb
checkpoint-status |  |  | checkpoint | Flashings installed around doors windows
checkpoint-status |  |  | checkpoint | Any damage
checkpoint-status |  |  | checkpoint | Main contractor sign off
checkpoint-status |  |  | checkpoint | Main contractor to protect
checklist-flat |  |  | checklist | Defect - |  |  |  |  | Yes | Add Defect | f79a3749-fc84-468b-906b-a84ceb2b3161
checkpoint-status |  |  | checkpoint | Defect details recorded
text | 9b18e909-7530-4d08-ad54-acb417409980 |  | textbox | Explanation of defect:
text | 3af60290-922d-4e09-aeb9-b795186cbbd5 |  | textbox | Area:
text | da7b5fcc-182d-4ccf-ade5-02dfaae6dedb |  | textbox | Party responsible for damages:
text | f37cdc9e-47d2-43c7-b8ce-36034d624bbc |  | textbox | Efforts required for repair:
text | 16d78d9b-0a7d-4e07-bb38-68e664e6d30e |  | textbox | Man hours required for repair:
holdpoint |  |  | signoff | Request Approval from Main Contractor
checkpoint-status |  |  | checkpoint | Defect Fixed
holdpoint |  |  | signoff | Request Defect signoff