## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Sheet Tanking System Checklist |  |  |  |  | Yes | QA - Sheet Tanking System Checklist | 14bf945b-4c94-47bb-aafa-a8e9c0ad81f3
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Primer
checkpoint-status |  |  | checkpoint | Applied as per specification on dry substrate at 5m2 per litre
checkpoint-group |  |  | section | Membrane
checkpoint-status |  |  | checkpoint | Temperature must be over 4 degrees for membrane install
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear
checkpoint-status |  |  | checkpoint | Membrane applied with min 50mm overlap
checkpoint-status |  |  | checkpoint | Overlap is to pressure applied or rolled for seal
checkpoint-group |  |  | section | Protection
checkpoint-status |  |  | checkpoint | Works to be protected by main contractor
checklist-flat |  |  | checklist | Defect - |  |  |  |  | Yes | Add Defect Checklist | 73554810-7587-4136-ab90-0915e9e1dbe2
checkpoint-status |  |  | checkpoint | Defect details recorded
text | 9b18e909-7530-4d08-ad54-acb417409980 |  | textbox | Explanation of defect:
text | 3af60290-922d-4e09-aeb9-b795186cbbd5 |  | textbox | Area:
text | da7b5fcc-182d-4ccf-ade5-02dfaae6dedb |  | textbox | Party responsible for damages:
text | f37cdc9e-47d2-43c7-b8ce-36034d624bbc |  | textbox | Efforts required for repair:
text | 16d78d9b-0a7d-4e07-bb38-68e664e6d30e |  | textbox | Man hours required for repair:
holdpoint |  |  | signoff | Request Approval from Main Contractor
checkpoint-status |  |  | checkpoint | Defect Fixed
holdpoint |  |  | signoff | Request Defect signoff
checklist-sectioned |  |  | checklist | Torch On Warmroof to Concrete Checklist |  |  |  |  | Yes | QA - Torch On Warmroof to Concrete Checklist | 492437f4-cf0e-4a8f-abf1-c7d41c429464
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Concrete
checkpoint-status |  |  | checkpoint | Concrete clean and dry. Free from dirt/debris and ready for priming
checkpoint-status |  |  | checkpoint | All lumps and sharp concrete bits ground down/hammered down
checkpoint-status |  |  | checkpoint | Large holes filled with grout
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with load washer
checkpoint-status |  |  | checkpoint | Prime of Securrock
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check of all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint-status |  |  | checkpoint | Clamps / rings / baskets press into overflows and outlets
checkpoint-status |  |  | checkpoint | Flood test / ELD tested
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Torch on Warmroof Over Plywood Checklist |  |  |  |  | Yes | QA - Torch on Warmroof Over Plywood Checklist | b20ca4b3-8468-45f4-b2cd-b483096c3bff
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Plywood
checkpoint-status |  |  | checkpoint | Plywood clean and dry. Free from dirt/debris and and ready for priming
checkpoint-status |  |  | checkpoint | No screws/nails/fixings popping up
checkpoint-status |  |  | checkpoint | Plywood joints flush and even
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with recessed flat plates
checkpoint-status |  |  | checkpoint | Prime of Securrock
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check of all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint-status |  |  | checkpoint | Clamps / rings / baskets installed and press into overflows and outlets
checkpoint-status |  |  | checkpoint | Flood test / ILD checked
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Metal cladding checklist |  |  |  |  | Yes | Metal cladding checklist | 6657f820-863c-4b44-8a08-697d096d6e0b
checkpoint-group |  |  | section | Pre start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Building wrap installed check plans and specifications and QA / handover received from main contactor
checkpoint-status |  |  | checkpoint | Battens installed with the correct spacings check plans and specifications QA / handover received from previous trade from main contactor
checkpoint-status |  |  | checkpoint | visual inspection by SWP
checkpoint-group |  |  | section | Rohm rails Install
checkpoint-status |  |  | checkpoint | flashing tape installed check plans and specifications
checkpoint-status |  |  | checkpoint | Rohm rails installed with the correct spacings check plans and specifications
checkpoint-status |  |  | checkpoint | Rohm rails installed to fixing plan
checkpoint-group |  |  | section | Cladding install
checkpoint-status |  |  | checkpoint | Cladding installed plump and straight
checkpoint-status |  |  | checkpoint | Screw pattern according to plan/specs/best practice
checkpoint-status |  |  | checkpoint | Closure foam installed
checkpoint-status |  |  | checkpoint | Top end turned up
checkpoint-group |  |  | section | Flashing install
checkpoint-status |  |  | checkpoint | Sealant installed with 2 continues beads
checkpoint-status |  |  | checkpoint | Clean excess sealant
checkpoint-status |  |  | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
checkpoint-status |  |  | checkpoint | Flashings installed as per drawings and specifications
checkpoint-status |  |  | checkpoint | Fixings installed as per drawings and specifications
checkpoint-group |  |  | section | Review and sign off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work completed, checked and reviewed as per specifications
holdpoint |  |  | signoff | Client/main contractor sign off
checklist-flat |  |  | checklist | Final inspection |  |  |  |  | Yes | Add Final Inspection Checklist | 13645b74-c2b0-47f7-bc5b-6d794583dfba
checkpoint-status |  |  | checkpoint | Final inspection
text | 5c48b2f9-7155-5010-a625-9c61273b1f4a |  | textbox | Date
text | cd590b2d-dfd9-5926-aa7f-cbbffee96ba3 |  | textbox | Area/elevation/grids
text | f185db39-ef5a-566f-a627-b84ed061402b |  | textbox | Description
label | bc73c8d4-7e08-5fa4-a4f2-97028cc937d1 |  | note | Attach Photos
holdpoint |  |  | signoff | Request Signature Signoff
checklist-flat |  |  | checklist | Daily Cassette Log - |  |  |  |  | Yes | Add Daily Cassette Log | d887a7ec-32a8-4460-8fd9-2b88cb25d057
checkpoint-no-status |  |  | checkpoint | Date:
text | e5ab19af-90b5-4328-9a8b-ee0707087643 |  | textbox
checkpoint-no-status |  |  | checkpoint | Cassette Number:
text | 8e11a44b-51f7-4a8f-9494-ec9e467452ec |  | textbox
checkpoint-no-status |  |  | checkpoint | Record any delays:
text | 22cd20b8-86af-49a9-97d4-39d5b860ca1a |  | textbox
checkpoint-no-status |  |  | checkpoint | Wind/Weather Conditions:
text | 5114a122-dcf7-44a7-be38-8623182196af |  | textbox
checkpoint-no-status |  |  | checkpoint | Comments/Issues/Observations:
text | a6aebd36-6433-4aca-b8f4-ef6216c059cf |  | textbox
checklist-flat |  |  | checklist | Variation Details - |  |  |  |  | Yes | Add Variation Checklist | 975c6e74-f00e-4b22-a81f-1bd8fe0954ec
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Reference/Drawing/Instruction Number
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Variation Area
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Materials & labour breakdown
holdpoint |  |  | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  |  | signoff | Request Variation Signoff
checklist-flat |  |  | checklist | Dayworks - |  |  |  |  | Yes | Add Dayworks Checklist | 494df41c-3b67-49a7-854f-43800155fade
checkpoint-status |  |  | checkpoint | Day Work Details
text | d27d8079-cce6-47f2-bc8f-5447bd0b63c3 |  | textbox | NTSC / SI #:
text | d63889f7-ee5a-4b1a-8284-614d5f938189 |  | textbox | Labours (HR)
text | 926bb36c-59db-4b70-828c-6bc1bf2ce049 |  | textbox | Work Description:
text | 693bbb1a-ade5-4140-a549-223cae16f4cb |  | textbox | Materials:
text | 6d1abe7d-16c2-45ff-b354-7f74775359b8 |  | textbox | SWP Representative. Prepared By:
text | 7e548609-67fa-4b3f-91fa-027d546e556f |  | textbox | Client Representative. Confirmed By:
holdpoint |  |  | signoff | Request Signature Signoff
checklist-sectioned |  |  | checklist | FiberTite to plywood warm roof checklist |  |  |  |  | Yes | FiberTite to plywood warm roof checklist | 61113bdb-03de-4090-9674-b8b20f88dbfe
checkpoint-group |  |  | section | Pre start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Visual inspection of substrate ready for SWP
checkpoint-status |  |  | checkpoint | QA document received from previous trade from main contractor
checkpoint-status |  |  | checkpoint | Visual check no screws/nails/fixings popping up
checkpoint-status |  |  | checkpoint | Visual check that joints are flush and even
checkpoint-group |  |  | section | Plywood Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for VCL
checkpoint-group |  |  | section | Vapor control layer
checkpoint-status |  |  | checkpoint | Substrate clean, dry, free of debris
checkpoint-status |  |  | checkpoint | Z flashing installed
checkpoint-status |  |  | checkpoint | VCL installed and covered all surface
checkpoint-status |  |  | checkpoint | VCL lapped with a minimum of 100mm side and end laps
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | VCL clean, dry, free of debris prior to install
checkpoint-status |  |  | checkpoint | VCL has been checked for damages and repaired
checkpoint-status |  |  | checkpoint | Closure flashings installed correctly
checkpoint-status |  |  | checkpoint | Specified insulation board installed
checkpoint-status |  |  | checkpoint | Boards tightly butted
checkpoint-status |  |  | checkpoint | Fixing plan attached
checkpoint-status |  |  | checkpoint | Installed as per fixing plan if no HDP board
checkpoint-group |  |  | section | ILD system installed
checkpoint-status |  |  | checkpoint | ILD System installed as per specs
checkpoint-status |  |  | checkpoint | ILD test plate installed
checkpoint-group |  |  | section | HDP board
checkpoint-status |  |  | checkpoint | PIR clean, dry, free of debris prior to install
checkpoint-status |  |  | checkpoint | Fixing plan attached
checkpoint-status |  |  | checkpoint | HDP installed tightly butted in brick pattern
checkpoint-status |  |  | checkpoint | Installed as per fixing plan
checkpoint-group |  |  | section | FiberTite
checkpoint-status |  |  | checkpoint | Prime substrate where required
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with welding machine
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-group |  |  | section | Sumps
checkpoint-status |  |  | checkpoint | Sealant installed to dropper flange under membrane
checkpoint-status |  |  | checkpoint | Membrane dressed in to outlets
checkpoint-status |  |  | checkpoint | Clamp/rings/basket installed
checkpoint-status |  |  | checkpoint | Flood test
checkpoint-group |  |  | section | ILD report
checkpoint-status |  |  | checkpoint | ILD report
checkpoint-group |  |  | section | Fibre clad flashing
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications ( right way around )
checkpoint-status |  |  | checkpoint | Fixing and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-group |  |  | section | Pressure bar installed
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications ( right way around )
checkpoint-status |  |  | checkpoint | Fixings done according to specifications and details
checkpoint-status |  |  | checkpoint | Prime of Substrate where required
checkpoint-status |  |  | checkpoint | Sealant installed
checkpoint-group |  |  | section | Over flashings
checkpoint-status |  |  | checkpoint | Over flashings has a separation barrier
checkpoint-status |  |  | checkpoint | Fixings done according to specifications and details
checkpoint-status |  |  | checkpoint | Prime of Substrate where required
checkpoint-status |  |  | checkpoint | Sealant installed
checkpoint-group |  |  | section | Review and sign off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work completed, checked and reviewed as per specifications
holdpoint |  |  | signoff | Client/main contractor sign off
checklist-sectioned |  |  | checklist | Torch On to Concrete Checklist |  |  |  |  | Yes | QA - Torch On to Concrete Checklist | f52bcb99-7095-4199-9648-040b808ea31f
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Concrete Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status |  |  | checkpoint | All lumps and sharp concrete bits ground/hammered down
checkpoint-status |  |  | checkpoint | Large holes filled with grout
checkpoint-group |  |  | section | Prime of Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and free from debris
checkpoint-status |  |  | checkpoint | Primer installed
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Install clamps/rings/baskets
checkpoint-status |  |  | checkpoint | Flood/ILD test
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | MSR cladding checklist |  |  |  |  | Yes | MSR cladding checklist | 097d4ea5-b32a-45bd-93cb-2cfa322f8e9a
checkpoint-group |  |  | section | Pre start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Purlins installed and QA / handover received from previous trade from main contractor
checkpoint-status |  |  | checkpoint | visual inspection by SWP
checkpoint-group |  |  | section | Vapor control layer
checkpoint-status |  |  | checkpoint | Substrate clean, dry, free of debris
checkpoint-status |  |  | checkpoint | VCL installed and covered all surface
checkpoint-status |  |  | checkpoint | VCL lapped with a minimum of 100mm side and end laps
checkpoint-group |  |  | section | Rohm rails Install
checkpoint-status |  |  | checkpoint | C channel flashings installed
checkpoint-status |  |  | checkpoint | flashing tape installed check plans and specifications
checkpoint-status |  |  | checkpoint | Rohm rails installed with the correct spacings check plans and specifications
checkpoint-status |  |  | checkpoint | Rohm rails installed to fixing plan
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Boards tightly butted all areas covered
checkpoint-status |  |  | checkpoint | Correct PIR installed as per spec
checkpoint-group |  |  | section | Underlay installed
checkpoint-status |  |  | checkpoint | Correct underlay installed as per specifications
checkpoint-status |  |  | checkpoint | Overlapped a minimum 150mm side laps and 200mm end laps
checkpoint-status |  |  | checkpoint | All areas covered
checkpoint-status |  |  | checkpoint | Underlay installed as per specifications
checkpoint-status |  |  | checkpoint | Joints taped together as per drawings and specifications
checkpoint-group |  |  | section | Cladding installation
checkpoint-status |  |  | checkpoint | Starter flashings installed
checkpoint-status |  |  | checkpoint | Laid straight and perpendicular to gutter/purlins
checkpoint-status |  |  | checkpoint | Top end turned up
checkpoint-status |  |  | checkpoint | Closure foam installed
checkpoint-status |  |  | checkpoint | Screw pattern according to plan/specs/fixing plan
checkpoint-group |  |  | section | Flashing install
checkpoint-status |  |  | checkpoint | Sealant installed with 2 continues beads
checkpoint-status |  |  | checkpoint | Clean excess sealant
checkpoint-status |  |  | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
checkpoint-status |  |  | checkpoint | Flashings installed as per drawings and specifications
checkpoint-status |  |  | checkpoint | Fixings installed as per drawings and specifications
checkpoint-group |  |  | section | Review and sign off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work completed, checked and reviewed as per specifications
holdpoint |  |  | signoff | Client/main contractor sign off
checklist-flat |  |  | checklist | Job Details |  |  |  |  | Yes | SYS - PT - Job Details | d49f7027-e08f-4028-be73-19e14713a53c
checkpoint-status |  |  | checkpoint | Site Info
text | 4e739149-fe6d-425d-b45e-4a4ff63e7c1e |  | textbox | Site Address
text | e326d577-6e3a-40b7-870a-8e178eda7195 |  | textbox | Main Contractor Details
text | 6c1ef37c-4d31-4405-b668-f398c4ad1275 |  | textbox | Project Managers Details
text | 351c3436-2ae9-42ae-9ee9-1146e81bffa2 |  | textbox | Site Manager Details
checkpoint-status |  |  | checkpoint | Latest Drawings
checkpoint-status |  |  | checkpoint | Scope of Works Attached
checkpoint-status |  |  | checkpoint | Additional Pre Start Docs
checkpoint-status |  |  | checkpoint | Fixing Plan Attached
checklist-sectioned |  |  | checklist | FiberTite Checklist - Area: |  |  |  |  | Yes | Xtreme FibreTite Checklist | 6c249880-08bb-4f25-9a62-60a2a0693ade
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP (metal/concrete/ply)
checkpoint-status |  |  | checkpoint | Perimeter support installed installed if metal deck substrate
checkpoint-group |  |  | section | Metal Deck
checkpoint-status |  |  | checkpoint | Timber to have separation barrier
checkpoint-status |  |  | checkpoint | Base deck screwed down in every pan
checkpoint-status |  |  | checkpoint | Sheet edges stiched together at 300mm centres
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Acoustic Board
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | correct length screw with recessed flat plates
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed in a brick pattern
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-status |  |  | checkpoint | Fixings at correct spacing according to spec if no Securock in system.
checkpoint-group |  |  | section | HDP Roofboard
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | correct length screw with recessed flat plates
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
checkpoint-group |  |  | section | FiberTite
checkpoint-status |  |  | checkpoint | Test weld with welding machine
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into the adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean of laps prior to welding
checkpoint-status |  |  | checkpoint | Probe of seams with QA hook
checkpoint-status |  |  | checkpoint | Clamp and weld of outlets and overflows
checkpoint-status |  |  | checkpoint | Flood test of outlets
checkpoint-group |  |  | section | Fiberclad flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications (Right way around)
checkpoint-status |  |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of weld with QA hook
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Area Complete (Request MC Signoff)
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Site Visit date: |  |  |  |  | Yes | Supplier Site Visit | 4325987c-5633-429b-b27a-077e0c587ca4
checkpoint-no-status |  |  | checkpoint | Site Details
text | 6d41fa6a-4e1a-577e-a624-6bd736f97876 |  | textbox | Job Name
text | 22044acf-ec81-5b86-a826-c71cabe41273 |  | textbox | Who is in attendance
text | 1235194d-88da-53a0-854a-ce85145c2b1e |  | textbox | Area/Gridlines/Detail
checkpoint-status |  |  | checkpoint | Photos
text | e4f72de6-232e-5c0f-a8f5-0b30ac9ea698 |  | textbox | Inspection Notes
holdpoint |  |  | signoff | Signoff Required
checklist-sectioned |  |  | checklist | Metal gutter and downpipe checklist |  |  |  |  | Yes | Metal gutter and downpipe checklist | 4efa3907-7694-4b44-9e6c-4710b862f9c7
checkpoint-group |  |  | section | Pre start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Visual inspection of substrate ready for SWP
checkpoint-status |  |  | checkpoint | QA document received from previous trade from main contractor
checkpoint-group |  |  | section | Gutter install
checkpoint-status |  |  | checkpoint | Brackets installed according to drawings and specifications
checkpoint-status |  |  | checkpoint | Gutter lapped and sealed correctly according drawings and specifications
checkpoint-status |  |  | checkpoint | All terminations and ends folded and sealed
checkpoint-status |  |  | checkpoint | Expansion joints installed
checkpoint-status |  |  | checkpoint | Expansion joints roof flashings installed
checkpoint-group |  |  | section | Downpipe install
checkpoint-status |  |  | checkpoint | Correct size dropper installed, riveted and sealed
checkpoint-status |  |  | checkpoint | Correct downpipe brackets installed with the correct spacings
checkpoint-status |  |  | checkpoint | Down pipe installed plumb and straight
checkpoint-group |  |  | section | Review and sign off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work completed, checked and reviewed as per specifications
holdpoint |  |  | signoff | Client/main contractor sign off
checklist-sectioned |  |  | checklist | Carpark MMA Checklist |  |  |  |  | Yes | QA - Carpark MMA Checklist | 7727a854-4d78-44b5-a7c8-c1070dc2693f
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | SSSP onsite
checkpoint-status |  |  | checkpoint | Photos of any existing linemarkings installed
checkpoint-status |  |  | checkpoint | Fencing demarcation installed
checkpoint-status |  |  | checkpoint | Site signage installed
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Surface Prep
checkpoint-status |  |  | checkpoint | Removal of coatings
checkpoint-status |  |  | checkpoint | Grind of substrate
checkpoint-status |  |  | checkpoint | Shotblast of substrate to achieve suitable profile
checkpoint-group |  |  | section | Pre-start of membrane install
checkpoint-status |  |  | checkpoint | Substrate dry
checkpoint-group |  |  | section | Membrane install
checkpoint-status |  |  | checkpoint | Prime of substrate
checkpoint-status |  |  | checkpoint | Stripe out cracks
checkpoint-status |  |  | checkpoint | Map out areas based on coverage rates for install
checkpoint-status |  |  | checkpoint | Membrane layer installed
checkpoint-status |  |  | checkpoint | Wear layer installed and broadcast
checkpoint-status |  |  | checkpoint | Excess broadcast swept and removed
checkpoint-status |  |  | checkpoint | 1st Top coat
checkpoint-status |  |  | checkpoint | 2nd top coat
checkpoint-status |  |  | checkpoint | Linemarking installed
checkpoint-status |  |  | checkpoint | Site cleared and broken down
checkpoint-status |  |  | checkpoint | Site cleared and broken down
checklist-sectioned |  |  | checklist | Fiberglass System Checklist |  |  |  |  | Yes | QA - Fiberglass System Checklist | 2c08dbad-6330-4798-a61d-92f957abf563
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Surface Prep
checkpoint-status |  |  | checkpoint | Concrete free of contaminants
checkpoint-status |  |  | checkpoint | Concrete flat and smooth
checkpoint-status |  |  | checkpoint | Bug holes in plinths filled and smooth
checkpoint-status |  |  | checkpoint | All 90deg corners chamfered
checkpoint-group |  |  | section | Membrane install
checkpoint-status |  |  | checkpoint | Install sealant angle fillets to all wall floor junctions
checkpoint-status |  |  | checkpoint | Prime surfaces with Epistixx
checkpoint-status |  |  | checkpoint | 1st body coat with 300gram fiberglass installed
checkpoint-status |  |  | checkpoint | 2nd body coat
checkpoint-status |  |  | checkpoint | 3rd body coat
checkpoint-status |  |  | checkpoint | Traxx 2000 wear coat.
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | FiberTite to plywood checklist |  |  |  |  | Yes | FiberTite to plywood checklist | 568a8249-cb92-4b16-b607-2fa87b9bb653
checkpoint-group |  |  | section | Pre start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Visual inspection of substrate ready for SWP
checkpoint-status |  |  | checkpoint | QA document received from previous trade from main contractor
checkpoint-status |  |  | checkpoint | Visual check no screws/nails/fixings popping up
checkpoint-status |  |  | checkpoint | Visual check that joints are flush and even
checkpoint-group |  |  | section | Plywood Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-group |  |  | section | ILD Mesh System installed
checkpoint-status |  |  | checkpoint | ILD System installed as per specification
checkpoint-status |  |  | checkpoint | ILD test plate installed
checkpoint-group |  |  | section | FiberTite
checkpoint-status |  |  | checkpoint | Prime substrate where required
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with welding machine
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-group |  |  | section | Sumps
checkpoint-status |  |  | checkpoint | Sealant installed to dropper flange under membrane
checkpoint-status |  |  | checkpoint | Membrane dressed into outlets
checkpoint-status |  |  | checkpoint | Clamp/rings/basket installed
checkpoint-status |  |  | checkpoint | Flood test
checkpoint-group |  |  | section | ILD report
checkpoint-status |  |  | checkpoint | ILD report
checkpoint-group |  |  | section | Fibre clad flashing
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications ( right way around )
checkpoint-status |  |  | checkpoint | Fixing and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-group |  |  | section | Pressure bar installed
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications ( right way around )
checkpoint-status |  |  | checkpoint | Fixings done according to specifications and details
checkpoint-status |  |  | checkpoint | Prime of Substrate where required
checkpoint-status |  |  | checkpoint | Sealant installed
checkpoint-group |  |  | section | Over flashings
checkpoint-status |  |  | checkpoint | Over flashings has a separation barrier
checkpoint-status |  |  | checkpoint | Fixings done according to specifications and details
checkpoint-status |  |  | checkpoint | Prime of Substrate where required
checkpoint-status |  |  | checkpoint | Sealant installed
checkpoint-group |  |  | section | Review and sign off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work completed, checked and reviewed as per specifications
holdpoint |  |  | signoff | Client/main contractor sign off
checklist-sectioned |  |  | checklist | Weather Monitoring |  |  |  |  | Yes | Weather Monitoring | f8d82df7-2259-4496-9b44-fbde8d97af00
checkpoint-group |  |  | section | Current Weather
checkpoint-status |  |  | checkpoint | Todays date & Time
checkpoint-status |  |  | checkpoint | Wind / weather conditions
checkpoint-status |  |  | checkpoint | Record any delays
checkpoint-status |  |  | checkpoint | area / gridlines
checkpoint-status |  |  | checkpoint | Comments / issues / observations
checkpoint-group |  |  | section | Weather Forecast
checkpoint-status |  |  | checkpoint | What is the weather forecast this week
checkpoint-status |  |  | checkpoint | Record any delays
checkpoint-status |  |  | checkpoint | area / gridlines
checkpoint-status |  |  | checkpoint | Comments / issues / observations
checklist-flat |  |  | checklist | Delay Checklist |  |  |  |  | Yes | Add Delay Checklist | eaa64fc6-20cd-46d6-8fde-e41383a77674
checkpoint-no-status |  |  | checkpoint | Delay details.
text | ae5b692f-ee75-4a3d-90e7-43a6b2bca49e |  | textbox | Date:
text | 8e11a44b-51f7-4a8f-9494-ec9e467452ec |  | textbox | Description:
text | 22cd20b8-86af-49a9-97d4-39d5b860ca1a |  | textbox | Area/Grids:
text | e5ab19af-90b5-4328-9a8b-ee0707087643 |  | textbox | Wind/Weather Conditions:
checklist-sectioned |  |  | checklist | FiberTite warm roof to concrete fully adhered checklist |  |  |  |  | Yes | FiberTite warm roof to concrete fully adhered checklist | 8d4a45d3-ccca-46ec-9181-586066bef60b
checkpoint-group |  |  | section | Pre start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Visual inspection of substrate ready for SWP
checkpoint-status |  |  | checkpoint | QA document received from previous trade from main contractor
checkpoint-status |  |  | checkpoint | Large holes filled with grout by others
checkpoint-status |  |  | checkpoint | All lumps and sharp concrete bits ground/hammered down
checkpoint-group |  |  | section | Concrete Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for primer
checkpoint-status |  |  | checkpoint | installation of SA primer
checkpoint-group |  |  | section | Vapor control layer
checkpoint-status |  |  | checkpoint | Substrate clean, dry, free of debris
checkpoint-status |  |  | checkpoint | Z flashing installed
checkpoint-status |  |  | checkpoint | Install VCL over primer
checkpoint-status |  |  | checkpoint | VCL lapped with a minimum of 100mm side and end laps
checkpoint-status |  |  | checkpoint | Installation of SA primer
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | VCL clean, dry, free of debris prior to install
checkpoint-status |  |  | checkpoint | VCL has been checked for damages and repaired
checkpoint-status |  |  | checkpoint | Closure flashings installed correctly
checkpoint-status |  |  | checkpoint | Install board adhesive in specified pattern
checkpoint-status |  |  | checkpoint | Specified insulation board installed
checkpoint-status |  |  | checkpoint | Boards tightly butted
checkpoint-group |  |  | section | ILD system installed
checkpoint-status |  |  | checkpoint | ILD System installed as per specs
checkpoint-status |  |  | checkpoint | ILD test plate installed
checkpoint-group |  |  | section | HDP board
checkpoint-status |  |  | checkpoint | PIR clean, dry, free of debris prior to install
checkpoint-status |  |  | checkpoint | install board adhesive in specified pattern
checkpoint-status |  |  | checkpoint | HDP board installed in brick pattern where possible
checkpoint-group |  |  | section | FiberTite
checkpoint-status |  |  | checkpoint | Prime substrate where required
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with welding machine
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-group |  |  | section | Sumps
checkpoint-status |  |  | checkpoint | Sealant installed to dropper flange under membrane
checkpoint-status |  |  | checkpoint | Membrane dressed in to outlets
checkpoint-status |  |  | checkpoint | Clamp/rings/basket installed
checkpoint-status |  |  | checkpoint | Flood test
checkpoint-group |  |  | section | ILD report
checkpoint-status |  |  | checkpoint | ILD report
checkpoint-group |  |  | section | Fiberclad flashing
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications ( right way around )
checkpoint-status |  |  | checkpoint | Fixing and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-group |  |  | section | Pressure bar installed
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications ( right way around )
checkpoint-status |  |  | checkpoint | Fixings done according to specifications and details
checkpoint-status |  |  | checkpoint | Prime of Substrate where required
checkpoint-status |  |  | checkpoint | Sealant installed
checkpoint-group |  |  | section | Over flashings
checkpoint-status |  |  | checkpoint | Over flashings has a separation barrier
checkpoint-status |  |  | checkpoint | Fixings done according to specifications and details
checkpoint-status |  |  | checkpoint | Primer of Substrate
checkpoint-status |  |  | checkpoint | Sealant installed
checkpoint-group |  |  | section | Review and sign off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work completed, checked and reviewed as per specifications
holdpoint |  |  | signoff | Client/main contractor sign off
checklist-sectioned |  |  | checklist | Fibertherm Checklist |  |  |  |  | Yes | QA - Fibertherm Checklist | a3f7b109-61a3-4212-9d4f-a08941bc2109
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Metal Deck
checkpoint-status |  |  | checkpoint | Timber to have separation
checkpoint-status |  |  | checkpoint | End openings to have closure foam installed
checkpoint-status |  |  | checkpoint | Base deck screwed down in every pan
checkpoint-status |  |  | checkpoint | VCL tape to be installed to all sheet laps
checkpoint-status |  |  | checkpoint | VCL tape to all upstands
checkpoint-group |  |  | section | Post and Rail install
checkpoint-status |  |  | checkpoint | Post installed at correct fixing centers
checkpoint-status |  |  | checkpoint | Thermal break pad under post foot
checkpoint-status |  |  | checkpoint | Rail installed to posts
checkpoint-status |  |  | checkpoint | Gutter line colsure/drip edge flashing installed
checkpoint-group |  |  | section | Insulation install
checkpoint-status |  |  | checkpoint | Specified Insulation installed
checkpoint-status |  |  | checkpoint | No Gaps
checkpoint-group |  |  | section | Top Deck install
checkpoint-status |  |  | checkpoint | Lay sheets straight
checkpoint-status |  |  | checkpoint | Hang over into gutter min 75mm
checkpoint-status |  |  | checkpoint | Top end of sheets turned up
checkpoint-status |  |  | checkpoint | Bottom end of sheets turned down
checkpoint-status |  |  | checkpoint | Fixing back to rail
checkpoint-status |  |  | checkpoint | Profile washers
checkpoint-status |  |  | checkpoint | Screwed off as per fixing plan
checkpoint-group |  |  | section | Flashing install
checkpoint-status |  |  | checkpoint | Installed correctly, accoriding to spec's & drawings
checkpoint-status |  |  | checkpoint | Fixings according to specs & details
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-flat |  |  | checklist | Variation Details - |  |  |  |  | Yes | Variation Checklist | f8a2117b-bae5-4c25-851d-ec8b82aa4f1a
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Reference/Drawing/Instruction Number
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Variation Area
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Materials & labour breakdown
holdpoint |  |  | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  |  | signoff | Request Variation Signoff
checklist-flat |  |  | checklist | Flood Test Area: |  |  |  |  | Yes | Add Flood Testing Checklist | 22c95d72-dcc0-49a3-bdef-bdae9af4b94e
checkpoint-status |  |  | checkpoint | Is area fully finished, QA’d and ready to be tested
checkpoint-no-status |  |  | checkpoint | Flood test details
text | dc968f8f-9cf1-485a-a65f-e4087427ee32 |  | textbox | Date:
text | b0fb2bc4-3c3c-47bb-93fe-add4a651804d |  | textbox | Area tested:
text | befd486d-6456-4e39-ba95-1395566ebfda |  | textbox | Duration:
button | 3fff6840-5866-4f4c-96c8-494f7e9efd79 |  | button | Have you checked regularly for leaks | Yes, No, N/A
button | 050fef10-15f2-4590-ba62-2a0b1b1b0a29 |  | button | Is there rain in the forecast | Yes, No, N/A
button | 0816c7fc-09ce-4e48-9a88-625c7f8c9a23 |  | button | Have you eft some outlets/scuppers so that the building doesn't flood | Yes, No, N/A
button | b9de0cd4-9c7a-42cb-89ee-535d7ebdcd00 |  | button | Have all leaks been repaired | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Flood test complete
button | 5d04628a-e7a1-4bd7-b9ee-92a88ef12e94 |  | button | Have the plugs been removed from the drains | Yes, No, N/A
button | b74c91b9-0371-4641-ad5b-1c9d76ee0c77 |  | button | Debris and materials removed from the gutter/membrane/roof | Yes, No, N/A
holdpoint |  |  | signoff | Sign Off
checklist-sectioned |  |  | checklist | FiberTite to concrete checklist |  |  |  |  | Yes | FiberTite to concrete checklist | 2ad40d10-043f-4b62-9c9c-9f8a93bc6dea
checkpoint-group |  |  | section | Pre start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Visual inspection of substrate ready for SWP
checkpoint-status |  |  | checkpoint | QA document received from previous trade from main contractor
checkpoint-status |  |  | checkpoint | Large holes filled with grout by others
checkpoint-status |  |  | checkpoint | All lumps and sharp concrete bits ground/hammered down
checkpoint-group |  |  | section | Concrete substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-group |  |  | section | FiberTite
checkpoint-status |  |  | checkpoint | Prime substrate where required
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with welding machine
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-group |  |  | section | Sumps
checkpoint-status |  |  | checkpoint | Sealant installed to dropper flange under membrane
checkpoint-status |  |  | checkpoint | Membrane dressed in to outlets
checkpoint-status |  |  | checkpoint | Clamp/rings/basket installed
checkpoint-status |  |  | checkpoint | Flood test
checkpoint-group |  |  | section | ILD report
checkpoint-status |  |  | checkpoint | ILD report
checkpoint-group |  |  | section | Fiberclad flashing
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications ( right way around )
checkpoint-status |  |  | checkpoint | Fixing and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-group |  |  | section | Pressure bar installed
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications ( right way around )
checkpoint-status |  |  | checkpoint | Fixings done according to specifications and details
checkpoint-status |  |  | checkpoint | Prime of Substrate where required
checkpoint-status |  |  | checkpoint | Sealant installed
checkpoint-group |  |  | section | Over flashings
checkpoint-status |  |  | checkpoint | Over flashings has a separation barrier
checkpoint-status |  |  | checkpoint | Fixings done according to specifications and details
checkpoint-status |  |  | checkpoint | Primer of Substrate
checkpoint-status |  |  | checkpoint | Sealant installed
checkpoint-group |  |  | section | Review and sign off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work completed, checked and reviewed as per specifications
holdpoint |  |  | signoff | Client/main contractor sign off
checklist-sectioned |  |  | checklist | Torch on Warmroof Over Metal Deck Checklist |  |  |  |  | Yes | QA - Torch on Warmroof Over Metal Deck Checklist | 61392c15-0325-414d-a6c6-107fb38367b2
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Metal Deck
checkpoint-status |  |  | checkpoint | Timber to have separation barrier
checkpoint-status |  |  | checkpoint | Base deck screwed down in every pan
checkpoint-status |  |  | checkpoint | Sheet edges stitched together at 300mm centres
checkpoint-status |  |  | checkpoint | No sharp edges protruding
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with recessed flat plates
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-status |  |  | checkpoint | Prime of Securrock
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Bleed of bitumen on overlap should be up to 10mm
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check of all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint-status |  |  | checkpoint | Clamps / rings / baskets installed and press into overflows and outlets
checkpoint-status |  |  | checkpoint | Flood test / ILD tested
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | MSR checklist |  |  |  |  | Yes | MSR checklist | 7894970a-5e23-47ff-ba87-75f3d6175b4e
checkpoint-group |  |  | section | Pre start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Purlins installed and QA / handover received from main contractor
checkpoint-status |  |  | checkpoint | visual inspection by SWP
checkpoint-group |  |  | section | Liner deck
checkpoint-status |  |  | checkpoint | Liner deck fixed down in every purlin and every pan
checkpoint-status |  |  | checkpoint | Correct fixing installed
checkpoint-group |  |  | section | Vapor control layer
checkpoint-status |  |  | checkpoint | Substrate clean, dry, free of debris
checkpoint-status |  |  | checkpoint | Z flashing installed
checkpoint-status |  |  | checkpoint | VCL installed and covered all surface
checkpoint-status |  |  | checkpoint | VCL lapped with a minimum of 100mm side and end laps
checkpoint-group |  |  | section | Acoustic board install
checkpoint-status |  |  | checkpoint | VCL clean, no ponding water, free of debris prior to install
checkpoint-status |  |  | checkpoint | VCL has been cheeked for damages
checkpoint-status |  |  | checkpoint | All holes/penetrations patched
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Boards tightly butted all areas covered
checkpoint-status |  |  | checkpoint | Correct PIR installed as per spec
checkpoint-group |  |  | section | Underlay installed
checkpoint-status |  |  | checkpoint | Correct underlay installed as per specifications
checkpoint-status |  |  | checkpoint | Overlapped a minimum 150mm side laps and 200mm end laps
checkpoint-status |  |  | checkpoint | All areas covered
checkpoint-status |  |  | checkpoint | Underlay installed as per specifications
checkpoint-status |  |  | checkpoint | Joints taped together as per drawings and specifications
checkpoint-group |  |  | section | Metal roof installation
checkpoint-status |  |  | checkpoint | Drip edge installed as per drawings and specifications
checkpoint-status |  |  | checkpoint | Laid straight and perpendicular to gutter/purlins
checkpoint-status |  |  | checkpoint | Gutter overhang as per drawings and specifications
checkpoint-status |  |  | checkpoint | Top end turned up
checkpoint-status |  |  | checkpoint | Bottom ends turned down
checkpoint-status |  |  | checkpoint | Closure foam installed
checkpoint-status |  |  | checkpoint | Screw pattern according to plan/specs/fixing plan
checkpoint-group |  |  | section | Flashing install
checkpoint-status |  |  | checkpoint | Sealant installed with 2 continues beads
checkpoint-status |  |  | checkpoint | Clean excess sealant
checkpoint-status |  |  | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
checkpoint-status |  |  | checkpoint | Flashings installed as per drawings and specifications and facing away from waterflow
checkpoint-status |  |  | checkpoint | Fixings installed as per drawings and specifications
checkpoint-group |  |  | section | Review and sign off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work completed, checked and reviewed as per specifications
holdpoint |  |  | signoff | Client/main contractor sign off
checklist-sectioned |  |  | checklist | FiberTite warm roof to Base deck checklist |  |  |  |  | Yes | FiberTite warm roof to Base deck checklist | d08afa2a-ed63-4246-876c-aa2323ee1698
checkpoint-group |  |  | section | Pre start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Visual inspection of substrate ready for SWP
checkpoint-status |  |  | checkpoint | QA document received from previous trade from main contractor
checkpoint-group |  |  | section | Metal deck
checkpoint-status |  |  | checkpoint | Base deck screwed down in every pan and every purlin
checkpoint-status |  |  | checkpoint | Base deck laps stitched together at 300mm centres
checkpoint-status |  |  | checkpoint | Correct fixing
checkpoint-group |  |  | section | Vapor control layer
checkpoint-status |  |  | checkpoint | Substrate clean, dry, free of debris
checkpoint-status |  |  | checkpoint | Z flashing installed
checkpoint-status |  |  | checkpoint | VCL installed and covered all surface
checkpoint-status |  |  | checkpoint | VCL lapped with a minimum of 100mm side and end laps
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | VCL clean, dry, free of debris prior to install
checkpoint-status |  |  | checkpoint | VCL has been cheeked for damages and repaired
checkpoint-status |  |  | checkpoint | Closure flashings installed correctly
checkpoint-status |  |  | checkpoint | Specified insulation board installed
checkpoint-status |  |  | checkpoint | Boards tightly butted
checkpoint-status |  |  | checkpoint | Fixing plan attached
checkpoint-status |  |  | checkpoint | Installed as per fixing plan if no HDP board
checkpoint-group |  |  | section | ILD system installed
checkpoint-status |  |  | checkpoint | ILD System installed as per specs
checkpoint-status |  |  | checkpoint | ILD test plate installed
checkpoint-group |  |  | section | HDP board
checkpoint-status |  |  | checkpoint | PIR clean, dry, free of debris prior to install
checkpoint-status |  |  | checkpoint | Fixing plan attached
checkpoint-status |  |  | checkpoint | HDP installed tightly butted in brick pattern
checkpoint-status |  |  | checkpoint | Installed as per fixing plan
checkpoint-group |  |  | section | FiberTite
checkpoint-status |  |  | checkpoint | Prime substrate where required
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with welding machine
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-group |  |  | section | Sumps
checkpoint-status |  |  | checkpoint | Sealant installed to dropper flange under membrane
checkpoint-status |  |  | checkpoint | Membrane dressed in to outlets
checkpoint-status |  |  | checkpoint | Clamp/rings/basket installed
checkpoint-status |  |  | checkpoint | Flood test
checkpoint-group |  |  | section | ILD report
checkpoint-status |  |  | checkpoint | ILD report
checkpoint-group |  |  | section | Fibre clad flashing
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications ( right way around )
checkpoint-status |  |  | checkpoint | Fixing and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-group |  |  | section | Pressure bar installed
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications ( right way around )
checkpoint-status |  |  | checkpoint | Fixings done according to specifications and details
checkpoint-status |  |  | checkpoint | Prime of Substrate where required
checkpoint-status |  |  | checkpoint | Sealant installed
checkpoint-group |  |  | section | Over flashings
checkpoint-status |  |  | checkpoint | Over flashings has a separation barrier
checkpoint-status |  |  | checkpoint | Fixings done according to specifications and details
checkpoint-status |  |  | checkpoint | Prime of Substrate where required
checkpoint-status |  |  | checkpoint | Sealant installed
checkpoint-group |  |  | section | Review and sign off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work completed, checked and reviewed as per specifications
checkpoint-status |  |  | checkpoint | Client/main contractor sign off
checkpoint-status |  |  | checkpoint | All installation work completed, checked and reviewed as per specifications
holdpoint |  |  | signoff | Client/main contractor sign off
checklist-sectioned |  |  | checklist | Metal Roof checklist |  |  |  |  | Yes | Metal Roof checklist | 4654f1e5-efa9-4ed6-bea3-76e194d1e47f
checkpoint-group |  |  | section | Pre start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Purlins installed and QA / handover received from previous trade from main contractor
checkpoint-status |  |  | checkpoint | visual inspection by SWP
checkpoint-group |  |  | section | Safety Mesh install
checkpoint-status |  |  | checkpoint | Laid and secured perpendicular to the purlins
checkpoint-status |  |  | checkpoint | Lap side joins by min 1 grid section
checkpoint-group |  |  | section | Underlay installed
checkpoint-status |  |  | checkpoint | Correct underlay installed as per specifications
checkpoint-status |  |  | checkpoint | Overlapped a minimum 150mm side laps and 200mm end laps
checkpoint-status |  |  | checkpoint | All areas covered
checkpoint-status |  |  | checkpoint | Underlay installed as per specifications
checkpoint-status |  |  | checkpoint | Joints taped together as per drawings and specifications
checkpoint-group |  |  | section | Metal roof installation
checkpoint-status |  |  | checkpoint | Drip edge installed as per drawings and specifications
checkpoint-status |  |  | checkpoint | Laid straight and perpendicular to gutter/purlins
checkpoint-status |  |  | checkpoint | Gutter overhang as per drawings and specifications
checkpoint-status |  |  | checkpoint | Top end turned up
checkpoint-status |  |  | checkpoint | Bottom ends turned down
checkpoint-status |  |  | checkpoint | Closure foam installed
checkpoint-status |  |  | checkpoint | Sheets fixed in to the purlins
checkpoint-status |  |  | checkpoint | Screw pattern according to plan/specs/best practice
checkpoint-group |  |  | section | Flashing install
checkpoint-status |  |  | checkpoint | Sealant installed with 2 continues beads
checkpoint-status |  |  | checkpoint | Clean excess sealant
checkpoint-status |  |  | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
checkpoint-status |  |  | checkpoint | Flashings installed as per drawings and specifications
checkpoint-status |  |  | checkpoint | Fixings installed as per drawings and specifications
checkpoint-group |  |  | section | Review and sign off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work completed, checked and reviewed as per specifications
holdpoint |  |  | signoff | Client/main contractor sign off
checklist-sectioned |  |  | checklist | Torch On to Plywood Checklist |  |  |  |  | Yes | QA - Torch On to Plywood Checklist | 2f860b6f-9d6b-4b87-8014-05ef3307bb5a
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Plywood Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status |  |  | checkpoint | No Screws/nails/fixings popping up
checkpoint-status |  |  | checkpoint | Joints flush and even
checkpoint-group |  |  | section | Prime of Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and free from debris
checkpoint-status |  |  | checkpoint | Primer installed
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Install clamps/rings/baskets
checkpoint-status |  |  | checkpoint | Flood/ILD test
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off