## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Carpet ITP | [5 empty] | Carpet ITP (Building A & B)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
checkpoint | Area free of building debris and trade tools
checkpoint | Walls plastered and first coat of paint
checkpoint | All adjacent finishes completed and ready to receive finishes. Area to be flagged if LF cannot finish 100%
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
checkpoint | Barricaded areas
checkpoint | Vacuum area and minor patch as required
checkpoint | Apply Intertact Pressure Sensitive adhesive
checkpoint | Installation pattern and direction followed
checkpoint | Installation complete and rubbish placed in bins provided
checkpoint | Install 150mm feather edge skirting
checkpoint | Protection - woven plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms
checklist | Carpet ITP | [5 empty] | Carpet ITP (Building A & B) BTN
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
radio | Area free of building debris and trade tools | Complete,Pass
radio | Walls plastered and first coat of paint | Complete,Pass
radio | All adjacent finishes completed and ready to receive finishes. Area to be flagged if LF cannot finish 100% | Complete,Pass
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
radio | Barricaded areas | Complete,Pass
radio | Vacuum area and minor patch as required | Complete,Pass
radio | Apply Intertact Pressure Sensitive adhesive | Complete,Pass
radio | Installation pattern and direction followed | Complete,Pass
radio | Installation complete and rubbish placed in bins provided | Complete,Pass
checkpoint | Install 150mm feather edge skirting
checkpoint | Protection - woven plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms