## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 04.08 - Embankment | itp |  |  |  |  | 04.08 - Embankment
section | Details
checkpoint | Prior to incorporating any Earth or Rock Fill Material into the Works, the Contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrate the source meets the specified material requirements.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 10
label | Reference - MRTS04 Cl14.2.1
holdpoint | HOLD POINT
checkpoint | Rock Fill shall be sourced from a TMR regsitered quarry or other suitable source and shall comply with the properties states in Table 14.2.3.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl14.2.3
checkpoint | The foundation under rock fill shall be treated and shaped to maintain drainage and so erosion of the foundation will not occur.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl14.2.3
checkpoint | Rock fill shall be placed and spread in such a way to avoid segregation and contamination with foreign material. The uncompacted Rock Fill layer thickness must not exceed the thickness given in Table 15.4
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl14.2.3
checkpoint | Compact the Rock Fill using the mechanical interlock method of construction as per Clause 15.4
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl14.2.3
checkpoint | Embankments constructed to the shapes, zones and other requirements shown on the drawings or as otherwise specified.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl14.3.1
checkpoint | Geotextile placed at interchange between compaction methods
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl14.3.2
checkpoint | The ground surface on which embankments are to be constructed shall be stepped in accordance with the requirements of Cl14.3.3
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl14.3.3
checkpoint | The max thickness of an uncompacted layer shall be as per Table 15.4.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl15.4
checkpoint | Each layer rolled until the rolled surfaces do not exhibit any permanent deformation, rutting, yielding, signs of distress or instability.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point 6
label | Reference - MRTS04 Cl15.4
checkpoint | Final Verification
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off