## Sheet1
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
1 | AP40 Material Quality | Record TNZ/M4 Test Document | Confirm material meets M4 Crushing resistance test | Report | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | Verification | PE | Supplier
2 | Stabi Agent (Cement) | Record NZS 3122 | Confirm material as per NZS 3122 | Report | per Batch | Verification | PE | Supplier
3 | Weather Limitation | Measure temperature | "Minimum ambient air temp. Cement 5°C Lime 10°C" & Maximum windspeed of 25km/hr | Site notes | Daily | Witness | PS | Alliance
4 | Spreading rate | Average usage test | Target = 2.4kg/m2,Within ±0.5km/m² of the specified rate | Site notes | Daily | Verification | PS | Alliance
5 | Time limitation | Maximum time period from mixing to primary compaction | 2 hours, TNZB/5 | Site notes | Post stabilisation | Holdpoint | PS | Alliance
6 | In-situ Mixing | Cut depth | -5mm +15mm of design depth | Site notes | At both ends of cut & every 200m | Witness | PS | Alliance
7 | In-situ Mixing | Join Overlap | 100mm overlap | Site notes | Continuous | Witness | PS | Alliance
8 | In-situ Mixing | Particle Breakdown | Well mixed material with acceptable particle size distribution | Site notes | within the first 20m of each run, and where ever material changes | Witness | PS | Alliance
9 | Construction (Site Extent) | String line & survey | As per the design | Image | One for whole site | Witness | PE | Alliance
10 | Construction (Compaction & Degree of Saturation) | NDM - Maximum Dry Density & Degree of Saturation (DOS) | Base:Average ≥ 98% MDD Minimum ≥ 95% MDD") | Report | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | Holdpoint | PE | LAB
11 | Construction (Surface, Profile & layer thickness) | Visual inspection, Check string records, straight edge | No ponding if crossfall > 1% , Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design | Site notes | 1 test per 20m | Holdpoint | PE | Alliance
12 | Pavement finished surface | Ride quality & Mosaic surface | As per LDM | Site notes | 1 ride test for each lane following Basecourse completion prior to surfacing | Holdpoint | PE | Alliance
13 | Shoulders | Slope, Compaction & Soil support | Consistent slope, Vehicles can drive on shoulders without becoming stuck | Visual Inspection | All shoulders | Holdpoint | PS | Alliance
14 | Ready for sealing (Strength) | B Beam | Maximum deflection = 1.3mm | Report | Staggered every 10m | Holdpoint | PE | LAB
15 | Ready for sealing (Slope) | Levelling | 3m Straight edge deviation 10mm deviation | Image | Entire site | Verification | PS | Alliance
16 | Ready for sealing (Surface to seal texture) | Mosaic surface | NTLDM 4.17.5.2 | photos | Entire site | Witness | PS | Alliance
17 | Binder application | Verify m2 treated vs litres used | +-5% | QA operator | Entire site | Verification | PS | Alliance
18 | Traffic services | Marker pegs, sign & marking | Replaced in same position/height unless specified otherwise | Site notes | Entire site | Verification | PS | Alliance
19 | Asset As built Data |  | All relevant as built information collected | RAMM forms | During Construction | Verification | PS | Alliance