## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Sealed Pavement Maintenance - Stabilise (emulsion) | itp |  |  |  | Yes | Sealed Pavement Maintenance - Stabilise (emulsion) | 888e572a-ceca-405d-976f-4d138ff663c8
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | 1 - Cement
label | 782e8cc6-223f-5f0c-a326-b517c34c6fe4 |  | note | Inspection Point: Quality Control Activity - Cement added and raked evenly
label | c2762e4c-950d-511c-8536-5d66919de1da |  | note | Acceptance Criteria - 1 Bag per 10 m2, raked evenly
label | 8050c2e1-54a2-5512-9697-73531f646519 |  | note | Verifying Document - Visual, photo
label | a33ddb76-a6c5-59a7-915e-4f054642dcbb |  | note | Frequency - Once per patch
label | 4a5b6b29-ecca-566a-aabb-21576edf3967 |  | note | Inspection Type (Visual, other) - Verification
label | 1b1c3c71-fdc0-5c9d-b4db-9f459f1e00af |  | note | Inspection: By - Alliance
checkpoint-status |  |  | checkpoint | 2 - Emulsion Mill
label | 57162398-98cc-51f6-97c2-5d5f13a89881 |  | note | Inspection Point: Quality Control Activity - Litres of Emulsion used per m2
label | c95b2406-96e9-59b4-abc6-e478ea910e42 |  | note | Acceptance Criteria - Aim 8L per m2
label | 904c6666-6de4-5259-b151-b3847bef497a |  | note | Verifying Document - Add comment of Litres used
label | ba09601d-c037-5179-9949-a29f7ae1f989 |  | note | Frequency - Once per patch
label | e7f5cffa-bb17-5cce-9d75-dbe0d1b996d8 |  | note | Inspection Type (Visual, other) - Verification
label | 626c67cb-aaac-5613-84e5-650da8bd4a7d |  | note | Inspection: By - Alliance
checkpoint-status |  |  | checkpoint | 3 - Pavement Stength
label | 9e5e8089-823d-564e-af97-2554d6cda2c3 |  | note | Inspection Point: Quality Control Activity - Clegg testing to be done
label | 564d4603-dea2-5684-8556-1f3d10dcb3f6 |  | note | Acceptance Criteria - Clegg Impact Value to be greater than 35
label | 28584bc6-caa3-56fe-99af-8874d14b4bd5 |  | note | Verifying Document - Photos, Field testing document
label | 2fdadd6f-1bfd-5c83-9b36-efc55fbf7e3d |  | note | Frequency - Minimum 1 per 20m2
label | 584bf8c6-a203-5398-ab06-95e11c09caee |  | note | Inspection Type (Visual, other) - Hold Point
label | cd53178d-4707-569d-95d1-bc7441bf00cb |  | note | Inspection: By - Alliance
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Ready for Sealing
label | 62239452-8a36-5db7-bf42-1fca3a663fc7 |  | note | Verifying Document - Photo
label | ee60067d-773b-5d09-9cb0-e3b0cbf7a85e |  | note | Inspection Type (Visual, other) - Verification
label | 6635e920-67a9-5bf4-98ef-47f426ebf684 |  | note | Inspection: By - Alliance
checklist-sectioned |  |  | checklist | Sealed Pavement Maintenance - Digouts all depths | itp |  |  |  | Yes | Sealed Pavement Maintenance - Digouts all depths | 9c31a82c-cd59-4293-9e29-d9ab6d8d66c9
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | 1 - Service Locates
label | 4c96b043-3feb-5548-b942-849a016470a1 |  | note | Acceptance Criteria - Services located by Chorus and Delta prior to works commencing.
label | 116f87c4-9f2e-56e9-9631-0f8dbf398220 |  | note | Verifying Document - Photos
label | 827dbe59-5676-5df6-8e73-97a95d7d9d4d |  | note | Frequency - Once for each work location
label | 696a3052-01b5-54ad-a94a-e04e3c0a2ea6 |  | note | Inspection Type (Visual, other) - Hold Point
label | d4aba7df-94f7-5e1b-a166-44c49e5e3288 |  | note | Inspection: By - Alliance
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - AP40 Material Quality
label | 1e255379-435c-56b4-b931-07d55c9e83fc |  | note | Inspection Point: Quality Control Activity - Record M4 Test Document
label | 6d0bda3a-2023-56d3-b6a2-e433b89f0db5 |  | note | Acceptance Criteria - Confirm material meets M4 Spec
label | 0f728b64-58d2-5ac2-b1df-3446a1a031e9 |  | note | Verifying Document - Photos
label | 40ba5e05-7795-571d-bad2-ad083499fd98 |  | note | Frequency - Once for each work location
label | 731fb0b7-b894-5e73-aa46-f4f68ccf2526 |  | note | Inspection Type (Visual, other) - Verification
label | 776f4219-c2df-5842-8696-f6d7addc57af |  | note | Inspection: By - Alliance
checkpoint-status |  |  | checkpoint | 3 - Scala Penetrometer
label | efe121ea-4473-5697-8e18-aade60e2218f |  | note | Inspection Point: Quality Control Activity - Scala on fault to determine digout depth
label | 605449b0-647a-5c1a-88ff-0063d734359b |  | note | Verifying Document - Photos, Field testing document
label | 85adf26b-860d-5644-844b-510cc240bf1c |  | note | Frequency - One set of tests for each patch
label | c0fe0925-8195-516b-bba2-2023d1a31cc8 |  | note | Inspection Type (Visual, other) - Hold Point
label | d4f3f492-d99d-5dd9-a7b5-05f346df007b |  | note | Inspection: By - Alliance
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Digout
label | 22a3bd7e-122c-5b49-9576-b4654ed45ded |  | note | Inspection Point: Quality Control Activity - Digout complete to required depth. Stability of subgrade assessed
label | b75c115c-fd5e-5b32-ad33-fa5d601655cb |  | note | Acceptance Criteria - No soft spots, uneven areas or potential issues affecting roads foundations
label | 312e675a-7542-5249-b581-f695c1dafb22 |  | note | Verifying Document - Visual, Photo
label | fa0d763e-f4bd-54c5-928d-8ebaa6bc724f |  | note | Inspection Type (Visual, other) - Verification
label | 002aa14c-1f7e-55c4-8b5f-d23a9d811bab |  | note | Inspection: By - Alliance
checkpoint-status |  |  | checkpoint | 5 - AP65 Backfill
label | f72b0414-bdd0-50ec-ab28-de31ea942b20 |  | note | Inspection Point: Quality Control Activity - Clegg testing to be done on backfill
label | ec1e3598-9111-513e-b9b9-a02517639587 |  | note | Acceptance Criteria - Clegg Impact Value to be greater than 25
label | e2b7f596-3f79-53d0-a875-c22a0ac3f22a |  | note | Verifying Document - Photos, Field testing document
label | f60bf15b-76d0-5ad3-b134-7dc40bc1c0a4 |  | note | Frequency - Every 150mm lift, Minimum 1 per 20m2
label | 24a17d91-e027-59fb-a43c-b388cafac3d5 |  | note | Inspection Type (Visual, other) - Hold Point
label | 617cbc89-d712-582b-8bfc-a79ad2ff29ce |  | note | Inspection: By - Alliance
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - AP40 Backfill
label | d7f154ed-d758-57c9-bc9a-0add660f57d8 |  | note | Inspection Point: Quality Control Activity - Clegg testing to be done on backfill
label | 79ed613e-6038-566b-b940-4ad553a34663 |  | note | Acceptance Criteria - Clegg Impact Value to be greater than 35
label | bbbc6467-e852-562d-ae00-8992d224dc1a |  | note | Verifying Document - Photos, Field testing document
label | c9d6e1e5-cbcc-54e2-826d-c1b96807e8ad |  | note | Frequency - Every 150mm lift, Minimum 1 per 20m2
label | f67c2871-96ed-54f8-8b78-e6de7034a80f |  | note | Inspection Type (Visual, other) - Hold Point
label | 1e6fb061-1113-553b-9f01-6519d0e0b8ca |  | note | Inspection: By - Alliance
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Ready for sealing
label | 6d2f8eab-36c1-5378-9b86-60304c1ecaac |  | note | Verifying Document - Photo
label | 2700deaf-17e8-5503-b0e7-7e54d277f1c4 |  | note | Inspection Type (Visual, other) - Verification
label | ef91bce4-04d2-5c8f-b1ac-41d45e026974 |  | note | Inspection: By - Alliance